## Summary
Packages Summary
0059 ¦ Pursuit of a Radical Rhapsody ¦ Tower 8 |  | Total | Released Till Date | Released Till Dec 23 | Balance | AR | Planned Packages CY 24 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 24 | Q1 | Q2 | Q3 | Q4 | Planned Packages CY 25 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 25 | Q1 | Q2 | Q3 | Q4 | Planned Packages CY 26 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 26 | Q1 | Q2 | Q3 | Q4 | ST | Planned Packages CY 24 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 24 | Q1 | Q2 | Q3 | Q4 |  | Planned Packages CY 25 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 25 | Q1 | Q2 | Q3 | Q4 |  | Planned Packages CY 26 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 26 | Q1 | Q2 | Q3 | Q4 |  | MEP |  | Planned Packages CY 24 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 24 | Q1 | Q2 | Q3 | Q4 |  | Planned Packages CY 25 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 25 | Q1 | Q2 | Q3 | Q4 |  | Planned Packages CY 26 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 26 | Q1 | Q2 | Q3 | Q4 |  | UDLS |  | Planned Packages CY 24 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 24 | Q1 | Q2 | Q3 | Q4 |  | Planned Packages CY 25 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 25 | Q1 | Q2 | Q3 | Q4 |  | Planned Packages CY 26 | Q1 | Q2 | Q3 | Q4 | Actual Packages CY 26 | Q1 | Q2 | Q3 | Q4
Design Packages |  | 94 | 32 | 23 | 62 |  | 28 | 14 | 6 | 3 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 8 | 0 | 0 | 3 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 20 | 0 | 0 | 10 | 10 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 13 | 4 | 2 | 2 | 5 | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Design Fees
DESIGN |  | 16 | 16 | 16 | 0
1 | Contract + Design Brief | 1 | 1 | 1 | 0 | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
1 | Vision Statement |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
2 | Land - Topographical Survey with information as per defined standard, |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
3 | Zoning & Development Regulations |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
4 | Design Brief |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
2 | Schematic Concept | 4 | 4 | 4 | 0 | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
1 | Master Plan |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
2 | Blocks and Products |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
3 | Amenities & Facilities |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
4 | Design Basis |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
3 | Pre Construction Set | 4 | 4 | 4 | 0 | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
1 | Master Plan |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
2 | Blocks |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
3 | Products |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
4 | Amenities & Facilities |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
5 | Design Basis |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
4 | Approvals | 3 | 3 | 3 | 0 | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
1 | Development Plan |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
2 | Building Plan |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
3 | Fire Safety |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
4 | Environment |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
5 | Water Supply and Sewerage |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
6 | Power Supply |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
7 | Airport Authority |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
5 | Marketing and Sales | 4 | 4 | 4 | 0 | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
1 | Masterplan |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
2 | Blocks |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
3 | Products |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
4 | Specifications |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
5 | Clubhouse Design with list of Amenities |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
6 | Renders, Walk-through and Scaled model |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
7 | Project Entrance and Boundary wall |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
8 | Sales Centre and Experience Homes [Construction Docs] |  |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
CONSTRUCTION DOCUMENTS |  | 74 | 16 | 7 | 58
BB01 | GFC ¦ Tower—08 | 21 | 7 | 3 | 14 | 10 | 9 | 6 | 3 | 0 | 0 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 7 | 3 | 0 | 0 | 1 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 4 |  | 4 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
T08-1 | Foundation and Grade Slab | 3 | 3 | 2 | 0 | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | ✔ | ✔ | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
T08-2 | Parking Level-Sub grade | 2 | 1 | 0 | 1 | ✔ | ✔ | ✔ | - | - | - | ✔ | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
T08-3 | Building Envelope and Common Areas [Basement] | 1 | 0 | 0 | 1 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
T08-4 | Habitable Level 01 | 3 | 1 | 1 | 2 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
T08-5 | Habitable Level - Even | 2 | 1 | 0 | 1 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - |  | ✔ | ✔ | - | - | - | ✔ | ✔ | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
T08-6 | Habitable Level - Odd | 2 | 1 | 0 | 1 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - |  | ✔ | ✔ | - | - | - | ✔ | ✔ | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
T08-7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 | 0 | 0 | 1 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
T08-8 | Penthouse Levels | 3 | 0 | 0 | 3 | ✔ | ✔ | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
T08-9 | Terrace Level | 3 | 0 | 0 | 3 | ✔ | ✔ | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
T08-10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1 | 0 | 0 | 1 | ✔ | ✔ | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
BB02 | GFC ¦ Independent Subgrade Structure - Tower 8 | 9 | 1 | 1 | 8 | 3 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB02-1 | Earthwork | 1 | 1 | 1 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
BB02-2 | Foundations & Grade Slab | 3 | 0 | 0 | 3 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
BB02-3 | Podium Slab | 3 | 0 | 0 | 3 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
BB02-4 | Building Envelope and Common Areas | 2 | 0 | 0 | 2 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
PD | GFC ¦ Individual Homes | 24 | 8 | 3 | 16 | 8 | 7 | 3 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 7 | 0 | 0 | 3 | 4 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 0 | 7 | 3 | 0 | 0 | 4 | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R25-1 | R25 Default and it's variants | 3 | 3 | 3 | 0 | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
L20-1 | L20 Default and it's variants | 3 | 1 | 0 | 2 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | ✔ | - | - | - | ✔ | - | - | ✔ | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
D35-1 | D35 Default and it's variants | 3 | 1 | 0 | 2 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | ✔ | - | - | - | ✔ | - | - | ✔ | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
L22-1 | L22 Default and it's variants | 3 | 2 | 0 | 1 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | ✔ | - | - | - | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | ✔ | - | - | - | ✔ | - | - | - | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
R25P-1 | R25 P Default and it's variants | 3 | 1 | 0 | 2 | ✔ | ✔ | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | ✔ | - | - | - | ✔ |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
L20P-1 | L20 P Default and it's variants | 3 | 0 | 0 | 3 | ✔ | ✔ | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
D35P-1 | D35 P Default and it's variants | 3 | 0 | 0 | 3 | ✔ | ✔ | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
L22P-1 | L22 P Default and it's variants | 3 | 0 | 0 | 3 | ✔ | ✔ | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
MP | GFC ¦ Master Plan | 10 | 0 | 0 | 10 | 4 | 4 | 2 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 0 | 2 | 1 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SDV-1 | Master Plan | 3 | 0 | 0 | 3 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | ✔ | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
SDV-2 | Site Development | 2 | 0 | 0 | 2 | ✔ | ✔ | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
SDV-3 | Site MEP | 3 | 0 | 0 | 3 | ✔ | ✔ | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
SDV-4 | Landscaping | 2 | 0 | 0 | 2 | ✔ | ✔ | - | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
AM | GFC ¦ Amenities & Facilities | 10 | 0 | 0 | 10 | 4 | 4 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 0 | 3 | 0 | 2 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AMN-1 | Clubhouse—Structure and Envelope | 0 | 0 | 0 | 0 | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
AMN-2 | Clubhouse—Interiors and Facilities | 3 | 0 | 0 | 3 | ✔ | ✔ | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | ✔ | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
AMN-3 | Clubhouse—Outdoor Spaces and Pool | 3 | 0 | 0 | 3 | ✔ | ✔ | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | ✔ | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
AMN-4 | Community spaces [Board Walk, Children play area] | 2 | 0 | 0 | 2 | ✔ | ✔ | - | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | ✔ | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
AMN-5 | Sporting Facilities | 2 | 0 | 0 | 2 | ✔ | ✔ | - | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -
POST-CONSTRUCTION |  | 4 | 0 | 0 | 4
1 | Archives | 4 | 0 | 0 | 4 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 |  | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Complete set of "As-Built" drawings, final BoQ and project costs, | 4 | 0 | 0 | 4 | ✔ | ✔ | - | - | - | ✔ | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | - | ✔ | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | ✔ |  | ✔ | - | - | - | ✔ | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | - |  | - | - | - | - | - | - | - | - | - | -

## Design Fee
|  | Packages Design Fee |  |  | 2024 | Planned Billing CY 2024 |  |  |  |  | Actual Billing for CY 2024 |  |  |  |  | 2025 | Planned Billing CY 2025 |  |  |  |  | Actual Billing for CY 2025 |  |  |  |  | 2026 | Planned Billing CY 2026 |  |  |  |  | Actual Billing for CY 2026 |  |  |  |  | 1% | 1% |  |  | 2024 | Planned Billing CY 2024 |  |  |  |  | Actual Billing for CY 2024 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 24 |  |  |  |  | Issued Packages CY 24 |  |  |  |  | 2025 | Planned Billing CY 2025 |  |  |  |  | Actual Billing for CY 2025 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 25 |  |  |  |  | Issued Packages CY 25 |  |  |  |  | 2026 | Planned Billing CY 2026 |  |  |  |  | Actual Billing for CY 2026 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 26 |  |  |  |  | Issued Packages CY 26 | [8 empty] | 2024 | Planned Billing CY 2024 |  |  |  |  | Actual Billing for CY 2024 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 24 |  |  |  |  | Issued Packages CY 24 |  |  |  |  | 2025 | Planned Billing CY 2025 |  |  |  |  | Actual Billing for CY 2025 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 25 |  |  |  |  | Issued Packages CY 25 |  |  |  |  | 2026 | Planned Billing CY 2026 |  |  |  |  | Actual Billing for CY 2026 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 26 |  |  |  |  | Issued Packages CY 26 | [7 empty] | 2024 | Planned Billing CY 2024 |  |  |  |  | Actual Billing for CY 2024 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 24 |  |  |  |  | Issued Packages CY 24 |  |  |  |  | 2025 | Planned Billing CY 2025 |  |  |  |  | Actual Billing for CY 2025 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 25 |  |  |  |  | Issued Packages CY 25 |  |  |  |  | 2026 | Planned Billing CY 2026 |  |  |  |  | Actual Billing for CY 2026 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 26 |  |  |  |  | Issued Packages CY 26 | [7 empty] | 2024 | Planned Billing CY 2024 |  |  |  |  | Actual Billing for CY 2024 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 24 |  |  |  |  | Issued Packages CY 24 |  |  |  |  | 2025 | Planned Billing CY 2025 |  |  |  |  | Actual Billing for CY 2025 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 25 |  |  |  |  | Issued Packages CY 25 |  |  |  |  | 2026 | Planned Billing CY 2026 |  |  |  |  | Actual Billing for CY 2026 | [5 empty] | Status [in %] |  |  |  | Status [GFC's] |  | Planned Packages CY 26 |  |  |  |  | Issued Packages CY 26
0059 ¦ Pursuit of a Radical Rhapsody ¦ Tower 8 |  | Total Fee | Released Till Date | Balance | Billed till Dec'23 | Planned Billing CY 24 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 24 | Q1 | Q2 | Q3 | Q4 | Billed till Dec'24 | Planned Billing CY 25 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 25 | Q1 | Q2 | Q3 | Q4 | Billed till Dec'25 | Planned Billing CY 26 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 26 | Q1 | Q2 | Q3 | Q4 |  | AR | Fee | Billed YTD | Billed till Dec'23 | Planned Billing CY 24 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 24 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'23 | Plan in FY: 24 | Actual in CY : 24 |  | Total | Issued till Dec'23 | Plan in FY - 24 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 24 | Q1 | Q2 | Q3 | Q4 | Billed till Dec'24 | Planned Billing CY 25 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 25 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'24 | Plan in FY: 25 | Actual in CY : 25 |  | Total | Issued till Dec'24 | Plan in FY - 25 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 25 | Q1 | Q2 | Q3 | Q4 | Billed till Dec'25 | Planned Billing CY 26 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 26 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'25 | Plan in FY: 26 | Actual in CY : 26 |  | Total | Issued till Dec'25 | Plan in FY - 26 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 26 | Q1 | Q2 | Q3 | Q4 | ST |  | Fee | Billed YTD | Billed till Dec'23 | Planned Billing CY 24 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 24 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'23 | Plan in FY: 24 | Actual in CY : 24 |  | Total | Issued till Dec'23 | Plan in FY - 24 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 24 | Q1 | Q2 | Q3 | Q4 | Billed till Dec'24 | Planned Billing CY 25 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 25 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'24 | Plan in FY: 25 | Actual in CY : 25 |  | Total | Issued till Dec'24 | Plan in FY - 25 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 25 | Q1 | Q2 | Q3 | Q4 | Billed till Dec'25 | Planned Billing CY 26 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 26 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'25 | Plan in FY: 26 | Actual in CY : 26 |  | Total | Issued till Dec'25 | Plan in FY - 26 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 26 | Q1 | Q2 | Q3 | Q4 | MEP | Fee | Billed YTD | Billed till Dec'23 | Planned Billing CY 24 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 24 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'23 | Plan in FY: 24 | Actual in CY : 24 |  | Total | Issued till Dec'23 | Plan in FY - 24 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 24 | Q1 | Q2 | Q3 | Q4 | Billed till Dec'24 | Planned Billing CY 25 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 25 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'24 | Plan in FY: 25 | Actual in CY : 25 |  | Total | Issued till Dec'24 | Plan in FY - 25 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 25 | Q1 | Q2 | Q3 | Q4 | Billed till Dec'25 | Planned Billing CY 26 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 26 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'25 | Plan in FY: 26 | Actual in CY : 26 |  | Total | Issued till Dec'25 | Plan in FY - 26 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 26 | Q1 | Q2 | Q3 | Q4 | LDS | Fee | Billed YTD | Billed till Dec'23 | Planned Billing CY 24 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 24 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'23 | Plan in FY: 24 | Actual in CY : 24 |  | Total | Issued till Dec'23 | Plan in FY - 24 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 24 | Q1 | Q2 | Q3 | Q4 | Billed till Dec'24 | Planned Billing CY 25 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 25 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'24 | Plan in FY: 25 | Actual in CY : 25 |  | Total | Issued till Dec'24 | Plan in FY - 25 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 25 | Q1 | Q2 | Q3 | Q4 | Billed till Dec'25 | Planned Billing CY 26 | Q1 | Q2 | Q3 | Q4 | Actual Billing CY 26 | Q1 | Q2 | Q3 | Q4 |  | Completed till Dec'25 | Plan in FY: 26 | Actual in CY : 26 |  | Total | Issued till Dec'25 | Plan in FY - 26 | Q1 | Q2 | Q3 | Q4 | Actual in CY - 26 | Q1 | Q2 | Q3 | Q4 | REMARKS
Design Packages |  | 99 | 34 | 65 | 25 | 72 | 19 | 8 | 20 | 25 | 6 | 0 | 1 | 2 | 3 | 0 | 2 | 2 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 37 | 9 | 8 | 29 | 15 | 6 | 3 | 5 | 1 | 0 | 1 | 0 | 0 | 0 | Status |  |  |  | GFC Release | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Status |  |  |  | GFC Release | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Status |  |  |  | GFC Release | [11 empty] | 3% |  | 17 | 8 | 6 | 9 | 0 | 0 | 4 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | Status |  |  |  | GFC Release | [12 empty] | 2 | 2 | 0 | 0 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | Status |  |  |  | GFC Release | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Status |  |  |  | GFC Release | [11 empty] | 2% | 26 | 8 | 5 | 21 | 0 | 0 | 11 | 10 | 2 | 0 | 0 | 0 | 2 | 0 | Status |  |  |  | GFC Release | [12 empty] | 0 | 0 | 0 | 0 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | Status |  |  |  | GFC Release | [12 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Status |  |  |  | GFC Release | [11 empty] | 7% | 19 | 9 | 6 | 13 | 4 | 2 | 2 | 5 | 3 | 0 | 0 | 2 | 1 | 0 | Status |  |  |  | GFC Release | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Status |  |  |  | GFC Release | [11 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Status |  |  |  | GFC Release
Design Fees |  | 31.0015 | 16.1886 | 14.8129 | 15.3477 | 13.7056 | 6.5638 | 1.8125 | 1.6376 | 5.2418 | 0.35698 | 0 | 0.24096 | 0.0013219 | 0.11469 | 0 | 0.3982 | 0.3982 | 0 | 0 | 0 | 0.48394 | 0.48394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 22.89 | 11.5456 | 11.3046 | 11.5854 | 6.5414 | 1.754 | 0.0565 | 3.2334 | 0.24096 | 0 | 0.24096 | 0 | 0 | [5 empty] | 792 | 69 | 723 | 399 | 73 | 96 | 155 | 1 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 6.1895 | 3.7782 | 3.38 | 2.4114 | 0 | 0 | 1.0605 | 1.3509 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 67 | 19 | 41 | 10 | 0 | 13 | 18 | 12 | 10 | 0 | 0 | 2 |  | 0.3982 | 0.3982 | 0 | 0 | 0 | 0.3982 | 0.3982 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 74 | 0 | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.6358 | 0.74753 | 0.54776 | 1.0881 | 0 | 0 | 0.44748 | 0.64058 | 0.11403 | 0 | 0 | 0 | 0.11403 |  | 0 | 0 | 0 |  | 319 | 16 | 303 | 0 | 0 | 179 | 124 | 42 | 0 | 0 | 0 | 42 |  | 0 | 0 | 0 | 0 | 0 | 0.08574 | 0.08574 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 319 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.28616 | 0.11726 | 0.11528 | 0.17088 | 0.022342 | 0.058439 | 0.073131 | 0.016971 | 0.0019828 | 0 | 0 | 0.0013219 | 0.00066095 |  | 0 | 0 | 0 |  | 88 | 10 | 78 | 33 | 7 | 4 | 34 | 24 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[59 empty] | ITD23 | P23 | 1 | 2 | 3 | 4 | A23 | 5 | 6 | 7 | 8 | [17 empty] | ITD24 | P24 | 9 | 10 | 11 | 12 | A24 | 13 | 14 | 15 | 16 | [17 empty] | ITD25 | P25 | 17 | 18 | 19 | 20 | A25 | 21 | 22 | 23 | 24 | [21 empty] | ITD23 | P23 | 1 | 2 | 3 | 4 | A23 | 5 | 6 | 7 | 8 | [17 empty] | ITD24 | P24 | 9 | 10 | 11 | 12 | A24 | 13 | 14 | 15 | 16 | [17 empty] | ITD25 | P25 | 17 | 18 | 19 | 20 | A25 | 21 | 22 | 23 | 24 | [20 empty] | ITD23 | P23 | 1 | 2 | 3 | 4 | A23 | 5 | 6 | 7 | 8 | [17 empty] | ITD24 | P24 | 9 | 10 | 11 | 12 | A24 | 13 | 14 | 15 | 16 | [17 empty] | ITD25 | P25 | 17 | 18 | 19 | 20 | A25 | 21 | 22 | 23 | 24 | [20 empty] | ITD23 | P23 | 1 | 2 | 3 | 4 | A23 | 5 | 6 | 7 | 8 | [17 empty] | ITD24 | P24 | 9 | 10 | 11 | 12 | A24 | 13 | 14 | 15 | 16 | [17 empty] | ITD25 | P25 | 17 | 18 | 19 | 20 | A25 | 21 | 22 | 23 | 24
DESIGN |  | 13.3817 | 13.3817 | 0 | 13.3817 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 10.3005 | 10.3005 | 10.3005 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 2.4758 | 2.4758 | 2.4758 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.49075 | 0.49075 | 0.49075 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.11462 | 0.11462 | 0.11462 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Contract + Design Brief | 1.1445 | 1.1445 | 0 | 1.1445 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 1.1445 | 1.1445 | 1.1445 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Vision Statement
2 | Land - Topographical Survey with information as per defined standard,
3 | Zoning & Development Regulations
4 | Design Brief
2 | Schematic Concept | 3.0184 | 3.0184 | 0 | 3.0184 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10% | 2.289 | 2.289 | 2.289 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 10% |  | 0.61895 | 0.61895 | 0.61895 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 5% | 0.081791 | 0.081791 | 0.081791 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 10% | 0.028655 | 0.028655 | 0.028655 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Master Plan
2 | Blocks and Products
3 | Amenities & Facilities
4 | Design Basis
3 | Pre Construction Set | 3.7048 | 3.7048 | 0 | 3.7048 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10% | 2.289 | 2.289 | 2.289 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 20% |  | 1.2379 | 1.2379 | 1.2379 |  |  | 0 | 0 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 10% | 0.16358 | 0.16358 | 0.16358 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 5% | 0.014327 | 0.014327 | 0.014327 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Master Plan
2 | Blocks
3 | Products
4 | Amenities & Facilities
5 | Design Basis
4 | Approvals | 2.4956 | 2.4956 | 0 | 2.4956 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10% | 2.289 | 2.289 | 2.289 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 10% | 0.16358 | 0.16358 | 0.16358 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 15% | 0.042982 | 0.042982 | 0.042982 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Development Plan
2 | Building Plan
3 | Fire Safety
4 | Environment
5 | Water Supply and Sewerage
6 | Power Supply
7 | Airport Authority
5 | Experience Home + Project Experience | 1.8596 | 1.8596 | 0 | 1.8596 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 1.1445 | 1.1445 | 1.1445 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 10% |  | 0.61895 | 0.61895 | 0.61895 |  |  | 0 | 0 | 0 | 0 | 0 | [7 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 5% | 0.081791 | 0.081791 | 0.081791 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 5% | 0.014327 | 0.014327 | 0.014327 |  |  | 0 | 0 | 0 |  |  | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Project Entrance and Boundary wall
2 | Sales Centre and Experience Homes [Construction Docs]
3 | Tree Planting Plan
6 | Marketing and Sales | 1.1588 | 1.1588 | 0 | 1.1588 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 1.1445 | 1.1445 | 1.1445 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [8 empty] | 0 |  | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0% | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 5% | 0.014327 | 0.014327 | 0.014327 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [6 empty] | 0 | 0 | 0 | 0 | 0 | [9 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Masterplan
2 | Blocks
3 | Products
4 | Specifications
5 | Clubhouse Design with list of Amenities
6 | Renders, Walk-through and Scaled model
7 | Project Entrance and Boundary wall
8 | Sales Centre and Experience Homes [Construction Docs]
CONSTRUCTION DOCUMENTS |  | 16.0697 | 2.8069 | 13.2628 | 1.966 | 13.7056 | 6.5638 | 1.8125 | 1.6376 | 3.6917 | 0.35698 | 0 | 0.24096 | 0.0013219 | 0.11469 | 0 | 0.3982 | 0.3982 | 0 | 0 | 0 | 0.48394 | 0.48394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 11.445 | 1.2451 | 1.0041 | 10.4409 | 6.5414 | 1.754 | 0.0565 | 2.0889 | 0.24096 | 0 | 0.24096 | 0 | 0 |  |  |  |  | 0 | 792 | 69 | 723 | 399 | 73 | 96 | 155 | 1 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 792 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 3.4042 | 1.3024 | 0.90417 | 2.1019 | 0 | 0 | 1.0605 | 1.0414 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0% | 67 | 19 | 41 | 10 | 0 | 13 | 18 | 12 | 10 | 0 | 0 | 2 |  | 0.3982 | 0.3982 | 0 | 0 | 0 | 0.3982 | 0.3982 | 0 | 0 | 0 |  |  |  |  | 0 | 74 | 0 | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 74 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1.0633 | 0.25678 | 0.057015 | 1.0063 | 0 | 0 | 0.44748 | 0.55879 | 0.11403 | 0 | 0 | 0 | 0.11403 |  |  |  |  | 0 | 319 | 16 | 303 | 0 | 0 | 179 | 124 | 42 | 0 | 0 | 0 | 42 |  | 0 | 0 | 0 | 0 | 0 | 0.08574 | 0.08574 | 0 | 0 | 0 |  |  |  |  | 0 | 319 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 319 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.15722 | 0.0026438 | 0.00066095 | 0.15656 | 0.022342 | 0.058439 | 0.073131 | 0.0026438 | 0.0019828 | 0 | 0 | 0.0013219 | 0.00066095 |  |  |  |  | 0 | 88 | 10 | 78 | 33 | 7 | 4 | 34 | 24 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB01 | GFC ¦ Tower—08 | 7.3809 | 2.0032 | 5.3777 | 1.2783 | 5.7044 | 2.6506 | 1.6867 | 0.59826 | 0.76878 | 0.24096 | 0 | 0.24096 | 0 | 0 | 0 | 0.3982 | 0.3982 | 0 | 0 | 0 | 0.48394 | 0.48394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50% | 4.8193 | 0.72289 | 0.48193 | 4.3373 | 2.6506 | 1.6867 | 0 | 0 | 0.24096 | 0 | 0.24096 | 0 | 0 |  |  |  |  | 0 | 88 | 22 | 66 | 58 | 8 | 0 | 0 | 1 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 88 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% |  | 2.1901 | 1.1946 | 0.7964 | 0.99551 | 0 | 0 | 0.3982 | 0.5973 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0% | 57 | 18 | 32 | 10 | 0 | 7 | 15 | 12 | 10 | 0 | 0 | 2 |  | 0.3982 | 0.3982 | 0 | 0 | 0 | 0.3982 | 0.3982 | 0 | 0 | 0 |  |  |  |  | 0 | 57 | 0 | 7 | 7 | 0 | 0 | 0 | 7 | 7 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 57 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65% | 0.37154 | 0.08574 | 0 | 0.37154 | 0 | 0 | 0.20006 | 0.17148 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 71 | 0 | 71 | 0 | 0 | 51 | 20 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0.08574 | 0.08574 | 0 | 0 | 0 |  |  |  |  | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 71 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB01-1 | Foundation and Grade Slab | 0.96587 | 0.96587 | 0 | 0.88013 | 0.08574 | 0 | 0 | 0.08574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.08574 | 0.08574 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 0.48193 | 0.48193 | 0.48193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | 0% | 0% |  | 22 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% |  | 0.3982 | 0.3982 | 0.3982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | 0% | 0% |  | 14 | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0.08574 | 0.08574 | 0 | 0.08574 | 0 | 0 | 0.08574 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 8 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0.08574 | 0.08574 | 0 | 0 | 0 |  | 0 | 0 | 1 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 8 | 8 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB01-2 | Parking Level-Sub grade | 0.63916 | 0.24096 | 0.3982 | 0 | 0.63916 | 0.24096 | 0 | 0.3982 | 0 | 0.24096 | 0 | 0.24096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.5% | 0.24096 | 0.24096 | 0 | 0.24096 | 0.24096 | 0 | 0 | 0 | 0.24096 | 0 | 0.24096 | 0 | 0 |  | 0% | 100% | 100% |  | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 1 | 0 | 1 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% |  | 0.3982 | 0 | 0 | 0.3982 | 0 | 0 | 0.3982 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 70.59% |  | 17 | 0 | 17 | 10 | 0 | 7 | 0 | 12 | 10 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB01-3 | Building Envelope and Common Areas [Basement] | 0.48193 | 0 | 0.48193 | 0 | 0.48193 | 0.48193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 0.48193 | 0 | 0 | 0.48193 | 0.48193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 25 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB01-4 | Habitable Level 01 | 0.99445 | 0.3982 | 0.59625 | 0.3982 | 0.59625 | 0.48193 | 0 | 0.11432 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 0.48193 | 0 | 0 | 0.48193 | 0.48193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% |  | 0.3982 | 0.3982 | 0.3982 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | 0% | 0% |  | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0.11432 | 0 | 0 | 0.11432 | 0 | 0 | 0.11432 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 43 | 0 | 43 | 0 | 0 | 43 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 43 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB01-5 | Habitable Level - Even | 0.44006 | 0.1991 | 0.24096 | 0 | 0.24096 | 0.24096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1991 | 0.1991 | 0 | 0 | 0 | 0.1991 | 0.1991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.5% | 0.24096 | 0 | 0 | 0.24096 | 0.24096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% |  | 0.1991 | 0.1991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.1991 | 0.1991 | 0 | 0 | 0 | 0.1991 | 0.1991 | 0 | 0 | 0 |  | 0 | 1 | 1 |  | 4 | 0 | 4 | 4 | 0 | 0 | 0 | 4 | 4 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB01-6 | Habitable Level - Odd | 0.44006 | 0.1991 | 0.24096 | 0 | 0.24096 | 0.24096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0.1991 | 0.1991 | 0 | 0 | 0 | 0.1991 | 0.1991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.5% | 0.24096 | 0 | 0 | 0.24096 | 0.24096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 1 | 0 | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% |  | 0.1991 | 0.1991 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.1991 | 0.1991 | 0 | 0 | 0 | 0.1991 | 0.1991 | 0 | 0 | 0 |  | 0 | 1 | 1 |  | 3 | 0 | 3 | 3 | 0 | 0 | 0 | 3 | 3 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB01-7 | Building Envelope and Common Areas [Typical Tower Levels] | 0.96385 | 0 | 0.96385 | 0 | 0.96385 | 0.96385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10% | 0.96385 | 0 | 0 | 0.96385 | 0.96385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 21 | 0 | 21 | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 21 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB01-8 | Penthouse Levels | 0.76677 | 0 | 0.76677 | 0 | 0.76677 | 0 | 0.48193 | 0 | 0.28484 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 0.48193 | 0 | 0 | 0.48193 | 0 | 0.48193 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% |  | 0.1991 | 0 | 0 | 0.1991 | 0 | 0 | 0 | 0.1991 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 9 | 0 | 9 | 0 | 0 | 0 | 9 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0.08574 | 0 | 0 | 0.08574 | 0 | 0 | 0 | 0.08574 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 6 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB01-9 | Terrace Level | 0.7249 | 0 | 0.7249 | 0 | 0.7249 | 0 | 0.24096 | 0 | 0.48394 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 2.5% | 0.24096 | 0 | 0 | 0.24096 | 0 | 0.24096 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% |  | 0.3982 | 0 | 0 | 0.3982 | 0 | 0 | 0 | 0.3982 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 6 | 0 | 6 | 0 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0.08574 | 0 | 0 | 0.08574 | 0 | 0 | 0 | 0.08574 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 14 | 0 | 14 | 0 | 0 | 0 | 14 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 14 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB01-10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 0.96385 | 0 | 0.96385 | 0 | 0.96385 | 0 | 0.96385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10% | 0.96385 | 0 | 0 | 0.96385 | 0 | 0.96385 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB02 | GFC ¦ Independent Subgrade Structure - Tower 8 | 3.3021 | 0.10777 | 3.1944 | 0.10777 | 3.1944 | 2.045 | 0 | 0.7183 | 0.43106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50% | 2.045 | 0 | 0 | 2.045 | 2.045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 48 | 0 | 48 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 48 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% |  | 1.1854 | 0.10777 | 0.10777 | 1.0777 | 0 | 0 | 0.6466 | 0.43106 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0% | 10 | 1 | 9 | 0 | 0 | 6 | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65% | 0.071708 | 0 | 0 | 0.071708 | 0 | 0 | 0.071708 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 34 | 0 | 34 | 0 | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 34 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB02-1 | Earthwork | 0.10777 | 0.10777 | 0 | 0.10777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% |  | 0.10777 | 0.10777 | 0.10777 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | 0% | 0% |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB02-2 | Foundations & Grade Slab | 0.53883 | 0 | 0.53883 | 0 | 0.53883 | 0.2045 | 0 | 0.33433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 0.2045 | 0 | 0 | 0.2045 | 0.2045 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 16 | 0 | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15% |  | 0.3233 | 0 | 0 | 0.3233 | 0 | 0 | 0.3233 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 0.011032 | 0 | 0 | 0.011032 | 0 | 0 | 0.011032 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB02-3 | Parking level Subgrade | 0.74333 | 0 | 0.74333 | 0 | 0.74333 | 0.409 | 0 | 0.33433 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10% | 0.409 | 0 | 0 | 0.409 | 0.409 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 5 | 0 | 5 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15% |  | 0.3233 | 0 | 0 | 0.3233 | 0 | 0 | 0.3233 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 0.011032 | 0 | 0 | 0.011032 | 0 | 0 | 0.011032 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 19 | 0 | 19 | 0 | 0 | 19 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 19 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB02-4 | Podium Slab | 1.0721 | 0 | 1.0721 | 0 | 1.0721 | 0.6135 | 0 | 0.02758 | 0.43106 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15% | 0.6135 | 0 | 0 | 0.6135 | 0.6135 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 25 | 0 | 25 | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% |  | 0.43106 | 0 | 0 | 0.43106 | 0 | 0 | 0 | 0.43106 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0.02758 | 0 | 0 | 0.02758 | 0 | 0 | 0.02758 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 6 | 0 | 6 | 0 | 0 | 6 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 6 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
BB02-5 | Building Envelope and Common Areas | 0.84006 | 0 | 0.84006 | 0 | 0.84006 | 0.818 | 0 | 0.022064 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20% | 0.818 | 0 | 0 | 0.818 | 0.818 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 2 | 0 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0.022064 | 0 | 0 | 0.022064 | 0 | 0 | 0.022064 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 8 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
[48 empty] | 0 | 0 | 0 |  | 0 | [23 empty] | 0 | 0 | 0 |  | 0 | [23 empty] | 0 | 0 | 0 |  | 0 | [27 empty] | 0 | 0 | 0 |  | 0 | [23 empty] | 0 | 0 | 0 |  | 0 | [23 empty] | 0 | 0 | 0 |  | 0 | [26 empty] | 0 | 0 | 0 |  | 0 | [23 empty] | 0 | 0 | 0 |  | 0 | [23 empty] | 0 | 0 | 0 |  | 0 | [26 empty] | 0 | 0 | 0 |  | 0 | [23 empty] | 0 | 0 | 0 |  | 0 | [23 empty] | 0 | 0 | 0 |  | 0
PD | GFC ¦ Individual Homes | 4.6392 | 0.69591 | 3.9432 | 0.57989 | 4.0593 | 1.5686 | 0 | 0.17104 | 2.3196 | 0.11601 | 0 | 0 | 0.0013219 | 0.11469 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50% | 4.1778 | 0.52222 | 0.52222 | 3.6555 | 1.5667 | 0 | 0 | 2.0889 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 310 | 47 | 263 | 108 | 0 | 0 | 155 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 310 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65% | 0.45612 | 0.17104 | 0.057015 | 0.3991 | 0 | 0 | 0.17104 | 0.22806 | 0.11403 | 0 | 0 | 0 | 0.11403 | [5 empty] | 183 | 16 | 167 | 0 | 0 | 75 | 92 | 42 | 0 | 0 | 0 | 42 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 183 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0.0052876 | 0.0026438 | 0.00066095 | 0.0046266 | 0.0019828 | 0 | 0 | 0.0026438 | 0.0019828 | 0 | 0 | 0.0013219 | 0.00066095 | [5 empty] | 68 | 10 | 58 | 24 | 0 | 0 | 34 | 24 | 0 | 0 | 16 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 68 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R25-1 | R25 Default and it's variants | 0.57989 | 0.57989 | 0 | 0.57989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6.25% | 0.52222 | 0.52222 | 0.52222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 100% | 0% | 0% |  | 47 | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.125% | 0.057015 | 0.057015 | 0.057015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 16 | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 16 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.875% | 0.00066095 | 0.00066095 | 0.00066095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 1 | 0 | 0 |  | 10 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L20-1 | L20 Default and it's variants | 0.57989 | 0.00066095 | 0.57923 | 0 | 0.57989 | 0.52288 | 0 | 0.057015 | 0 | 0.00066095 | 0 | 0 | 0.00066095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6.25% | 0.52222 | 0 | 0 | 0.52222 | 0.52222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 36 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.125% | 0.057015 | 0 | 0 | 0.057015 | 0 | 0 | 0.057015 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 25 | 0 | 25 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.875% | 0.00066095 | 0.00066095 | 0 | 0.00066095 | 0.00066095 | 0 | 0 | 0 | 0.00066095 | 0 | 0 | 0.00066095 | 0 |  | 0 | 1 | 1 |  | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D35-1 | D35 Default and it's variants | 0.57989 | 0.00066095 | 0.57923 | 0 | 0.57989 | 0.52288 | 0 | 0.057015 | 0 | 0.00066095 | 0 | 0 | 0.00066095 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6.25% | 0.52222 | 0 | 0 | 0.52222 | 0.52222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 36 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.125% | 0.057015 | 0 | 0 | 0.057015 | 0 | 0 | 0.057015 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0.074074 |  | 27 | 0 | 27 | 0 | 0 | 27 | 0 | 2 | 0 | 0 | 0 | 2 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.875% | 0.00066095 | 0.00066095 | 0 | 0.00066095 | 0.00066095 | 0 | 0 | 0 | 0.00066095 | 0 | 0 | 0.00066095 | 0 |  | 0 | 1 | 1 |  | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L22-1 | L22 Default and it's variants | 0.57989 | 0.057676 | 0.52222 | 0 | 0.57989 | 0.52288 | 0 | 0.057015 | 0 | 0.057676 | 0 | 0 | 0 | 0.057676 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6.25% | 0.52222 | 0 | 0 | 0.52222 | 0.52222 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 36 | 0 | 36 | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.125% | 0.057015 | 0.057015 | 0 | 0.057015 | 0 | 0 | 0.057015 | 0 | 0.057015 | 0 | 0 | 0 | 0.057015 |  | 0 | 1 | 1 |  | 23 | 0 | 23 | 0 | 0 | 23 | 0 | 23 | 0 | 0 | 0 | 23 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 23 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.875% | 0.00066095 | 0.00066095 | 0 | 0.00066095 | 0.00066095 | 0 | 0 | 0 | 0.00066095 | 0 | 0 | 0 | 0.00066095 |  | 0 | 1 | 1 |  | 8 | 0 | 8 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
R25P-1 | R25 P Default and it's variants | 0.57989 | 0.057015 | 0.52288 | 0 | 0.57989 | 0 | 0 | 0 | 0.57989 | 0.057015 | 0 | 0 | 0 | 0.057015 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6.25% | 0.52222 | 0 | 0 | 0.52222 | 0 | 0 | 0 | 0.52222 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 47 | 0 | 47 | 0 | 0 | 0 | 47 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 47 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.125% | 0.057015 | 0.057015 | 0 | 0.057015 | 0 | 0 | 0 | 0.057015 | 0.057015 | 0 | 0 | 0 | 0.057015 |  | 0 | 1 | 1 |  | 17 | 0 | 17 | 0 | 0 | 0 | 17 | 17 | 0 | 0 | 0 | 17 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 17 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.875% | 0.00066095 | 0 | 0 | 0.00066095 | 0 | 0 | 0 | 0.00066095 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 10 | 0 | 10 | 0 | 0 | 0 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L20P-1 | L20 P Default and it's variants | 0.57989 | 0 | 0.57989 | 0 | 0.57989 | 0 | 0 | 0 | 0.57989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6.25% | 0.52222 | 0 | 0 | 0.52222 | 0 | 0 | 0 | 0.52222 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 36 | 0 | 36 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.125% | 0.057015 | 0 | 0 | 0.057015 | 0 | 0 | 0 | 0.057015 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 25 | 0 | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.875% | 0.00066095 | 0 | 0 | 0.00066095 | 0 | 0 | 0 | 0.00066095 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
D35P-1 | D35 P Default and it's variants | 0.57989 | 0 | 0.57989 | 0 | 0.57989 | 0 | 0 | 0 | 0.57989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6.25% | 0.52222 | 0 | 0 | 0.52222 | 0 | 0 | 0 | 0.52222 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 36 | 0 | 36 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.125% | 0.057015 | 0 | 0 | 0.057015 | 0 | 0 | 0 | 0.057015 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 25 | 0 | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.875% | 0.00066095 | 0 | 0 | 0.00066095 | 0 | 0 | 0 | 0.00066095 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
L22P-1 | L22 P Default and it's variants | 0.57989 | 0 | 0.57989 | 0 | 0.57989 | 0 | 0 | 0 | 0.57989 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 6.25% | 0.52222 | 0 | 0 | 0.52222 | 0 | 0 | 0 | 0.52222 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 36 | 0 | 36 | 0 | 0 | 0 | 36 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 36 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 8.125% | 0.057015 | 0 | 0 | 0.057015 | 0 | 0 | 0 | 0.057015 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 25 | 0 | 25 | 0 | 0 | 0 | 25 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 25 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 6.875% | 0.00066095 | 0 | 0 | 0.00066095 | 0 | 0 | 0 | 0.00066095 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 8 | 0 | 8 | 0 | 0 | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MP | GFC ¦ Master Plan | 0.58136 | 0 | 0.58136 | 0 | 0.58136 | 0.29956 | 0.0349 | 0.074991 | 0.17191 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50% | 0.349 | 0 | 0 | 0.349 | 0.2792 | 0.0349 | 0.0349 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 167 | 0 | 167 | 158 | 2 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 167 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% |  | 0.02871 | 0 | 0 | 0.02871 | 0 | 0 | 0.01566 | 0.01305 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0% | 7 | 0 | 7 | 0 | 0 | 4 | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65% | 0.15886 | 0 | 0 | 0.15886 | 0 | 0 | 0 | 0.15886 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 22 | 0 | 22 | 0 | 0 | 11 | 11 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 22 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0.044791 | 0 | 0 | 0.044791 | 0.02036 | 0 | 0.024431 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 12 | 0 | 12 | 9 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 12 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MP-1 | Master Plan | 0.23152 | 0 | 0.23152 | 0 | 0.23152 | 0.19486 | 0 | 0 | 0.03666 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 25% | 0.1745 | 0 | 0 | 0.1745 | 0.1745 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 60 | 0 | 60 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15% | 0.03666 | 0 | 0 | 0.03666 | 0 | 0 | 0 | 0.03666 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 13 | 0 | 13 | 0 | 0 | 10 | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 13 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0.02036 | 0 | 0 | 0.02036 | 0.02036 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 9 | 0 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MP-2 | Site Development | 0.12036 | 0 | 0.12036 | 0 | 0.12036 | 0.1047 | 0 | 0.01566 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15% | 0.1047 | 0 | 0 | 0.1047 | 0.1047 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 98 | 0 | 98 | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 98 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% |  | 0.01566 | 0 | 0 | 0.01566 | 0 | 0 | 0.01566 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 4 | 0 | 4 | 0 | 0 | 4 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MP-3 | Site MEP | 0.17015 | 0 | 0.17015 | 0 | 0.17015 | 0 | 0.0349 | 0 | 0.13525 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 0.0349 | 0 | 0 | 0.0349 | 0 | 0.0349 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% |  | 0.01305 | 0 | 0 | 0.01305 | 0 | 0 | 0 | 0.01305 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 3 | 0 | 3 | 0 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0.1222 | 0 | 0 | 0.1222 | 0 | 0 | 0 | 0.1222 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 9 | 0 | 9 | 0 | 0 | 1 | 8 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
MP-4 | Landscaping | 0.059331 | 0 | 0.059331 | 0 | 0.059331 | 0 | 0 | 0.059331 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 0.0349 | 0 | 0 | 0.0349 | 0 | 0 | 0.0349 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 7 | 0 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30% | 0.024431 | 0 | 0 | 0.024431 | 0 | 0 | 0.024431 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 3 | 0 | 3 | 0 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AM | GFC ¦ Amenities & Facilities | 0.1662 | 0 | 0.1662 | 0 | 0.1662 | 0 | 0.090839 | 0.074968 | 0.000389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 50% | 0.054 | 0 | 0 | 0.054 | 0 | 0.0324 | 0.0216 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 179 | 0 | 179 | 27 | 63 | 89 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 179 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 65% | 0.005057 | 0 | 0 | 0.005057 | 0 | 0 | 0.004668 | 0.000389 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 9 | 0 | 9 | 0 | 0 | 8 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 9 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 55% | 0.10714 | 0 | 0 | 0.10714 | 0 | 0.058439 | 0.0487 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 8 | 0 | 7 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 8 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AM-1 | Clubhouse—Structure and Envelope | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 27 | 0 | 27 | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 27 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | ` |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AM-2 | Clubhouse—Interiors and Facilities | 0.04497 | 0 | 0.04497 | 0 | 0.04497 | 0 | 0.04108 | 0.00389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 20% | 0.0216 | 0 | 0 | 0.0216 | 0 | 0.0216 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 60 | 0 | 60 | 0 | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 60 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50% | 0.00389 | 0 | 0 | 0.00389 | 0 | 0 | 0.00389 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 7 | 0 | 7 | 0 | 0 | 7 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 7 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 0.01948 | 0 | 0 | 0.01948 | 0 | 0.01948 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 5 | 0 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 5 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AM-3 | Clubhouse—Outdoor Spaces and Pool | 0.050538 | 0 | 0.050538 | 0 | 0.050538 | 0 | 0.04976 | 0.000778 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10% | 0.0108 | 0 | 0 | 0.0108 | 0 | 0.0108 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 3 | 0 | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10% | 0.000778 | 0 | 0 | 0.000778 | 0 | 0 | 0.000778 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20% | 0.03896 | 0 | 0 | 0.03896 | 0 | 0.03896 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 2 | 0 | 2 | 0 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AM-4 | Community spaces [Board Walk, Children play area] | 0.0595 | 0 | 0.0595 | 0 | 0.0595 | 0 | 0 | 0.0595 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10% | 0.0108 | 0 | 0 | 0.0108 | 0 | 0 | 0.0108 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 52 | 0 | 52 | 0 | 0 | 52 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 52 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 25% | 0.0487 | 0 | 0 | 0.0487 | 0 | 0 | 0.0487 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 1 | 0 | 1 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
AM-5 | Sporting Facilities | 0.011189 | 0 | 0.011189 | 0 | 0.011189 | 0 | 0 | 0.0108 | 0.000389 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 10% | 0.0108 | 0 | 0 | 0.0108 | 0 | 0 | 0.0108 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 100% | 0% |  | 37 | 0 | 37 | 0 | 0 | 37 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 37 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 0.000389 | 0 | 0 | 0.000389 | 0 | 0 | 0 | 0.000389 | 0 | 0 | 0 | 0 | 0 |  | 0 | 1 | 0 |  | 1 | 0 | 1 | 0 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
POST-CONSTRUCTION |  | 1.5501 | 0 | 1.5501 | 0 | 1.5501 | 0 | 0 | 0 | 1.5501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 1.1445 | 0 | 0 | 1.1445 | 0 | 0 | 0 | 1.1445 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  | 0.30948 | 0 | 0 | 0.30948 | 0 | 0 | 0 | 0.30948 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.081791 | 0 | 0 | 0.081791 | 0 | 0 | 0 | 0.081791 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0.014327 | 0 | 0 | 0.014327 | 0 | 0 | 0 | 0.014327 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Archives | 1.5501 | 0 | 1.5501 | 0 | 1.5501 | 0 | 0 | 0 | 1.5501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 1.1445 | 0 | 0 | 1.1445 | 0 | 0 | 0 | 1.1445 | 0 | 0 | 0 | 0 | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% |  | 0.30948 | 0 | 0 | 0.30948 | 0 | 0 | 0 | 0.30948 | 0 | 0 | 0 | 0 | 0 |  | 0% | 0% | 0% |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 0.081791 | 0 | 0 | 0.081791 | 0 | 0 | 0 | 0.081791 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5% | 0.014327 | 0 | 0 | 0.014327 | 0 | 0 | 0 | 0.014327 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Complete set of "As-Built" drawings, final BoQ and project costs, | 1.5501 | 0 | 1.5501 | 0 | 1.5501 | 0 | 0 | 0 | 1.5501 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 5% | 1.1445 |  |  | 1.1445 |  |  |  | 1.1445 | [78 empty] | 5% |  | 0.30948 |  |  | 0.30948 |  |  |  | 0.30948 | [78 empty] | 5% | 0.081791 |  |  | 0.081791 |  |  |  | 0.081791 | [78 empty] | 5% | 0.014327 |  |  | 0.014327 |  |  |  | 0.014327

## AR ¦ Drawing List
[8 empty] | ITD23 |  | P23 | 1 | 2 | 3 | 4 | A23 | 5 | 6 | 7 | 8 | ITD24 |  | P24 | 9 | 10 | 11 | 12 | A24 | 13 | 14 | 15 | 16 | ITD25 |  | P25 | 17 | 18 | 19 | 20 | A25 | 21 | 22 | 23 | 24
0059 ¦ Pursuit of a Radical Rhapsody |  |  |  |  | Location | Batch Code | Batch | Issued till Dec 23 | Revision | Plan in FY 24 | 399 | 73 | 96 | 155 | Issued in FY 24 | 0 | 1 | 0 | 0 | Issued till Dec 24 | Revision | Plan in FY 25 | 0 | 0 | 0 | 0 | Issued in FY 25 | 0 | 0 | 0 | 0 | Issued till Dec 25 | Revision | Plan in FY 26 | 0 | 0 | 0 | 0 | Issued in FY 26 | 0 | 0 | 0 | 0
AR ¦ DRAWING LIST | [10 empty] | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  |  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  |  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Reference Batch
Independent Subgrade Structure [Tower 8] |  |  |  |  | Location | Batch Code | Batch | [36 empty] | Batch
GENERAL
| A | BA1 | 0000 | COVER SHEET | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | BA1 | 0001 | ABBREVIATIONS AND SYMBOLS | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | BA1 | 0002 | GA - KEY PLAN | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
BASEMENT DRAWINGS
| A | BA1 | 1001 | OVERALL BASEMENT GA PLAN & SECTIONS | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
ELECTRICAL PLANS
| A | BA1 | 1401 | T08 BASEMENT ELECTRICAL LAYOUT | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | BA1 | 1431 | ELECTRICAL – SSL 01 - PODIUM | BB02 | BB02-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
REFLECTED CEILING PLANS
| A | BA1 | 1501 | RCP - GRADE SLAB - BASEMENT | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | BA1 | 1531 | RCP – SSL 01 - STILT | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
DRAINAGE PLANS - 16XX
| A | BA1 | 1601 | DRAINAGE PLAN – GRADE SLAB | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | BA1 | 1601 | DRAINAGE PLAN - SSL 01 - STILT | BB02 | BB02-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
PART PLANS - 41XX
| A | BA1 | 4101 | DRIVERS & MAIDS LOUNGE | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | BA1 | 4102 | GARBAGE ROOMS | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | BA1 | 4103 | COMMUNICATION ROOMS | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | BA1 | 4104 | IBMS ROOM | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | BA1 | 4105 | UGT 1 DETAILS | BB02 | BB02-5 | 5 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | BA1 | 4106 | STP 1 DETAILS | BB02 | BB02-5 | 5 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
PART SECTION - 43XX
| A | BA1 | 4301 | PART SECTION 1 | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | BA1 | 4302 | PART SECTION 2 | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | BA1 | 4303 | PART SECTION 3 | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
GENERAL ARRANGEMENT ELEVATIONS - 20XX
| A | C01 | 2001 | GENERAL ELEVATION 1 | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | C01 | 2002 | GENERAL ELEVATION 2 | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | C01 | 2003 | GENERAL ELEVATION 3 | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT SECTIONS - 30XX
| A | C01 | 3001 | GENERAL SECTION 1 | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | C01 | 3002 | GENERAL SECTION 2 | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT PLANS - 10XX
| A | T9B | 1001 | FLOOR PLAN - BASEMENT 3 | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | T9B | 1002 | FLOOR PLAN - BASEMENT 2 | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | T9B | 1003 | FLOOR PLAN – BASEMENT 1 | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
STAIRCASE DETAILS - 46XX
| A | T9B | 4601 | STAIRCASE 1 - BASEMENT 3 TO BASEMENT 1 | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | T9B | 4602 | STAIRCASE 1 - BASEMENT 1 TO LEVEL 1 | BB02 | BB02-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
MASONRY PLANS - 11XX
| A | T9B | 1101 | MASONRY SETOUT PLAN - BASEMENT 3 | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 1102 | MASONRY SETOUT PLAN - BASEMENT 2 | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 1103 | MASONRY SETOUT PLAN - BASEMENT 1 | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
FLOORING & DRAINAGE PLANS - 13XX
| A | T9B | 1301 | FLOORING AND DRAINAGE PLAN - BASEMENT 3 | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 1302 | FLOORING AND DRAINAGE PLAN - BASEMENT 2 | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 1303 | FLOORING AND DRAINAGE PLAN - BASEMENT 1 | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
ELECTRICAL & REFLECTED CEILING PLANS - 14XX
| A | T9B | 1401 | ELECTRICAL PLAN - BASEMENT 3 | BB02 | BB02-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T9B | 1402 | ELECTRICAL PLAN - BASEMENT 2 | BB02 | BB02-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T9B | 1403 | ELECTRICAL PLAN - BASEMENT 1 | BB02 | BB02-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
DETAILED INTERIOR PLANS - 40XX
| A | T9B | 4001 | INTERIOR PLAN - STAFF AREAS - BASEMENTS | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
PART PLANS - 41XX
| A | T9B | 4101 | FLOOR PLAN- BASEMENT 3 - PART A | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 4102 | FLOOR PLAN- BASEMENT 3 - PART B | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 4103 | FLOOR PLAN- BASEMENT 3 - PART C | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 4106 | FLOOR PLAN- BASEMENT 2 - PART A | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 4107 | FLOOR PLAN- BASEMENT 2 - PART B | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 4108 | FLOOR PLAN- BASEMENT 2 - PART C | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 4111 | FLOOR PLAN- BASEMENT 1 - PART A | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 4112 | FLOOR PLAN- BASEMENT 1 - PART B | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T9B | 4113 | FLOOR PLAN- BASEMENT 1 - PART C | BB02 | BB02-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
Tower—08 | [43 empty] | Batch
GENERAL - 0000
| A | T8 | 0000 | COVER SHEET | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 0001 | ABBREVIATIONS AND SYMBOLS | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
SETTING OUT PLANS
| A | T8 | 0101 | SETTING OUT PLAN - RAFT | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 0102 | LOWER BASEMENT SETTING OUT PLAN | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 0103 | LEVEL 1 SETTING OUT PLAN | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
GENERAL ARRANGEMENT PLANS - 10XX
| A | T8B | 1031 | GRADE SLAB – BASEMENT LEVEL PLAN | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 1001 | SSL 01 - LEVEL 1 PLAN | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 1002 | SSL 02 - TYPICAL EVEN LEVEL PLAN | BB01 | BB01-2 | 2 | 0 |  | 1 | 1 |  |  |  | 1 |  | 1 | [26 empty] | 1
| A | T8 | 1003 | SSL 03 - LEVEL 3 PLAN | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 1004 | SSL04 - LEVEL 4 PLAN | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 1005 | TYPICAL ODD LEVEL PLAN | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 1027 | SSL 27 - LEVEL 27 PLAN - PENTHOUSE LOWER LEVEL | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 1028 | SSL 28 - LEVEL 28 PLAN - PENTHOUSE/OHT UPPER LEVEL | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 1029 | SSL 29 - LEVEL 29 PLAN - TERRACE LEVEL | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 1030 | SSL 30 - TERRACE PLAN | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
MASONRY PLANS - 11XX
| A | T8 | 1100 | MASONRY WALL LEGEND | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8B | 1101 | MASONRY SETOUT PLAN – GRADE SLAB – BASEMENT | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8B | 1102 | MASONRY SECTIONS - BASEMENT LEVEL | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 1101 | MASONRY SETOUT PLAN – SSL 1 – LEVEL 1 | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 1102 | MASONRY SETOUT PLAN - TYPICAL EVEN LEVEL | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 1103 | MASONRY SETOUT PLAN - TYPICAL ODD LEVEL | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 1104 | MASONRY SETOUT PLAN – SSL 27 – LEVEL 27 - PENTHOUSE LOWER LEVEL | BB01 | BB01-8 | 8 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 8
| A | T8 | 1105 | MASONRY SETOUT PLAN – SSL 28 – LEVEL 28 - OHT & PENTHOUSE UPPER LEVEL | BB01 | BB01-8 | 8 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 8
FLOORING PLANS - 13XX
| A | T8B | 1301 | FLOORING PLAN – SSL 0 – BASEMENT | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 1301 | FLOORING PLAN – SSL 1 – LEVEL 1 | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
ELECTRICAL PLANS - 14XX
| A | T8 | 1400 | TOWER 1 ELECTRICAL SCHEDULE | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 1401 | ELECTRICAL LAYOUT - LEVEL 1 RCP | BB01 | BB01-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | T8 | 1402 | ELECTRICAL LAYOUT - TYP. EVEN LEVEL RCP | BB01 | BB01-5 | 5 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T8 | 1403 | ELECTRICAL LAYOUT - TYP. ODD LEVEL RCP | BB01 | BB01-6 | 6 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 6
| A | T8 | 1404 | ELECTRICAL LAYOUT - 1031 & 1041 RCP | BB01 | BB01-5 | 5 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 5
| A | T8 | 1405 | ELECTRICAL CEILING PLAN – SSL 28 – OHT & PENTHOUSE UPPER LEVEL | BB01 | BB01-8 | 8 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 8
DRAINAGE PLANS - 16XX
| A | T8 | 1601 | DRAINAGE PLAN - SSL 1 - LEVEL 1 | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 2
| A | T8 | 1602 | DRAINAGE PLAN - SSL 28 - LEVEL 28 | BB01 | BB01-9 | 9 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 9
GENERAL ARRANGEMENT ELEVATIONS - 20XX
| A | T8 | 2001 | BLOCK ELEVATIONS-1 | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 2002 | BLOCK ELEVATIONS-2 | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
GENERAL ARRANGEMENT SECTIONS - 30XX
| A | T8 | 3001 | BLOCK SECTIONS | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 3002 | BLOCK SECTIONS | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
DETAILED INTERIOR PLANS - 40XX
| A | T8B | 4001 | PLANS - LIFT LOBBY & SERVICE CORE – GRADE SLAB & SSL 1 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4002 | PLANS - LIFT LOBBY AND SERVICE CORE – SSL 2-27 - TYPICAL ODD & EVEN LEVELS | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 4003 | PLANS - LIFT LOBBY & SERVICE CORE - SSL 28- PENTHOUSE UL & OHT | BB01 | BB01-10 | 10 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 10
PART PLANS - 41XX
| A | T8 | 4101 | LIFT LOBBY DETAILS | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
DETAILED SECTIONS / PART SECTIONS - 43XX
| A | T8B | 4301 | SSL 0 - BASEMENT SLAB SECTIONS | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4302 | SSL 01 - LEVEL 1 SLAB SECTIONS | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 4303 | SSL 01 - LEVEL 1 DETAILED SLAB SECTIONS | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 4304 | SSL 02 & 03 - DETAILED SLAB SECTIONS | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
EXTERNAL BUILDING ENEVELOPE - 44XX
| A | T8 | 4400 | KEY PLAN - WALL SECTIONS (EXTERNAL) | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 4401 | WALL SECTION-A SHEAR WALL & WIRE-CUT BRICK DETAILS (1/3) | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 4402 | WALL SECTION-A SHEAR WALL & WIRE-CUT BRICK DETAILS (2/3) | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 4403 | WALL SECTION-A SHEAR WALL & WIRE-CUT BRICK DETAILS (3/3) | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 4411 | DETAILS OF PERGOLAS CONNECTING BLOCKS 1 AND 2 | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 4413 | DETAILS OF CHAJJA FOR PENTHOUSE UNITS | BB01 | BB01-10 | 10 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 10
STAIRCASE DETAILS - 46XX
| A | T8 | 4601 | STAIRCASE DETAILS - TYPE A,B,C,D & E(TYPICAL) - 1/3 | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 4602 | STAIRCASE DETAILS - TYPE A,B,C,D & E(TYPICAL) - 2/3 | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | T8 | 4603 | STAIRCASE DETAILS - TYPE A,B,C,D & E(TYPICAL) - 3/3 | BB01 | BB01-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
DOOR AND WINDOW DETAILS - 47XX
| A | T8 | 4701 | DOOR DETAIL - D1 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4702 | DOOR DETAIL - D2 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4703 | DOOR DETAIL - D3 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4704 | DOOR WINDOW DETAIL - DW1 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4705 | DOOR WINDOW DETAIL - DW2 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4706 | WINDOW DETAIL - W2 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4707 | WINDOW DETAIL - W3 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4708 | WINDOW DETAIL - W8 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4709 | WINDOW DETAIL - W2-6N-TH | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4710 | WINDOW DETAIL - W10 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4711 | WINDOW DETAIL - W11 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4712 | FRENCH WINDOW DETAIL - FW1 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4713 | FRENCH WINDOW DETAIL - FW2 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4714 | FRENCH WINDOW DETAIL - FW3/1 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4715 | FRENCH WINDOW DETAIL - FW3/2 | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4716 | UTILITY SHAFT - COVER | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4731 | COMMON AREA DOOR DRAWINGS | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
| A | T8 | 4732 | SERVICE DOORS | BB01 | BB01-3 | 3 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 3
FLOORING DETAILS - 59XX
| A | T8 | 5901 | FLOORING DETAILS - LOBBIES, BASEMENT, STAIRS | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
CEILING DETAILS - 60XX
| A | T8 | 6001 | CEILING DETAILS - LOBBIES, BASEMENT | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
TERRACE GARDEN DETAILS - 62XX
| A | T8 | 6201 | TERRACE GARDEN - DETAILS - 1 OF 3 | BB01 | BB01-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | T8 | 6202 | TERRACE GARDEN - DETAILS - 2 OF 3 | BB01 | BB01-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | T8 | 6203 | TERRACE GARDEN - DETAILS - 3 OF 3 | BB01 | BB01-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | T8 | 6204 | TERRACE GARDEN - DETAILS - LEVEL 1 | BB01 | BB01-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | T8 | 6205 | GUEST BEDROOM BALCONY DETAILS | BB01 | BB01-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | T8 | 6206 | SERVICE PLATFORM DETAILS | BB01 | BB01-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
| A | T8 | 6207 | TERRACE GARDEN SHAFT RAILINGS | BB01 | BB01-4 | 4 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 4
TERRACE / SKYWALK DETAILS - 63XX
| A | T8 | 6300 | TERRACE/SKYWALK LEVEL PERGOLA DETAIL | BB01 | BB01-9 | 9 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 9
| A | T8 | 6502 | CONNECTING BRIDGE DETAILS | BB01 | BB01-9 | 9 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 9
SPECIFICATIONS / SCHEDULES - 7XXX
| A | T8 | 7100 | DOORS AND WINDOWS SCHEDULE | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 7200 | FINISHES SCHEDULE | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 7300 | PLUMBING AND SANITARY SCHEDULE | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 7400 | SWITCHBOARD SCHEDULE | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
| A | T8 | 7450 | LUMINAIRE SCHEDULE | BB01 | BB01-7 | 7 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 7
Individual Homes
DEFAULT UNIT SET - R25
UNIT PLANS
| A | R25 | 1001 | INTERIOR PLAN | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 1101 | MASONRY SET- OUT PLAN | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 1301 | FLOORING PLANS | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 1401 | ELECTRICAL PLANS - 3.6M HEIGHT (C25G AS WELL) | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 1405 | ELECTRICAL PLANS - 3.0M HEIGHT | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 1501 | REFLECTED CELING PLANS- 3.6M HEIGHT | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 1502 | REFLECTED CELING PLANS - 3.0M HEIGHT | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 1601 | VACUUM LAYOUT PLANS | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
DETAILED SECTIONS - 43XX
| A | R25 | 4330 | UNIT SECTIONS C25A (ODD LEVEL) | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4331 | UNIT SECTIONS C25A (ODD LEVEL) | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
DOOR WINDOW DRAWINGS
| A | R25 | 4701 | DOOR AND WINDOW DETAILS – 1 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4702 | DOOR AND WINDOW DETAILS – 2 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4703 | DOOR AND WINDOW DETAILS – 3 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4704 | DOOR AND WINDOW DETAILS – 4 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4705 | DOOR AND WINDOW DETAILS – 5 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4706 | DOOR AND WINDOW DETAILS – 6 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4707 | DOOR AND WINDOW DETAILS – 7 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4708 | DOOR AND WINDOW DETAILS – 8 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4709 | DOOR AND WINDOW DETAILS – 9 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4710 | DOOR AND WINDOW DETAILS – 10 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4711 | DOOR AND WINDOW DETAILS – 11 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4712 | DOOR AND WINDOW DETAILS – 12 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 4713 | DOOR AND WINDOW DETAILS – 13 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
KITCHEN DETAILS - 54XX
| A | R25 | 5401 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS - PLAN | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 5402 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 1 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 5403 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 2 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 5404 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 3 | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
BATHROOM DETAILS - 55XX
| A | R25 | 5501 | DETAILS - TYP. MASTER BATHROOM - 3.6M HEIGHT | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 5502 | DETAILS - TYP. MASTER BATHROOM - 3.0M HEIGHT | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 5503 | DETAILS - TYP. CHILDREN'S BATHROOM - 3.6M HEIGHT | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 5504 | DETAILS - TYP. CHILDREN'S BATHROOM - 3.0M HEIGHT | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 5505 | DETAILS - TYP. GUEST BATHROOM - 3.6M HEIGHT | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 5506 | DETAILS - TYP. GUEST BATHROOM - 3.0M HEIGHT | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
SPECIFICATIONS / SCHEDULES - 7XXX
| A | R25 | 7410 | CLIENT EXCEPTIONS | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7420 | DOORS AND WINDOWS SCHEDULE | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7430 | FINISHES SCHEDULE | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7440 | PLUMBING AND SANITARY SCHEDULE | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7450 | CABINETRY SCHEDULE | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7461 | KITCHEN SPECIFICATION | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7462 | PANTRY SPECIFICATION | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7463 | BAR UNIT SPECIFICATION | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7470 | SWITCHBOARD SCHEDULE | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7480 | SERVICES SUMMARY | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7490 | SERVICES DETAILS : Home Automation | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7500 | LUMINAIRE SCHEDULE | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7510 | GENERAL SELECTIONS | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| A | R25 | 7520 | FURNITURE, FIXTURES AND EQUIPMENTS SCHEDULE | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
DEFAULT UNIT SET - L20
UNIT PLANS
| A | L20 | 1001 | INTERIOR PLAN | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 1101 | MASONRY SET- OUT PLAN | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 1301 | FLOORING PLANS | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 1401 | ELECTRICAL PLANS - L20 ag | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 1402 | ELECTRICAL PLANS - L20 a & b | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 1501 | REFLECTED CELING PLANS L20ag | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 1502 | REFLECTED CELING PLANS L20 a & b | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 1601 | VACUUM LAYOUT PLANS | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 1701 | CHANNEL MUSIC ? | [5 empty] | 0 |  |  |  |  | 0
DETAILED SECTIONS - 43XX
| A | L20 | 4330 | UNIT SECTIONS C25A (ODD LEVEL) | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 4331 | UNIT SECTIONS C25A (ODD LEVEL) | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
DOOR WINDOW DRAWINGS
| A | L20 | 4701 | DOOR AND WINDOW DETAILS – 1 | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 4702 | DOOR AND WINDOW DETAILS – 2 | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 4703 | DOOR AND WINDOW DETAILS – 3 | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 4704 | DOOR AND WINDOW DETAILS – 4 | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
KITCHEN DETAILS - 54XX
| A | L20 | 5401 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS - PLAN | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 5402 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 1 | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 5403 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 2 | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 5404 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 3 | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
BATHROOM DETAILS - 55XX
| A | L20 | 5501 | DETAILS - TYP. MASTER BATHROOM | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 5503 | DETAILS - TYP. CHILDREN'S BATHROOM | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 5505 | DETAILS - TYP. GUEST BATHROOM | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 5505 | DETAILS - MAIDS TOILET | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
SPECIFICATIONS / SCHEDULES - 7XXX
| A | L20 | 7410 | CLIENT EXCEPTIONS | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7420 | DOORS AND WINDOWS SCHEDULE | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7430 | FINISHES SCHEDULE | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7440 | PLUMBING AND SANITARY SCHEDULE | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7450 | CABINETRY SCHEDULE | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7461 | KITCHEN SPECIFICATION | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7462 | PANTRY SPECIFICATION | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7463 | BAR UNIT SPECIFICATION | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7470 | SWITCHBOARD SCHEDULE | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7480 | SERVICES SUMMARY | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7490 | SERVICES DETAILS : Home Automation | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7500 | LUMINAIRE SCHEDULE | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7510 | GENERAL SELECTIONS | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L20 | 7520 | FURNITURE, FIXTURES AND EQUIPMENTS SCHEDULE | L20 | L20-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
DEFAULT UNIT SET - D35
UNIT PLANS
| A | D35 | 1001 | INTERIOR PLAN | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 1101 | MASONRY SET- OUT PLAN | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 1301 | FLOORING PLANS | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 1401 | ELECTRICAL PLANS - D35 ag | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 1402 | ELECTRICAL PLANS - D35 a & b | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 1501 | REFLECTED CELING PLANS D35ag | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 1502 | REFLECTED CELING PLANS D35 a & b | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 1601 | VACUUM LAYOUT PLANS | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 1701 | CHANNEL MUSIC ? | [5 empty] | 0 |  |  |  |  | 0
DETAILED SECTIONS - 43XX
| A | D35 | 4330 | UNIT SECTIONS C25A (ODD LEVEL) | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 4331 | UNIT SECTIONS C25A (ODD LEVEL) | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
DOOR WINDOW DRAWINGS
| A | D35 | 4701 | DOOR AND WINDOW DETAILS – 1 | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 4702 | DOOR AND WINDOW DETAILS – 2 | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 4703 | DOOR AND WINDOW DETAILS – 3 | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 4704 | DOOR AND WINDOW DETAILS – 4 | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
KITCHEN DETAILS - 54XX
| A | D35 | 5401 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS - PLAN | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 5402 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 1 | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 5403 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 2 | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 5404 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 3 | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
BATHROOM DETAILS - 55XX
| A | D35 | 5501 | DETAILS - TYP. MASTER BATHROOM | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 5503 | DETAILS - TYP. CHILDREN'S BATHROOM | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 5505 | DETAILS - TYP. GUEST BATHROOM | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 5505 | DETAILS - MAIDS TOILET | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
SPECIFICATIONS / SCHEDULES - 7XXX
| A | D35 | 7410 | CLIENT EXCEPTIONS | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7420 | DOORS AND WINDOWS SCHEDULE | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7430 | FINISHES SCHEDULE | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7440 | PLUMBING AND SANITARY SCHEDULE | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7450 | CABINETRY SCHEDULE | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7461 | KITCHEN SPECIFICATION | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7462 | PANTRY SPECIFICATION | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7463 | BAR UNIT SPECIFICATION | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7470 | SWITCHBOARD SCHEDULE | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7480 | SERVICES SUMMARY | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7490 | SERVICES DETAILS : Home Automation | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7500 | LUMINAIRE SCHEDULE | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7510 | GENERAL SELECTIONS | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | D35 | 7520 | FURNITURE, FIXTURES AND EQUIPMENTS SCHEDULE | D35 | D35-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
DEFAULT UNIT SET - L22
UNIT PLANS
| A | L22 | 1001 | INTERIOR PLAN | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 1101 | MASONRY SET- OUT PLAN | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 1301 | FLOORING PLANS | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 1401 | ELECTRICAL PLANS - L19 ag | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 1402 | ELECTRICAL PLANS - L19 a & b | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 1501 | REFLECTED CELING PLANS L19ag | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 1502 | REFLECTED CELING PLANS L19 a & b | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 1601 | VACUUM LAYOUT PLANS | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
DETAILED SECTIONS - 43XX
| A | L22 | 4330 | UNIT SECTIONS C25A (ODD LEVEL) | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 4331 | UNIT SECTIONS C25A (ODD LEVEL) | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
DOOR WINDOW DRAWINGS
| A | L22 | 4701 | DOOR AND WINDOW DETAILS – 1 | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 4702 | DOOR AND WINDOW DETAILS – 2 | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 4703 | DOOR AND WINDOW DETAILS – 3 | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 4704 | DOOR AND WINDOW DETAILS – 4 | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
KITCHEN DETAILS - 54XX
| A | L22 | 5401 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS - PLAN | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 5402 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 1 | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 5403 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 2 | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 5404 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 3 | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
BATHROOM DETAILS - 55XX
| A | L22 | 5501 | DETAILS - TYP. MASTER BATHROOM | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 5503 | DETAILS - TYP. CHILDREN'S BATHROOM | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 5505 | DETAILS - TYP. GUEST BATHROOM | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 5505 | DETAILS - MAIDS TOILET | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
SPECIFICATIONS / SCHEDULES - 7XXX
| A | L22 | 7410 | CLIENT EXCEPTIONS | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7420 | DOORS AND WINDOWS SCHEDULE | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7430 | FINISHES SCHEDULE | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7440 | PLUMBING AND SANITARY SCHEDULE | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7450 | CABINETRY SCHEDULE | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7461 | KITCHEN SPECIFICATION | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7462 | PANTRY SPECIFICATION | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7463 | BAR UNIT SPECIFICATION | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7470 | SWITCHBOARD SCHEDULE | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7480 | SERVICES SUMMARY | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7490 | SERVICES DETAILS : Home Automation | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7500 | LUMINAIRE SCHEDULE | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7510 | GENERAL SELECTIONS | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | L22 | 7520 | FURNITURE, FIXTURES AND EQUIPMENTS SCHEDULE | L22 | L22-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
DEFAULT UNIT SET - R25P
UNIT PLANS
| A | R25P | 1001 | INTERIOR PLAN | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 1101 | MASONRY SET- OUT PLAN | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 1301 | FLOORING PLANS | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 1401 | ELECTRICAL PLANS - 3.6M HEIGHT (C25G AS WELL) | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 1405 | ELECTRICAL PLANS - 3.0M HEIGHT | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 1501 | REFLECTED CELING PLANS- 3.6M HEIGHT | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 1502 | REFLECTED CELING PLANS - 3.0M HEIGHT | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 1601 | VACUUM LAYOUT PLANS | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
DETAILED SECTIONS - 43XX
| A | R25P | 4330 | UNIT SECTIONS C25A (ODD LEVEL) | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4331 | UNIT SECTIONS C25A (ODD LEVEL) | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
DOOR WINDOW DRAWINGS
| A | R25P | 4701 | DOOR AND WINDOW DETAILS – 1 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4702 | DOOR AND WINDOW DETAILS – 2 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4703 | DOOR AND WINDOW DETAILS – 3 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4704 | DOOR AND WINDOW DETAILS – 4 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4705 | DOOR AND WINDOW DETAILS – 5 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4706 | DOOR AND WINDOW DETAILS – 6 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4707 | DOOR AND WINDOW DETAILS – 7 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4708 | DOOR AND WINDOW DETAILS – 8 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4709 | DOOR AND WINDOW DETAILS – 9 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4710 | DOOR AND WINDOW DETAILS – 10 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4711 | DOOR AND WINDOW DETAILS – 11 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4712 | DOOR AND WINDOW DETAILS – 12 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 4713 | DOOR AND WINDOW DETAILS – 13 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
KITCHEN DETAILS - 54XX
| A | R25P | 5401 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS - PLAN | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 5402 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 1 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 5403 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 2 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 5404 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 3 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
BATHROOM DETAILS - 55XX
| A | R25P | 5501 | DETAILS - TYP. MASTER BATHROOM - 3.6M HEIGHT | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 5502 | DETAILS - TYP. MASTER BATHROOM - 3.0M HEIGHT | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 5503 | DETAILS - TYP. CHILDREN'S BATHROOM - 3.6M HEIGHT | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 5504 | DETAILS - TYP. CHILDREN'S BATHROOM - 3.0M HEIGHT | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 5505 | DETAILS - TYP. GUEST BATHROOM - 3.6M HEIGHT | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 5506 | DETAILS - TYP. GUEST BATHROOM - 3.0M HEIGHT | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
SPECIFICATIONS / SCHEDULES - 7XXX
| A | R25P | 7410 | CLIENT EXCEPTIONS | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7420 | DOORS AND WINDOWS SCHEDULE | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7430 | FINISHES SCHEDULE | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7440 | PLUMBING AND SANITARY SCHEDULE | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7450 | CABINETRY SCHEDULE | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7461 | KITCHEN SPECIFICATION | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7462 | PANTRY SPECIFICATION | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7463 | BAR UNIT SPECIFICATION | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7470 | SWITCHBOARD SCHEDULE | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7480 | SERVICES SUMMARY | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7490 | SERVICES DETAILS : Home Automation | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7500 | LUMINAIRE SCHEDULE | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7510 | GENERAL SELECTIONS | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | R25P | 7520 | FURNITURE, FIXTURES AND EQUIPMENTS SCHEDULE | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
DEFAULT UNIT SET - L20P
UNIT PLANS
| A | L20P | 1001 | INTERIOR PLAN | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 1101 | MASONRY SET- OUT PLAN | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 1301 | FLOORING PLANS | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 1401 | ELECTRICAL PLANS - L20P ag | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 1402 | ELECTRICAL PLANS - L20P a & b | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 1501 | REFLECTED CELING PLANS L20Pag | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 1502 | REFLECTED CELING PLANS L20P a & b | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 1601 | VACUUM LAYOUT PLANS | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 1701 | CHANNEL MUSIC ? | [5 empty] | 0 |  |  |  |  | 0
DETAILED SECTIONS - 43XX
| A | L20P | 4330 | UNIT SECTIONS C25A (ODD LEVEL) | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 4331 | UNIT SECTIONS C25A (ODD LEVEL) | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
DOOR WINDOW DRAWINGS
| A | L20P | 4701 | DOOR AND WINDOW DETAILS – 1 | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 4702 | DOOR AND WINDOW DETAILS – 2 | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 4703 | DOOR AND WINDOW DETAILS – 3 | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 4704 | DOOR AND WINDOW DETAILS – 4 | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
KITCHEN DETAILS - 54XX
| A | L20P | 5401 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS - PLAN | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 5402 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 1 | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 5403 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 2 | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 5404 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 3 | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
BATHROOM DETAILS - 55XX
| A | L20P | 5501 | DETAILS - TYP. MASTER BATHROOM | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 5503 | DETAILS - TYP. CHILDREN'S BATHROOM | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 5505 | DETAILS - TYP. GUEST BATHROOM | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 5505 | DETAILS - MAIDS TOILET | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
SPECIFICATIONS / SCHEDULES - 7XXX
| A | L20P | 7410 | CLIENT EXCEPTIONS | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7420 | DOORS AND WINDOWS SCHEDULE | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7430 | FINISHES SCHEDULE | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7440 | PLUMBING AND SANITARY SCHEDULE | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7450 | CABINETRY SCHEDULE | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7461 | KITCHEN SPECIFICATION | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7462 | PANTRY SPECIFICATION | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7463 | BAR UNIT SPECIFICATION | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7470 | SWITCHBOARD SCHEDULE | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7480 | SERVICES SUMMARY | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7490 | SERVICES DETAILS : Home Automation | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7500 | LUMINAIRE SCHEDULE | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7510 | GENERAL SELECTIONS | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L20P | 7520 | FURNITURE, FIXTURES AND EQUIPMENTS SCHEDULE | L20P | L20P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
DEFAULT UNIT SET - D35P
UNIT PLANS
| A | D35P | 1001 | INTERIOR PLAN | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 1101 | MASONRY SET- OUT PLAN | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 1301 | FLOORING PLANS | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 1401 | ELECTRICAL PLANS - D35P ag | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 1402 | ELECTRICAL PLANS - D35P a & b | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 1501 | REFLECTED CELING PLANS D35Pag | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 1502 | REFLECTED CELING PLANS D35P a & b | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 1601 | VACUUM LAYOUT PLANS | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 1701 | CHANNEL MUSIC ? | [5 empty] | 0 |  |  |  |  | 0
DETAILED SECTIONS - 43XX
| A | D35P | 4330 | UNIT SECTIONS C25A (ODD LEVEL) | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 4331 | UNIT SECTIONS C25A (ODD LEVEL) | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
DOOR WINDOW DRAWINGS
| A | D35P | 4701 | DOOR AND WINDOW DETAILS – 1 | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 4702 | DOOR AND WINDOW DETAILS – 2 | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 4703 | DOOR AND WINDOW DETAILS – 3 | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 4704 | DOOR AND WINDOW DETAILS – 4 | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
KITCHEN DETAILS - 54XX
| A | D35P | 5401 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS - PLAN | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 5402 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 1 | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 5403 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 2 | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 5404 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 3 | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
BATHROOM DETAILS - 55XX
| A | D35P | 5501 | DETAILS - TYP. MASTER BATHROOM | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 5503 | DETAILS - TYP. CHILDREN'S BATHROOM | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 5505 | DETAILS - TYP. GUEST BATHROOM | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 5505 | DETAILS - MAIDS TOILET | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
SPECIFICATIONS / SCHEDULES - 7XXX
| A | D35P | 7410 | CLIENT EXCEPTIONS | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7420 | DOORS AND WINDOWS SCHEDULE | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7430 | FINISHES SCHEDULE | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7440 | PLUMBING AND SANITARY SCHEDULE | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7450 | CABINETRY SCHEDULE | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7461 | KITCHEN SPECIFICATION | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7462 | PANTRY SPECIFICATION | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7463 | BAR UNIT SPECIFICATION | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7470 | SWITCHBOARD SCHEDULE | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7480 | SERVICES SUMMARY | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7490 | SERVICES DETAILS : Home Automation | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7500 | LUMINAIRE SCHEDULE | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7510 | GENERAL SELECTIONS | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | D35P | 7520 | FURNITURE, FIXTURES AND EQUIPMENTS SCHEDULE | D35P | D35P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
DEFAULT UNIT SET - L22P
UNIT PLANS
| A | L22P | 1001 | INTERIOR PLAN | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 1101 | MASONRY SET- OUT PLAN | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 1301 | FLOORING PLANS | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 1401 | ELECTRICAL PLANS - L19 ag | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 1402 | ELECTRICAL PLANS - L19 a & b | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 1501 | REFLECTED CELING PLANS L19ag | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 1502 | REFLECTED CELING PLANS L19 a & b | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 1601 | VACUUM LAYOUT PLANS | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
DETAILED SECTIONS - 43XX
| A | L22P | 4330 | UNIT SECTIONS C25A (ODD LEVEL) | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 4331 | UNIT SECTIONS C25A (ODD LEVEL) | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
DOOR WINDOW DRAWINGS
| A | L22P | 4701 | DOOR AND WINDOW DETAILS – 1 | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 4702 | DOOR AND WINDOW DETAILS – 2 | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 4703 | DOOR AND WINDOW DETAILS – 3 | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 4704 | DOOR AND WINDOW DETAILS – 4 | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
KITCHEN DETAILS - 54XX
| A | L22P | 5401 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS - PLAN | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 5402 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 1 | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 5403 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 2 | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 5404 | MAIN KITCHEN ELECTRICAL AND PLUMBING DETAILS – ELEVATION SHEET 3 | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
BATHROOM DETAILS - 55XX
| A | L22P | 5501 | DETAILS - TYP. MASTER BATHROOM | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 5503 | DETAILS - TYP. CHILDREN'S BATHROOM | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 5505 | DETAILS - TYP. GUEST BATHROOM | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 5505 | DETAILS - MAIDS TOILET | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
SPECIFICATIONS / SCHEDULES - 7XXX
| A | L22P | 7410 | CLIENT EXCEPTIONS | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7420 | DOORS AND WINDOWS SCHEDULE | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7430 | FINISHES SCHEDULE | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7440 | PLUMBING AND SANITARY SCHEDULE | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7450 | CABINETRY SCHEDULE | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7461 | KITCHEN SPECIFICATION | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7462 | PANTRY SPECIFICATION | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7463 | BAR UNIT SPECIFICATION | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7470 | SWITCHBOARD SCHEDULE | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7480 | SERVICES SUMMARY | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7490 | SERVICES DETAILS : Home Automation | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7500 | LUMINAIRE SCHEDULE | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7510 | GENERAL SELECTIONS | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| A | L22P | 7520 | FURNITURE, FIXTURES AND EQUIPMENTS SCHEDULE | L22P | L22P-1 | 1 | 0 |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
Site Development | [43 empty] | Batch
GENERAL
| A | 00 | 0000 | COVER SHEET | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0001 | ABBREVIATIONS AND SYMBOLS | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0002 | SITE MASTER KEY PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
PLANS
| A | 00 | 0011 | MASTERPLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0012 | SITE PLAN - LEVEL 1 | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0013 | GRADING PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0014 | DRAINAGE PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0015 | FINISHES PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0016 | LANDSCAPE PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0021 | VILLA SITE PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0022 | PARTIAL SITE PLAN - BLOCK 1-7 LEVEL 1 PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0031 | VILLA CLUSTER 1 PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0032 | VILLA CLUSTER 2 PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0033 | VILLA CLUSTER 3 PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0050 | ELECTRICAL | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0060 | METAL FABRICATION | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0070 | SIGNAGE AND FURNITURE | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
ELECTRICAL - 14XX
| A | 00 | 0011 | SITE - STREET LIGHTING LAYOUT | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0012 | VILLAS - STREET LIGHTING LAYOUT | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 0013 | VILLAS - TREE TUB STREET LIGHTING DETAILS | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
GENERAL ARRANGEMENT ELEVATIONS
| A | 00 | 2000 | ELEVATION (EAST) | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 2010 | ELEVATION (WEST) | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 2020 | ELEVATION (NORTH) | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 2030 | ELEVATION (SOUTH) | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
GENERAL ARRANGEMENT SECTIONS
| A | 00 | 3010 | SITE SECTION THROUGH BLOCK 3 | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 3020 | SITE SECTION THROUGH BLOCK 2 | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 3022 | SITE SECTION ALONG CENTRAL GREEN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 3023 | SITE SECTION THROUGH TOWER 8 | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 3023 | SITE SECTION THROUGH TOWER 9 | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 3030 | SITE SECTION ALONG BASAVANAGAR MAIN ROAD | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
PARTIAL PLANS
| A | 00 | 4111 | PART PLAN - SOUTH WEST ENTRANCE | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
PARTIAL SECTIONS
| A | 00 | 4301 | DETAILED SECTIONS - 1 - SECTION THROUGH EXTENDED BASEMENT AND LAKE | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 4302 | DETAILED SECTIONS - 2 | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
EXTERNAL BUILDING ENVELOPE DETAILS
| A | 00 | 4401 | EXTERNAL BUILDING ELEMENTS - 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | 00 | 4402 | EXTERNAL BUILDING ELEMENTS - 2 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
ENCLOSURE AND FENCING DETAILS
| A | 00 | 5001 | WEST BOUNDARY WALL DETAIL - 01 | MP | MP-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | 00 | 5002 | WEST BOUNDARY WALL DETAIL - 02 | MP | MP-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | 00 | 5003 | ENCLOSURE AND FENCING - PHASE 1 TRANSFORMER YARD | MP | MP-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | 00 | 5004 | ENCLOSURE AND FENCING - PHASE 1 DG YARD | MP | MP-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | 00 | 5005 | ENCLOSURE AND FENCING - PHASE 2 TRANSFORMER YARD | MP | MP-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | 00 | 5006 | ENCLOSURE AND FENCING - PHASE 2 DG YARD | MP | MP-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
RAMP DETAILS
| A | 00 | 5103 | RAMP DETAILS - 3 - RAMP ADJACENT TO STEPPED TOWER 7 | MP | MP-3 | 3 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 3
| A | 00 | 5104 | RAMP DETAILS - 4 - RAMP ADJACENT TO STEPPED TOWER 8 | MP | MP-3 | 3 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 3
OUTDOOR STRUCTURES
| A | 00 | 5301 | OUTDOOR STRUCTURES - 1 - VILLA ELECTRICAL PANEL ROOM | MP | MP-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | 00 | 5301 | OUTDOOR STRUCTURES -Property Management Staff and Store rooms | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
SERVICE INFORMATION DRAWINGS
| A | 00 | 5801 | CHAMBER SETTING OUT - TYPICAL BLOCK PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 5802 | CHAMBER SETTING OUT - 1-NS-VILLA PARKING | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 5803 | CHAMBER SETTING OUT - 2-NS-VILLA PARKING | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 5805 | 1-NS TYPICAL SECTION THROUGH TREE TUB | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 5806 | 1-NS TYPICAL SECTION THROUGH PARKING | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 5807 | 1-NS TYPICAL SECTION THROUGH GUEST PARKING | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 5808 | 2-NS TPICAL SECTION THROUGH TREE TUB | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | 00 | 5809 | 2-NS TYPICAL SECTION THROUGH PARKING | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
SIGNAGE AND BRANDING
| A | 00 | 8001 | PHASE 1 SIGNAGE PLAN | MP | MP-9 | 9 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 9
| A | 00 | 8002 | PHASE 1 SIGNAGE DETAILS | MP | MP-9 | 9 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 9
STREET LIGHTING
| A | 00 | 1401 | SITE - STREET LIGHTING LAYOUT | MP | MP-9 | 9 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 9
|  |  | 1402 | VILLAS - STREET LIGHTING LAYOUT | MP | MP-9 | 9 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 9
| A | 00 | 1411 | VILLAS - TREE TUB STREET LIGHTING DETAILS | MP | MP-9 | 9 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 9
INFRASTRUCTURE DRAWINGS
| A | INFRA | 001 | OVER ALL SITE PLAN WITH SHEET INDEX | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | INFRA | 002 | 1-EW, 2-EW, 1-NS AND 2-NS PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | INFRA | 003 | 1-EW, 2-EW, 1-NS AND 2-NS PROFILE (L-SECTION) | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | INFRA | 004 | MAIN ENTRANCE ROAD PLAN, PRILE (L-SECTION) AND CROSS SECTION | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | INFRA | 005 | 4-EW, 5-EW AND 5-NS PLAN AND PROFILE (L-SECTION) | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | INFRA | 006 | TYPICAL VILLA DRIVE WAY ENTRANCE AND INTERSECTION 1 AND 3 DETAILS | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | INFRA | 007 | SECONDARY ENTRANCE, INTERSECTION - 2 AND CUL-DE-SAC DETAIL | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | INFRA | 008 | ROAD CROSS SECTIONS | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | INFRA | 009 | ROAD CENTER LINE SET OUT PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | INFRA | 010 | ROAD CENTER LINE SET OUT TABLE | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | SD | 002 | STORM DRAIN PLAN | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | SD | 003 | STORM DRAIN - PROFILE L-SECTION | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | SD | 004 | STORM DRAIN - PROFILE L-SECTION | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | SD | 005 | STORM DRAIN - PROFILE L-SECTION | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | SD | 006 | STORM DRAIN - PROFILE L-SECTION | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | SD | 007 | STORM DRAIN - STRUCTURE TABLES | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | SD | 008 | STORM DRAIN - STRUCTURE TABLES | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | SD | 009 | STORM DRAIN - STRUCTURE TABLES | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | SD | 010 | STORM DRAIN - STRUCTURE TABLES & MANHOLE DETAILS | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | SD | 011 | STORM DRAIN PIPE TABLES AND RAIN WATER RECHARGE PIT DETAIL | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | SD | 012 | MANHOLE DETAILS | MP | MP-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
ORGANIC WASTE CONVERTER
GENERAL 0000
| A | OW | 0000 | ABBREVIATIONS, SYMBOLS AND ANNOTATIONS | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
SETTING OUT PLANS 00XX
| A | OW | 0011 | SETOUT PLAN - COLUMNS | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
GENERAL ARRANGEMENT - PLANS - 10XX
| A | OW | 1001 | G.A. PLAN – SSL 1 - LEVEL 1 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 1002 | G.A. PLAN – SSL 2 - LEVEL 2 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 1002 | G.A. PLAN – ROOF LEVEL | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
MASONARY PLANS 11XX
| A | OW | 1101 | MASONRY SETOUT PLAN – SSL 1 - LEVEL 1 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 1102 | MASONRY SETOUT PLAN – SSL 1 - LEVEL 2 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
FLOORING PLANS 13XX
| A | OW | 1301 | FLOORING PLAN – SSL 1 - LEVEL 2 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 1302 | FLOORING PLAN – SSL 1 - LEVEL 1 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 1303 | FLOORING PLAN – ROOF | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
ELECTRICAL (co-orinated) - 14XX
| A | OW | 1401 | ELECTRICAL - LEVEL -1 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 1402 | ELECTRICAL - LEVEL -2 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 1403 | ELECTRICAL - ROOF | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 1404 | SWITCH SCHEDULE | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 1405 | LIGHTING FIXTURE SCHEDULE | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
GENERAL ARRANGEMENT - ELEVATIONS - 20XX
| A | OW | 2001 | GA - ELEVATIONS | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 2001 | GA - ELEVATIONS | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
GENERAL ARRANGEMENT - SECTIONS - 30XX
| A | OW | 3001 | GA -SECTIONS | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 3002 | GA -SECTIONS | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
BUILDING ENVOLOPE DETAILS - 44XX
| A | OW | 4401 | WALL SECTION - 1 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 4402 | WALL SECTION - 2 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 4408 | ROOF SECTION | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
STAIRCASE DETAILS - 46XX
| A | OW | 4601 | STAIRCASE 1 - DETAIL | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
DOOR WINDOW- 47XX
| A | OW | 4701 | DOOR AND WINDOW DETAILS – 1 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 4702 | DOOR AND WINDOW DETAILS – 2 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 4703 | DOOR AND WINDOW DETAILS – 3 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 4704 | DOOR AND WINDOW DETAILS – 4 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
AREA PLANS - 66XX
| A | OW | 6601 | AREA PLAN - LEVEL 1 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | OW | 6602 | AREA PLAN - LEVEL 2 | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
SIGNAGE & BRANDING - 81XX
| A | CH | 8101 | LEVEL 1 SIGNAGE | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
| A | CH | 8101 | LEVEL 2 SIGNAGE | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
RENDERS & VIEWS - 82XX
| A | CH | 8201 | EXTERNAL VIEWS | MP | MP-8 | 8 | 0 |  | 0 |  |  |  |  | 0 | [28 empty] | 8
MAIN SECURITY CABIN
GENERAL 0000
| A | SC1 | 0000 | ABBREVIATIONS, SYMBOLS AND ANNOTATIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
SETTING OUT PLANS 00XX
| A | SC1 | 0011 | SETOUT PLAN - COLUMNS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT - PLANS - 10XX
| A | SC1 | 1001 | G.A. PLAN – SSL 1 - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC1 | 1002 | G.A. PLAN – ROOF LEVEL | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
MASONARY PLANS 11XX
| A | SC1 | 1101 | MASONRY SETOUT PLAN – SSL 1 - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
FLOORING PLANS 13XX
| A | SC1 | 1301 | FLOORING PLAN - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC1 | 1303 | FLOORING PLAN – ROOF | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
ELECTRICAL (co-orinated) - 14XX
| A | SC1 | 1401 | ELECTRICAL - LEVEL -1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC1 | 1402 | ELECTRICAL - ROOF | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC1 | 1403 | SWITCH SCHEDULE | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC1 | 1404 | LIGHTING FIXTURE SCHEDULE | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT - ELEVATIONS - 20XX
| A | SC1 | 2001 | GA - ELEVATIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC1 | 2001 | GA - ELEVATIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT - SECTIONS - 30XX
| A | SC1 | 3001 | GA -SECTIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC1 | 3002 | GA -SECTIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
BUILDING ENVOLOPE DETAILS - 44XX
| A | SC1 | 4401 | WALL SECTION - 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC1 | 4402 | ROOF SECTION | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
DOOR WINDOW- 47XX
| A | SC1 | 4701 | DOOR AND WINDOW DETAILS – 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC1 | 4702 | DOOR AND WINDOW DETAILS – 2 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC1 | 4703 | DOOR AND WINDOW DETAILS – 3 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC1 | 4704 | DOOR AND WINDOW DETAILS – 4 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
AREA PLANS - 66XX
| A | SC1 | 6601 | AREA PLAN - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
SIGNAGE & BRANDING - 81XX
| A | SC1 | 8101 | LEVEL 1 SIGNAGE | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
RENDERS & VIEWS - 82XX
| A | SC1 | 8201 | EXTERNAL VIEWS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
RESIDENTIAL SECURITY CABIN 1
GENERAL 0000
| A | SC2 | 0000 | ABBREVIATIONS, SYMBOLS AND ANNOTATIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
SETTING OUT PLANS 00XX
| A | SC2 | 0011 | SETOUT PLAN - COLUMNS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT - PLANS - 10XX
| A | SC2 | 1001 | G.A. PLAN – SSL 1 - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC2 | 1002 | G.A. PLAN – ROOF LEVEL | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
MASONARY PLANS 11XX
| A | SC2 | 1101 | MASONRY SETOUT PLAN – SSL 1 - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
FLOORING PLANS 13XX
| A | SC2 | 1301 | FLOORING PLAN - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC2 | 1303 | FLOORING PLAN – ROOF | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
ELECTRICAL (co-orinated) - 14XX
| A | SC2 | 1401 | ELECTRICAL - LEVEL -1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC2 | 1402 | ELECTRICAL - ROOF | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC2 | 1403 | SWITCH SCHEDULE | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC2 | 1404 | LIGHTING FIXTURE SCHEDULE | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT - ELEVATIONS - 20XX
| A | SC2 | 2001 | GA - ELEVATIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC2 | 2001 | GA - ELEVATIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT - SECTIONS - 30XX
| A | SC2 | 3001 | GA -SECTIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC2 | 3002 | GA -SECTIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
BUILDING ENVOLOPE DETAILS - 44XX
| A | SC2 | 4401 | WALL SECTION - 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC2 | 4402 | ROOF SECTION | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
DOOR WINDOW- 47XX
| A | SC2 | 4701 | DOOR AND WINDOW DETAILS – 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC2 | 4702 | DOOR AND WINDOW DETAILS – 2 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC2 | 4703 | DOOR AND WINDOW DETAILS – 3 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC2 | 4704 | DOOR AND WINDOW DETAILS – 4 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
AREA PLANS - 66XX
| A | SC2 | 6601 | AREA PLAN - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
SIGNAGE & BRANDING - 81XX
| A | SC2 | 8101 | LEVEL 1 SIGNAGE | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
RENDERS & VIEWS - 82XX
| A | SC2 | 8201 | EXTERNAL VIEWS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
RESIDENTIAL SECURITY CABIN 2 - BASAVANAGAR MAIN ROAD
GENERAL 0000
| A | SC3 | 0000 | ABBREVIATIONS, SYMBOLS AND ANNOTATIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
SETTING OUT PLANS 00XX
| A | SC3 | 0011 | SETOUT PLAN - COLUMNS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT - PLANS - 10XX
| A | SC3 | 1001 | G.A. PLAN – SSL 1 - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC3 | 1002 | G.A. PLAN – ROOF LEVEL | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
MASONARY PLANS 11XX
| A | SC3 | 1101 | MASONRY SETOUT PLAN – SSL 1 - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
FLOORING PLANS 13XX
| A | SC3 | 1301 | FLOORING PLAN - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC3 | 1303 | FLOORING PLAN – ROOF | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
ELECTRICAL (co-orinated) - 14XX
| A | SC3 | 1401 | ELECTRICAL - LEVEL -1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC3 | 1402 | ELECTRICAL - ROOF | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC3 | 1403 | SWITCH SCHEDULE | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC3 | 1404 | LIGHTING FIXTURE SCHEDULE | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT - ELEVATIONS - 20XX
| A | SC3 | 2001 | GA - ELEVATIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC3 | 2001 | GA - ELEVATIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT - SECTIONS - 30XX
| A | SC3 | 3001 | GA -SECTIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC3 | 3002 | GA -SECTIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
BUILDING ENVOLOPE DETAILS - 44XX
| A | SC3 | 4401 | WALL SECTION - 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC3 | 4402 | ROOF SECTION | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
DOOR WINDOW- 47XX
| A | SC3 | 4701 | DOOR AND WINDOW DETAILS – 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC3 | 4702 | DOOR AND WINDOW DETAILS – 2 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC3 | 4703 | DOOR AND WINDOW DETAILS – 3 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | SC3 | 4704 | DOOR AND WINDOW DETAILS – 4 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
AREA PLANS - 66XX
| A | SC3 | 6601 | AREA PLAN - LEVEL 1 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
SIGNAGE & BRANDING - 81XX
| A | SC3 | 8101 | LEVEL 1 SIGNAGE | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
RENDERS & VIEWS - 82XX
| A | SC3 | 8201 | EXTERNAL VIEWS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
TEMPORARY ENTRANCE GATE
| A | TMP | 0000 | LOCATION MAP, VICINITY MAP AND INDEX OF DRAWINGS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 0001 | ABBREVATIONS AND SYMBOLS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 1000 | DEMOLITION PLAN | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 1001 | PARTIAL SITE PLAN | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 1002 | ROAD LAYOUT AND SET-OUT PLAN | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 1003 | PARTIAL PLAN - SECURITY CABIN | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 1004 | ROOF PLAN | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 2000 | ELEVATIONS - TEMPORARY ENTRY | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 2001 | ELEVATIONS - SECURITY CABIN | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 3100 | SECURITY CABIN - SECTIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 3200 | WALL DETAILS - TYPICAL SECTIONS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 3201 | WALL DETAILS - TYPICAL SECTION 2 | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 4004 | SECURITY CABIN DETAILS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 4002 | SECURITY CABIN DETAILS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 4003 | GATE DETAILS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 4004 | GATE DETAILS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 4006 | WINDOW DETAILS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 4100 | SECURITY CABIN TOILET DETAILS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 4110 | SIGNAGE DETAILS | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 5000 | ELECTRICAL LAYOUT - ARCHITECTURAL | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| A | TMP | 5001 | ELECTRICAL SCHEDULE | MP | MP-2 | 2 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
Amenities & Facilities | [43 empty] | Batch
CLUBHOUSE
GENERAL 0000
| A | CH | 0000 | ABBREVIATIONS, SYMBOLS AND ANNOTATIONS | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
SETTING OUT PLANS 00XX
| A | CH | 0011 | SETOUT PLAN - COLUMNS | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
GENERAL ARRANGEMENT - PLANS - 10XX
| A | CH | 1001 | G.A. PLAN – SSL 1 - LEVEL 1 | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1002 | G.A. PLAN – SSL 2 - LEVEL 2 | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1002 | G.A. PLAN – ROOF LEVEL | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1002 | G.A. PLAN – SSL 1 - LEVEL 2 - PART PLAN - BLOCK-A | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1003 | G.A. PLAN – SSL 1 - LEVEL 2 - PART PLAN - BLOCK-B&C | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1005 | G.A. PLAN – SSL 1 - LEVEL 1 - PART PLAN - BLOCK-A | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1006 | G.A. PLAN – SSL 1 - LEVEL 1 - PART PLAN - BLOCK-B&C | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
MASONARY PLANS 11XX
| A | CH | 1101 | MASONRY SETOUT PLAN – SSL 1 - LEVEL 2 - PART PLAN - BLOCK-A | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1102 | MASONRY SETOUT PLAN – SSL 1 - LEVEL 2 - PART PLAN - BLOCK-B&C | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1103 | MASONRY SETOUT PLAN – SSL 1 - LEVEL 1 - PART PLAN - BLOCK-A | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1104 | MASONRY SETOUT PLAN –SSL 1 - LEVEL 1 - PART PLAN - BLOCK-B&C | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
FLOORING PLANS 13XX
| A | CH | 1301 | FLOORING PLAN – SSL 1 - LEVEL 2 | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1302 | FLOORING PLAN – SSL 1 - LEVEL 1 | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1303 | SURFACE DRAINAGE PLAN - POOL DECK | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
ELECTRICAL (co-orinated) - 14XX
| A | CH | 1401 | ELECTRICAL - LEVEL -2 | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1401a | ELECTRICAL - LEVEL -2 - PART PLANS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 1402 | ELECTRICAL - LEVEL -1 | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 1402a | ELECTRICAL - LEVEL -1 - PART PLAN - BLOCK-A | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 1402b | ELECTRICAL - LEVEL -1 - PART PLAN - BLOCK-B&C | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 1403 | ELECTRICAL - EXTERIOR LIGHTING | AM | AM-3 | 3 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 3
| A | CH | 1403a | ELECTRICAL - EXTERIOR LIGHTING PART A | AM | AM-3 | 3 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 3
| A | CH | 1403b | ELECTRICAL - EXTERIOR LIGHTING PART B | AM | AM-3 | 3 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 3
| A | CH | 1404 | SWITCH SCHEDULE | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 1405 | LIGHTING FIXTURE SCHEDULE | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
REFLECTED CEILING PLANS WITH SLEEVE INFORMATION (co-orinated) - 15XX
| A | CH | 1501 | REFLECTED CEILING PLAN – SSL 1 - LEVEL 2 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 1502 | REFLECTED CEILING PLAN – SSL 1 - LEVEL 2 - BLOCK-A | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 1503 | REFLECTED CEILING PLAN – SSL 1 - LEVEL 2 - BLOCL B&C | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 1504 | REFLECTED CEILING PLAN – SSL 2 - LEVEL 1 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 1505 | REFLECTED CEILING PLAN – SSL 1 - LEVEL 2 - BLOCK-A | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 1506 | REFLECTED CEILING PLAN – SSL 1 - LEVEL 2 - BLOCL B&C | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
GENERAL ARRANGEMENT - ELEVATIONS - 20XX
| A | CH | 2001 | GA - ELEVATIONS | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
GENERAL ARRANGEMENT - SECTIONS - 30XX
| A | CH | 3001 | GA -SECTIONS | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 3002 | GA -SECTIONS | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 3003 | GA -SECTIONS | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
DETAILED PLANS ( with false ceiling) - 40XX
| A | CH | 4003 | SQUASH COURT 1 - LEVEL 1 - PLAN AND ELEVATIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4004 | SQUASH COURT 2 - LEVEL 1 - PLAN AND ELEVATIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4005 | THEATRE AND AV ROOM - LEVEL 1 - PLAN AND SECTIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4006 | MULTIPURPOSE HALL - LEVEL 1 - PLAN AND ELEVATIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4007 | MULTIPURPOSE HALL - LEVEL 1 - PLAN AND ELEVATIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4008 | MULTIPURPOSE HALL - LEVEL 1 - ELEVATIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4009 | YOGA / DANCE STUDIO - LEVEL 1 - PLAN AND ELEVATIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4010 | GYM - LEVEL 2 - PLAN AND ELEVATIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4011 | GYM - LEVEL 2 - ELEVATIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4012 | SUITE - LEVEL 2 - PLAN AND ELEVATIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4013 | SUITE - LEVEL 2 - PLAN AND ELEVATIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4014 | SUITE BATHROOM - LEVEL 2 - PLAN AND ELEVATIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
BUILDING ENVOLOPE DETAILS - 44XX
| A | CH | 4319 | CLUB HOUSE EXTERIOR ENVELOPE DETAILS | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 4320 | CLUB HOUSE EXTERIOR ENVELOPE DETAILS | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 4405 | MAIN ENTRANCE DETAILS | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
STAIRCASE DETAILS - 46XX
| A | CH | 4601 | STAIRCASE 1 - DETAIL, STAIRCASE 2, 3 TYPICAL DETAIL | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| A | CH | 4601 | STAIRCASE 1 - DETAIL, STAIRCASE 2, 3 TYPICAL DETAIL | AM | AM-1 | 1 | 0 |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
WATER BODY - 52XX
| A | CH | 5201 | POOL AREA | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
MECHANICAL SERVICE DETAILS - 62XX
| A | CH | 6201 | LEVEL 2 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 6202 | LEVEL 1 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
DOOR WINDOW- 47XX
| A | CH | 4701 | WINDOW 1 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4702 | DOOR 3 AND WINDOW 2 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4704 | WINDOW 4 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4705 | DOOR 12 AND WINDOW 5 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4706 | WINDOW 6 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4707 | DOOR 8 AND WINDOW 7 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4708 | WINDOW 8 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4709 | WINDOW 9 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4710 | DOOR 8 AND WINDOW 10 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4711 | WINDOW 11 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 4712 | WINDOW 12 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
KITCHEN DETAILS - 54XX
| A | CH | 5401 | KITCHEN 1 - LEVEL 1 - PLAN | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 5402 | KITCHEN 1 - LEVEL 1 - ELEVATIONS(A) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 5403 | KITCHEN 1 - LEVEL 1 - ELEVATIONS(B) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 5404 | KITCHEN 2 - LEVEL 1 - PLAN | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 5405 | KITCHEN 2 - LEVEL 1 - ELEVATIONS(A) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 5406 | KITCHEN 2 - LEVEL 1 - ELEVATIONS(B) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
TOILET DETAILS - 55XX
| A | CH | 5501 | MEN'S TOILET - LEVEL 2 - PLAN AND SECTIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 5502 | MEN'S TOILET - LEVEL 2 - PLANS AND SECTIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 5503 | WOMEN'S TOILET - LEVEL 2 - PLAN AND SECTIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 5504 | WOMEN'S TOILET - LEVEL 2 - PLAN AND SECTIONS | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 5506 | MEN'S TOILET - LEVEL 2 - REFLECTED CEILING PLAN | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 5507 | WOMEN'S TOILET - LEVEL 2 - REFLECTED CEILING PLAN | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
AREA PLANS - 66XX
| A | CH | 6601 | AREA PLAN - LEVEL 1 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 6602 | AREA PLAN - LEVEL 2 | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
RENDERS & VIEWS - 80XX
| A | CH | 8001 | EXTERNAL VIEWS (A) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 8002 | EXTERNAL VIEWS (B) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 8003 | EXTERNAL VIEWS (C) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 8004 | EXTERNAL VIEWS (D) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 8005 | INTERNAL VIEWS (A) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 8006 | INTERNAL VIEWS (B) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 8007 | INTERNAL VIEWS (C) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 8008 | INTERNAL VIEWS (D) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| A | CH | 8009 | INTERNAL VIEWS (E) | AM | AM-2 | 2 | 0 |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
CHILDREN'S PARK
GENERAL 0000
| A | CP | 0000 | ABBREVIATIONS, SYMBOLS AND ANNOTATIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
SETTING OUT PLANS 00XX
| A | CP | 0011 | SETOUT PLAN | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
GENERAL ARRANGEMENT - PLANS - 10XX
| A | CP | 1001 | G.A. PLAN – LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
MASONARY PLANS 11XX
| A | CP | 1101 | MASONRY SETOUT PLAN – LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
FLOORING PLANS 13XX
| A | CP | 1301 | FLOORING PLAN – LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
ELECTRICAL (co-orinated) - 14XX
| A | CP | 1401 | ELECTRICAL - LEVEL -1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | CP | 1404 | SWITCH SCHEDULE | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | CP | 1405 | LIGHTING FIXTURE SCHEDULE | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
GENERAL ARRANGEMENT - ELEVATIONS - 20XX
| A | CP | 2001 | GA - ELEVATIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
GENERAL ARRANGEMENT - SECTIONS - 30XX
| A | CP | 3001 | GA -SECTIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | CP | 3002 | GA -SECTIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
DETAILED PLANS - 40XX
| A | CP | 4001 | DETAILED PLAN - 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | CP | 4002 | DETAILED PLAN - 2 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | CP | 4003 | DETAILED PLAN - 3 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
AREA PLANS - 66XX
| A | CH | 6601 | AREA PLAN - LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
RENDERS & VIEWS - 80XX
| A | CH | 8001 | SIGNAGE PLAN - LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
RENDERS & VIEWS - 81XX
| A | CH | 8005 | INTERNAL VIEWS (A) | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | CH | 8006 | INTERNAL VIEWS (B) | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
|  |  |  | 5 | [5 empty] | 0 |  |  |  |  | 0
DOG PARK
GENERAL 0000
| A | DP | 0000 | ABBREVIATIONS, SYMBOLS AND ANNOTATIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
SETTING OUT PLANS 00XX
| A | DP | 0011 | SETOUT PLAN | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
GENERAL ARRANGEMENT - PLANS - 10XX
| A | DP | 1001 | G.A. PLAN – LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
MASONARY PLANS 11XX
| A | DP | 1101 | MASONRY SETOUT PLAN – LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
FLOORING PLANS 13XX
| A | DP | 1301 | FLOORING PLAN – LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
ELECTRICAL (co-orinated) - 14XX
| A | DP | 1401 | ELECTRICAL - LEVEL -1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | DP | 1404 | SWITCH SCHEDULE | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | DP | 1405 | LIGHTING FIXTURE SCHEDULE | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
GENERAL ARRANGEMENT - ELEVATIONS - 20XX
| A | DP | 2001 | GA - ELEVATIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
GENERAL ARRANGEMENT - SECTIONS - 30XX
| A | DP | 3001 | GA -SECTIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | DP | 3002 | GA -SECTIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
DETAILED PLANS - 40XX
| A | DP | 4001 | DETAILED PLAN - 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | DP | 4002 | DETAILED PLAN - 2 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
AREA PLANS - 66XX
| A | DP | 6601 | AREA PLAN - LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
RENDERS & VIEWS - 80XX
| A | DP | 8001 | SIGNAGE PLAN - LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
RENDERS & VIEWS - 81XX
| A | DP | 8005 | INTERNAL VIEWS (A) | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | DP | 8006 | INTERNAL VIEWS (B) | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
BOARD WALK
GENERAL 0000
| A | BW | 0000 | ABBREVIATIONS, SYMBOLS AND ANNOTATIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
SETTING OUT PLANS 00XX
| A | BW | 0011 | SETOUT PLAN | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
GENERAL ARRANGEMENT - PLANS - 10XX
| A | BW | 1001 | G.A. PLAN – LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
MASONARY PLANS 11XX
| A | BW | 1101 | MASONRY SETOUT PLAN – LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
FLOORING PLANS 13XX
| A | BW | 1301 | FLOORING PLAN – LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
ELECTRICAL (co-orinated) - 14XX
| A | BW | 1401 | ELECTRICAL - LEVEL -1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | BW | 1404 | SWITCH SCHEDULE | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | BW | 1405 | LIGHTING FIXTURE SCHEDULE | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
GENERAL ARRANGEMENT - ELEVATIONS - 20XX
| A | BW | 2001 | GA - ELEVATIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
GENERAL ARRANGEMENT - SECTIONS - 30XX
| A | BW | 3001 | GA -SECTIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | BW | 3002 | GA -SECTIONS | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
DETAILED PLANS - 40XX
| A | BW | 4001 | DETAILED PLAN - 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | BW | 4002 | DETAILED PLAN - 2 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
AREA PLANS - 66XX
| A | BW | 6601 | AREA PLAN - LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
RENDERS & VIEWS - 80XX
| A | BW | 8001 | SIGNAGE PLAN - LEVEL 1 | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
RENDERS & VIEWS - 81XX
| A | BW | 8005 | INTERNAL VIEWS (A) | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
| A | BW | 8006 | INTERNAL VIEWS (B) | AM | AM-4 | 4 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 4
COURTS
GENERAL 0000
| A | CO | 0000 | ABBREVIATIONS, SYMBOLS AND ANNOTATIONS | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
SETTING OUT PLANS 00XX
| A | CO | 0011 | SETOUT PLAN - COLUMNS | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
GENERAL ARRANGEMENT - PLANS - 10XX
| A | CO | 1001 | G.A. PLAN – SSL 1 - LEVEL 1 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 1002 | G.A. PLAN – SSL 2 - LEVEL 2 ROOF | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
MASONARY PLANS 11XX
| A | CO | 1101 | MASONRY SETOUT PLAN – LEVEL 1 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 1102 | MASONRY SETOUT PLAN - LEVEL 2 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
FLOORING PLANS 13XX
| A | CO | 1301 | FLOORING PLAN – LEVEL 1 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 1302 | FLOORING PLAN – LEVEL 2 ROOF | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
ELECTRICAL (co-orinated) - 14XX
| A | CO | 1401 | ELECTRICAL - LEVEL -1 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 1402 | ELECTRICAL - LEVEL -2 ROOF | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 1404 | SWITCH SCHEDULE | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 1405 | LIGHTING FIXTURE SCHEDULE | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
REFLECTED CEILING PLANS WITH SLEEVE INFORMATION (co-orinated) - 15XX
| A | CO | 1501 | REFLECTED CEILING PLAN – SSL 1 - LEVEL 1 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 1502 | REFLECTED CEILING PLAN – SSL 1 - LEVEL 2 - ROOF | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
GENERAL ARRANGEMENT - ELEVATIONS - 20XX
| A | CO | 2001 | GA - ELEVATIONS | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
GENERAL ARRANGEMENT - SECTIONS - 30XX
| A | CO | 3001 | GA -SECTIONS | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 3002 | GA -SECTIONS | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
DETAILED PLANS ( with false ceiling) - 40XX
| A | CO | 4001 | BADMINTON COURT DETAILS 1 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 4002 | BADMINTON COURT DETAILS 2 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 4003 | TENNIS COURT DETAILS 1 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 4004 | TENNIS COURT DETAILS 2 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
BUILDING ENVOLOPE DETAILS - 44XX
| A | CO | 4401 | WALL SECTION - 1 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 4402 | WALL SECTION - 2 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
STAIRCASE DETAILS - 46XX
| A | CO | 4601 | STAIRCASE 1 - DETAIL | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
DOOR WINDOW- 47XX
| A | CO | 4701 | DOOR AND WINDOW DETAILS – 1 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 4702 | DOOR AND WINDOW DETAILS – 2 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 4703 | DOOR AND WINDOW DETAILS – 3 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CO | 4704 | DOOR AND WINDOW DETAILS – 4 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
TOILET DETAILS - 55XX
| A | CH | 5501 | TOILET 1 & 2 - LEVEL 1 - PLAN | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CH | 5502 | TOILET 1 - LEVEL 1 - ELEVATIONS | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CH | 5503 | TOILET 2 - LEVEL 1 - ELEVATIONS | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
AREA PLANS - 66XX
| A | CH | 6601 | AREA PLAN - LEVEL 1 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CH | 6602 | AREA PLAN - LEVEL 2 | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
SIGNAGE & BRANDING - 80XX
| A | CH | 8001 | LEVEL 1 SIGNAGE | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CH | 8002 | LEVEL 2 SIGNAGE | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
RENDERS & VIEWS - 81XX
| A | CH | 8101 | EXTERNAL VIEWS (A) | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
| A | CH | 8102 | EXTERNAL VIEWS (B) | AM | AM-5 | 5 | 0 |  | 1 |  |  | 1 |  | 0 | [28 empty] | 5
TOWER 8
GENERAL - 00XX
| A | T8 | 0 | COVER SHEET | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1 | ABBREVIATIONS AND SYMBOLS | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
SITE & SETTING OUT DRGS - 0XXX
| A | T8B | 5 | PLAN SITE PLAN (STILT / PODIUM LEVEL (SSL04) | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 6 | SETTING OUT PLAN - BASEMENT 4 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
GENERAL ARRANGEMENT PLANS - 10XX
| A | T8B | 1001 | PLAN - BASEMENT 1 (SSL03) | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 1002 | PLAN - BASEMENT 2 (SSL02) | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 1003 | PLAN - BASEMENT 3 (SSL01) | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 1004 | PLAN - BASEMENT 4 (GRADE SLAB) | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1000 | PLAN - SITE & STILT / PODIUM LEVEL (SSL04) | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1001 | PLAN - LEVEL 1 (SSL05) | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1002 | PLAN - TYPICAL EVEN LEVELS | BB01 |  | 5 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1003 | PLAN - TYPICAL ODD LEVELS | BB01 |  | 6 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1019 | PLAN - LEVELS 19 & 29 (SSL 23 & 33) | BB01 |  | 6 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1031 | PLAN - LEVEL 31 (SSL 35) | BB01 |  | 6 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1032 | PLAN - LEVEL 32 (SSL 36) | BB01 |  | 5 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1033 | PLAN - LEVEL 33 (SSL 37) | BB01 |  | 8 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1034 | PLAN - LEVEL 34 (SSL 38) - TERRACE, LMR & ROOF | BB01 |  | 9 | 0 |  | 0 |  |  |  |  | 0
MASONRY & FLOORING PLANS - 11XX
| A | T8B | 1101 | MASONRY PLAN - BASEMENT 1 (SSL03) | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 1102 | MASONRY PLAN - BASEMENT 2 (SSL02) | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 1103 | MASONRY PLAN - BASEMENT 3 (SSL01) | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 1104 | MASONRY PLAN - BASEMENT 4 (GRADE SLAB) | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1100 | MASONRY PLAN - STILT / PODIUM LEVEL (SSL04) | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 1101 | MASONRY PLAN - LEVEL 1 (SSL05) - WING 1 | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 1102 | MASONRY PLAN - TYPICAL EVEN LEVELS - WING 1 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 1103 | MASONRY PLAN - TYPICAL ODD LEVELS - WING 1 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 1119 | MASONRY PLAN - LEVELS 19 & 29 (SSL 23 & 33) - WING 1 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 1131 | MASONRY PLAN - LEVEL 31 (SSL 35) - WING 1 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 1132 | MASONRY PLAN - LEVEL 32 (SSL 36) - WING 1 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 1133 | MASONRY PLAN - LEVEL 33 (SSL 37) - WING 1 | BB01 |  | 10 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 1101 | MASONRY PLAN - LEVEL 1 (SSL05) - WING 2 | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 1102 | MASONRY PLAN - TYPICAL EVEN LEVELS - WING 2 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 1103 | MASONRY PLAN - TYPICAL ODD LEVELS - WING 2 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 1119 | MASONRY PLAN - LEVELS 19 & 29 (SSL 23 & 33) - WING 2 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 1131 | MASONRY PLAN - LEVEL 31 (SSL 35) - WING 2 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 1132 | MASONRY PLAN - LEVEL 32 (SSL 36) - WING 2 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 1133 | MASONRY PLAN - LEVEL 33 (SSL 37) - WING 2 | BB01 |  | 10 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1134 | MASONRY PLAN - LEVEL 34 (SSL 38) - TERRACE, LMR & ROOF | BB01 |  | 10 | 0 |  | 0 |  |  |  |  | 0
ELECTRICAL DRAWINGS - 14XX
| A | T8B | 1400 | ELECTRICAL SCHEDULE - TOWER 8 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 1401 | ELECTRICAL PLAN (RCP) - BASEMENT 1 (SSL03) | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 1402 | ELECTRICAL PLAN (RCP) - BASEMENT 2 (SSL02) | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 1403 | ELECTRICAL PLAN (RCP) - BASEMENT 3 (SSL01) | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 1404 | ELECTRICAL PLAN (RCP) - BASEMENT 4 (GRADE SLAB) | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1400 | ELECTRICAL PLAN (RCP) - STILT / PODIUM LEVEL (SSL04) | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1401 | ELECTRICAL PLAN (RCP) - LEVEL 1 (SSL05) | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1402 | ELECTRICAL PLAN (RCP) - TYPICAL EVEN LEVELS | BB01 |  | 5 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1403 | ELECTRICAL PLAN (RCP) - TYPICAL ODD LEVELS | BB01 |  | 6 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1419 | ELECTRICAL PLAN (RCP) - LEVELS 19 & 29 (SSL 23 & 33) | BB01 |  | 6 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1431 | ELECTRICAL PLAN (RCP) - LEVEL 31 (SSL 35) | BB01 |  | 6 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1432 | ELECTRICAL PLAN (RCP) - LEVEL 32 (SSL 36) | BB01 |  | 5 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1433 | ELECTRICAL PLAN (RCP) - LEVEL 33 (SSL 37) | BB01 |  | 8 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 1434 | ELECTRICAL PLAN (RCP) - LEVEL 34 (SSL 38) - TERRACE | BB01 |  | 9 | 0 |  | 0 |  |  |  |  | 0
GENERAL ARRANGEMENT ELEVATIONS - 20XX
| A | T8 | 2001 | BLOCK ELEVATION - 1 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 2002 | BLOCK ELEVATION - 2 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 2003 | BLOCK ELEVATION - 3 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 2004 | BLOCK ELEVATION - 4 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
GENERAL ARRANGEMENT SECTIONS - 30XX
| A | T8 | 3001 | BLOCK SECTION - 1 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 3002 | BLOCK SECTION - 2 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 3003 | BLOCK SECTION - 3 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 3004 | BLOCK SECTION - 4 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 3005 | BLOCK SECTION - 5 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 3006 | BLOCK SECTION - 6 | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
DETAILED INTERIOR PLANS - 40XX
| A | T8 | 4000 | PLAN (GA) - LOBBIES & CLUBHOUSE | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4001 | PLAN - RECEPTION LOBBY - STILT LEVEL | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4002 | PLAN - RECEPTION LOBBY - STILT LEVEL | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4003 | PLAN - RECEPTION - VISITOR'S TOILET | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4005 | PLAN - CAFE | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4011 | PLAN - MULTIPURPOSE HALL | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4015 | PLAN - GYM | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4021 | PLAN - CRECHE | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4025 | PLAN STUDIOS (YOGA ROOM, ETC) | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
PART PLANS - 41XX
| A | T8.1 | 4101 | LIFT LOBBY AND SERVICE CORE DETAILS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 4102 | LIFT LOBBY AND SERVICE CORE DETAILS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 4103 | LIFT LOBBY AND SERVICE CORE DETAILS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4111 | FIRE CONTROL ROOM 1 & 2 - STILT LEVEL | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4113 | COMMUNICATION ROOM - W1 - BASEMENT 1 | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4114 | COMMUNICATION ROOM - W2 - BASEMENT 1 | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4115 | ELECTRICAL PANEL ROOM W1 - BASEMENT 1 | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4116 | ELECTRICAL PANEL ROOM W1 - BASEMENT 1 | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4117 | ELECTRICAL PANEL ROOM W2 - BASEMENT 1 | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4118 | ELECTRICAL PANEL ROOM W2 - BASEMENT 1 | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 4120 | GARBAGE ROOM - BASEMENT 1 | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 4121 | DRIVER'S/STAFF LOUNGE | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 4122 | DRIVER'S/STAFF TOILETS | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 4125 | UGT DETAILS | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 4126 | UGT DETAILS | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 4127 | UGT DETAILS | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 4130 | STP DETAILS | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 4131 | STP DETAILS | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 4132 | STP DETAILS | BB01 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 4135 | LMR DETAILS-W1 | BB01 |  | 9 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 4136 | LMR DETAILS-W1 | BB01 |  | 9 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 4137 | LMR DETAILS-W2 | BB01 |  | 9 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 4138 | LMR DETAILS-W2 | BB01 |  | 9 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 4140 | VENTILATION SHAFTS STURCTURE - STILT LEVEL | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8B | 4141 | VENTILATION SHAFTS STRUCTURE- STILT LEVEL | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
EXTERNAL BUILDING ENVELOPE - 44XX
| A | T8.1 | 4401 | KEY PLAN - WALL SECTIONS (EXTERNAL) | BB01 |  | 1 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 4402 | EXTERNAL WALL SECTIONS | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 4403 | EXTERNAL WALL SECTIONS | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 4404 | EXTERNAL WALL SECTIONS | BB01 |  | 4 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 4405 | WALL SECTION & WIRE-CUT BRICK DETAILS - CURVED WALL W1 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 4406 | WALL SECTION & WIRE-CUT BRICK DETAILS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 4407 | WALL SECTION & WIRE-CUT BRICK DETAILS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 4401 | KEY PLAN - WALL SECTIONS (EXTERNAL) | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 4402 | EXTERNAL WALL SECTIONS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 4403 | EXTERNAL WALL SECTIONS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 4404 | EXTERNAL WALL SECTIONS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 4402 | WALL SECTION & WIRE-CUT BRICK DETAILS - CURVED WALL W2 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 4403 | WALL SECTION & WIRE-CUT BRICK DETAILS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.2 | 4404 | WALL SECTION & WIRE-CUT BRICK DETAILS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4421 | FRAMING ELEVATION | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4422 | FRAMING ELEVATION | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4423 | FRAMING ELEVATION | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4424 | FRAMING ELEVATION | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4425 | FRAMING ELEVATION | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4426 | FRAMING ELEVATION | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4427 | FRAMING ELEVATION | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4428 | FRAMING ELEVATION | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4429 | FRAMING ELEVATION - WING 1 INTERIOR SIDE ELEVATIONS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4430 | FRAMING ELEVATION - WING 1 INTERIOR SIDE ELEVATIONS | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4435 | PERGOLA DETAIL | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4436 | PERGOLA DETAIL | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
STAIRCASE DETAILS - 46XX
| A | T8 | 4601 | STAIRCASE DETAILS - TYPE W1-1 - 1/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4602 | STAIRCASE DETAILS - TYPE W1-1 - 2/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4603 | STAIRCASE DETAILS - TYPE W1-1 - 3/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4606 | STAIRCASE DETAILS - TYPE W1-2 - 1/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4607 | STAIRCASE DETAILS - TYPE W1-2 - 2/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4608 | STAIRCASE DETAILS - TYPE W1-2 - 3/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4611 | STAIRCASE DETAILS - TYPE W2-1 - 1/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4612 | STAIRCASE DETAILS - TYPE W2-1 - 2/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4613 | STAIRCASE DETAILS - TYPE W2-1 - 3/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4616 | STAIRCASE DETAILS - TYPE W2-2 - 1/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4617 | STAIRCASE DETAILS - TYPE W2-2 - 2/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4618 | STAIRCASE DETAILS - TYPE W2-2 - 3/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4621 | STAIRCASE DETAILS - TYPE 3 - 1/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4622 | STAIRCASE DETAILS - TYPE 3 - 2/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4623 | STAIRCASE DETAILS - TYPE 3 - 3/3 | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
DOOR AND WINDOW DETAILS - 47XX
| A | T8 | 4701 | DOOR DETAIL - D01 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4702 | DOOR DETAIL - D08 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4703 | DOOR DETAIL - D09 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4704 | DOOR DETAIL - D10 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4705 | DOOR DETAIL - D11 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4706 | DOOR DETAIL - D12 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4707 | DOOR DETAIL - D13 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4708 | DOOR DETAIL - D14 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4709 | DOOR DETAIL - D15 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4710 | DOOR DETAIL - UGT | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4711 | DOOR DETAIL - STP | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4715 | WINDOW DETAIL - RW01 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4716 | WINDOW DETAIL - RW02 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4717 | WINDOW DETAIL - RW03 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4718 | WINDOW DETAIL - RW04 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4719 | WINDOW DETAIL - TW01 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4720 | WINDOW DETAIL - TW02 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4721 | WINDOW DETAIL - TW03 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4722 | WINDOW DETAIL - TW04 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4723 | WINDOW DETAIL - TW05 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4724 | WINDOW DETAIL - DW1 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4725 | WINDOW DETAIL - DW2 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4726 | WINDOW DETAIL - DW3 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4727 | WINDOW DETAIL - DW03** | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4728 | WINDOW DETAIL - DW4 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4729 | WINDOW DETAIL - DW04 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4730 | WINDOW DETAIL - DW8 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4731 | WINDOW DETAIL - DW08 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4732 | WINDOW DETAIL - LW1 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4733 | WINDOW DETAIL - LW2 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4734 | WINDOW DETAIL - LW3 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4735 | WINDOW DETAIL - W4 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4736 | WINDOW DETAIL - W5 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4737 | WINDOW DETAIL - W6 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4731 | SHAFT DOOR DETAIL - SD01 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4732 | SHAFT DOOR DETAIL - SD02 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4733 | SHAFT DOOR DETAIL - SD03 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4734 | SHAFT DOOR DETAIL - SD04 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4735 | SHAFT DOOR DETAIL - SD05 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4736 | SHAFT DOOR DETAIL - SD06 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4741 | FRENCH DOOR DETAIL - DFD01 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4742 | FRENCH DOOR DETAIL - DFD02 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4743 | FRENCH DOOR DETAIL - DFD03 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4744 | FRENCH DOOR DETAIL - DFD04 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4745 | FRENCH DOOR DETAIL - DFD05 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4746 | FRENCH DOOR DETAIL - LFD01 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4747 | FRENCH DOOR DETAIL - LFD02 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4748 | FRENCH DOOR DETAIL - LFD03 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4749 | FRENCH DOOR DETAIL - RFD01 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4750 | FRENCH DOOR DETAIL - RFD02 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4751 | FRENCH DOOR DETAIL - TFD01 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4752 | FRENCH DOOR DETAIL - TFD02 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4753 | FRENCH DOOR DETAIL - TFD03 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 4754 | FRENCH DOOR DETAIL - TFD04 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
RAMP DRAWINGS - 51XX
| A | T8 | 5101 | ENTRY RAMP DETAILS | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 5105 | ENTRY RAMP DETAILS | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 5106 | EXIT RAMP DETAILS | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 5110 | EXIT RAMP DETAILS | BB01 |  | 2 | 0 |  | 0 |  |  |  |  | 0
TERRACE GARDEN DETAILS - 62XX
| A | T8 | 6201 | R25 TYP. TERRACE GARDEN - DETAILS - 1 OF 3 | R25 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6202 | R25 TYP. TERRACE GARDEN - DETAILS - 2 OF 3 | R25 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6203 | R25 TYP. TERRACE GARDEN - DETAILS - 3 OF 3 | R25 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6204 | SERVICE PLATFORM - DETAILS | R25 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6206 | L22 TYP. TERRACE GARDEN - DETAILS - 1 OF 3 | L22 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6207 | L22 TYP. TERRACE GARDEN - DETAILS - 2 OF 3 | L22 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6208 | L22 TYP. TERRACE GARDEN - DETAILS - 3 OF 3 | L22 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6209 | SERVICE PLATFORM - DETAILS | L22 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6211 | L20 TYP. TERRACE GARDEN - DETAILS - 1 OF 3 | L20 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6212 | L20 TYP. TERRACE GARDEN - DETAILS - 2 OF 3 | L20 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6213 | L20 TYP. TERRACE GARDEN - DETAILS - 3 OF 3 | L20 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6214 | SERVICE PLATFORM - DETAILS | L20 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6216 | D35 TERRACE GARDEN - DETAILS - 1 OF 3 | D35 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6217 | D35 TERRACE GARDEN - DETAILS - 2 OF 3 | D35 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6218 | D35 TERRACE GARDEN - DETAILS - 3 OF 3 | D35 |  | 3 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6219 | SERVICE PLATFORM - DETAILS | D35 |  | 3 | 0 |  | 0 |  |  |  |  | 0
TERRACE DETAILS - 63XX
| A | T8.1 | 6301 | SKYLIGHT DETAILS - W1 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8.1 | 6302 | SKYLIGHT DETAILS - W1 | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
SIGNAGE DRAWINGS - 66XX
| A | T8 | 6601 | BASEMENT - PARKING ALLOTMENT | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6602 | STILT FLOOR | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6603 | TYPICAL FLOOR | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6604 | REFUGE FLOOR | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
| A | T8 | 6605 | TERRACE FLOOR | BB01 |  | 7 | 0 |  | 0 |  |  |  |  | 0
1
GFC ¦ Tower—08
BB01-1 | Foundation and Grade Slab
BB01-2 | Parking Level-Sub grade
BB01-3 | Building Envelope and Common Areas [Basement]
BB01-4 | Habitable Level 01
BB01-5 | Habitable Level - Even
BB01-6 | Habitable Level - Odd
BB01-7 | Building Envelope and Common Areas [Typical Tower Levels]
BB01-8 | Penthouse Levels
BB01-9 | Terrace Level
BB01-10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level]
GFC ¦ Independent Subgrade Structure - Tower 8
BB02-1 | Earthwork
BB02-2 | Foundations & Grade Slab
BB02-3 | Podium Slab
BB02-4 | Building Envelope and Common Areas
GFC ¦ Individual Homes
R25-1 | R25 Default and it's variants
L20-1 | L20 Default and it's variants
D35-1 | D35 Default and it's variants
L22-1 | L22 Default and it's variants
R25P-1 | R25 P Default and it's variants
L20P-1 | L20 P Default and it's variants
D35P-1 | D35 P Default and it's variants
L22P-1 | L22 P Default and it's variants
GFC ¦ Master Plan
MP-1 | Master Plan
MP-2 | Site Development
MP-3 | Site MEP
MP-4 | Landscaping
GFC ¦ Amenities & Facilities
AM-1 | Clubhouse—Structure and Envelope
AM-2 | Clubhouse—Interiors and Facilities
AM-3 | Clubhouse—Outdoor Spaces and Pool
AM-4 | Community spaces [Board Walk, Children play area]

## ST ¦ Drawing List
[7 empty] | Please do not delete this row | ITD23 |  | P23 | 1 | 2 | 3 | 4 | A23 | 5 | 6 | 7 | 8 | ITD24 |  | P24 | 9 | 10 | 11 | 12 | A24 | 13 | 14 | 15 | 16 | ITD25 |  | P25 | 17 | 18 | 19 | 20 | A25 | 21 | 22 | 23 | 24
0059 ¦ Pursuit of a Radical Rhapsody |  |  |  |  | Location | Batch Code | Batch | Issued till Dec 23 | Revision | Plan in FY 24 |  |  |  |  | Issued in FY 24 |  |  |  |  | Issued till Dec 24 | Revision | Plan in FY 25 |  |  |  |  | Issued in FY 25 |  |  |  |  | Issued till Dec 25 | Revision | Plan in FY 26 |  |  |  |  | Issued in FY 26
ST ¦ DRAWING LIST | [10 empty] | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  |  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  |  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4
Independent Subgrade Structure [Block Z]
BB02-1 | Earthwork
| ST | ISSZ | FD | EXCAVATION DRAWING | BB02 | BB02-1 | 1 | 1
BB02-2 | Foundations & Grade Slab
| ST | ISSZ | FD | FOUNDATION DETAILS | BB02 | BB02-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
| ST | ISSZ | CL | COLUMN DETAILS | BB02 | BB02-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
| ST | ISSZ | RW | WALL DETAILS | BB02 | BB02-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
BB02-3 | Parking Level Subgrade
| ST | ISSZ | FP | FRAMING PLAN AT SSL1 | BB02 | BB02-3 | 3 | 0 |  | 1 |  |  | 1 |  | 0
| ST | ISSZ | BM | BEAM REINFORCEMENT DETAILS—SSL1 | BB02 | BB02-3 | 3 | 0 |  | 1 |  |  | 1 |  | 0
| ST | ISSZ | SB | SLAB REINFORCEMENT DETAILS—SSL1 | BB02 | BB02-3 | 3 | 0 |  | 1 |  |  | 1 |  | 0
BB02-4 | Podium Slab
| ST | ISSZ | FP | FRAMING PLAN AT SSL2 | BB02 | BB02-4 | 4 | 0 |  | 1 |  |  |  | 1 | 0
| ST | ISSZ | BM | BEAM REINFORCEMENT DETAILS—SSL2 | BB02 | BB02-4 | 4 | 0 |  | 1 |  |  |  | 1 | 0
| ST | ISSZ | SB | SLAB REINFORCEMENT DETAILS—SSL2 | BB02 | BB02-4 | 4 | 0 |  | 1 |  |  |  | 1 | 0
Tower—08
BB01-1 | Foundation and Grade Slab
| ST | T08 | FD | PCC LAYOUT | BB01 | BB01-1 | 1 | 1
| ST | T08 | FD | FOUNDATION LAYOUT | BB01 | BB01-1 | 1 | 1
| ST | T08 | FD | RAFT REINFORCEMENT DETAILS | BB01 | BB01-1 | 1 | 1
| ST | T08 | FD | NTA FOOTING DETAILS | BB01 | BB01-1 | 1 | 1
| ST | T08 | CL | GENERAL COLUMN DETAILS | BB01 | BB01-1 | 1 | 1
| ST | T08 | CL | TYPICAL COLUMN LAPPING DETAILS | BB01 | BB01-1 | 1 | 1
| ST | T08 | CL | TOWER COLUMN DETAILS | BB01 | BB01-1 | 1 | 1
| ST | T08 | ST | STAIRCASE - 1 DETAILS | BB01 | BB01-1 | 1 | 1
| ST | T08 | ST | STAIRCASE - 2 DETAILS | BB01 | BB01-1 | 1 | 1
| ST | T08 | ST | STAIRCASE - 3 DETAILS | BB01 | BB01-1 | 1 | 1
| ST | T08 | ST | STAIRCASE - 4 DETAILS | BB01 | BB01-1 | 1 | 1
| ST | T08 | ST | NTA STAIRCASE-1 DETAILS | BB01 | BB01-1 | 1 | 1
| ST | T08 | RP | EXIT RAMP DETAILS_FP, BEAMS, SLABS | BB01 | BB01-1 | 1 | 1
| ST | T08 | RP | ENTRY RAMP DETAILS_FP, BEAMS, SLABS | BB01 | BB01-1 | 1 | 1
BB01-2 | Parking Level-Sub grade
| ST | T08 | RW | RETAINING WALL DETAILS(SSL3-SSL4) | BB01 | BB01-2 | 2 | 0 |  | 1 |  |  | 1 |  | 1 |  |  |  | 1
| ST | T08 | RW | RETAINING WALL CUTOUT DETAILS | BB01 | BB01-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
| ST | T08 | FP | FRAMING PLAN SSL 1 | BB01 | BB01-2 | 2 | 0 |  | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | FP | FRAMING PLAN SSL 2 | BB01 | BB01-2 | 2 | 0 |  | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | FP | FRAMING PLAN SSL 3 | BB01 | BB01-2 | 2 | 0 |  | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | FP | FRAMING PLAN SSL 4 | BB01 | BB01-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
| ST | T08 | BM | GENERAL NOTES - BEAMS | BB01 | BB01-2 | 2 | 0 |  | 1 |  |  | 1 |  | 1 |  |  |  | 1
| ST | T08 | BM | BEAM DETAILS SSL 1 | BB01 | BB01-2 | 2 | 0 |  | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | BM | BEAM DETAILS SSL 2 | BB01 | BB01-2 | 2 | 0 |  | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | BM | BEAM DETAILS SSL 3 | BB01 | BB01-2 | 2 | 0 |  | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | BM | BEAM DETAILS SSL 4 | BB01 | BB01-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
| ST | T08 | SB | GENERAL NOTES - SLABS | BB01 | BB01-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
| ST | T08 | SB | SLAB DETAILS SSL 1 | BB01 | BB01-2 | 2 | 0 |  | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | SB | SLAB DETAILS SSL 2 | BB01 | BB01-2 | 2 | 0 |  | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | SB | SLAB DETAILS SSL 3 | BB01 | BB01-2 | 2 | 0 |  | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | SB | SLAB DETAILS SSL 4 | BB01 | BB01-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
| ST | T08 | SL | SLEEVE DETAILS - SSL 5 | BB01 | BB01-2 | 2 | 0 |  | 1 | 1 |  |  |  | 1 | 1
BB01-4 | Habitable Level 01
| ST | T08 | BM | BEAM DETAILS SSL 5 | BB01 | BB01-4 | 4 | 1
| ST | T08 | SB | SLAB DETAILS SSL 5 | BB01 | BB01-4 | 4 | 1
| ST | T08 | SL | SLEEVE DETAILS - SSL 6-35 | BB01 | BB01-4 | 4 | 1
| ST | T08 | FP | FRAMING PLAN SSL 5 | BB01 | BB01-4 | 4 | 1
BB01-5 | Habitable Level - Even
| ST | T08 | CL | NON-TOWER COLUMN DETAILS | BB01 | BB01-5 | 5 | 0 | [13 empty] | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | FP | FRAMING PLAN SSL 6,8,10,12,14....34 | BB01 | BB01-5 | 5 | 0 | [13 empty] | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | BM | BEAM DETAILS SSL 6,8,10,12,14....34 | BB01 | BB01-5 | 5 | 0 | [13 empty] | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | SB | SLAB DETAILS SSL 6 - 35 | BB01 | BB01-5 | 5 | 0 | [13 empty] | 1 | 1 |  |  |  | 1 | 1
BB01-6 | Habitable Level - Odd
| ST | T08 | FP | FRAMING PLAN SSL 7,9,11,13,15....35 | BB01 | BB01-6 | 6 | 0 | [13 empty] | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | BM | BEAM DETAILS SSL 7,9,11,13,15....35 | BB01 | BB01-6 | 6 | 0 | [13 empty] | 1 | 1 |  |  |  | 1 | 1
| ST | T08 | SB | SLAB DETAILS SSL 6 - 35 | BB01 | BB01-6 | 6 | 0 | [13 empty] | 1 | 1 |  |  |  | 1 | 1
BB01-8 | Penthouse Levels
| ST | T08 | FP | FRAMING PLAN SSL36 (penthouse lower level) | BB01 | BB01-8 | 8 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | FP | FRAMING PLAN SSL37(penthouse upper level) | BB01 | BB01-8 | 8 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | BM | BEAM DETAILS SSL36 | BB01 | BB01-8 | 8 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | BM | BEAM DETAILS SSL37 | BB01 | BB01-8 | 8 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | SB | SLAB DETAILS SSL36 | BB01 | BB01-8 | 8 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | SB | SLAB DETAILS SSL37 | BB01 | BB01-8 | 8 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | SL | SLEEVE DETAILS - SSL36 | BB01 | BB01-8 | 8 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | SL | SLEEVE DETAILS - SSL37 | BB01 | BB01-8 | 8 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | SL | SLEEVE DETAILS - SSL38 | BB01 | BB01-8 | 8 | 0 |  | 1 |  |  |  | 1 | 0
BB01-9 | Terrace Level
| ST | T08 | FP | FRAMING PLAN SSL38(TERRACE) | BB01 | BB01-9 | 9 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | FP | FRAMING PLAN OF OHT AND LMR | BB01 | BB01-9 | 9 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | BM | BEAM DETAILS SSL38(TERRACE) | BB01 | BB01-9 | 9 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | BM | BEAM DETAILS OF OHT AND LMR | BB01 | BB01-9 | 9 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | SB | SLAB DETAILS SSL38(TERRACE) | BB01 | BB01-9 | 9 | 0 |  | 1 |  |  |  | 1 | 0
| ST | T08 | SB | SLAB DETAILS OF OHT AND LMR | BB01 | BB01-9 | 9 | 0 |  | 1 |  |  |  | 1 | 0
Site Development
MP-2 | Site Development
| ST | SI |  | COMPOUND WALL AND BOUNDARY WALLS | MP | MP-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
| ST | SI |  | STORM WATER DRAINAGE | MP | MP-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
| ST | SI |  | CULVERT DETAILS | MP | MP-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
| ST | SI |  | LANDSCAPE DETAILS | MP | MP-2 | 2 | 0 |  | 1 |  |  | 1 |  | 0
MP-3 | Site MEP
| ST | SI |  | HVAC TUNNELS | MP | MP-3 | 3 | 0 |  | 1 |  |  |  | 1 | 0
| ST | SI |  | TRANSFORMER YARD DETAILS | MP | MP-3 | 3 | 0 |  | 1 |  |  |  | 1 | 0
| ST | SI |  | DG YARD DETAILS | MP | MP-3 | 3 | 0 |  | 1 |  |  |  | 1 | 0

## MEP ¦ Drawing List
[7 empty] | Please do not delete this row | ITD23 |  | P23 | 1 | 2 | 3 | 4 | A23 | 5 | 6 | 7 | 8 | ITD24 |  | P24 | 9 | 10 | 11 | 12 | A24 | 13 | 14 | 15 | 16 | ITD25 |  | P25 | 17 | 18 | 19 | 20 | A25 | 21 | 22 | 23 | 24
0059 ¦ Pursuit of a Radical Rhapsody |  |  |  |  | Location | Batch Code | Batch | Issued till Dec 23 | Revision | Plan in FY 24 |  |  |  |  | Issued in FY 24 |  |  |  |  | Issued till Dec 24 | Revision | Plan in FY 25 |  |  |  |  | Issued in FY 25 |  |  |  |  | Issued till Dec 25 | Revision | Plan in FY 26 |  |  |  |  | Issued in FY 26
MEP ¦ DRAWING LIST | [10 empty] | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  |  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  |  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4
Independent Subgrade Structure [Block Z]
BB02-2 | Foundations & Grade Slab
Basement | PHE | T08 |  | U G Sump Plan and Sectional Detail | BB02 | BB02-2 | 2 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 2
BB02-3 | Parking Level Subgrade
Basement | FPS | T08 |  | Basement-4 Floor Plan - Fire Protection System Layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | FPS | T08 |  | Basement-4 - Fire Protection co ordinated System Layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | FPS | T08 |  | Basement-3 Floor Plan - Fire Protection System Layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | FPS | T08 |  | Basement-3 - Fire Protection co ordinated System Layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | FPS | T08 |  | Basement-2 Floor Plan - Fire Protection System Layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | FPS | T08 |  | Basement-2 - Fire Protection co ordinated System Layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1002 | Basement-2 lighting layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1006 | Basement-2 lighting layout -DB Scheme | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1011 | Basement-2 cable tray routing layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1003 | Basement-3 lighting layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1007 | Basement-3 lighting layout -DB Scheme | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1012 | Basement-3 cable tray routing layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1004 | Basement-4 lighting layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1008 | Basement-4 lighting layout -DB Scheme | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1013 | Basement-4 cable tray routing layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | HVAC | T08 | 1002 | Basement-2 Mechanical ventilation layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | HVAC | T08 | 1003 | Basement-3 Mechanical ventilation layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | HVAC | T08 | 1004 | Basement-4 Mechanical ventilation layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
BB02-4 | Podium Slab
Basement | FPS | T08 |  | Basement-1 Floor Plan - Fire Protection System Layout | BB02 | BB02-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Basement | FPS | T08 |  | Basement-1- Fire Protection co ordinated System Layout | BB02 | BB02-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1001 | Basement-1 Lighting layout | BB02 | BB02-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1005 | Basement-1 Lighting layout -DB Scheme | BB02 | BB02-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Basement | HVAC | T08 | 1001 | Basement-1 Mechanical ventilation layout | BB02 | BB02-3 | 3 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1009 | Basement-1 Equipment & cable tray routing layout | BB02 | BB02-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Basement | ELE | T08 | 1010 | Basement-1 Equipment & cable tray routing layout -Section | BB02 | BB02-4 | 4 |  |  | 1 |  |  | 1 |  | 0
BB02-5 | Building Envelope and Common Areas
Basement | PHE | T08 |  | Basement-1 -PHE CO-ordinated services [water supply, sewerage and rain water disposal] | BB02 | BB02-5 | 5 |  |  | 1 |  |  | 1 |  | 0
Basement | PHE | T08 |  | Basement-1 -MEP CO-ordinated services | BB02 | BB02-5 | 5 |  |  | 1 |  |  | 1 |  | 0
Basement | PHE | T08 |  | Basement-4 -PHE CO-ordinated services [water supply, sewerage and rain water disposal] | BB02 | BB02-5 | 5 |  |  | 1 |  |  | 1 |  | 0
Basement | PHE | T08 |  | Basement-4 -MEP CO-ordinated services | BB02 | BB02-5 | 5 |  |  | 1 |  |  | 1 |  | 0
Basement | PHE | T08 |  | Basement-3 -PHE CO-ordinated services [water supply, sewerage and rain water disposal] | BB02 | BB02-5 | 5 |  |  | 1 |  |  | 1 |  | 0
Basement | PHE | T08 |  | Basement-3 -MEP CO-ordinated services | BB02 | BB02-5 | 5 |  |  | 1 |  |  | 1 |  | 0
Basement | PHE | T08 |  | Basement-2 -PHE CO-ordinated services [water supply, sewerage and rain water disposal] | BB02 | BB02-5 | 5 |  |  | 1 |  |  | 1 |  | 0
Basement | PHE | T08 |  | Basement-2 -MEP CO-ordinated services | BB02 | BB02-5 | 5 |  |  | 1 |  |  | 1 |  | 0
Tower—08 | [43 empty] | Batch
BB01-1 | Foundation and Grade Slab
Basement | PHE | T08 |  | Basement-4 Floor Plan - Surface Drainage System Layout | BB01 | BB01-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [11 empty] | 1 | 1
Basement | PHE | T08 |  | Basement-4 Floor Plan - Subsoil Drainage System Layout | BB01 | BB01-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [11 empty] | 1 | 1
Basement | PHE | T08 |  | Basement-4 Floor Plan - Storm Water collection Sump details and sections | BB01 | BB01-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [11 empty] | 1 | 1
Basement | PHE | T08 |  | Basement-3 Floor Plan - Surface Drainage Layout | BB01 | BB01-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [11 empty] | 1 | 1
Basement | PHE | T08 |  | Basement-2 Floor Plan - Surface Drainage Layout | BB01 | BB01-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [11 empty] | 1 | 1
Basement | PHE | T08 |  | Basement-1 Floor Plan - Surface Drainage Layout | BB01 | BB01-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [11 empty] | 1 | 1
Basement | ELE | T08 | 1018 | Staricase lighting layout Wing-1 | BB01 | BB01-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [11 empty] | 1 | 1
Basement | ELE | T08 | 1019 | Staricase lighting layout Wing-2 | BB01 | BB01-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [11 empty] | 1 | 1
BB01-4 | Habitable Level 01
Tower | FPS | T08 |  | Fire Sprinklers and Hydrant System Schematic Diagram | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | FPS | T08 |  | FAPA Schematic Diagram | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | PHE | T08 |  | Water Supply Schematic Diagram | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | FPS | T08 |  | Level 1 (SSL05)-Fire Protection System Layout | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08 | 1016 | Stilt level Electrical layout | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08 | 1017 | Stilt level Electrical layout -DB scheme | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | HVAC | T08w1 | 1010 | Stilt level HVAC layout-Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | HVAC | T08w2 | 1011 | Stilt level HVAC layout-Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W1 | 1120 | Level-1 Electrical layout (SSl05) -Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W1 | 1121 | Level-1 Electrical layout - DB scheme -Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W2 | 1034 | Level-1 Electrical layout (SSl05) -Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W2 | 1035 | Level-1 Electrical layout - DB scheme -Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
`
BB01-7 | Building Envelope and Common Areas [Typical Tower Levels] |  |  |  | All the below drawings were initially in P7 but was asked to be moved to P4 in the Q7 MEP goals discussion meeting held on 8-7-24 at 12.30 PM in Meeting room no. 2
Tower | PHE | T08 |  | Typical Even Level - PHE Layout (Drainage and Water Supply) | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 9
Tower | PHE | T08 |  | Typical Odd Level - PHE Layout (Drainage and Water Supply) | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 9
Tower | PHE | T08 |  | Level - 19 & 29 (SSL 23 & 33)-PHE Layout (Drainage and Water Supply) | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 9
Tower | PHE | T08 |  | Level - 31 (SSL 35) - PHE Layout (Drainage and Water Supply) | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 9
Tower | PHE | T08 |  | Level - 32 (SSL 36) - PHE Layout (Drainage and Water Supply) | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | FPS | T08 |  | Typical Even Level - Fire Protection System Layout | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | FPS | T08 |  | Typical Odd Level - Fire Protection System Layout | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | FPS | T08 |  | Level - 19 & 29 (SSL 23 & 33)-Fire Protection System Layout | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | FPS | T08 |  | Level - 31 (SSL 35) - Fire Protection System Layout | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | FPS | T08 |  | Level - 32 (SSL 36) - Fire Protection System Layout | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W1 | 1022 | Typical odd level Electrical layout (SSl05) -Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W1 | 1023 | Typical odd level Electrical layout - DB scheme -Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W1 | 1024 | Typical Even level Electrical layout (SSl05) -Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W1 | 1025 | Typical Even level Electrical layout - DB scheme -Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W1 | 1026 | Level 19 & 29 Electrical layout - Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W1 | 1027 | Level 19 & 29 Electrical layout -DB scheme- Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W1 | 1028 | Level 31 Electrical layout-Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W1 | 1029 | Level 31 Electrical layout-DB scheme-Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W2 | 1036 | Typical odd level Electrical layout (SSl05) -Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W2 | 1037 | Typical odd level Electrical layout - DB scheme -Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W2 | 1038 | Typical Even level Electrical layout (SSl05) -Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W2 | 1039 | Typical Even level Electrical layout - DB scheme -Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W2 | 1040 | Level 19 & 29 Electrical layout - Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W2 | 1041 | Level 19 & 29 Electrical layout -DB scheme- Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W2 | 1042 | Level 31 Electrical layout-Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08W2 | 1043 | Level 31 Electrical layout-DB scheme-Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | ELE | T08 | 1051 | Typical floor Electrical & communication shaft detail | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | HVAC | T08w1 | 1012 | Typical odd level HVAC shaft layout-Wing1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | HVAC | T08w1 | 1013 | Typical even level HVAC shaft layout-Wing-1 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | HVAC | T08w2 | 1012 | Typical odd level HVAC shaft layout-Wing2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
Tower | HVAC | T08w2 | 1013 | Typical even level HVAC shaft layout-Wing-2 | BB01 | BB01-4 | 4 |  |  | 1 |  |  | 1 |  | 0
BB01-8 | Penthouse Levels
Tower | PHE | T08 |  | Level - 33 (SSL 37) - PHE Layout (Drainage and Water Supply) | BB01 | BB01-8 | 8 |  |  | 1 |  |  |  | 1 | 0
Tower | FPS | T08 |  | Level - 33 (SSL 37) - Fire Protection System Layout | BB01 | BB01-8 | 8 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08W1 | 1030 | Level 32 Electrical layout-Wing1 | BB01 | BB01-8 | 8 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08W1 | 1031 | Level 32 Electrical layout-DB scheme-Wing1 | BB01 | BB01-8 | 8 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08W2 | 1044 | Level 32 Electrical layout-Wing2 | BB01 | BB01-8 | 8 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08W2 | 1045 | Level 32 Electrical layout-DB scheme-Wing1 | BB01 | BB01-8 | 8 |  |  | 1 |  |  |  | 1 | 0
BB01-9 | Terrace Level
Tower | PHE | T08 |  | Level - 34 (SSL 38) - PHE Layout -Drainage System Layout | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | PHE | T08 |  | Level - 34 (SSL 38) - PHE Layout -Water Supply Layout | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | PHE | T08 |  | OHT Plan and Sectinal Detail | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | FPS | T08 |  | Level - 34 (SSL 38) - Fire Protection System Layout | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08W1 | 1032 | Level 33 Electrical layout-Wing1 | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08W1 | 1033 | Level 33 Electrical layout-DB scheme-Wing1 | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08W2 | 1046 | Level 33 Electrical layout-Wing1 | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08W2 | 1047 | Level 33 Electrical layout-DB scheme-Wing2 | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08 | 1047 | Terrace lightning arrester layout | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08 | 1048 | Site plan- LA earth pit location layout | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08 | 1049 | LA-Down conductor routing -1 | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | ELE | T08 | 1050 | LA-Down conductor routing -2 | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | HVAC | T08w1 | 1014 | Terrace level HVAC equipment layout-Wing1 | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Tower | HVAC | T08w2 | 1015 | Terrace level HVAC equipment layout-Wing2 | BB01 | BB01-9 | 9 |  |  | 1 |  |  |  | 1 | 0
Individual Homes | [43 empty] | Batch
R25-1 | R25 Default and it's variants
PLUMBING
TOILET DETAILS & WALL ELEVATIONS
| PHE | T08 | 4011 | Enlarged toilet details and Wall Elevation Master Bath | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| PHE | T08 | 4012 | Enlarged toilet details and Wall Elevation Master Bath | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| PHE | T08 | 4021 | Enlarged toilet details and Wall Elevation Guest Bath | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| PHE | T08 | 4022 | Enlarged toilet details and Wall Elevation Guest Bath | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| PHE | T08 | 4031 | Enlarged toilet details and Wall Elevation Children's Bath | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| PHE | T08 | 4032 | Enlarged toilet details and Wall Elevation Children's Bath | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| PHE | T08 | 4071 | Enlarged Kitchen & Utility Plumbing details and Wall Elevation | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| PHE | T08 | 4072 | Enlarged Kitchen & Utility Plumbing details and Wall Elevation | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| PHE | T08 | 4073 | Enlarged Kitchen & Utility Plumbing details and Wall Elevation | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| ELECTRICAL |  |  | Will be released in the floor level drawing
HVAC
| HVAC | T08 | 1AA1 | Typical Unit R25 HVAC layout | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
COORDINATED DRAWINGS
| CO | T08 | 4011 | Co-ordinated Enlarged toilet details and Wall Elevation BTR 1 | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| CO | T08 | 4021 | Co-ordinated Enlarged toilet details and Wall Elevation BTR 2 | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| CO | T08 | 4031 | Co-ordinated Enlarged toilet details and Wall Elevation BTR 3 | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| CO | T08 | 4071 | Co-ordinated Enlarged Kitchen & Utility Plumbing details and Wall Elevation | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
HOME AUTOMATION
| HA | R25 | 1001 | R25 Home Automation Layout | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
| HA | R25 | 9001 | R25 Client Specification Sheet | R25 | R25-1 | 1 | 1 | [6 empty] | 0 | [28 empty] | 1
L20-1 | L20 Default and it's variants
PLUMBING
TOILET DETAILS & WALL ELEVATIONS
| PHE | T08 | 4051 | Enlarged toilet details and Wall Elevation L20 BTR 1 of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4061 | Enlarged toilet details and Wall Elevation L20 BTR 2 of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4071 | Enlarged toilet details and Wall Elevation L20 BTR 3 of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4081 | Enlarged toilet details and Wall Elevation L20 BTR 4 of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4091 | Enlarged L20 Maids Toilet Plumbing details and Wall Elevation of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4101 | Enlarged L20 Dry Kitchen Plumbing details and Wall Elevation of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4105 | Enlarged L20 Wet Kitchen Plumbing details and Wall Elevation of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4111 | Enlarged L20 Utility Plumbing details and Wall Elevation of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4115 | Enlarged L20 Powder Toilet Plumbing details and Wall Elevation of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 |  | Heat Pump Layout | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| ELECTRICAL |  |  | Will be released in the floor level drawing | [5 empty] | 0 |  |  |  |  | 0
HVAC
| HVAC | T08 | 1AA1 | Typical L20 HVAC layout VRV Option- Tower 8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| HVAC | T08 | 1AA5 | Typical L20 HVAC layout Split Option- Tower 8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
COORDINATED DRAWING
| CO | T08 | 4051 | Co-ordinated Enlarged toilet details and Wall Elevation L20 BTR 1 of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4061 | Co-ordinated Enlarged toilet details and Wall Elevation L20 BTR 2 of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4071 | Co-ordinated Enlarged toilet details and Wall Elevation L20 BTR 3 of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4081 | Co-ordinated Enlarged toilet details and Wall Elevation L20 BTR 4 of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4091 | Co-ordinated Enlarged L20 Maids Toilet Plumbing details and Wall Elevation of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4101 | Co-ordinated Enlarged L20 Dry Kitchen Plumbing details and Wall Elevation of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4101 | Co-ordinated Enlarged L20 Wet Kitchen Plumbing details and Wall Elevation of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4111 | Co-ordinated Enlarged L20 Utility Plumbing details and Wall Elevation of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4111 | Co-ordinated Enlarged L20 Pantry Plumbing details and Wall Elevation of T8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 1015 | Co-ordinated Typical L20 Sleeves Layout VRV Option- Tower 8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 1017 | Co-ordinated Typical L20 Sleeves Layout Split Option- Tower 8 | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
HOME AUTOMATION
| HA | T08 | 1001 | L20 Home Automation Layout | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| HA | T08 | 9001 | L20 Client Specification Sheet | L20 | L20-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
D35-1 | D35 Default and it's variants
PLUMBING
TOILET DETAILS & WALL ELEVATIONS
| PHE | T08 | 4051 | Enlarged toilet details and Wall Elevation D35 BTR 1 of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4061 | Enlarged toilet details and Wall Elevation D35 BTR 2 of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4071 | Enlarged toilet details and Wall Elevation D35 BTR 3 of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4081 | Enlarged toilet details and Wall Elevation D35 BTR 4 of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4091 | Enlarged D35 Maids Toilet Plumbing details and Wall Elevation of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4101 | Enlarged D35 Dry Kitchen Plumbing details and Wall Elevation of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4105 | Enlarged D35 Wet Kitchen Plumbing details and Wall Elevation of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4111 | Enlarged D35 Utility Plumbing details and Wall Elevation of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 | 4115 | Enlarged D35 Powder Toilet Plumbing details and Wall Elevation of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| PHE | T08 |  | Heat Pump Layout | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| ELECTRICAL |  |  | Will be released in the floor level drawing | [5 empty] | 0 |  |  |  |  | 0
HVAC
| HVAC | T08 | 1AA1 | Typical D35 HVAC layout VRV Option- Tower 8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| HVAC | T08 | 1AA5 | Typical D35 HVAC layout Split Option- Tower 8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
COORDINATED DRAWING
| CO | T08 | 4051 | Co-ordinated Enlarged toilet details and Wall Elevation D35 BTR 1 of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4061 | Co-ordinated Enlarged toilet details and Wall Elevation D35 BTR 2 of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4071 | Co-ordinated Enlarged toilet details and Wall Elevation D35 BTR 3 of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4081 | Co-ordinated Enlarged toilet details and Wall Elevation D35 BTR 4 of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4091 | Co-ordinated Enlarged D35 Maids Toilet Plumbing details and Wall Elevation of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4101 | Co-ordinated Enlarged D35 Dry Kitchen Plumbing details and Wall Elevation of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4101 | Co-ordinated Enlarged D35 Wet Kitchen Plumbing details and Wall Elevation of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4111 | Co-ordinated Enlarged D35 Utility Plumbing details and Wall Elevation of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 4111 | Co-ordinated Enlarged D35 Pantry Plumbing details and Wall Elevation of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 1015 | Co-ordinated Typical D35 Sleeves Layout VRV Option- Tower 8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| CO | T08 | 1017 | Co-ordinated Typical D35 Sleeves Layout Split Option- Tower 8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
HOME AUTOMATION
| HA | T08 | 1001 | D35 Home Automation Layout | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
| HA | T08 | 9001 | D35 Client Specification Sheet | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 1
L22-1 | L22 Default and it's variants
PLUMBING
TOILET DETAILS & WALL ELEVATIONS
| PHE | T08 | 4051 | Enlarged toilet details and Wall Elevation L19 BTR 1 ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4061 | Enlarged toilet details and Wall Elevation L19 BTR 2 ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4071 | Enlarged toilet details and Wall Elevation L19 BTR 3 ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4081 | Enlarged toilet details and Wall Elevation L19 BTR 4 ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4091 | Enlarged L19 Maids Toilet Plumbing details and Wall Elevation ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4101 | Enlarged L19 Dry Kitchen Plumbing details and Wall Elevation ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4105 | Enlarged L19 Wet Kitchen Plumbing details and Wall Elevation ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4111 | Enlarged L19 Utility Plumbing details and Wall Elevation ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4115 | Enlarged L19 Powder Toilet Plumbing details and Wall Elevation of T8 | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 |  | Heat Pump Layout | D35 | D35-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1
| ELECTRICAL |  |  | Will be released in the floor level drawing
HVAC
| HVAC | T02V | 1AA1 | Typical L19 HVAC layout VRV Option- Tower 8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| HVAC | T02V | 1AA5 | Typical L19 HVAC layout Split Option- Tower 8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
COORDINATED DRAWING
| CO | T02V | 4051 | Co-ordinated Enlarged toilet details and Wall Elevation L19 BTR 1 ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T02V | 4061 | Co-ordinated Enlarged toilet details and Wall Elevation L19 BTR 2 ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T02V | 4071 | Co-ordinated Enlarged toilet details and Wall Elevation L19 BTR 3 ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T02V | 4081 | Co-ordinated Enlarged toilet details and Wall Elevation L19 BTR 4 ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T02V | 4091 | Co-ordinated Enlarged L19 Maids Toilet Plumbing details and Wall Elevation ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T02V | 4101 | Co-ordinated Enlarged L19 Dry Kitchen Plumbing details and Wall Elevation ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T02V | 4101 | Co-ordinated Enlarged L19 Wet Kitchen Plumbing details and Wall Elevation ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T02V | 4111 | Co-ordinated Enlarged L19 Utility Plumbing details and Wall Elevation ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T02V | 4111 | Co-ordinated Enlarged L19 Pantry Plumbing details and Wall Elevation ofT8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T02V | 1015 | Co-ordinated Typical L19 Sleeves Layout VRV Option- Tower 8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T02V | 1017 | Co-ordinated Typical L19 Sleeves Layout Split Option- Tower 8 | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
HOME AUTOMATION
| HA | T08 | 1001 | L22 Home Automation Layout | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
| HA | T08 | 9001 | L22 Client Specification Sheet | L22 | L22-1 | 1 |  |  | 1 |  |  | 1 |  | 1 |  |  |  | 1 | [24 empty] | 1
R25P-1 | R25 P Default and it's variants
PLUMBING
TOILET DETAILS & WALL ELEVATIONS
| PHE | T08 | 4011 | Enlarged toilet details and Wall Elevation Master Bath | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4012 | Enlarged toilet details and Wall Elevation Master Bath | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4021 | Enlarged toilet details and Wall Elevation Guest Bath | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4022 | Enlarged toilet details and Wall Elevation Guest Bath | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4031 | Enlarged toilet details and Wall Elevation Children's Bath | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4032 | Enlarged toilet details and Wall Elevation Children's Bath | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4071 | Enlarged Kitchen & Utility Plumbing details and Wall Elevation | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4072 | Enlarged Kitchen & Utility Plumbing details and Wall Elevation | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 | 4115 | Enlarged R25P Powder Toilet Plumbing details and Wall Elevation of T8 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| PHE | T08 |  | Heat Pump Layout | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1
| ELECTRICAL |  |  | Will be released in the floor level drawing
HVAC
| HVAC | T08 | 1AA1 | Typical Unit R25P HVAC layout | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
COORDINATED DRAWINGS
| CO | T08 | 4011 | Co-ordinated Enlarged toilet details and Wall Elevation BTR 1 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T08 | 4021 | Co-ordinated Enlarged toilet details and Wall Elevation BTR 2 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T08 | 4031 | Co-ordinated Enlarged toilet details and Wall Elevation BTR 3 | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| CO | T08 | 4071 | Co-ordinated Enlarged Kitchen & Utility Plumbing details and Wall Elevation | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
HOME AUTOMATION
| HA | R25P | 1001 | R25P Home Automation Layout | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
| HA | R25P | 9001 | R25P Client Specification Sheet | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 1 |  |  |  | 1 | [24 empty] | 1
L20P-1 | L20 P Default and it's variants
PLUMBING
TOILET DETAILS & WALL ELEVATIONS
| PHE | T08 | 4051 | Enlarged toilet details and Wall Elevation L20P BTR 1 of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4061 | Enlarged toilet details and Wall Elevation L20P BTR 2 of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4071 | Enlarged toilet details and Wall Elevation L20P BTR 3 of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4081 | Enlarged toilet details and Wall Elevation L20P BTR 4 of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4091 | Enlarged L20P Maids Toilet Plumbing details and Wall Elevation of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4101 | Enlarged L20P Dry Kitchen Plumbing details and Wall Elevation of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4105 | Enlarged L20P Wet Kitchen Plumbing details and Wall Elevation of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4111 | Enlarged L20P Utility Plumbing details and Wall Elevation of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4115 | Enlarged L20P Powder Toilet Plumbing details and Wall Elevation of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 |  | Heat Pump Layout | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0
| ELECTRICAL |  |  | Will be released in the floor level drawing | [5 empty] | 0 |  |  |  |  | 0
HVAC
| HVAC | T08 | 1AA1 | Typical L20P HVAC layout VRV Option- Tower 8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| HVAC | T08 | 1AA5 | Typical L20P HVAC layout Split Option- Tower 8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
COORDINATED DRAWING
| CO | T08 | 4051 | Co-ordinated Enlarged toilet details and Wall Elevation L20P BTR 1 of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4061 | Co-ordinated Enlarged toilet details and Wall Elevation L20P BTR 2 of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4071 | Co-ordinated Enlarged toilet details and Wall Elevation L20P BTR 3 of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4081 | Co-ordinated Enlarged toilet details and Wall Elevation L20P BTR 4 of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4091 | Co-ordinated Enlarged L20P Maids Toilet Plumbing details and Wall Elevation of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4101 | Co-ordinated Enlarged L20P Dry Kitchen Plumbing details and Wall Elevation of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4101 | Co-ordinated Enlarged L20P Wet Kitchen Plumbing details and Wall Elevation of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4111 | Co-ordinated Enlarged L20P Utility Plumbing details and Wall Elevation of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4111 | Co-ordinated Enlarged L20P Pantry Plumbing details and Wall Elevation of T8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 1015 | Co-ordinated Typical L20P Sleeves Layout VRV Option- Tower 8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 1017 | Co-ordinated Typical L20P Sleeves Layout Split Option- Tower 8 | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
HOME AUTOMATION
| HA | T08 | 1001 | L20P Home Automation Layout | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| HA | T08 | 9001 | L20P Client Specification Sheet | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
D35P-1 | D35 P Default and it's variants
PLUMBING
TOILET DETAILS & WALL ELEVATIONS
| PHE | T08 | 4051 | Enlarged toilet details and Wall Elevation D35P BTR 1 of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4061 | Enlarged toilet details and Wall Elevation D35P BTR 2 of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4071 | Enlarged toilet details and Wall Elevation D35P BTR 3 of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4081 | Enlarged toilet details and Wall Elevation D35P BTR 4 of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4091 | Enlarged D35P Maids Toilet Plumbing details and Wall Elevation of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4101 | Enlarged D35P Dry Kitchen Plumbing details and Wall Elevation of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4105 | Enlarged D35P Wet Kitchen Plumbing details and Wall Elevation of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4111 | Enlarged D35P Utility Plumbing details and Wall Elevation of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4115 | Enlarged D35P Powder Toilet Plumbing details and Wall Elevation of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 |  | Heat Pump Layout | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0
| ELECTRICAL |  |  | Will be released in the floor level drawing
HVAC
| HVAC | T08 | 1AA1 | Typical D35P HVAC layout VRV Option- Tower 8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| HVAC | T08 | 1AA5 | Typical D35P HVAC layout Split Option- Tower 8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
COORDINATED DRAWING
| CO | T08 | 4051 | Co-ordinated Enlarged toilet details and Wall Elevation D35P BTR 1 of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4061 | Co-ordinated Enlarged toilet details and Wall Elevation D35P BTR 2 of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4071 | Co-ordinated Enlarged toilet details and Wall Elevation D35P BTR 3 of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4081 | Co-ordinated Enlarged toilet details and Wall Elevation D35P BTR 4 of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4091 | Co-ordinated Enlarged D35P Maids Toilet Plumbing details and Wall Elevation of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4101 | Co-ordinated Enlarged D35P Dry Kitchen Plumbing details and Wall Elevation of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4101 | Co-ordinated Enlarged D35P Wet Kitchen Plumbing details and Wall Elevation of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4111 | Co-ordinated Enlarged D35P Utility Plumbing details and Wall Elevation of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 4111 | Co-ordinated Enlarged D35P Pantry Plumbing details and Wall Elevation of T8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 1015 | Co-ordinated Typical D35P Sleeves Layout VRV Option- Tower 8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T08 | 1017 | Co-ordinated Typical D35P Sleeves Layout Split Option- Tower 8 | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
HOME AUTOMATION
| HA | T08 | 1001 | D35P Home Automation Layout | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| HA | T08 | 9001 | D35P Client Specification Sheet | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
L22P-1 | L22 P Default and it's variants
PLUMBING
TOILET DETAILS & WALL ELEVATIONS
| PHE | T02V | 4051 | Enlarged toilet details and Wall Elevation L22P BTR 1 ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T02V | 4061 | Enlarged toilet details and Wall Elevation L22P BTR 2 ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T02V | 4071 | Enlarged toilet details and Wall Elevation L22P BTR 3 ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T02V | 4081 | Enlarged toilet details and Wall Elevation L22P BTR 4 ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T02V | 4091 | Enlarged L22P Maids Toilet Plumbing details and Wall Elevation ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T02V | 4101 | Enlarged L22P Dry Kitchen Plumbing details and Wall Elevation ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T02V | 4105 | Enlarged L22P Wet Kitchen Plumbing details and Wall Elevation ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T02V | 4111 | Enlarged L22P Utility Plumbing details and Wall Elevation ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 | 4115 | Enlarged L22P Powder Toilet Plumbing details and Wall Elevation of T8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| PHE | T08 |  | Heat Pump Layout | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0
| ELECTRICAL |  |  | Will be released in the floor level drawing
HVAC
| HVAC | T02V | 1AA1 | Typical L19 HVAC layout VRV Option- Tower 8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| HVAC | T02V | 1AA5 | Typical L19 HVAC layout Split Option- Tower 8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
COORDINATED DRAWING
| CO | T02V | 4051 | Co-ordinated Enlarged toilet details and Wall Elevation L19 BTR 1 ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T02V | 4061 | Co-ordinated Enlarged toilet details and Wall Elevation L19 BTR 2 ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T02V | 4071 | Co-ordinated Enlarged toilet details and Wall Elevation L19 BTR 3 ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T02V | 4081 | Co-ordinated Enlarged toilet details and Wall Elevation L19 BTR 4 ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T02V | 4091 | Co-ordinated Enlarged L19 Maids Toilet Plumbing details and Wall Elevation ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T02V | 4101 | Co-ordinated Enlarged L19 Dry Kitchen Plumbing details and Wall Elevation ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T02V | 4101 | Co-ordinated Enlarged L19 Wet Kitchen Plumbing details and Wall Elevation ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T02V | 4111 | Co-ordinated Enlarged L19 Utility Plumbing details and Wall Elevation ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T02V | 4111 | Co-ordinated Enlarged L19 Pantry Plumbing details and Wall Elevation ofT8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T02V | 1015 | Co-ordinated Typical L19 Sleeves Layout VRV Option- Tower 8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| CO | T02V | 1017 | Co-ordinated Typical L19 Sleeves Layout Split Option- Tower 8 | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
HOME AUTOMATION
| HA | T08 | 1001 | L22P Home Automation Layout | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| HA | T08 | 9001 | L22P Client Specification Sheet | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
Master Plan | [43 empty] | Batch
MP-1 | Master Plan
| HVAC | T08 | 1005 | Podium level Mechanical ventilation layout | MP | MP-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| PHE | T08 |  | Site Plan -PHE -Spatial Requirements | MP | MP-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| FPS | T08 |  | Site Plan -FIRE -Spatial Requirements | MP | MP-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| ELE | T08 | GN01 | Electrical Standard Notes | MP | MP-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| ELE | T08 | 0003 | Site plan- External cable routing layout | MP | MP-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| ELE | T08 | 0004 | Site plan- External cable routing layout -Section | MP | MP-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| ELE | T08 | 0005 | Site plan- Earthing layout | MP | MP-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| ELE | T08 | 0006 | Site plan- Earthing Scheme | MP | MP-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| ELE | T08 | 0007 | External & Street lighting layout | MP | MP-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| ELE | T08 | 0008 | Main single line diagram-Sheet-1 | MP | MP-1 | 1 |  |  | 1 |  |  | 1 |  | 0
| PHE | T08 |  | Site Plan -PHE CO-ordinated services [water supply, sewerage and rain water disposal] | MP | MP-1 | 1 |  |  | 1 |  |  |  | 1 | 0
| FPS | T08 |  | Site Plan -FIRE CO-ordinated services | MP | MP-1 | 1 |  |  | 1 |  |  |  | 1 | 0
| PHE | T08 |  | Site Plan -MEP CO-ordinated services | MP | MP-1 | 1 |  |  | 1 |  |  |  | 1 | 0
MP-3 | Site MEP
| ELE | T08 | 0009 | Main single line diagram-Sheet-2 | MP | MP-3 | 3 |  |  | 1 |  |  |  | 1 | 0
| ELE | T08 | 0001 | Site plan- Transformer &DG yard layout | MP | MP-3 | 3 |  |  | 1 |  |  |  | 1 | 0
| ELE | T08 | 0002 | Site plan- Transformer &DG yard layout -Section | MP | MP-3 | 3 |  |  | 1 |  |  |  | 1 | 0
| ELE | T08 | 0010 | Main single line diagram-Sheet-3 | MP | MP-3 | 3 |  |  | 1 |  |  |  | 1 | 0
| PHE | T08 |  | STP Sump Plan and Sectional Detail | MP | MP-3 | 3 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 3
| ELE | T08 | 1014 | STP Cable tray routing layout | MP | MP-3 | 3 |  |  | 1 |  |  |  | 1 | 0
| ELE | T08 | 1015 | UGT Cable tray routing layout | MP | MP-3 | 3 |  |  | 1 |  |  |  | 1 | 0
| HVAC | T08 | 1014 | STP Mechanical Ventilation | MP | MP-3 | 3 |  |  | 1 |  |  |  | 1 | 0
| HVAC | T08 | 1015 | UGT Mechanical Ventilation | MP | MP-3 | 3 |  |  | 1 |  |  |  | 1 | 0
Amenities & Facilities | [43 empty] | Batch
AM-2 | Clubhouse—Interiors and Facilities
| PHE | CH | 4011 | Enlarged toilet details and Wall Elevation Pool Male | AM | AM-2 | 2 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 2
| PHE | CH | 4021 | Enlarged toilet details and Wall Elevation Pool Female | AM | AM-2 | 2 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 2
| PHE | CH | 4031 | Enlarged toilet details and Wall Elevation Pool Handicap | AM | AM-2 | 2 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 2
| PHE | CH | 4041 | Enlarged toilet details and Wall Elevation Male Washroom | AM | AM-2 | 2 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 2
| PHE | CH | 4051 | Enlarged toilet details and Wall Elevation Female Washroom | AM | AM-2 | 2 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 2
| PHE | CH | 4061 | Enlarged toilet details and Wall Elevation Handicap Washroom | AM | AM-2 | 2 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 2
| PHE | CH | 4071 | Enlarged toilet details and Wall Elevation Green Room | AM | AM-2 | 2 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 2
AM-3 | Clubhouse—Outdoor Spaces and Pool
|  |  |  | Clubhouse—Outdoor Spaces and Pool | AM | AM-3 | 3 |  |  | 1 |  |  | 1 |  | 0
AM-5 | Sporting Facilities
|  |  |  | Sporting Facilities | AM | AM-5 | 5 |  |  | 1 |  |  |  | 1 | 0
Note on E466: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: TBD by Kamal

## LS ¦ Drawing List
[7 empty] | ITD23 |  | P23 | 1 | 2 | 3 | 4 | A23 | 5 | 6 | 7 | 8 | ITD24 |  | P24 | 9 | 10 | 11 | 12 | A24 | 13 | 14 | 15 | 16 | ITD25 |  | P25 | 17 | 18 | 19 | 20 | A25 | 21 | 22 | 23 | 24
0059 ¦ Pursuit of a Radical Rhapsody |  |  |  | Location | Batch Code | Batch | Issued till Dec 23 | Revision | Plan in FY 24 |  |  |  |  | Issued in FY 24 |  |  |  |  | Issued till Dec 24 | Revision | Plan in FY 25 |  |  |  |  | Issued in FY 25 |  |  |  |  | Issued till Dec 25 | Revision | Plan in FY 26 |  |  |  |  | Issued in FY 26
LS ¦ DRAWING LIST | [9 empty] | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  |  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 |  |  |  | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4
19:44
GFC ¦ Individual Homes
R25-1 | R25 Default and it's variants
| LS | R25 | PLANTING & MATERIAL PLAN | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| LS | R25 | SETTING OUT PLAN | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| LS | R25 | LEVELS & DRAINAGE PLAN | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| LS | R25 | SUB SURFACE DRAINAGE PLAN | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| LS | R25 | LIGHTING PLAN | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| LS | R25 | IRRIGATION PLAN | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| LS | R25 | SECTIONS | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| LS | R25 | DETAILS | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| LS | R25 | GRAB BAR DETAILS | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
| LS | R25 | ELECTRO MECHANICAL LAYOUT | R25 | R25-1 | 1 | 1 |  | 0 |  |  |  |  | 0 | [28 empty] | 1
L20-1 | L20 Default and it's variants
| LS | L20 | PLANTING & MATERIAL PLAN | L20 | L20-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | L20 | SETTING OUT PLAN | L20 | L20-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | L20 | LEVELS & DRAINAGE PLAN | L20 | L20-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | L20 | SUB SURFACE DRAINAGE PLAN | L20 | L20-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | L20 | LIGHTING PLAN | L20 | L20-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | L20 | IRRIGATION PLAN | L20 | L20-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | L20 | SECTIONS | L20 | L20-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | L20 | DETAILS | L20 | L20-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
D35-1 | D35 Default and it's variants
| LS | D35 | PLANTING & MATERIAL PLAN | D35 | D35-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | D35 | SETTING OUT PLAN | D35 | D35-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | D35 | LEVELS & DRAINAGE PLAN | D35 | D35-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | D35 | SUB SURFACE DRAINAGE PLAN | D35 | D35-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | D35 | LIGHTING PLAN | D35 | D35-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | D35 | IRRIGATION PLAN | D35 | D35-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | D35 | SECTIONS | D35 | D35-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
| LS | D35 | DETAILS | D35 | D35-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  | 1 | [25 empty] | 1
L22-1 | L22 Default and it's variants
| LS | L22 | PLANTING & MATERIAL PLAN | L22 | L22-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | [24 empty] | 1
| LS | L22 | SETTING OUT PLAN | L22 | L22-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | [24 empty] | 1
| LS | L22 | LEVELS & DRAINAGE PLAN | L22 | L22-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | [24 empty] | 1
| LS | L22 | SUB SURFACE DRAINAGE PLAN | L22 | L22-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | [24 empty] | 1
| LS | L22 | LIGHTING PLAN | L22 | L22-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | [24 empty] | 1
| LS | L22 | IRRIGATION PLAN | L22 | L22-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | [24 empty] | 1
| LS | L22 | SECTIONS | L22 | L22-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | [24 empty] | 1
| LS | L22 | DETAILS | L22 | L22-1 | 1 |  |  | 1 | 1 |  |  |  | 1 |  |  |  | 1 | [24 empty] | 1
R25P-1 | R25 P Default and it's variants
| LS | R25P | PLANTING & MATERIAL PLAN | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | R25P | SETTING OUT PLAN | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | R25P | LEVELS & DRAINAGE PLAN | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | R25P | SUB SURFACE DRAINAGE PLAN | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | R25P | LIGHTING PLAN | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | R25P | IRRIGATION PLAN | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | R25P | SECTIONS | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | R25P | DETAILS | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | R25P | GRAB BAR DETAILS | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | R25P | ELECTRO MECHANICAL LAYOUT | R25P | R25P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
L20P-1 | L20 P Default and it's variants
| LS | L20P | PLANTING & MATERIAL PLAN | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L20P | SETTING OUT PLAN | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L20P | LEVELS & DRAINAGE PLAN | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L20P | SUB SURFACE DRAINAGE PLAN | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L20P | LIGHTING PLAN | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L20P | IRRIGATION PLAN | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L20P | SECTIONS | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L20P | DETAILS | L20P | L20P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
D35P-1 | D35 P Default and it's variants
| LS | D35P | PLANTING & MATERIAL PLAN | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | D35P | SETTING OUT PLAN | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | D35P | LEVELS & DRAINAGE PLAN | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | D35P | SUB SURFACE DRAINAGE PLAN | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | D35P | LIGHTING PLAN | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | D35P | IRRIGATION PLAN | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | D35P | SECTIONS | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | D35P | DETAILS | D35P | D35P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
L22P-1 | L22 P Default and it's variants
| LS | L22P | PLANTING & MATERIAL PLAN | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L22P | SETTING OUT PLAN | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L22P | LEVELS & DRAINAGE PLAN | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L22P | SUB SURFACE DRAINAGE PLAN | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L22P | LIGHTING PLAN | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L22P | IRRIGATION PLAN | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L22P | SECTIONS | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
| LS | L22P | DETAILS | L22P | L22P-1 | 1 |  |  | 1 |  |  |  | 1 | 0 | [28 empty] | 1
GFC ¦ Master Plan
MP-1 | Master Plan
| LS | SITE | General arrangement Plan | MP | MP-1 | 1 |  |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| LS | SITE | Setting out plan | MP | MP-1 | 1 |  |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| LS | SITE | Drainage plan | MP | MP-1 | 1 |  |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| LS | SITE | Lighting plan | MP | MP-1 | 1 |  |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| LS | SITE | Material plan | MP | MP-1 | 1 |  |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
| LS | SITE | Shrubs planting plan | MP | MP-1 | 1 |  |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| LS | SITE | Irrigation plan | MP | MP-1 | 1 |  |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| LS | SITE | sections | MP | MP-1 | 1 |  |  | 1 | 1 |  |  |  | 0 | [28 empty] | 2
| LS | SITE | Details | MP | MP-1 | 1 |  |  | 1 | 1 |  |  |  | 0 | [28 empty] | 1
MP-4 | Landscaping
| LS | SITE | Grading Plan | MP | MP-4 | 4 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 9
| LS | SITE | Tree Planting plan | MP | MP-4 | 4 |  |  | 1 |  |  | 1 |  | 0 | [28 empty] | 9
| LS | SITE | Community spaces [Board Walk, Children play area] | MP | MP-4 | 4 |  |  | 1 |  |  | 1 |  | 0
GFC ¦ Amenities & Facilities
AM-2 | Clubhouse—Interiors and Facilities
| LS | CH | Planting & material plan | AM | AM-2 | 2 |  |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| LS | CH | Lighting plan | AM | AM-2 | 2 |  |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| LS | CH | Subsurface drainage plan | AM | AM-2 | 2 |  |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| LS | CH | Irrigation plan | AM | AM-2 | 2 |  |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
| LS | CH | Sections & Details | AM | AM-2 | 2 |  |  | 1 |  | 1 |  |  | 0 | [28 empty] | 2
AM-3 | Clubhouse—Outdoor Spaces and Pool
| LS | CH | Levels & drainage plan | AM | AM-3 | 3 |  |  | 1 |  | 1 |  |  | 0 | [28 empty] | 3
| LS | CH | Swimming pool electromechanical drawings | AM | AM-3 | 3 |  |  | 1 |  | 1 |  |  | 0 | [28 empty] | 3
AM-4 | Community spaces [Board Walk, Children play area]
| LS | SITE | Community spaces [Board Walk, Children play area] | AM | AM-4 | 4 |  |  | 1 |  |  | 1 |  | 0

## Batches Plan (hidden)
|  | Initial |  |  |  | Current
|  | Ar | St | MEP | LDS | Ar | St | MEP | LDS
1 | GFC ¦ Tower—08
1 | Foundation and Grade Slab | Q1 | Q2 | Q1 | Q1 | Q1 | Q2 |  |  | foundation and columns upto roof |  | update framing plans and loads as per intent | Loading &framing signoff by March 31st
2 | Parking Level-Sub grade | Q2 | Q3 | Q2 | Q2 | Q2 | Q3 |  |  | ssl1,2,3 | subgrade | share framing plans for signoff by first week of April | confirmation on framing plans - approval latest by April end
3 | Building Envelope and Common Areas [Basement] | Q2 | Q4 | Q2 | Q2 |  | Q4 |  |  | ssl4 | stilit - common area | share framing plans for signoff by first week of April | confirmation on framing plans - approval latest by April end
4 | Habitable Level 01 | Q3 | Q4 | Q3 | Q3 |  | Q4 |  |  | ssl5 | habitable level 1 | share framing plans for signoff by first week of April | confirmation on framing plans - approval latest by April end
5 | Habitable Level - Even | Q3 | 24 Q1 | Q3 | Q3 |  | 24 Q1 |  |  | ssl6,8,10.. | even | share framing plans for signoff by first week of April | confirmation on framing plans - approval latest by April end
6 | Habitable Level - Odd | Q4 | 24 Q1 | Q4 | Q4 |  | 24 Q1 |  |  | ssl7,9,11.. | odd | share framing plans for signoff by first week of April | confirmation on framing plans - approval latest by April end
7 | Building Envelope and Common Areas [Typical Tower Levels] | Q4 |  | Q4 | Q4
8 | Penthouse Levels | Q4 | 24 Q2 | Q4 | Q4 |  | 24 Q2 |  |  | ssl37 |  | consider typical level framing but customization loads for penthouse lower and upper levels
9 | Terrace Level | 24 Q1 | 24 Q2 | 24 Q1 | 24 Q1 |  | 24 Q2 |  |  | ssl38,OHT |  | consider OHT, lift services - areas shown_framing typical
10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 24 Q1 |  | 24 Q1 | 24 Q1
2 | GFC ¦ Independent Subgrade Structure - Tower 8
1 | Earthwork | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2
2 | Foundations & Grade Slab | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2 | Q2
3 | Podium Slab | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3
4 | Building Envelope and Common Areas | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4
2.1 | GFC ¦ Independent Subgrade Structure—Block 01
1 | Foundations & Grade Slab |  | Q3 |  |  |  | Q3
2 | Podium Slab |  | Q4 |  |  |  | Q4
3 | GFC ¦ Individual Homes
1 | R25 Default and it's variants | Q1 |  | Q1 | Q1
2 | L20 Default and it's variants | Q2 |  | Q2 | Q2
3 | D35 Default and it's variants | Q3 |  | Q3 | Q3
4 | L22 Default and it's variants | Q4 |  | Q4 | Q4
4 | GFC ¦ Site Development
1 | Master Plan and Below Grade Structures | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3
2 | Boundary wall and Site Structures | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3 | Q3
3 | Roads and Pavements | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4
4 | Utility Structure—Power Supply and Backup | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4 | Q4
5 | Utility Structure—Water Supply and FPS | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1
6 | Utility Structure—Sewerage ¦ Wastewater | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1
7 | Utility Structure—Reticulated Gas | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2
8 | Utility Structure—Garbage Disposal ¦ OWC | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2
9 | Landscaping, Site Lighting and Signage | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2
5 | GFC ¦ Amenities & Facilities
1 | Clubhouse—Structure and Envelope | Q3 | Q3 | Q3 | Q3 | Q2 | Q2 | Q2 | Q2
2 | Clubhouse—Interiors and Facilities | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | Q3 | Q3 | Q3 | Q3
3 | Clubhouse—Outdoor Spaces and Pool | 24 Q2 | 24 Q2 | 24 Q2 | 24 Q2 | Q3 | Q3 | Q3 | Q3
4 | Community spaces [Board Walk, Children play area] | 24 Q3 | 24 Q3 | 24 Q3 | 24 Q3 | Q4 | Q4 | Q4 | Q4
5 | Sporting Facilities | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1 | 24 Q1

## BOQ COST
| AR | ST | SR | LS
Total | 457.8 | 206.318 | 81.7911 | 4.0936
GFC ¦ Parking(8) | 81.8 | 71.844 | 5.516 |  |  | T8 Built up area | 1059284 | sqft
GFC ¦ Tower1 | 0 | 0 | 0 | 0
GFC ¦ Tower2 | 0 | 0 | 0 | 0
GFC ¦ Tower3 | 0 | 0 | 0 | 0
GFC ¦ Tower4 | 0 | 0 | 0 | 0
GFC ¦ Tower5 | 0 | 0 | 0 | 0
GFC ¦ Tower6 | 0 | 0 | 0 | 0
GFC ¦ Tower7 |  | 0 | 0 | 0
GFC ¦ Tower8 | 192.77 | 132.734 | 28.58 | 0.01 |  | T8 Site Area | 201690.966 | sqft
GFC ¦ Villas | 0 | 0 | 0 | 0
GFC ¦ Individual Homes | 167.11 |  | 35.0861 | 0.13734 |  | Site Dev rate | 160.52
GFC ¦ Site Development and Site Services | 13.96 | 1.74 | 12.22 | 1.1634 |  | Service rate | 63.61
GFC ¦ Amenities & Facilities | 2.16 |  | 0.389 | 2.7828 |  | Aminities Rate | 4755
Check | [8 empty] | [16:16] Pragati Prasoon
| 22.89 | 6.1895 | 1.6358 | 0.28655 | From Residential sheet Percentage wise
| 22.89 | 6.1895 | 1.6358 | 0.28616 |  | ST | SR | LS | 1.General arrangement Plan | 1 | General arrangement Plan
| 0 | 0 | 0 | 0.000385 | SD & SS | 0.40538 | 0.68468 | 0.18919 |  | #VALUE!
[5 empty] | A&F | 0.24616 | 0.68468 | 0.12865 | 2.Setting out plan | 2 | Setting out plan
[5 empty] | Ind Homes |  | 0.20996 | 0.0024272 |  | #VALUE!
[9 empty] | 3.Grading Plan | 3 | Grading Plan
#VALUE!
[9 empty] | 4.Drainage plan | 4 | Drainage plan
#VALUE!
[9 empty] | 5.Lighting plan | 5 | Lighting plan
#VALUE!
[9 empty] | 6.Material plan | 6 | Material plan
#VALUE!
[9 empty] | 7.Tree Planting plan | 7 | Tree Planting plan
#VALUE!
[9 empty] | 8.Shrubs planting plan | 8 | Shrubs planting plan
#VALUE!
[9 empty] | 9.Irrigation plan | 9 | Irrigation plan
#VALUE!
[9 empty] | 10.sections | 10 | sections
#VALUE!
[9 empty] | 11.Details | 11 | Details

## old LS (hidden)
0059 ¦ Pursuit of a Radical Rhapsody |  |  |  | Location | Batch Code | Batch | Issue Status |  | Plan in FY: 21-22 | [12 empty] | Issued in FY: 21-22
LS ¦ DRAWING LIST | [6 empty] | Till Mar'21 | Revision |  | Apr-21 | May-21 | Jun-21 | Jul-21 | Aug-21 | Sep-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22 | Feb-22 | Mar - 21 |  | Apr-21 | May-21 | Jun-21 | Jul-21 | Aug-21 | Sep-21 | Oct-21 | Nov-21 | Dec-21 | Jan-22 | Feb-22 | Mar - 21
Tower—01 |  |  |  | Location | Batch Code | Batch
| LS | T1 | IRRIGATION WATER SUPPLY SCHEMATIC - T1 | T01 | LS-T01-4 | 4 | 1
Tower—2V |  |  |  | Location | Batch Code | Batch
| LS | T2V | IRRIGATION WATER SUPPLY SCHEMATIC - T2 | T2V | LS-T2V-4 | 4 | 1
Tower—2S |  |  |  | Location | Batch Code | Batch
| LS | T2S | IRRIGATION WATER SUPPLY SCHEMATIC - T2S | T2S | LS-T2S-4 | 4 | 1
| LS | T2S | PLANTING PLAN | T2S | LS-T2S-4 | 4 | 1
| LS | T2S | SETTING OUT PLAN | T2S | LS-T2S-4 | 4 | 1
| LS | T2S | LEVELS & DRAINAGE PLAN | T2S | LS-T2S-4 | 4 | 1
| LS | T2S | SECTIONS 01 | T2S | LS-T2S-4 | 4 | 1
| LS | T2S | SECTIONS 02 | T2S | LS-T2S-4 | 4 | 1
| LS | T2S | DETAILS | T2S | LS-T2S-4 | 4 | 1
| LS | T2S | LIGHTING PLAN | T2S | LS-T2S-4 | 4 | 1
| LS | T2S | IRRIGATION PLAN | T2S | LS-T2S-4 | 4 | 1
| LS | T2S | GRAB BAR DETAILS | T2S | LS-T2S-4 | 4 | 1
| LS | T2S | ELECTRO MECHANICAL LAYOUT | T2S | LS-T2S-4 | 4 | 1
Tower—3V-5V |  |  |  | Location | Batch Code | Batch
| LS | T3V | IRRIGATION WATER SUPPLY SCHEMATIC - T3V-5V | TXV | LS-TXV-4 | 4 |  |  | 1
Tower—3S-5S |  |  |  | Location | Batch Code | Batch
| LS | T3S | IRRIGATION WATER SUPPLY SCHEMATIC - T3S-5S | TXS | LS-TXS-4 | 4 |  |  | 1
| LS | T3S | PLANTING PLAN | TXS | LS-TXS-4 | 4 |  |  | 1
| LS | T3S | SETTING OUT PLAN | TXS | LS-TXS-4 | 4 |  |  | 1
| LS | T3S | LEVELS & DRAINAGE PLAN | TXS | LS-TXS-4 | 4 |  |  | 1
| LS | T3S | SECTIONS 01 | TXS | LS-TXS-4 | 4 |  |  | 1
| LS | T3S | SECTIONS 02 | TXS | LS-TXS-4 | 4 |  |  | 1
| LS | T3S | DETAILS | TXS | LS-TXS-4 | 4 |  |  | 1
| LS | T3S | LIGHTING PLAN | TXS | LS-TXS-4 | 4 |  |  | 1
| LS | T3S | IRRIGATION PLAN | TXS | LS-TXS-4 | 4 |  |  | 1
| LS | T3S | GRAB BAR DETAILS | TXS | LS-TXS-4 | 4 |  |  | 1
| LS | T3S | ELECTRO MECHANICAL LAYOUT | TXS | LS-TXS-4 | 4
Tower—6V |  |  |  | Location | Batch Code | Batch
| LS | T6V | IRRIGATION WATER SUPPLY SCHEMATIC - T6 | T6V | LS-T6V-4 | 4 | 1
Tower—6S |  |  |  | Location | Batch Code | Batch
| LS | T6S | IRRIGATION WATER SUPPLY SCHEMATIC - T6S | T6S | LS-T6S-4 | 4 |  |  | 1
| LS | T6S | PLANTING PLAN | T6S | LS-T6S-4 | 4 |  |  | 1
| LS | T6S | SETTING OUT PLAN | T6S | LS-T6S-4 | 4 |  |  | 1
| LS | T6S | LEVELS & DRAINAGE PLAN | T6S | LS-T6S-4 | 4 |  |  | 1
| LS | T6S | SECTIONS 01 | T6S | LS-T6S-4 | 4 |  |  | 1
| LS | T6S | SECTIONS 02 | T6S | LS-T6S-4 | 4 |  |  | 1
| LS | T6S | DETAILS | T6S | LS-T6S-4 | 4 |  |  | 1
| LS | T6S | LIGHTING PLAN | T6S | LS-T6S-4 | 4 |  |  | 1
| LS | T6S | IRRIGATION PLAN | T6S | LS-T6S-4 | 4 |  |  | 1
| LS | T6S | GRAB BAR DETAILS | T6S | LS-T6S-4 | 4 |  |  | 1
| LS | T6S | ELECTRO MECHANICAL LAYOUT | T6S | LS-T6S-4 | 4 |  |  | 1
Tower—07 |  |  |  | Location | Batch Code | Batch
| LS | T7 | IRRIGATION WATER SUPPLY SCHEMATIC - T7 | T07 | LS-T07-4 | 4 | 1
Tower—08 |  |  |  | Location | Batch Code | Batch
| LS | T8 | IRRIGATION WATER SUPPLY SCHEMATIC - T1 | T08 | LS-T08-4 | 4 | 1
Tower—09 [Commercial] |  |  |  | Location | Batch Code | Batch
| LS | T9 | IRRIGATION WATER SUPPLY SCHEMATIC - T9 | T09 | LS-T09-4 | 4 |  |  | 1
Villa Block - Cluster 1 & 2
| LS | VO1 | PLANTING PLAN | V01 | LS-V01-3 | 3 |  |  | 1
| LS | VO1 | SETTING OUT PLAN | V01 | LS-V01-3 | 3 |  |  | 1
| LS | VO1 | LEVELS & DRAINAGE PLAN | V01 | LS-V01-3 | 3 |  |  | 1
| LS | VO1 | SECTIONS 01 | V01 | LS-V01-3 | 3 |  |  | 1
| LS | VO1 | SECTIONS 02 | V01 | LS-V01-3 | 3 |  |  | 1
| LS | VO1 | DETAILS | V01 | LS-V01-3 | 3 |  |  | 1
| LS | VO1 | LIGHTING PLAN | V01 | LS-V01-3 | 3 |  |  | 1
| LS | VO1 | IRRIGATION PLAN | V01 | LS-V01-3 | 3 |  |  | 1
| LS | VO1 | ELECTRO MECHANICAL LAYOUT | V01 | LS-V01-3 | 3 |  |  | 1
Villa Block - Cluster 3
| LS | VO1 | PLANTING PLAN | V03 | LS-V03-3 | 3 |  |  | 1
| LS | VO1 | SETTING OUT PLAN | V03 | LS-V03-3 | 3 |  |  | 1
| LS | VO1 | LEVELS & DRAINAGE PLAN | V03 | LS-V03-3 | 3 |  |  | 1
| LS | VO1 | SECTIONS 01 | V03 | LS-V03-3 | 3 |  |  | 1
| LS | VO1 | SECTIONS 02 | V03 | LS-V03-3 | 3 |  |  | 1
| LS | VO1 | DETAILS | V03 | LS-V03-3 | 3 |  |  | 1
| LS | VO1 | LIGHTING PLAN | V03 | LS-V03-3 | 3 |  |  | 1
| LS | VO1 | IRRIGATION PLAN | V03 | LS-V03-3 | 3 |  |  | 1
| LS | VO1 | ELECTRO MECHANICAL LAYOUT | V03 | LS-V03-3 | 3 |  |  | 1
Individual Homes |  |  |  | Location | Batch Code | Batch
Individual Home V50
| LS | V50 | PLANTING PLAN | V50 | LS-V50-1 | 1 | 1
| LS | V50 | SETTING OUT PLAN | V50 | LS-V50-1 | 1 | 1
| LS | V50 | LEVELS & DRAINAGE PLAN | V50 | LS-V50-1 | 1 | 1
| LS | V50 | SECTIONS 01 | V50 | LS-V50-1 | 1 | 1
| LS | V50 | SECTIONS 02 | V50 | LS-V50-1 | 1 | 1
| LS | V50 | DETAILS | V50 | LS-V50-1 | 1 | 1
| LS | V50 | LIGHTING PLAN | V50 | LS-V50-1 | 1 | 1
| LS | V50 | IRRIGATION PLAN | V50 | LS-V50-1 | 1 | 1
| LS | V50 | GRAB BAR DETAILS | V50 | LS-V50-1 | 1 | 1
| LS | V50 | ELECTRO MECHANICAL LAYOUT | V50 | LS-V50-1 | 1 | 1
Individual Home L30
| LS | L30 | PLANTING PLAN | L30 | LS-L30-1 | 1 | 1
| LS | L30 | SETTING OUT PLAN | L30 | LS-L30-1 | 1 | 1
| LS | L30 | LEVELS & DRAINAGE PLAN | L30 | LS-L30-1 | 1 | 1
| LS | L30 | SECTIONS 01 | L30 | LS-L30-1 | 1 | 1
| LS | L30 | SECTIONS 02 | L30 | LS-L30-1 | 1 | 1
| LS | L30 | DETAILS | L30 | LS-L30-1 | 1 | 1
| LS | L30 | LIGHTING PLAN | L30 | LS-L30-1 | 1 | 1
| LS | L30 | IRRIGATION PLAN | L30 | LS-L30-1 | 1 | 1
Individual Home V40
| LS | V40 | PLANTING PLAN | V40 | LS-V40-1 | 1 |  |  | 1
| LS | V40 | SETTING OUT PLAN | V40 | LS-V40-1 | 1 |  |  | 1
| LS | V40 | LEVELS & DRAINAGE PLAN | V40 | LS-V40-1 | 1 |  |  | 1
| LS | V40 | SECTIONS 01 | V40 | LS-V40-1 | 1 |  |  | 1
| LS | V40 | SECTIONS 02 | V40 | LS-V40-1 | 1 |  |  | 1
| LS | V40 | DETAILS | V40 | LS-V40-1 | 1 |  |  | 1
| LS | V40 | LIGHTING PLAN | V40 | LS-V40-1 | 1 |  |  | 1
| LS | V40 | IRRIGATION PLAN | V40 | LS-V40-1 | 1 |  |  | 1
Individual Home C20
| LS | C20 | PLANTING PLAN | C20 | LS-C20-1 | 1 | 1
| LS | C20 | SETTING OUT PLAN | C20 | LS-C20-1 | 1 | 1
| LS | C20 | LEVELS & DRAINAGE PLAN | C20 | LS-C20-1 | 1 | 1
| LS | C20 | SECTIONS 01 | C20 | LS-C20-1 | 1 | 1
| LS | C20 | SECTIONS 02 | C20 | LS-C20-1 | 1 | 1
| LS | C20 | LIGHTING PLAN | C20 | LS-C20-1 | 1 | 1
| LS | C20 | IRRIGATION PLAN | C20 | LS-C20-1 | 1 | 1
Individual Home L45
| LS | L45 | PLANTING PLAN | L45 | LS-L45-1 | 1 |  |  | 1
| LS | L45 | SETTING OUT PLAN | L45 | LS-L45-1 | 1 |  |  | 1
| LS | L45 | LEVELS & DRAINAGE PLAN | L45 | LS-L45-1 | 1 |  |  | 1
| LS | L45 | SECTIONS 01 | L45 | LS-L45-1 | 1 |  |  | 1
| LS | L45 | SECTIONS 02 | L45 | LS-L45-1 | 1 |  |  | 1
| LS | L45 | DETAILS | L45 | LS-L45-1 | 1 |  |  | 1
| LS | L45 | LIGHTING PLAN | L45 | LS-L45-1 | 1 |  |  | 1
| LS | L45 | IRRIGATION PLAN | L45 | LS-L45-1 | 1 |  |  | 1
Site Development |  |  |  | Location | Batch Code | Batch
| LS | SITE | LANDSCAPE DEVELOPMENT PLAN | SDV | LS-SDV-1 | 1 |  |  | 1
| LS | SITE | PLANTING PLAN | SDV | LS-SDV-2 | 2 |  |  | 1
| LS | SITE | SETTING OUT PLAN | SDV | LS-SDV-1 | 1 |  |  | 1
| LS | SITE | HARDSCAPE LAYOUT – IF REQUIRED | SDV | LS-SDV-2 | 2 |  |  | 1
| LS | SITE | LEVELS & DRAINAGE PLAN | SDV | LS-SDV-2 | 2 |  |  | 1
| LS | SITE | SECTIONS 01 | SDV | LS-SDV-1 | 1 |  |  | 1
| LS | SITE | SECTIONS 02 | SDV | LS-SDV-1 | 1 |  |  | 1
| LS | SITE | SECTIONS 03 | SDV | LS-SDV-1 | 1 |  |  | 1
| LS | SITE | DETAILS | SDV | LS-SDV-9 | 9 |  |  | 1
| LS | SITE | LIGHTING PLAN | SDV | LS-SDV-9 | 9 |  |  | 1
| LS | SITE | IRRIGATION PLAN | SDV | LS-SDV-2 | 2 |  |  | 1
| LS | SITE | PROJECT ENTRANCE | SDV | LS-SDV-9 | 9 |  |  | 1
| LS | SITE | TEMPORARY ENTRANCE | SDV | LS-SDV-9 | 9 |  |  | 1
Amenities & Facilities |  |  |  | Location | Batch Code | Batch
| LS | CH | CLUB HOUSE LANDSCAPE LAYOUT—ALL LEVELS | AMN | LS-AMN-2 | 2 |  |  | 1
| LS | CH | CLUB HOUSE LANDSCAPE LAYOUT—ROOF LEVEL | AMN | LS-AMN-2 | 2 |  |  | 1
| LS | CH | CLUB HOUSE LANDSCAPE LAYOUT—COMMON AREA | AMN | LS-AMN-3 | 3 |  |  | 1
| LS | AMN | CENTRAL GREEN AREA LAYOUT | AMN | LS-AMN-4 | 4 |  |  | 1
| LS | AMN | CHILDREN'S PLAY AREA LAYOUT | AMN | LS-AMN-4 | 4 |  |  | 1
| LS | AMN | DOG PARK | AMN | LS-AMN-4 | 4 |  |  | 1
| LS | AMN | BOARD WALK | AMN | LS-AMN-4 | 4 |  |  | 1

## Sheet1 (hidden)
Architecture
Indpendent 1 to 7
Remaining drawings (All batches) | June and July
Indpendent 9
Batch 5 details are remaining | Sept
Tower 1
Batch 8,9 & 10 | June
Tower 2V
Batch 7(Some drawings) | July
Batch 8 | June
Batch 9 & 10 | July
Tower 2s
Batch 5 & 6 | August
Batch 7 | Sept
batch 8 | Oct
batch 9 & 10 | Nov
Villa Cluster 3
Batch 1 | Sep
Batch 2 & 3 | Oct
Commercial
Batch 7 | Aug & Sep
Batch 8 | Dec