## Summary
# | Package | Drawing / Detail | Package | Resposible | Closure Date | Dependency on | Department | Dependency Closure Date | Revision | Nature of work | Status - 17th Feb
STRUCTURES
Lincy R
1 |  | T09 - HDFC Strong Room | T09 | Lincy R | Released |  |  |  | R0 | New - Unplanned - Strengthening | Structural GFC drawings to be issued by EOD.
2 |  | T09 - Learning age & Saloon | T09 | Lincy R |  | Vishnu | ARCH |  | R0 | New - Unplanned - Steel mezzanine | more Details requested - feasiblity communicated
3 |  | T09 - ODU support details | T09 | Lincy R | Released |  |  |  | R0 | New - Unplanned - Steel | Details sent to arch - new intent received
4 |  | T08 - SSL05 Sleeve details | Res - Rev | Lincy R | Released |  |  |  | R1 | Revision - Design changes | Structural reinforcement detailing work in progress
5 |  | T08 - Penthouse level details | T08-Penthouse | Lincy R |  | Vivek | ARCH |  | R0 | New - planned | Framing plan approval awaited. Services details pending
6 |  | T08 - ISS - UGT & STP | ISS-Foundation | Lincy R |  | Vivek | ARCH |  | R0 | New - planned | Layout coordination in progress
7 |  | Amenities - Changing room details | Res New Main Pool | Lincy R |  |  |  |  | R0 | New - unplanned | Design of SSL1 and SSL2 reinf in progress
8 |  | T2V - T6V - Double height parking cover details | Res - Rev | Lincy R |  | Latha | ARCH | 2026-02-20 | R0 | New - unplanned - Steel mezzanine | Design requirement to cover open parking spaces - feasiblity and details to be worked out
9 |  | Amenities - Heated pool | New Heated Pool | Lincy R |  |  |  |  | R0 | New - unplanned - Site constraints & Design requirements | New site constraints and requirements for sump tank and adjacent footing rework
10 |  | Site Development - Bollard | Res - Site Dev | Lincy R |  |  |  |  | R0 | New - planned | Details sent to arch for approval
11 |  | T2S - Services corecuts | Res - Rev | Lincy R |  | Arshad / Deepu | ARCH | 2026-02-20 | R0 | New - unplanned - Design (MEP) error | Feasiblity to be checked in floating beam supporting beams
12 |  | Amenities - Sports complex | Sports Complex | Lincy R |  | Sathwik | ARCH |  | R0 | New - planned | Coordination in progress
13 |  | V40 - Street light pole details | Res - Site Dev | Lincy R |  |  |  |  | R0 | New - unplanned | Details received from arch - details to be worked out
14 |  | T08 - typical level framing plan and sleeves revision | Res - Rev | Lincy R |  |  |  |  | R1 | Revision - Design changes | To be updated as per Mivan latest updates and services requirements. To be shared fpr approval on 18th Feb
15 |  | V50 - Railing above partition wall | Res - Site Dev | Lincy R |  |  |  |  | R0 | New - unplanned | Details sent to arch
16 |  | T09 - Staff Dining - Tensile roof | T09 | Lincy R |  |  |  |  | R0 | New - unplanned | Revised details to be reviewed - connections to be designed
17 |  | T3V - Theatre Design | Res - Rev | Lincy R |  |  |  |  | R0 | New - unplanned | More details requested - max load restrictions suggested
18 |  | L30 penthouse - Lift feasiblity | Res - Rev | Lincy R |  |  |  |  | R0 | New - unplanned | Load feasiblity check - to be done - details received
19 |  | Site Development - V40 side boundary wall | Res - Site Dev | Lincy R | 2026-02-27 |  |  |  | R0 | New - Planned | Updated levels received from arch
20 |  | Site Development - Clubhouse side - Boundary wall | Res - Rev | Lincy R |  |  |  |  | R3 | Revision - Site error | Masonry wall is done at site instead of RC wall (issued details not followed) - to be redone with RC as per site constraints
21 |  | Site Development - Transformer yard - Fencing | Res - Rev | Lincy R |  |  |  |  | R3 | Revision - Unplanned | Fencing of 3.6 m added - feasiblity and cast in ancors communicated to arch
22 |  | T08 - SSL05 - Shaft closure details | T08 - Habitable level 1 | Lincy R |  |  |  |  | R0 | New - planned | Reinforcment details to be worked
23 |  | T08 - Concrete cube failures |  | Lincy R | Closed |  |  |  | NA | New - unplanned - site issue | All concrete members checked for reduced capacity
24 |  | V40 - Concrete cube failures |  | Lincy R | Closed |  |  |  | NA | New - unplanned - site issue | All concrete members checked for reduced capacity
25 |  | T08 - East boundary wall - Vaswani side | Res - Rev | Lincy R |  |  |  |  | NA | New - planned | Coordination and Geotech report to be reviewed
ARCHITECTURE
Sathwik
1 |  | Sports Complex | Sports Complex | Sathwik |  |  |  |  | R0 |  | Awaiting Structure Drawing
2 |  | Tennis Court | Sports Complex | Sathwik | 2026-02-28 |  |  |  | R0 |  | WIP
3 |  | OWC | OWC | Sathwik |  |  |  |  | R0 |  | We will pick up this if we dont get sports complex drawings
|  | GA PLAN |  | Sathwik
4 |  | Cul-De-Sac | Res - Rev | Sathwik | 2026-02-28 |  |  |  | R0 |  | WIP
5 |  | Villa 25 - Retaining Wall Detail | Res - Rev | Sathwik | 2026-03-07 |  |  |  | R0 |  | WIP
6 |  | PH-2 DG Yard - Revision | Res - Rev | Sathwik | 2026-03-06 |  |  |  | R1 |  | WIP
7 |  | T09 PHE Riser Logo | T09 | Sathwik | 18-Mar-26 20-Mar-26 |  |  |  | R0 |  | Logo intent to be shared to marketing team
8 |  | Site Signage Vendor coordination | Res - Rev | Sathwik |  |  |  |  | R0 |  | Received shop drawing from TEMC. After checking will be shared to Vendor for wattage. Wattage will be shared to MEP team for layout GFC
9 |  | Temp Villa Pet Area | Res - Rev | Sathwik | 2026-02-20 |  |  |  | R0 |  | Intent will be released.
Gokul
1 |  | VC3 - EXTERNAL BUILDING ENVELOPE | VC3 - BECA | Gokul | 2026-02-25 | Lincy | STR | 2026-02-19 | R0 |  | Awaiting Structure Drawing
2 |  | VC3 - DETAILED DRAWINGS | VC3 - BECA | Gokul | 2026-03-02 |  |  |  | R0 |  | WIP
3 |  | VC3 - SETTING OUT - TREE TUB | Res - Rev | Gokul | 2026-02-25 | Lincy | STR | 2026-02-19 | R1 |  | Awaiting Structure Drawing
4 |  | VC3 - SKYLIGHT DETAILS | VC3 - BECA | Gokul | 2026-03-18 |  |  |  | R0 |  | WIP
5 |  | VC3 - EXTERNAL CANOPY DETAILS | VC3 - BECA | Gokul | 2026-03-18 |  |  |  | R0 |  | WIP
6 |  | VC3 - CAR CANOPY DETAILS | VC3 - BECA | Gokul | 2026-03-18 |  |  |  | R0 |  | WIP
7 |  | SITE/VC3 - STREET LIGHT DETAILS | Res - Site Dev | Gokul | 2026-03-04 |  |  |  | R0 |  | WIP
8 |  | V50 - LIVING GARDEN COPING |  | Gokul | Released |  |  |  | R0 |  | Released
9 |  | V40 - DEFAULT SET | V40 - Def | Gokul | 2026-03-27 |  |  |  | R0 |  | In progress - updating model for costing
10 |  | V40 - DEFAULT FENESTRATION SET | V40 - Def | Gokul | 2026-03-27 |  |  |  | R0 |  | In progress - updating model for costing
|  | Arshad |  | Arshad
1 |  | Service Yard Drawing | Res - Rev | Arshad | 2026-02-20 |  |  |  | R1 |  | Updated area based on the new heated pool design.Drawing will release by 20.02.2026
2 |  | Connecting Brigde Drawing | Res - Rev | Arshad | 2026-02-10 |  |  |  | R2 |  | Levels are changed .Drawing wil release by 10.02.2026
3 |  | Stilt Level Garden - Triangular potion | Res - Rev | Arshad | 2026-02-20 |  |  |  | R0 |  | Landscape drawing is released. Arch Drawing will release by 17.02.2026
4 |  | Signage Detail | Res - Rev | Arshad | 2026-02-27 |  |  |  | R1 |  | Some signages are added. Updated excel file already shared to estimation. Drawing willl release by 27.02.2026
5 |  | Level 06 Wedge area detail | Res - Rev | Arshad | 2026-02-12 |  |  |  | R1 |  | Drawing shared to waterproofing team. Will release once we get confirmation. Release by 12.02.2026
6 |  | Signage Detail | Res - Rev | Arshad | 2026-02-27 |  |  |  | R0 |  | Drawing willl release by 27.02.2026
7 |  | Basement Shaft enclosure detail | Res - Rev | Arshad | 2026-02-24 |  |  |  | R0 |  | Drawing willl release by 24.02.2026
8 |  | T3V GFC Coordination |  | Arshad |  |  |  |  | R0
Simran
1 |  | Central Green Changing room - Masonry and flooring details | Amn - Outdoor Pool | Simran | 24-Feb-26 13-Mar-26 |  |  |  | R0 |  | Glass wall details were add later. Site ventilation details need to be figured out.
2 |  | Central Green Changing room - Wall section details | Amn - Outdoor Pool | Simran | 24-Feb-26 13-Mar-26 |  |  |  | R0 |  | Awaiting Glass blocks from vendor
3 |  | T09 - Reception lounge - Masonry and Flooring drawings | T09 | Simran | 23-Feb-26 09-Mar-26 |  |  |  | R0 |  | WIP - to be coordinated with MEP teams
4 |  | T09 - Reception lounge - Electrical and RCP drawings | T09 | Simran | 23-Feb-26 09-Mar-26 |  |  |  | R0 |  | WIP - to be coordinated with MEP teams
9 |  |  |  | Simran
10 |  |  |  | Simran
Vishnu
1 |  | Ramp Groove Cutting |  | Vishnu |  |  |  |  | R0 |  | Closed
2 |  | Fire evacuation plan signage | T09 | Vishnu |  |  |  |  | R0 |  | Updated signage drawings/details are to be shared.
3 |  | HDFC Strong Room | T09 | Vishnu |  |  |  |  | R0 |  | Structural GFC drawings to be issued by EOD.
4 |  | Laerning Age | T09 | Vishnu |  |  |  |  | R0 |  | Intermediate slab details are to be provided. The structural team is currently working on the GFCs. While this approach is not as per standard practice, it is being carried out based on Sameer’s insistence, with approvals to be obtained from the concerned authorities.
5 |  | Shuttle Elevator Smoke Vent Provision | T09 | Vishnu | [6 empty] | Shridhar is working on the drawings; GFC is expected to be issued today.
6 |  | Level 1 A Toilet GFC | T09 | Vishnu | [6 empty] | Currently under discussion with Kamal.
7 |  | Staff Dining - Furniture Spec | T09 | Vishnu | [6 empty] | Furniture specifications are to be finalized. Approval is awaited from Shibanee. Vishnu to review the specifications with Saji.
8 |  | Service Platform for AC | T09 | Vishnu | [6 empty] | GFC issued
9 |  | Retail Signages | T09 | Vishnu | [6 empty] | GFC Issued
10 |  | All Level Water Supply | T09 | Vishnu | [6 empty] | Requirement sent to Deepu. Awaiting his response.
5 |  | Chiller Plant Location | T09 | Vishnu | [6 empty] | Location finalized. Chill water routing is being worked out. Coordination for pedestals and water tank MS Platform is happening with Str team
6 |  | Level 23 Other Half Space design | T09 | Vishnu | [6 empty] | Use case yet to be finalized.
7 |  | Based Build Toilet Drawing Revision | T09 | Vishnu | [6 empty] | Based on Nudge Toilets, base build toilets need to be revised
8 |  | BTU Meter | T09 | Vishnu | [6 empty] | Awaiting response from Vendor
9 |  |  |  | Vishnu
10 |  |  |  | Vishnu
Preethi
2 |  | Heated Pool - Walls sections | New Heated Pool | Preethi | 23-Feb-26 02-Mar-26 | [5 empty] | Partly dependent on roof details from Ornate- drawing in progress. Vendor not finalized yet. Only wall sections will be released by 2nd March
3 |  | Heated Pool - Surface drainage layout | New Heated Pool | Preethi | 2026-03-10 | Deepu |  |  |  |  | Deepu to release drain details- drawing in progress
4 |  | Heated Pool Roof design | New Heated Pool | Preethi | -- | Vasanth |  |  |  |  | Ornate- Solar panel vendor to be awarded contract to start design process- budget to be approved by Vasanth
5
6
7
8
9
10
Latha
1 |  | T2V Pergola Covering for Parking Slab-Ssl 05 Roof | Res - Rev | Latha | 2026-03-31 |  |  |  | R0 |  | Structural team checked feasibility. It is aprroved. Design intent to be shared by 20th Feb. In discussion with TEMC. Coordination pending with Str and MEP
2 |  | T1 & T2V Parking Allocation | Res - Rev | Latha | 2026-03-31 |  |  |  | R0 |  | T1 GFC by 3rd Mar. T2V by 31st Mar
3 |  | T2V - Weld Mesh Screening Layout @ Double Height Space | Res - Rev | Latha | 2026-03-31 |  |  |  | R0 |  | Waiting for TEMC team to share the product drawing and their costing.
4 |  | Solar Panel System Layout T01 To T07 Vertical | Res - Rev | Latha |  |  |  |  | R0 |  | Waiting for Vendor shop drawing
5 |  | The Roof XPS Insulation Dwg - Tower 1, Tower 7 | Res - Rev | Latha |  |  |  |  | R0 |  | Yet to start
7 |  | EV Charging Layout | Res - Rev | Latha |  |  |  |  | R0 |  | Coordination with structural team for new/additonal core cut provision.
8 |  | T1 & T7 Lift Pressization Duct @Terrace Level | Res - Rev | Latha | [6 empty] | Pressurization duct running through the Fire Staircase.
MEP
Hareesha
1 |  | Site plan External lighting layout -T1-7 | Res - Rev | Hareesha |  | Vivek | ARCH |  | R0 |  | Arch Plan awaited
2 |  | Site plan -Equipment & cable routing layout-T1-7 | Res - Rev | Hareesha |  | Vivek | ARCH |  | R5 |  | Sent for approval
3 |  | Villa - Jet flash point cable routing layout | Res - Rev | Hareesha |  |  |  |  | R0 |  | WIP
4 |  | EV charging layouts for T1-7 | Res - Rev | Hareesha |  | Latha | ARCH |  | R0 |  | Sent for approval
5 |  | Tower-8 site plan Electrical equipment & cable routing layout |  | Hareesha |  | Vivek | ARCH |  | R0 |  | Sent for approval
6 |  | Tower-8 -Earthing layout |  | Hareesha |  | Vivek | ARCH |  | R0 |  | Sent for approval
7 |  | Tower-8 Terrace Electrical layout |  | Hareesha |  | Vivek | ARCH |  | R0 |  | Arch Plan awaited
8 |  | Tower-8 Lightning arrester layout |  | Hareesha | 2026-03-31 | Vivek | ARCH |  | R0 |  | WIP. For approval by 31-3-26
9 |  | Tower-8 Penthouse Electrical layouts |  | Hareesha |  | Vivek | ARCH |  | R0 |  | Arch Plan awaited
10 |  | Heated pool Electrical layout | Res - Rev | Hareesha |  | Preethi | ARCH |  | R0 |  | Arch Plan awaited
11 |  | Sporting facility Electrical layout |  | Hareesha |  |  | ARCH |  | R0 |  | Arch Plan awaited
12 |  | Tower-8 ¦ R25 Electrical layout | Res - Rev | Hareesha |  |  | ARCH |  | R1 |  | Sent for approval
13 |  | Tower-8 ¦ STP Electrical layout |  | Hareesha |  |  | ARCH |  | R0 |  | Arch Plan awaited
14 |  | Sporting facility HVAC layout | Sports Complex | Hareesha |  |  |  |  | R0 |  | WIP
15 |  | Heated pool mechanical ventilation layout | New Heated Pool | Hareesha |  |  |  |  | R0 |  | Arch Plan awaited
16 |  | Tower-9 ¦ Baby chiller location & CWP routing | T9 | Hareesha |  |  |  |  | R0 |  | WIP
17 |  | Tower-8 ¦ L20 & D35 default unit HVAC layout | Res - Rev | Hareesha |  |  |  |  | R1 |  | WIP
18 |  | Tower-8 ¦ R25 HVAC layout | Res - Rev | Hareesha |  |  |  |  | R1 |  | Sent for approval
21 |  | Tower-5 Theatre HVAC layout | Res - Rev | Hareesha |  |  |  |  | R0 |  | WIP
22 |  | Clubhouse Kitchen ventilation layout | Res - Rev | Hareesha |  |  |  |  | R0 |  | Arch Plan awaited
23 |  | Tower-8 ¦ terrace HVAC /fire layout |  | Hareesha |  |  |  |  | R0 |  | WIP
24 |  | Tower-8 ¦ STP ventilation layout |  | Hareesha |  |  |  |  | R0 |  | Arch Plan awaited
Deepu
1 |  | Sporting facility plumbing layouts | Sports Complex | Deepu |  |  |  |  | R0 | R0 | Arch Plan awaited
2 |  | Central green pool changing room toilet details | Amn - Outdoor Pool | Deepu |  |  |  |  | R0 | R0 | Arch Plan awaited
3 |  | Tower -8¦ L20 PHE layouts | T8 L20 Def | Deepu | 2026-02-27 |  |  |  | R0 | R0 | Comments received recently even after approval from Arch
3 |  | Tower -8¦ D35 PHE layouts | T8 D35 Def | Deepu | 2026-03-27 |  |  |  | R0 | R0 | Updated drawing will be shared by 26th Feb
4 |  | Tower-3 Theatre toilet layout | Res - Rev | Deepu |  |  |  |  | R0 | R0 | Sharing for AR Aproval by 27 Feb
5 |  | Tower-8 ¦ Terrace PHE layout | T8 - Terrace | Deepu |  |  |  |  | R0 | R0 | Not in Q1
6 |  | Tower-8 ¦ Penthouses PHE layout | T8 - Penthouse | Deepu |  |  |  |  | R0 | R0 | Not in Q1
7 |  | Boardwalk area coordinated site plan | Res - Rev | Deepu |  |  |  |  | R3 | R3 | For approval by 25th. GFC Dependent on site draingae approval from BBMP
8 |  | Heated pool roof discharge layout | New Heated Pool | Deepu |  |  |  |  | R0 | R0 | Arch Plan awaited
9 |  | Tower-9 ¦ retail shops water supply and drawinage layout | T9 | Deepu |  |  |  |  | R0 | R0 | For approval by 4th Mar
10 |  | Tower-9 ¦ STP to chiller water supply layout | T9 | Deepu |  |  |  |  | R0 | R0 | Fro approval by 24th Feb
11 |  | Tower-8 STP / UGT PHE layout | T8 - ISS - Fdn | Deepu |  |  |  |  | R0 | R0 | Revised GFC by 20th Mar for approval
12 |  | Tower-8 ¦ site plan coordinated layout | T8 - MP - MP | Deepu |  |  |  |  | R0 | R0 | Awaited AUM details
16 |  | R22 - Experience home PHE details | R22 Def | Deepu |  |  |  |  | R0 | R0 | Closed | To be added in Q1 WPS
Vallivel
1 |  | Tower-8 ¦ Site plan -Fire layout | T8 - MP - MP | Vallivel |  |  |  |  | R0 |  | WIP
2 |  | Sporting facility FPS layout | Sports Complex | Vallivel |  |  |  |  | R0 |  | WIP
Landscape
Apoorva
1 |  | T7-T9 Ramp Planter Box - Planting Plan | Res - Rev | [5 empty] | R? |  | Based on Kamal's input need to change the planting plan
2 |  | Landscape plan near V25-26 | Res - Rev |  |  | Sathwik | Arch |  | R0 |  | Final intent from AR awaited
3 |  | Villa Guest Parking and V40 coumpound wall surrounding Landscape | Res - Rev |  |  | Sathwik | Arch |  | R0 |  | Final intent from AR awaited. Currently is is used for site mobilization route. Will taken up after V40 construction is completed.
4 |  | Amphetheater and Changing Room Landscape | Amn - Outdoor Pool |  | 2025-03-25 |  |  |  | R0 |  | Work in progress
5 |  | Sporting Complex | Sports Complex |  | 2025-03-25 |  |  |  | R0 |  | Intent received. WIP
Chetan
1
2
3
4
5

## Sheet1 (hidden)
# | GFC | Responsible | Department | Baseline Finish | Projected Finish | Delay [Weeks]
1 | New Heated Pool Landscaping Drawings [Only Plumbing Plans and sections] | Apoorva S | Design_UDLS |  | 2026-03-25
3 | Central Green Coordinated GFC | Deepu V | Design_MEP | 2025-03-31 | 2026-03-30 | 36w 4d
4 | UGT-1 Revised GFC | Deepu V | Design_MEP |  | 2026-03-30
5 | UGT 2 and 3 Revised GFC | Deepu V | Design_MEP |  | 2026-03-30
6 | General Arrangement - Plans Sports Complex | Sathwik S | Design_Arch | 2025-03-19 | 2026-02-28 | 38w 3d
10 | Solar Panel details - T2 to T7 | Latha B | Design_Arch | 2025-03-31 | 2026-01-31 | 37w 4d
12 | HVAC revised GFC | Hareesha D K | Design_MEP |  | 2026-02-28
13 | Temporary Sports area | K Gokul | Design_Arch | 2025-03-31 | 2026-02-28 | 37w 4d
15 | Theatre in T3V Stilt Level | Arshad S | Design_Arch | 2025-03-31 | 2026-03-30 | 36w 4d
16 | T09 reception : Baggage scanner details | Simran S | Design_Arch | 2025-01-21 | 2026-03-30 | 46w 3d
19 | V40 Revised UNIT PLANS | K Gokul | Design_Arch | 2025-04-07 | 2026-03-30 | 36w 1d
20 | Compound Wall and Boundary Walls (Master Plan Showing Boundary Wall Extent Details) | Lincy R | Design_Struct | 2025-06-20 | 2026-03-30 | 25w 2d
21 | V40 Revised MASONRY PLANS | K Gokul | Design_Arch | 2025-04-09 | 2026-03-30 | 36w
22 | Site Development - V40 side boundary wall | Lincy R | Design_Struct |  | 2026-02-27
23 | Tennis Court | Sathwik S | Design_Arch |  | 2026-02-28
24 | Cul-De-Sac | Sathwik S | Design_Arch |  | 2026-02-28
25 | Villa 25 - Retaining Wall Detail | Sathwik S | Design_Arch |  | 2026-03-07
26 | PH-2 DG Yard - Revision | Sathwik S | Design_Arch |  | 2026-03-07
27 | T09 PHE Riser Logo | Sathwik S | Design_Arch |  | 2026-03-20
28 | Temp Villa Pet Area | Sathwik S | Design_Arch |  | 2026-02-23
29 | VC3 - EXTERNAL BUILDING ENVELOPE | K Gokul | Design_Arch |  | 2026-02-25
30 | VC3 - DETAILED DRAWINGS | K Gokul | Design_Arch |  | 2026-03-02
31 | VC3 - SETTING OUT - TREE TUB | K Gokul | Design_Arch |  | 2026-02-25
32 | VC3 - SKYLIGHT DETAILS | K Gokul | Design_Arch |  | 2026-02-18
33 | VC3 - EXTERNAL CANOPY DETAILS | K Gokul | Design_Arch |  | 2026-03-18
34 | VC3 - CAR CANOPY DETAILS | K Gokul | Design_Arch |  | 2026-03-18
35 | SITE/VC3 - STREET LIGHT DETAILS | K Gokul | Design_Arch |  | 2026-03-04
36 | V40 - DEFAULT SET | K Gokul | Design_Arch |  | 2026-03-27
37 | V40 - DEFAULT FENESTRATION SET | K Gokul | Design_Arch |  | 2026-03-27
38 | Service Yard Drawing | Arshad S | Design_Arch |  | 2026-02-20
39 | Connecting Brigde Drawing | Arshad S | Design_Arch |  | 2026-02-10
40 | Stilt Level Garden - Triangular potion | Arshad S | Design_Arch |  | 2026-02-20
41 | Signage Detail | Arshad S | Design_Arch |  | 2026-02-27
42 | Level 06 Wedge area detail | Arshad S | Design_Arch |  | 2026-02-12
43 | Signage Detail | Arshad S | Design_Arch |  | 2026-02-27
44 | Basement Shaft enclosure detail | Arshad S | Design_Arch |  | 2026-02-24
45 | Central Green Changing room - Masonry and flooring details | Simran S | Design_Arch |  | 2026-02-20
46 | Central Green Changing room - Wall section details | Simran S | Design_Arch |  | 2026-02-24
47 | T09 - Reception lounge - Masonry and Flooring drawings | Simran S | Design_Arch |  | 2026-02-23
48 | T09 - Reception lounge - Electrical and RCP drawings | Simran S | Design_Arch |  | 2026-02-23
49 | 7281 C20P - Living spaces design | C Preethi | Design_Arch |  | 2026-02-27
50 | Heated Pool - Walls sections | C Preethi | Design_Arch |  | 2026-02-23
51 | Heated Pool - Surface drainage layout | C Preethi | Design_Arch |  | 2026-03-10
# | GFC | Responsible | Department | Baseline Finish | Projected Finish | Delay [Weeks]
6 | General Arrangement - Plans Sports Complex | Sathwik S | Design_Arch | 2025-03-19 | 2026-02-28 | 38w 3d
10 | Solar Panel details - T2 to T7 | Latha B | Design_Arch | 2025-03-31 | 2026-01-31 | 37w 4d
12 | HVAC revised GFC | Hareesha D K | Design_MEP |  | 2026-02-28
13 | Temporary Sports area | K Gokul | Design_Arch | 2025-03-31 | 2026-02-28 | 37w 4d
22 | Site Development - V40 side boundary wall | Lincy R | Design_Struct |  | 2026-02-27
23 | Tennis Court | Sathwik S | Design_Arch |  | 2026-02-28
24 | Cul-De-Sac | Sathwik S | Design_Arch |  | 2026-02-28
28 | Temp Villa Pet Area | Sathwik S | Design_Arch |  | 2026-02-23
29 | VC3 - EXTERNAL BUILDING ENVELOPE | K Gokul | Design_Arch |  | 2026-02-25
31 | VC3 - SETTING OUT - TREE TUB | K Gokul | Design_Arch |  | 2026-02-25
32 | VC3 - SKYLIGHT DETAILS | K Gokul | Design_Arch |  | 2026-02-18
38 | Service Yard Drawing | Arshad S | Design_Arch |  | 2026-02-20
39 | Connecting Brigde Drawing | Arshad S | Design_Arch |  | 2026-02-10
40 | Stilt Level Garden - Triangular potion | Arshad S | Design_Arch |  | 2026-02-20
41 | Signage Detail | Arshad S | Design_Arch |  | 2026-02-27
42 | Level 06 Wedge area detail | Arshad S | Design_Arch |  | 2026-02-12
43 | Signage Detail | Arshad S | Design_Arch |  | 2026-02-27
44 | Basement Shaft enclosure detail | Arshad S | Design_Arch |  | 2026-02-24
45 | Central Green Changing room - Masonry and flooring details | Simran S | Design_Arch |  | 2026-02-20
46 | Central Green Changing room - Wall section details | Simran S | Design_Arch |  | 2026-02-24
47 | T09 - Reception lounge - Masonry and Flooring drawings | Simran S | Design_Arch |  | 2026-02-23
48 | T09 - Reception lounge - Electrical and RCP drawings | Simran S | Design_Arch |  | 2026-02-23
49 | 7281 C20P - Living spaces design | C Preethi | Design_Arch |  | 2026-02-27
50 | Heated Pool - Walls sections | C Preethi | Design_Arch |  | 2026-02-23

## Vivek
Category of the Drawing as listed in T8 Goals shared by CPMO | BATCH | DRAWING / BATCH |  | Date | Revised dates | Dependency |  | Comments
Site Development | MP-02 | BOUNDARY (East) |  | 2026-02-06 | 2026-03-13 | ARCH | Required for Drg Prep: Percolation pit location & size; Design of Plinth footings.
[6 empty] | LS | Percolation pits' size and locaiton. | Received details from Apoorva.Shared with Vasant's team. Meeting today.
[6 empty] | ELEC | Design of footings of Plinths of T/F and DG after coordination w/ Vendors
[6 empty] | FPS | FHC Lines to stay within Podium profile | Vallivel to share the revised layout
[6 empty] | HVAC | Café Exhaust duct's height needs to be adjusted per AR comment | Awaiting from Hareesha
[6 empty] | PHE | AR's concerns about Services lines' interaction is to be confirmed | Confirmation awaited
[6 empty] | STR | Coordination complete
[6 empty] | LIAISONING | Finalisation of Lake Discharge Scheme in compliance with Lake Dev Authority is very important for freezing the SWD
[6 empty] | INFRA CNSLTNT | Drawings to be shared w Consultant (incl Percn pits.) | Shared for review
[6 empty] | KAMAL | AR intent drawings have not been presented to Kamal for his inputs. | TBD with Saji
R25 Default [Modification for Dry Wall] | PD | DEFAULT UNIT (Re-submittal) ¦ R25 |  | 2026-02-16 |  | ARCH | Drawings are being updated per Workshop. Next Workshop shall be on 12th Feb
[6 empty] | LS | Drawings were shared in 2023. LS is likely working on updating all their design options.
[6 empty] | ELEC | Updated layout of Equipment room required
[6 empty] | FPS | Updated layout of Equipment room required
[6 empty] | HVAC | Updated layout of Service Platform required
[6 empty] | PHE | Floor trap under the kitchen sink needs to be thought about or connect it to the utility floor trap
Envelope and Common Areas [Typical Levels] | BB01-07 | TYPICAL LEVEL - SECTIONS, ELEVATIONS |  | 2026-02-20 | 2026-03-20 | ARCH | Drawings are being prepared
| BB01-07 | TYPICAL LEVEL - GARDENS |  | 2026-02-20 | 2026-03-20 | KAMAL | AR intent drawings have not been presented to Kamal for his inputs.
ISS - Foundations & Grade Slab, Parking Level Subgrade, Podium Slab & Building Envelope and Common Areas | BB02-ISS | ISS - STAFF TOILETS & LOUNGE |  | 2026-02-27 | 2026-03-20 | ARCH | AR Drawings are shared w STR for incorporation of changes - Staff Lounge & Tank Walls
| BB02-ISS | ISS - SETTING OUT |  | 2026-02-27 | 2026-03-20
| BB02-ISS | ISS - UGT |  | 2026-02-27 | 2026-03-20 | LS | N/A
| BB02-ISS | ISS - STP |  | 2026-02-27 | 2026-03-20 | ELEC | AR Drawings not shared.
| BB02-ISS | ISS - METAL FABRICATION |  | 2026-02-27 | 2026-03-20
[6 empty] | FPS | AR Drawings not shared.
[6 empty] | HVAC | AR Drawings not shared.
[6 empty] | PHE | Confirmation required that Eqpt. Hoisting System is sufficient.
[6 empty] | STR | To Confirm that AR drawings shared are ok.
INFRA CNSLTNT
L20 Default [Modification for Dry Wall] | PD | DEFAULT UNIT ¦ L20 |  | 2026-03-06 |  | ARCH | GFCs have been shared w eDesign for review.
[6 empty] | e-DESIGN | eDES is reviewing AR GFCs
[6 empty] | EST | Packages' CL code creation is ongoing. Costing nearly done.
[6 empty] | LS | - AR Drawings shared showing change in Garden profile (in plan) - Updated planting plans required. - Updating Costing has been shared by LS.
[6 empty] | ELEC | Drawings / information are shared w AR
FPS
HVAC
|  |  | CL code creation ongoing - Packages |  |  | PHE
STR
D35 Default [Modification for Dry Wall] | PD | DEFAULT UNIT ¦ D35 |  | 2026-03-06 |  | ARCH | GFCs have been shared w eDesign for review.
[6 empty] | e-DESIGN | eDES is reviewing AR GFCs
[6 empty] | EST | Packages' CL code creation is ongoing. Costing started.
[6 empty] | LS | - AR Drawings shared showing change in Garden profile (in plan) - Updated planting plans & Costing required. Likely to start 18th Feb.
AR is creating Fenestration codes
[6 empty] | ELEC | MEP needs to update AR comment
FPS
HVAC
PHE
STR
Habitable Level 01 (STILT / PODIUM) | BB01-4 | MASONRY - Podium (NTA) |  | 2026-03-13 | 2026-03-27 | ARCH | AR drawings to be reviewed internally on a final basis (lighting, planting, staff room skylights, etc.). Then to be shared w Kamal.
| BB01-4 | STILT - OPENINGS DETAILS |  | 2026-03-13 | 2026-03-28
[6 empty] | LS | Irrigation coordinated. Lighting and Planting plans are required.
[6 empty] | ELEC | AR drawings required. Lighting plan required from LS
[6 empty] | FPS | FHC Locations to be shared - may have an effect on Saucer Drain design. Manhole locations for Fire-fighting inlets to be shared.
[6 empty] | HVAC | N/A
[6 empty] | PHE | Drainage intent by AR is shared - needs review. AR Feedback on FHC locations needs to be incorp'd. Drainage of Planted Pockets must be verified / confirmed
[6 empty] | STR | Drainage & FHC core-cuts are to be shared by PHE & FPS for review
[6 empty] | INFRA CNSLTNT | AR drawings to be coord'd with PHE, FPS and LS and then shared w INFRA for podium drainage review for coordination w drainage of Site outside podium.
[6 empty] | KAMAL | AR intent drawings have not been presented to Kamal for his inputs.
Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | BB01-10 | PENTHOUSE - MASONRY & ELEC |  | 2026-03-13 | 2026-03-27 | ARCH | AR drawings to be reviewed internally on a final basis (lighting, planting, staff room skylights, etc.). Then to be shared w Kamal.
| BB01-10 | TERRACE - MASONRY, ELEC |  | 2026-03-13 | 2026-03-27
| BB01-10 | TERRACE - GLAZING |  | 2026-03-13 | 2026-03-27
[6 empty] | LS | Irrigation coordinated. Lighting and Planting plans are required.
[6 empty] | ELEC | AR drawings required. Lighting plan required from LS
[6 empty] | FPS | FHC Locations to be shared - may have an effect on Saucer Drain design. Manhole locations for Fire-fighting inlets to be shared.
[6 empty] | HVAC | N/A
[6 empty] | PHE | Drainage is coordinated. FHC locations need to be captured although this is not liekly to affect the design
[6 empty] | STR | Drainage & FHC core-cuts are to be shared by PHE & FPS for review
[6 empty] | INFRA CNSLTNT | AR drawings to be coord'd with PHE, FPS and LS and then shared w INFRA for podium drainage review for coordination w drainage of Site outside podium.
[6 empty] | KAMAL | AR intent drawings have not been presented to Kamal for his inputs.
Site Development | MP-02 | BOUNDARY (NORTH) |  | 2026-03-20 |  | ARCH | Coordination pending w STR, LS, Services, INFRA
| MP-02 | BOUNDARY (SOUTH & WEST) |  | 2026-03-20
[6 empty] | LS | AR Drgs not shared | Will be shared by 13th Mar
[6 empty] | ELEC | AR Drgs not shared
[6 empty] | FPS | AR Drgs not shared
[6 empty] | HVAC | AR Drgs not shared
[6 empty] | PHE | AR Drgs not shared
[6 empty] | STR | AR Drgs not shared
[6 empty] | INFRA CNSLTNT | AR Drgs not shared - AR set is under internal review | Shared with AUM for review
[6 empty] | KAMAL | AR intent drawings have not been presented to Kamal for his inputs.
Site Development | MP-01, 02 | SITE - STORMWATER DRAINAGE |  | 2026-03-20 |  | ARCH | AR set needs to be coordinated w INFRA. Shall be inititated this week after internal review
[6 empty] | LS | Plan signed by Kamal is shared by LS w AR. INFRA coordination is pending.
[6 empty] | ELEC | Site Electrical Layout has been shared w AR. INFRA coordination is pending.
[6 empty] | FPS | Connections for Fire Tender/ Firefighting are to be shared.
[6 empty] | HVAC | N/A
[6 empty] | PHE | Drainage is coordinated.
[6 empty] | STR | Retaining Wall coodination is pedding
[6 empty] | INFRA CNSLTNT | AR drawings to be coord'd with PHE, FPS and LS and then shared w INFRA for podium drainage review for coordination w drainage of Site outside podium.
Habitable Level 01 (STILT) | BB01-04 | INTERIORS - RECEPTION, FIRE CONTROL ROOMS, GAMES ROOM |  | 2026-03-27 |  | ARCH | AR Drawings are yet to be prepared
ELEC
FPS
HVAC
PHE
STR
[6 empty] | KAMAL | -
Habitable Level 01 (STILT) | BB01-04 | STILT - FENESTRATION |  | 2026-03-27 |  | ARCH | AR Drawings are yet to be prepared
ELEC
FPS
HVAC
PHE
STR
[6 empty] | KAMAL | -
Envelope and Common Areas [Basements] | BB01-06 | INTERIORS - REFUGE AREA |  | 2026-03-27 |  | ARCH | AR Drawings are yet to be prepared
ELEC
FPS
HVAC
PHE
STR
Envelope and Common Areas [Basements] | BB01-03 | SIGNAGE - BASEMENTS |  | 2026-03-27 |  | ARCH | AR Drawings are yet to be prepared
ELEC
FPS
HVAC
PHE
STR
Habitable Level 01 | BB01-04 | SIGNAGE - STILT & PODIUM |  | 2026-03-27 |  | ARCH | AR Drawings are yet to be prepared
ELEC
FPS
HVAC
PHE
STR
Envelope and Common Areas [Penthouse And Terrace] | BB01-07 | SIGNAGE - TYP., REFUGE & PENTHOUSE LEVELS |  | 2026-03-27 |  | ARCH | AR Drawings are yet to be prepared
| BB01-10 | SIGNAGE - TERRACE |  | 2026-03-27 |  | ELEC
FPS
HVAC
PHE
STR
Site Development | MP-02 | SIGNAGE - SITE |  | 2026-06-30 |  | ARCH | AR Drawings are yet to be prepared
ELEC
FPS
HVAC
PHE
STR
Master Plan | MP-03 | UTILITY STRUCTURES (DG, T/F) |  | 2026-03-31 |  | ARCH | Internal Review pending - Kamal has not seen these.
[6 empty] | LS | -
[6 empty] | ELEC | Elec Plan is not shared by AR. ELEC Eqpt. Vendors' feedback is required for Plinth Design
[6 empty] | FPS | Confirmation required if these buildings need any FPS
HVAC
PHE
STR
[6 empty] | KAMAL | AR intent drawings have not been presented to Kamal for his inputs.
Habitable Level 01 | BB01-04 | INTERIORS - STILT TOILETS |  | 2026-04-17 |  | ARCH | AR intent drawings have not been prepared. | Reason for postponement to Q2: A part of the Toilets may have to be converted to changing rooms for the Outdoor Pool. Until this is finalised, these drawings cannot be issued.
ELEC
FPS
HVAC
PHE
STR
[6 empty] | KAMAL | Does part of the Toilets have to be converted to changing rooms for the Outdoor Pool? Or can the toilets function as both with no change?
L22 Default | PD | DEFAULT UNIT ¦ L22 |  | 2026-05-01 |  | ARCH | Unit workshop has to be re-started for DryWalling. AR Drawings need to be developed . | Reason for postponement to Q2: New standard details or other developments from R25 unit's Default workshop are likely to be applied here. Then there is costing and CL codes. This is likely to take a lot of time.
[6 empty] | LS | Updated planting drawing & Costing required
[6 empty] | ELEC | R0 released. R1 Updated ETDs might be required when AR develops the default set
FPS
HVAC
PHE
[6 empty] | STR | -
Clubhouse + Amenities | AM-02 | BOARDWALK |  | 2026-06-30 |  | ARCH | Intent drawings are not started | Reason for postponement to Q2: Multiple iterations of the Design are likely to be done based on reviews with Kamal. This will take time.
[6 empty] | ELEC | Coordination done for first cut AR drawings
[6 empty] | FPS | Coordination done for first cut AR drawings
[6 empty] | HVAC | Coordination done for first cut AR drawings
[6 empty] | PHE | Coordination done for first cut AR drawings
[6 empty] | KAMAL | AR intent drawings have not been presented to Kamal for his inputs.
Clubhouse + Amenities | AM-02 | SIGNAGE - CLUBHOUSE SPACES |  | 2026-06-30 |  | ARCH | AR Drawings are yet to be prepared
ELEC
FPS
HVAC
PHE
STR
Clubhouse + Amenities | AM-02 | CLUBHOUSE (GYM, MPH, MPS, KITCHEN, CAFÉ) |  | 2026-06-30 |  | ARCH | Drawings are nit AR scope - LS intent to be captured in AR Master Plan | Reason for postponement to Q2: Multiple iterations of the Design are likely to be done based on reviews with Kamal. This will take time.
[6 empty] | LS | The design drawings are LS scope
[6 empty] | ELEC | LS scope
[6 empty] | FPS | LS scope
[6 empty] | HVAC | LS scope
[6 empty] | PHE | LS scope
[6 empty] | KAMAL | LS Scope
Clubhouse + Amenities | AM-02 | POOL |  | 2026-06-30 |  | ARCH | Drawings are nit AR scope - LS intent to be captured in AR Master Plan | Reason for postponement to Q2: Multiple iterations of the Design are likely to be done based on reviews with Kamal. This will take time.
[6 empty] | LS | The design drawings are LS scope
[6 empty] | ELEC | LS scope
[6 empty] | FPS | LS scope
[6 empty] | HVAC | LS scope
[6 empty] | PHE | LS scope
[6 empty] | KAMAL | LS Scope
Penthouse Defaults | PD | PENTHOUSE DEFAULTS - R25p, L22p, L20p & D35p |  | 2026-06-30 |  | ARCH | Marketing Collaterals are closed. Default Workshops have not been started.GFCs have been shared w eDesign for review. | Reason for postponement to Q2: Layouts were closed with Shibanee's help. Workshops cannot be started till the workshops for the non-Penthouse units are closed. Then costing and code creation shall follow. This will take time.
[6 empty] | e-DESIGN | -
[6 empty] | EST | Packages' CL code creation is ongoing. Costing nearly done.
[6 empty] | LS | - AR Drawings shared showing change in Garden profile (in plan) - Updated planting plans required. - Updating Costing has been shared by LS.
[6 empty] | ELEC | Drawings / information are shared w AR
FPS
HVAC
PHE
STR

## Sathwik (hidden)
# | Drawing / Detail | Discipline | Revision | Status | Date
1 | Sports Complex | Architecture | R0 | Awaiting Structure Drawing
2 | Tennis Court | Architecture | R0 | WIP | 2026-02-28
3 | OWC | Architecture | R0 | We will pick up this if we dont get sports complex drawings
GA PLAN
4 | Cul-De-Sac | Architecture | R0 | WIP | 2026-02-28
5 | Villa 25 - Retaining Wall Detail | Architecture | R0 | WIP | 2026-03-07
6 | PH-2 DG Yard - Revision | Architecture | R1 | WIP | 2026-03-07
| T09 PHE Riser Logo | Architecture | R0 | Logo intent to be shared to marketing team | 2026-02-18
| Site Signage Vendor coordination | Architecture | R0 | Received shop drawing from TEMC. After checking will be shared to Vendor for wattage. Wattage will be shared to MEP team for layout GFC
| Temp Villa Pet Area | Architecture | R0 | Intent will be released. Shared to landscape for inputs

## Gokul (hidden)
# | Drawing / Detail | Revision | Status | Target Dates
1 | VC3 - EXTERNAL BUILDING ENVELOPE | R0 | GFC for Next week
2 | VC3 - DETAILED DRAWINGS | R0
3 | VC3 - SETTING OUT - TREE TUB | R1 | Added street light - waiting for intent from STR
4 | VC3 - SKYLIGHT DETAILS | R0 | In progress - updating model for costing
5 | VC3 - EXTERNAL CANOPY DETAILS | R0 | In progress - updating model for costing
6 | VC3 - CAR CANOPY DETAILS | R0 | In progress - updating model for costing
7 | SITE/VC3 - STREET LIGHT DETAILS | R0 | Added street light - waiting for intent from STR
8 | V50 - LIVING GARDEN COPING | R0 | GFC for Next week
9 | V40 - DEFAULT SET | R0 | In progress - updating model for costing
10 | V40 - DEFAULT FENESTRATION SET | R0 | In progress - updating model for costing

## Latha (hidden)
# | Drawing / Detail | Revision | Status | Date
1 | T2V PERGOLA COVERING FOR PARKING SLAB-SSL 05 ROOF | R0 | Waiting for Structural teams to check the feasibility. |  | T2V Pergola Covering For Parking Slab-Ssl 05 Roof
2 | T1 & T2V PARKING ALLOCATION | R0 | Work in progress |  | T1 & T2V Parking Allocation
3 | T2V - WELD MESH SCREENING LAYOUT @ DOUBLE HEIGHT SPACE | R0 | Waiting for TEMC team to share the product drawing and their costing. |  | T2V - Weld Mesh Screening Layout @ Double Height Space
4 | SOLAR PANEL SYSTEM LAYOUT T01 TO T07 VERTICAL | R0 | Waiting for Vendor shop drawing |  | Solar Panel System Layout T01 To T07 Vertical
5 | The roof XPS insulation dwg - Tower 1, Tower 7 | R0 | Yet to start |  | The Roof Xps Insulation Dwg - Tower 1, Tower 7
| COORDINATION - |  |  |  | Coordination -
1 | EV CHARGING LAYOUT |  | COORDINATION WITH STRUCTURAL TEAM FOR NEW/ADDITONAL CORE CUT PROVISION. |  | Ev Charging Layout
8 | T1 & T7 Lift pressization duct @Terrace level |  |  |  | T1 & T7 Lift Pressization Duct @Terrace Level
9
10
11
Coordination with structural team for new/additonal core cut provision.

## Hareesha (hidden)
# | Drawing / Detail | Discipline | Revision | Status | Target Date
1 | Site plan External lighting layout -T1-7 | Electrical | R0 | Arch Plan awaited
2 | Site plan -Equipment & cable routing layout-T1-7 | Electrical | R5 | Sent for approval
3 | Villa - Jet flash point cable routing layout | Electrical | R0 | WIP
4 | EV charging layouts for T1-7 | Electrical | R0 | Sent for approval
5 | Tower-8 site plan Electrical equipment & cable routing layout | Electrical | R0 | Sent for approval
6 | Tower-8 -Earthing layout | Electrical | R0 | Sent for approval
7 | Tower-8 Terrace Electrical layout | Electrical | R0 | Arch Plan awaited
8 | Tower-8 Lightning arrester layout | Electrical | R0 | Arch Plan awaited
9 | Tower-8 Penthouse Electrical layouts | Electrical | R0 | Arch Plan awaited
10 | Heated pool Electrical layout | Electrical | R0 | Arch Plan awaited
11 | Sporting facility Electrical layout | Electrical | R0 | Arch Plan awaited
12 | Tower-8 ¦ R25 Electrical layout | Electrical | R1 | Sent for approval
13 | Tower-8 ¦ STP Electrical layout | Electrical | R0 | Arch Plan awaited
14 | Sporting facility HVAC layout | HVAC | R0 | WIP
15 | Heated pool mechanical ventilation layout | HVAC | R0 | Arch Plan awaited
16 | Tower-9 ¦ Baby chiller location & CWP routing | HVAC | R0 | WIP
17 | Tower-8 ¦ L20 & D35 default unit HVAC layout | HVAC /Fire | R1 | WIP
18 | Tower-8 ¦ R25 HVAC layout | HVAC /Fire | R1 | Sent for approval
19 | 3062-L45p HVAC layout | HVAC /Fire | R0 | WIP
20 | 4061-L45p HVAC layout | HVAC /Fire | R0 | WIP
21 | Tower-5 Theatre HVAC layout | HVAC | R0 | WIP
22 | Clubhouse Kitchen ventilation layout | HVAC | R0 | Arch Plan awaited
23 | Tower-8 ¦ terrace HVAC /fire layout | HVAC /Fire | R0 | WIP
24 | Tower-8 ¦ STP ventilation layout | HVAC | R0 | Arch Plan awaited

## Vallivel (hidden)
# | Drawing / Detail | Discipline | Revision | Status | Traget Date
1 | Tower-8 ¦ Site plan -Fire layout | Fire | R0 | WIP
2 | Sporting facility FPS layout | Fire | R0 | WIP

## Deepu (hidden)
# | Drawing / Detail | Discipline | Revision | Status | Traget Date
1 | Sporting facility plumbing layouts | PHE | R0 | Arch Plan awaited
2 | Central green pool changing room toilet details | PHE | R0 | Arch Plan awaited
3 | Tower -8¦ D35 PHE layouts | PHE | R0 | WIP
4 | Tower-5 Theatre toilet layout | PHE | R0 | WIP
5 | Tower-8 ¦ Terrace PHE layout | PHE | R0 | WIP
6 | Tower-8 ¦ Penthouses PHE layout | PHE | R0 | Arch Plan awaited
7 | Boardwalk area coordinated site plan | CO | R3 | WIP
8 | Heated pool roof discharge layout | PHE | R0 | Arch Plan awaited
9 | Tower-9 ¦ retail shops water supply layout | PHE | R0 | WIP
10 | Tower-9 ¦ STP to chiller water supply layout | PHE | R0 | WIP
11 | Tower-8 STP / UGT PHE layout | PHE | R0 | Arch Plan awaited
12 | Tower-8 ¦ site plan coordinated layout | CO | R0 | Awaited AUM details
13 | 4061-L45p PHE layout | PHE | R0 | WIP
14 | 3301-L45p PHE layout | PHE | R0 | WIP
15 | 4302-L45p PHE layout | PHE | R0 | WIP
16 | R22 - Experience home PHE details | PHE | R0 | WIP