## Assumption Cost
21.77a Violet Hill - [0118] [Fee calculations] |  |  |  | Cost |  |  |  | Fee | 5 | 3 | 2 | 7
[9 empty] | 5% | 1.06% | 0.59% | 0.33%
1 | Total Construction cost | 53.7097 |  | Construction | Structural | MEP | Landscaping |  | Architectural | Structural | MEP | Landscaping | Construction cost to be punched in D4
| Total | 100 | % | 53.7097 | 18.9774 | 15.8444 | 2.532 | 0 | 2.6855 | 0.56932 | 0.31689 | 0.17724 | Punch values in F15 and 16 respectively for Plotted land and Amenities
A | Residential | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | Once BOQ is available then use BOQ cost sheet for fee calculation
| Apartments | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Villas | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Townhouses | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Amenities | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
B | Plotted development | 100 | 1 | 53.7097 | 18.9774 | 15.8444 | 2.532 |  | 2.6855 | 0.56932 | 0.31689 | 0.17724
| Plotted Land | 100 | 1 | 48.641 | 17.1865 | 14.3491 | 2.2931 |  | 2.4321 | 0.5156 | 0.28698 | 0.16052
| Amenities | 0 | 0 | 5.0686 | 1.7909 | 1.4952 | 0.23895 |  | 0.25343 | 0.053727 | 0.029905 | 0.016726
C | Commercial | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Tower - Office | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Health + Wellness | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Hospitality (Resort) | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
D | Festival centre | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Festival centre | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Education - School | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0

## Design Fee
|  |  | 100% |  | 100% |  | 100% |  | 100%
Plotted Development |  |  | AR |  | ST |  | MEP |  | LS
1 | DESIGN CONCEPT |  | 45% | 1.2085 | 40% | 0.22773 | 30% | 0.095066 | 40% | 0.070897 | MP | Amenities
| DC 01 | Contract + Design Brief | 5% | 0.13427 | 0% |  | 0% |  | 0%
| DC 02 | Schematic Concept | 10% | 0.26855 | 10% | 0.056932 | 5% | 0.015844 | 10% | 0.017724 | 0.24321 | 0.025343
| DC 03 | Approvals | 10% | 0.26855 | 0% |  | 10% | 0.031689 | 15% | 0.026586 | 0.24321 | 0.025343
| DC 04 | Pre Construction Set | 10% | 0.26855 | 20% | 0.11386 | 10% | 0.031689 | 5% | 0.0088621 | 0.24321 | 0.025343
| DC 05 | Project Experience | 5% | 0.13427 | 10% | 0.056932 | 5% | 0.015844 | 5% | 0.0088621
| DC 06 | Marketing and Sales | 5% | 0.13427 | 0% |  | 0% |  | 5% | 0.0088621
CONSTRUCTION DOCUMENTS
2 | MP | Master Plan | 50% | 1.216 | 55% | 0.28358 | 65% | 0.18654 | 55% | 0.088284
| MP 01 | Infra - Grading | 10% | 0.24321 | 5% | 0.02578 | 0% | 0 | 0% | 0
| MP 02 | Infra - MEP | 5% | 0.1216 | 10% | 0.05156 | 15% | 0.043047 | 5% | 0.0080258
| MP 03 | BOQ & Technical Specifications | 10% | 0.24321 | 0% | 0 | 5% | 0.014349 | 5% | 0.0080258
| MP 04 | Infra - Coordinated | 0% | 0 | 0% | 0 | 10% | 0.028698 | 5% | 0.0080258
| MP 05 | Structures - Security Cabin and Entrance | 3% | 0.072962 | 5% | 0.02578 | 5% | 0.014349 | 5% | 0.0080258
| MP 06 | Infra - Plot Boundary & Enclosures | 3% | 0.072962 | 5% | 0.02578 | 0% | 0 | 5% | 0.0080258
| MP 07 | Infra - Signage & Street Lighting | 3% | 0.072962 | 5% | 0.02578 | 5% | 0.014349 | 5% | 0.0080258
| MP 08 | Structures - Electrical Room & Toilet Block | 3% | 0.072962 | 5% | 0.02578 | 5% | 0.014349 | 5% | 0.0080258
| MP 09 | Structures - UGT | 3% | 0.072962 | 5% | 0.02578 | 5% | 0.014349 | 5% | 0.0080258
| MP 10 | Structures - OHT | 3% | 0.072962 | 5% | 0.02578 | 5% | 0.014349 | 5% | 0.0080258
| MP 11 | Structures - STP | 3% | 0.072962 | 5% | 0.02578 | 5% | 0.014349 | 5% | 0.0080258
| MP 12 | Structures - OWC & other structure | 4% | 0.097282 | 5% | 0.02578 | 5% | 0.014349 | 5% | 0.0080258
3 | AM | Clubhouse + Amenities | 50% | 0.12672 | 55% | 0.02955 | 65% | 0.019438 | 55% | 0.0091996
| AM 01 | Clubhouse—Structure and Envelope | 15% | 0.038015 | 35% | 0.018805 | 35% | 0.010467 | 0%
| AM 02 | Clubhouse—Interiors and Facilities | 20% | 0.050686 | 0% |  | 15% | 0.0044857 | 10% | 0.0016726
| AM 03 | Clubhouse—Outdoor Spaces and pool | 5% | 0.012672 | 5% | 0.0026864 | 10% | 0.0029905 | 20% | 0.0033453
| AM 04 | Community spaces [Children play area, Open Park space] | 5% | 0.012672 | 5% | 0.0026864 |  |  | 25% | 0.0041816
| AM 05 | Sporting Facilities | 5% | 0.012672 | 10% | 0.0053727 | 5% | 0.0014952 | 0%
POST-CONSTRUCTION
4 | MA | Master Archives | 5% | 0.13427 | 5% | 0.028466 | 5% | 0.015844 | 5% | 0.0088621

## Packages deliverables
285 | Package Code | Package Description | Master Planning | Released Status |  | Released Status | MEP | Released Status |  | Released Status |  | Released Status | Structural | Released Status | Landscape | Released Status
[5 empty] | Infra Consultants |  | PHE |  | ELE |  | IBMS
Master Planning - Schematic
Traffic & Transporation
Reports
Earthworks & Site Grading:
Concept Exhibit Drawings
Budget Estimate
Roadways Engineering:
Budget Estimate
Storm Water Management:
Report with Schematic Drawings
Budget Estimate
Public Health Engineering - Infrastructure Services.
[5 empty] | Report with Schematic Drawings |  | Schematic for Utilities
Budget Estimate
Construction Documents
30 | Batch 01 | Infra - Grading
|  |  | Survey Drawing |  | Road Center Line, Setout Plan & Tables | [7 empty] | Boundary Wall Details
|  |  | Existing Structure Demolition Plan |  | Road plans & Profile Sections | [7 empty] | Typical Road Details
|  |  | Area Details & Plot Schedule |  | Isopach Plan | [7 empty] | Typical Planter Box Details
|  |  | Master Plan - GA |  | Typical Grading Sections
Part plans - Plot Set Outs, Tree Transplantation info, Road Set out.
Master Plan - Boundary Wall
Boundary Wall Details
Road Sections - GA
30 | Batch 02 | Infra - MEP
|  |  | Junction Details |  | Master Plan - Road Storm Drain Network with Sheet Index |  |  |  | Master Plan - Zoning, Equipment and Cable Routing Layout. |  | Site Plan CCTV Layout |  | Storm Water Drain & Chamber Details |  | LDS - 01
|  |  | Plot Entry Ramp Details |  | Storm Drain - Road Plan & Profile Sections, Open space Catch Basin Tap off points. |  |  |  | Enlarged plans for Cable Routing |  | Standard Details for CCTV |  | Sewage chmaber details |  | General Arrangement Plan
|  |  | Cul-de-sac Details |  | Storm Drain Pipe Details |  |  |  | Tranformer & DG Yard Details |  |  |  | Electrical Chamber Details |  | All Marking Plan
[5 empty] | Storm Drain Structure Table |  |  |  | Feeder Pillar Details |  |  |  | Trench Details |  | Material Details
[5 empty] | Storm Drain Details |  |  |  | Site Plan Earthing Layout |  |  |  | Plot Entry Ramp Details |  | Irrigation plan
[5 empty] | Master Plan - Sanitary and Sewer Network |  |  |  | Earthing Scheme |  |  |  | Tranformer & DG Yard Details |  | Tree and Shrub Planting plans
[5 empty] | Sanitary & Sewer - Road Plan & Profile Sections, including plot connections |  |  |  | Earthing layout for tranformer and DG Yrads | [5 empty] | Sections, Elevations & Details
[5 empty] | Pipe Table SS network |  |  |  | Standard Details for Street Lights
[5 empty] | Structure Table SS Network |  |  |  | Site - Power Disbibution Scheme
[5 empty] | Sanitary Sewer Details |  |  |  | Elctrical Chamber & Pipe Details
Master Plan - Water Supply Network
Water Supply Network Cover Sheet
Roads Water Supply Plans
Water Supply Structure Table
Water Supply Details
30 | Batch 03 | BOQ & Technical Specifications
|  |  | Design Brief Report |  | Design Brief Report |  | Design Brief Report |  | Design Brief Report |  | Design Brief Report |  |  |  | Design Brief Report |  | 30
|  |  | BOQ |  | BOQ |  | BOQ |  | BOQ |  | BOQ |  |  |  | BOQ |  | 30
|  |  | List of Approved Make |  | List of Approved make |  | List of Approved Make |  | List of Approved Make |  | List of Approved Make |  |  |  | Technical Specification |  | 30
|  |  | Technical Specification |  | Technical Specification |  | Technical Specification |  | Technical Specification |  | Technical Specification | [5 empty] | 15
|  |  | Material & Finishes Schedule | [13 empty] | 30
|  |  | Luminaire Schedule | [13 empty] | 15
15 | Batch 04 | Infra - Coordinated | [14 empty] | 15
[5 empty] | Master Plan - Coordinated MEP Layout | [9 empty] | LDS - 02 |  | 15
[5 empty] | Coordinated Road Section | [9 empty] | General Arrangement Plan |  | 30
[15 empty] | All Marking Plan |  | 30
[15 empty] | Material Details |  | 30
[15 empty] | Irrigation plan |  | 15
Tree and Shrub Planting plans
[15 empty] | Sections, Elevations & Details |  | 285 | 9.5
15 -Std | Batch 05 | Structures - Security Cabin and Entrance
45 |  |  | Security Cabin & Enterance Details |  |  |  | Security Cabin & Enterance Details |  | Security Cabin & Enterance Details |  |  |  | Security Cabin & Enterance Details |  | LDS - 02
General Arrangement Plan
All Marking Plan
Material Details
Irrigation plan
Tree and Shrub Planting plans
Sections, Elevations & Details
15 | Batch 06 | Infra - Plot Boundary & Enclosures
|  |  | Plot Compound wall details | [9 empty] | Plot Gate Structural Details |  | LDS - 03
|  |  | Plot Gate Details | [9 empty] | Plot Compound wall details |  | General Arrangement Plan
|  |  | Yard Fencing Details | [9 empty] | Light Pole Foundation |  | All Marking Plan
Material Details
Irrigation plan
Tree and Shrub Planting plans
Sections, Elevations & Details
15 | Batch 07 | Infra - Signage & Street Lighting
|  |  | Master Plan - Signage | [5 empty] | Site Plan - External Lighting Layout | [5 empty] | LDS - 04
|  |  | Signage Details | [5 empty] | External Lighting Distribution Scheme |  |  |  | footing |  | General Arrangement Plan
|  |  | Signage Specification & Schedule | [11 empty] | All Marking Plan
|  |  | Traffic Circulation | [11 empty] | Material Details
|  |  | Master Plan - Street Lighting | [11 empty] | Irrigation plan
|  |  | Street Light details | [11 empty] | Tree and Shrub Planting plans
|  |  | Street Light Schedule | [11 empty] | Sections, Elevations & Details
15 | Batch 08 | Structures - Electrical Room & Toilet Block
|  |  | Electrical Room Details | [5 empty] | Electrical Room Details |  |  |  | Electrical Room Details |  | LDS - 04
|  |  | Bus Stop Drawings |  |  |  | Toilet Pod Drawings |  | Toilet Pod Drawings |  |  |  | Bus Stop Details |  | General Arrangement Plan
|  |  | Toilet Pod Drawings | [9 empty] | Toilet Pod Drawings |  | All Marking Plan
Material Details
Irrigation plan
Tree and Shrub Planting plans
Sections, Elevations & Details
30 | Batch 09 | Structures - UGT
|  |  | UGT Layout & Details |  |  |  | UGT Layout & Details |  | UGT Layout & Details |  |  |  | UGT Layout & Details |  | LDS - 04
|  |  | WTP Layout, Details |  |  |  | WTP Layout, Details |  | WTP Electrical Layout |  |  |  | WTP Layout, Details |  | General Arrangement Plan
All Marking Plan
Material Details
Irrigation plan
Tree and Shrub Planting plans
Sections, Elevations & Details
15 | Batch 10 | Structures - OHT
|  |  | OHT Layout & Details |  |  |  | OHT Layout & Details |  | OHT Layout & Details |  |  |  | OHT Layout & Details |  | LDS - 04
General Arrangement Plan
All Marking Plan
Material Details
Irrigation plan
Tree and Shrub Planting plans
Sections, Elevations & Details
15 | Batch 11 | Structures - STP
|  |  | STP Layout, Details |  |  |  | STP Layout, Details |  | STP Electrical Layout |  |  |  | STP Layout, Details |  | Same as Above
30 | Batch 12 | Structures - OWC & Other Structures
Same as Above
|  |  | OWC Layout, Details |  |  |  | OWC Layout, Details |  | OWC Electrical Layout |  |  |  | OWC Layout, Details
|  |  | Culvert Details (if Any) | [11 empty] | Master General Arrangement Plan
|  |  | Other Details | [11 empty] | LDS - 06
|  |  | Other Architectural Elements. | [11 empty] | General Arrangement Plan
|  |  | Elevated Cycling Track | [9 empty] | Elevated Cycling Track Details |  | All Marking Plan
|  |  | Nallah Details | [9 empty] | Nala Details (If Any) |  | Material Details
Irrigation plan
Tree and Shrub Planting plans
Sections, Elevations & Details
Note on D24: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inputs for Tree Transplantation from LDS
Note on F53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inputs from Electrical.
Note on J70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inputs from MP Team
Note on F71: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inputs from Electrical.
Note on J78: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Inputs from MP Team

## BOQ cost
Project Name - [Code] (Fee calculations) |  | BOQ Cost |  |  |  | Design Fee | 5% | 3% | 2% | 7%
1 | Total Construction cost | Architectural | Structural | MEP | Landscaping |  | Architectural | Structural | MEP | Landscaping
| Total | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
A | Plotted development | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Site Development | [5 empty] | 0 | 0 | 0 | 0
| Site MEP | [5 empty] | 0 | 0 | 0 | 0
| Utilities | [5 empty] | 0 | 0 | 0 | 0
| Amenities | [5 empty] | 0 | 0 | 0 | 0
B | Commercial | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0
| Tower - Office | [5 empty] | 0 | 0 | 0 | 0
| Health + Wellness | [5 empty] | 0 | 0 | 0 | 0
| Hospitality (Resort) | [5 empty] | 0 | 0 | 0 | 0

## Drawing list ¦ MP & AR
| 0118 Violet Hill | [10 empty] | P26 | 1 | 2 | 3 | 4 | A26 | 5 | 6 | 7 | 8 |  | P27 | 9 | 10 | 11 | 12 | A27 | 13 | 14 | 15 | 16
| Sl. No. | Drawing No. |  |  | DRAWING NAME | Location | Batch Code | Batch | Issue Status |  |  | 33 | 33 | 0 | 0 | 0 | Issue in Yr 2026 | 0 | 33 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Issue in Yr 2027 | 0 | 0 | 0 | 0
| Discipline | Area of works | Sheet No | Dwg. No. |  |  |  |  | Till Dec'25 | Date of receipt | Revision | Plan for Yr 2026 | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Till Dec'26 | Plan for Yr 2027 | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4
GFC ¦ INFRA - GRADING
UD | MP | 000 | 0001 | MP-000-0001 | MASTER PLAN-GENERAL ARRANGEMENT | MP | 1 | UD-MP-1 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | 000 | 0003 | MP-000-0003 | MASTER PLAN-SETTING OUT-PLOTS & ROADS | MP | 1 | UD-MP-1 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | 000 | 0004 | MP-000-0004 | MASTER PLAN-SETTING OUT-SIGNAGE, CCTV, LIGHT POLES | MP | 1 | UD-MP-1 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | 000 | 0005 | MP-000-0005 | MASTER PLAN-PERIPHERAL BOUNDARY WALL | MP | 1 | UD-MP-1 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | GR | 0001 | MP-GR-0001 | MASTER PLAN-ROAD GRADING | MP | 1 | UD-MP-1 | -1 | 2026-04-23 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | GR | 0002 | MP-GR-0002 | MASTER PLAN-SITE SECTIONS | MP | 1 | UD-MP-1 | -1 | 2026-04-23 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | GR | 0003 | MP-GR-0003 | MASTER PLAN-ISOPACH | MP | 1 | UD-MP-1 | -1 | 2026-04-23 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | GR | 0004 | MP-GR-0004 | MASTER PLAN-RETAINING WALL | MP | 1 | UD-MP-1 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3011 | MP-RDS-3011 | ROAD SECTION-R30N SECTION 1 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3012 | MP-RDS-3012 | ROAD SECTION-R30N SECTION 2 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3013 | MP-RDS-3013 | ROAD SECTION-R30N SECTION 3 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3021 | MP-RDS-3021 | ROAD SECTION-R33N SECTION 1 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3022 | MP-RDS-3022 | ROAD SECTION-R33N SECTION 2 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3023 | MP-RDS-3023 | ROAD SECTION-R33N SECTION 3 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3031 | MP-RDS-3031 | ROAD SECTION-R40N SECTION 1 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3032 | MP-RDS-3032 | ROAD SECTION-R40N SECTION 2 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3033 | MP-RDS-3033 | ROAD SECTION-R40N SECTION 3 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3041 | MP-RDS-3041 | ROAD SECTION-R40D SECTION 1 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3042 | MP-RDS-3042 | ROAD SECTION-R40D SECTION 2 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | RDS | 3043 | MP-RDS-3043 | ROAD SECTION-R40D SECTION 3 | MP | 1 | UD-MP-1 | -1 | 2026-04-24 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
GFC ¦ INFRA - COORDINATED
UD | MP | CO | 0001 | =CONCATENATE(B26,"-",C26,"-",D26) | MASTER PLAN-CO-ORDINATED UTILITIES | MP | 1 | UD-MP-1 | -1 | 2026-08-17 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | CO | 3001 | =CONCATENATE(B27,"-",C27,"-",D27) | STREET SECTIONS 1-1', 2-2', 3-3', 4-4' | MP | 1 | UD-MP-1 | -1 | 2026-08-14 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | CO | 3002 | MP-CO-3002 | STREET SECTIONS 5-5', 6-6', 7-7', 8-8' | MP | 1 | UD-MP-1 | -1 | 2026-08-14 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | CO | 3003 | MP-CO-3003 | STREET SECTIONS 9-9', 10-10', 11-11', 12-12' | MP | 1 | UD-MP-1 | -1 | 2026-08-14 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | CO | 3004 | MP-CO-3004 | STREET SECTIONS 13-13', 14-14', 15-15' | MP | 1 | UD-MP-1 | -1 | 2026-08-14 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
GFC ¦ INFRA - MEP
UD | MP | SD | 0001 | MP-SD-0001 | MASTER PLAN-STORM DRAIN SLD | MP | 2 | UD-MP-2 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | SD | 0002 | MP-SD-0002 | MASTER PLAN-STORM DRAIN | MP | 2 | UD-MP-2 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | SS | 0001 | MP-SS-0001 | MASTER PLAN-SANITARY SEWER SLD | MP | 2 | UD-MP-2 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | SS | 0002 | MP-SS-0002 | MASTER PLAN-SANITARY SEWER | MP | 2 | UD-MP-2 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | WS | 0001 | MP-WS-0001 | MASTER PLAN-WATER SUPPLY SLD | MP | 2 | UD-MP-2 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | WS | 0002 | MP-WS-0002 | MASTER PLAN-WATER SUPPLY | MP | 2 | UD-MP-2 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | MP | WS | 0003 | MP-WS-0003 | MASTER PLAN-IRRIGATION SLD | MP | 2 | UD-MP-2 | -1 | 2026-08-10 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
GFC ¦ STRUCTURES - SECURITY CABIN AND ENTRANCE
UD | MP | SC1 | 0001 | MP-SC1-0001 | SC1- SITE PLAN & SECTION | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 1001 | MP-SC1-1001 | MASONRY AND FLOORING PLAN | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 1002 | MP-SC1-1002 | SECURITY CABIN 1 - ELECTRICAL PLAN | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 1003 | MP-SC1-1003 | SECURITY CABIN 1 - DRAINAGE PLAN | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 2001 | MP-SC1-2001 | ELEVATION & SECTIONS | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4001 | MP-SC1-4001 | GUARD ROOM PLAN | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4002 | MP-SC1-4002 | CONTROL ROOM PLAN | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4003 | MP-SC1-4003 | CIRCULAR SKY LIGHT - TERRACE DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4004 | MP-SC1-4004 | CUTOUT DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4005 | MP-SC1-4005 | STAFF TOILET PLAN | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4006 | MP-SC1-4006 | FEMALE WASH & SEATING DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4007 | MP-SC1-4007 | MALE WASH & URINAL DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4008 | MP-SC1-4008 | TYPICAL SHOWER DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4009 | MP-SC1-4009 | TYPICAL WC DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4010 | MP-SC1-4010 | STORM DRAIN - RAIN WATER GRATING DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4011 | MP-SC1-4011 | GATE DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4012 | MP-SC1-4012 | EXTERNAL JALLI DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | MP | SC1 | 4013 | MP-SC1-4013 | FENESTRATION DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
UD | ELE | SC1 | 1002 | ELE-SC1-1002 | SECURITY CABIN - ELECTRICAL SLD | MP | 5 | UD-MP-5 | 1 | 2025-09-12 | R0
GFC ¦ INFRA - PLOT BOUNDARY AND ENCLOSURES
UD | MP | TEM | 0001 | MP-TEM-0001 | MASTER PLAN TEMPORARY BOUNDARY WALL | MP | 6 | UD-MP-6 | -1 | 2026-03-06 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1

## Drawing list ¦ ST
| 0118 Violet Hill | [10 empty] | P26 | 1 | 2 | 3 | 4 | A26 | 5 | 6 | 7 | 8 |  | P27 | 9 | 10 | 11 | 12 | A27 | 13 | 14 | 15 | 16
| Sl. No. | Drawing No. |  |  | DRAWING NAME | Location | Batch Code | Batch | Issue Status |  |  | 0 | 0 | 0 | 0 | 0 | Issue in Yr 2026 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Issue in Yr 2027 | 0 | 0 | 0 | 0
| Discipline | Area of works | Sheet No | Dwg. No. |  |  |  |  | Till Dec'25 | Date of receipt | Revision | Plan for Yr 2026 | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Till Dec'26 | Plan for Yr 2027 | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4
GFC ¦ INFRA - GRADING
UD | S | BXX | RW0001 | S-BXX-RW0001 | ROAD RETAINING WALL / INDIVIDUAL PLOT BOUNDARY WALL DETAILS (SHEET-1) | MP | 2 | UD-MP-2 | -1 | 2026-05-14 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | S | BXX | RW0002 | S-BXX-RW0002 | ROAD RETAINING WALL / INDIVIDUAL PLOT BOUNDARY WALL DETAILS (SHEET-2) | MP | 2 | UD-MP-2 | -1 | 2026-05-14 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | S | BXX | RW0003 | S-BXX-RW0003 | ROAD RETAINING WALL / INDIVIDUAL PLOT BOUNDARY WALL DETAILS (SHEET-3) | MP | 2 | UD-MP-2 | -1 | 2026-05-14 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | S | BXX | RW0004 | S-BXX-RW0004 | RETAINING WALL MISCELLANEOUS DETAILS | MP | 2 | UD-MP-2 | -1 | 2026-05-14 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
GFC ¦ STRUCTURES - SECURITY CABIN AND ENTRANCE
UD | S | SC1 | FD0001 | S-SC1-FD0001 | FOUNDATION LAYOUT | MP | 5 | UD-MP-5 | 1 | 2025-09-05 | R0
UD | S | SC1 | FD0002 | S-SC1-FD0002 | FOOTING REINF. DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-05 | R0
UD | S | SC1 | FD0003 | S-SC1-FD0003 | FOOTING CF1 REINF. DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-05 | R0
UD | S | SC1 | FD0004 | S-SC1-FD0004 | FOOTING CF6 REINF. DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-05 | R0
UD | S | SC1 | CL0001 | S-SC1-CL0001 | COLUMN REINF. DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-05 | R0
UD | S | SC1 | FP0001 | S-SC1-FP0001 | FRAMING PLAN AT ROOF LEVEL | MP | 5 | UD-MP-5 | 1 | 2025-09-05 | R0
UD | S | SC1 | BM0001 | S-SC1-BM0001 | REINFORCEMENT DETAILS OF BEAM 0B1 & 0B2 | MP | 5 | UD-MP-5 | 1 | 2025-09-05 | R0
UD | S | SC1 | BM0002 | S-SC1-BM0002 | REINFORCEMENT DETAILS OF BEAM 0B3 & 0B4 | MP | 5 | UD-MP-5 | 1 | 2025-09-05 | R0
UD | S | SC1 | BM0003 | S-SC1-BM0003 | BEAM B1, B2, B3, & B4 REINFORCEMENT DETAILS | MP | 5 | UD-MP-5 | 1 | 2025-09-29 | R0
UD | S | SC1 | BM0004 | S-SC1-BM0004 | BBS OF BEAM B1, B2, B3 & B4 | MP | 5 | UD-MP-5 | 1 | 2025-09-29 | R0
UD | S | SC1 | SB0001 | S-SC1-SB0001 | SLAB BOTTOM REINF. DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-29 | R0
UD | S | SC1 | SB0002 | S-SC1-SB0002 | BBS FOR SLAB BOTTOM REINF. DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-29 | R0
UD | S | SC1 | SB0003 | S-SC1-SB0003 | SLAB TOP REINF. DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-29 | R0
UD | S | SC1 | SB0004 | S-SC1-SB0004 | BBS FOR SLAB TOP REINF. DETAIL | MP | 5 | UD-MP-5 | 1 | 2025-09-29 | R0
UD | S | SC1 | SB0005 | S-SC1-SB0005 | SLAB SHEAR REINF. DETAIL AND SECTIONS | MP | 5 | UD-MP-5 | 1 | 2025-09-29 | R0
GFC ¦ STRUCTURES - PROJECT EXPERIENCE
| S | AS01 | FD0101 | S-AS01-FD0101 | FOUNDATION LAYOUT | DC | 5 | UD-DC-5 | -1 | 2026-07-16 | R0 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
| S | AS01 | FD0102 | S-AS01-FD0102 | FOOTING & COLUMN BASE CONNECTION DETAILS | DC | 5 | UD-DC-5 | -1 | 2026-07-16 | R0 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
| S | AS01 | FD0101 | S-AS01-FP0101 | FRAMING PLAN AT SSL 01 | DC | 5 | UD-DC-5 | -1 | 2026-07-16 | R0 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
| S | AS01 | FD0101 | S-AS01-FP0102 | CANOPY SECTIONS DETAILS | DC | 5 | UD-DC-5 | -1 | 2026-07-16 | R0 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1
| S | AS01 | FD0101 | S-AS01-FP0201 | FRAMING PLAN AT SSL 02 | DC | 5 | UD-DC-5 | -1 | 2026-07-16 | R0 | 1 |  |  | 1 |  | 1 |  |  | 1 |  | 1

## Drawing list ¦ MEP
| 0118 Violet Hill | [10 empty] | P26 | 1 | 2 | 3 | 4 | A26 | 5 | 6 | 7 | 8 |  | P27 | 9 | 10 | 11 | 12 | A27 | 13 | 14 | 15 | 16
| Sl. No. | Drawing No. |  |  | DRAWING NAME | Location | Batch Code | Batch | Issue Status |  |  | 0 | 0 | 0 | 0 | 0 | Issue in Yr 2026 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | Issue in Yr 2027 | 0 | 0 | 0 | 0
| Discipline | Area of works | Sheet No | Dwg. No. |  |  |  |  | Till Dec'25 | Date of receipt | Revision | Plan for Yr 2026 | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4 | Till Dec'26 | Plan for Yr 2027 | Q1 | Q2 | Q3 | Q4 |  | Q1 | Q2 | Q3 | Q4
GFC ¦ INFRA - MEP
UD | IBMS | 000 | 0001 | IBMS-000-0001 | SITE PLAN CCTV LAYOUT | MP | 2 | UD-MP-2 | -1 | 2026-05-22 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | ELE | 00 | 0001 | ELE-00-0001 | SITE PLAN EQUIPMENT AND CABLE ROUTING LAYOUT | MP | 2 | UD-MP-2 | -1 | 2026-08-13 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | ELE | 00 | 0031 | ELE-00-0031 | SITE PLAN EARTHING LAYOUT | MP | 2 | UD-MP-2 | -1 | 2026-08-28 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | ELE | 00 | 0032 | ELE-00-0032 | TRANSFORMER YARD EARTHING LAYOUT | MP | 2 | UD-MP-2 | -1 | 2026-08-28 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | ELE | 00 | 0033 | ELE-00-0033 | SITE PLAN EARTHING SCHEME | MP | 2 | UD-MP-2 | -1 | 2026-08-28 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | ELE | 00 | 0041 | ELE-00-0041 | SITE PLAN EXTERNAL LIGHTING LAYOUT | MP | 2 | UD-MP-2 | -1 | 2026-05-22 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | ELE | 00 | 9001 | ELE-00-9001 | POWER DISTRIBUTION SCHEME | MP | 2 | UD-MP-2 | -1 | 2026-05-22 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | ELE | 00 | 9002 | ELE-00-9002 | STANDARD NOTES AND FEEDER PILLAR DETAILS | MP | 2 | UD-MP-2 | -1 | 2026-05-22 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | ELE | TY | 0021 | ELE-TY-0021 | ENLARGED VIEW OF TRANSFORMER YARD AND SECTION LAYOUT | MP | 2 | UD-MP-2 | -1 | 2026-08-28 | R2 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
UD | ELE | TY | 0022 | ELE-TY-0022 | FEEDER PILLAR LAYOUT | MP | 2 | UD-MP-2 | -1 | 2026-05-22 | R0 | 1 | 1 |  |  |  | 1 |  | 1 |  |  | 1
GFC ¦ STRUCTURES - SECURITY CABIN AND ENTRANCE
UD | PHE | SC1 | 0001 | PHE-SC1-0001 | SECURITY CABIN ENLARGED TOILET DETAILS DRAINAGE LAYOUT | MP | 5 | UD-MP-5 | 1 | 2025-09-15 | R0
UD | PHE | SC1 | 0002 | PHE-SC1-0002 | SECURITY CABIN DRAINAGE LAYOUT | MP | 5 | UD-MP-5 | 1 | 2025-09-15 | R0