## 0052 Imagine FY26-27Q3
0052 Imagine Campus ¦ Design package release FY26-27 Q3 |  |  |  |  | 1.49 | 6 | 0 | 0
Project | Description | Release date | Responsible | Remarks | Plan - Billing [Cr.] | Plan - Pkgs | Actuals - Billing [Cr.] | Actuals - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks
Imagine Campus | Package Release |  |  |  | 1.49 | 6 | 0 | 0
Architecture | Package Release [Complete LoD 100, 200] |  |  |  | 1.15 | 2 | 0 | 0
Imagine Campus | LoD 200 - Schematic Concept | 2026-12-14 | Naveen Y |  | 0.69 | 1 | 0 |  | Naveen Y | Akhila G | Fathima S
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
Imagine Campus | Approvals | 2026-12-17 | Naveen Y |  | 0.46 | 1 | 0 |  | Naveen Y | Akhila G | Fathima S
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
Structural | Package Release [Complete LoD 200] |  |  |  | 0.19 | 1 | 0 | 0
Imagine Campus | LoD 200 - Schematic Concept | 2026-12-14 | Prakash C |  | 0.19 | 1 | 0 |  | Prakash C | Lincy | Charan | - | Karthik |  | 0
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
MEP | Package Release [Complete LoD 200] |  |  |  | 0.1 | 2 | 0 | 0
Imagine Campus | LoD 200 - Schematic Concept | 2026-12-14 | Gagan |  | 0.05 | 1 | 0 |  | Gagan | Salomi | Hareesha Bhavya | Byahattimath Shreedhar Viresh
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
Imagine Campus | Approvals |  | Gagan |  | 0.05 | 1 | 0 |  | Gagan | Salomi | Hareesha Bhavya | Byahattimath Shreedhar Viresh
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
Landscape | Package Release [Complete LoD 200] |  |  |  | 0.05 | 1 | 0 | 0
Imagine Campus | Approvals | 2026-12-21 | Gagan |  | 0.05 | 1 | 0 |  | Gagan | Lajja | Aproova
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2

## 0052Imagine Pkgs Smmy (Status)
| 0052 ¦ Imagine Campus |  | AR | ST | MEP | LS |  | 1 | Completed
|  | Scope | 8 | 5 | 7 | 4 |  | -1 | Pending
|  | Actuals | 2 | 0 | 0 | 0 |  |  | NA
DESIGN CONCEPT
1 | 1 | Contract + Design Brief | 1
2 | 2 | Schematic Concept | -1 | -1 | -1 | -1
3 | 3 | Pre Construction Set | -1 | -1 | -1 | -1
4 | 4 | Approvals | 1 |  | -1 |  | MEPF Approvals pending
CONSTRUCTION DOCUMENTS
4 | 1 | GFC ¦ Tower—01
T01-01 | 1 | Foundation and Grade Slab | -1 | -1 | -1
T01-02 | 2 | Building Envelope and Plot development | -1 | -1 | -1 | -1
T01-03 | 3 | Interiors | -1 |  | -1
POST-CONSTRUCTION
1 | 1 | Archives
1 | 1 | Complete set of "As-Built" drawings, final BoQ and project costs, | -1 | -1 | -1 | -1

## Goals FY 26-27Q2 (hidden)
FY 2026-27 Q2 ¦ Design Goals + Billing |  |  |  |  | 1.49 | 6 | 0 | 0 | [7 empty] | 1.49 | 6
Project | Description | Release date | Responsible | Remarks | Plan - Billing [Cr.] | Plan - Pkgs | Actuals - Billing [Cr.] | Actuals - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | 0% | 0%
Imagine Campus | Package Release |  |  |  | 1.49 | 6 | 0 | 0
Architecture | Package Release [Complete LoD 100, 200] |  |  |  | 1.15 | 2 | 0 | 0
Imagine Campus | LoD 200 - Schematic Concept |  | Naveen Y |  | 0.69 | 1 | 0 |  | Naveen Y | Akhila G | Fathima S
Imagine Campus | Approvals |  | Naveen Y |  | 0.46 | 1 | 0 |  | Naveen Y | Akhila G | Fathima S
Structural | Package Release [Complete LoD 200] |  |  |  | 0.19 | 1 | 0 | 0
Imagine Campus | LoD 200 - Schematic Concept |  | Prakash C |  | 0.19 | 1 | 0 |  | Prakash C | Lincy | Charan | - | Karthik |  | 0
MEP | Package Release [Complete LoD 200] |  |  |  | 0.1 | 2 | 0 | 0
Imagine Campus | LoD 200 - Schematic Concept |  | Gagan |  | 0.05 | 1 | 0 |  | Gagan | Salomi | Hareesha Bhavya | Byahattimath Shreedhar Viresh
Imagine Campus | Approvals |  | Gagan |  | 0.05 | 1 | 0 |  | Gagan | Salomi | Hareesha Bhavya | Byahattimath Shreedhar Viresh
Landscape | Package Release [Complete LoD 200] |  |  |  | 0.05 | 1 | 0 | 0
Imagine Campus | Approvals |  | Gagan |  | 0.05 | 1 | 0 |  | Gagan | Lajja | Aproova