## 0059 PoaRR FY 26-27Q3
PoaRR ¦ Design package release FY26-27 Q3 |  |  |  |  | 10.1666 | 38 | 0.6 | 2
Project | Description | Release date | Responsible | Remarks | Plan - Billing [Cr.] | Plan - Pkgs | Actuals - Billing [Cr.] | Actuals - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson
PoaRR-Res | Package Release |  |  |  | 4.127 | 14 | 0.6 | 2
Architecture | Complete the project |  |  |  | 3.3659 | 8 | 0.6 | 2
PoaRR-Res | LOD 350 Villa Cluster 3 - All Levels | 2026-09-30 | Saji P |  | 0.17 | 1 | 0 |  | Saji A | Gokul | Krishnapriya
| Glazing Details - Skylight, Car Parking Canopy, External Canopy | 2026-09-24 | Gokul
| Courtyard Wall Details | 2026-09-24 | Gokul
| Wirecut Details - Car Parking & Rear Garden | 2026-09-24 | Gokul
| Wirecut Details - Corbel, End Villa 50, 69 | 2026-09-28 | Gokul
PoaRR-Res | LOD 350 Villa Cluster 3 - Building Envelope and Common Areas | 2026-09-30 | Saji P |  | 0.17 | 1 | 0 |  | Saji A | Gokul | Krishnapriya
| Rear Garden Fencing Details | 2026-09-24 | Gokul
| Expansion Joint Details | 2026-09-28 | Gokul | Pending discussion with Site team
PoaRR-Res | LOD 350 V40 Default and it's variants | 2026-10-05 | Saji P |  | 1.18 | 1 | 0 |  | Saji A | Nirupama
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-Res | LOD 350 ISS Building Envelope and Common Areas | 2026-12-23 | Saji P |  | 1.0659 | 1 | 0 |  | Saji A | Arshad | Latha
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-Res | LOD 350 Residential - Site Development | 2026-08-30 | Saji P | Completed | 0.45 | 1 | 0.45 | 1 | Saji A | Sathwik
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-Res | LOD 350 Masterplan - Site MEP | 2026-12-18 | Saji P |  | 0.15 | 1 | 0 |  | Saji A | Sathwik
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-Res | LOD 350 Masterplan - Landscaping | 2026-08-30 | Saji P | Completed | 0.15 | 1 | 0.15 | 1 | Saji A | Sathwik
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-Res | LOD 350 Amenities & Facilities - Sporting Facilities | 2026-12-30 | Saji P |  | 0.03 | 1 | 0 |  | Saji A | Sathwik | Abdul
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
Structural | Complete the project |  |  |  | 0.36 | 3 | 0 | 0
PoaRR-Res | LOD 350 Site Development | 2026-10-15 | Prakash C |  | 0.19 | 1 | 0 |  | Prakash C | Lincy | Subrahmanya |  | Darshan
Step 1 | Boundary walls - V40 and near stepped towers | 2026-10-15 | User 1 | Awaiting arch details ( 20 days)
PoaRR-Res | LOD 350 Site MEP | 2026-12-29 | Prakash C |  | 0.16 | 1 | 0 |  | Prakash C | Lincy | Subrahmanya |  | Darshan
Step 1 | OWC structure | 2026-10-15 | User 1 | Awaiting arch details (20 days)
PoaRR-Res | LOD 350 Sporting Facilities | 2026-10-30 | Prakash C |  | 0.01 | 1 | 0 |  | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan
Step 1 | Foundation layout, framing plans | 2026-10-15 | User 1 | issued
Step 2 | Details drawings (foundation, and all other levels) | 2026-10-30 | User 2 | Awaiting clarity and clearance - arch ( duration - based on extent of modifications)
MEP | Complete the project |  |  |  | 0.36109 | 2 | 0 | 0
PoaRR-Res | LOD 350 Site MEP | 2026-12-31 | Gagan |  | 0.36 | 1 | 0 |  | Gagan | Salomi | Hareesha Praveen | Byahattimath Shreedhar Mahadev Deepu Ajay
Step 1 | OWC drawings | 2026-10-15 | Praveen ST
PoaRR-Res | LOD 350 Sporting Facilities | 2026-12-30 | Gagan |  | 0.0010915 | 1 | 0 |  | Gagan | Salomi | Hareesha Praveen | Byahattimath Shreedhar Mahadev Deepu Ajay
| Electrical layouts | 2026-10-30 | Hareesha | Electrical layout & schedule required
| HVAC layouts | 2026-10-30 | Rinu
| PHE layouts | 2026-10-30 | Praveen ST | Updated arch plan awaited
| Fire fighting layouts | 2026-10-30 | Vallivel
Landscape | Complete the project |  |  |  | 0.04 | 1 | 0 | 0
PoaRR-Res | LOD 350 Amenities & Facilities - Community spaces [Sporting Facilities] | 2026-12-30 | Gagan |  | 0.04 | 1 | 0 |  | Gagan | Lajja | Apoorva
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-T08 | Package Release |  |  |  | 6.0396 | 24 | 0 | 0
Architecture | Package Release [Complete the project] |  |  |  | 3.8538 | 10 | 0 | 0
PoaRR-T08 | LOD 350 Habitable Level 01 | 2026-11-17 | Saji P |  | 0.48 | 1 | 0 |  | Saji A | Komal | Mononita
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 Building Envelope and Common Areas [Typical Tower Levels] | 2026-10-20 | Saji P |  | 0.96385 | 1 | 0 |  | Saji A | Komal | Mononita
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 L22 Default and variants [Modification for Dry Wall] | 2026-10-30 | Saji P |  | 0.52 | 1 | 0 |  | Saji A | Mononita | Shahbazz
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 R25 Default [Modification for Dry Wall] | 2026-10-05 | Saji P |  | 0.52 | 1 |  |  | Saji A | Aardra
Step 1 | Task description 1 | 2026-10-05 | User 1
Step 2 | Task description 2 | 2026-10-05 | User 2
PoaRR-T08 | LOD 350 L20 Default [Modification for Dry Wall] | 2026-10-05 | Saji P | BoQ closure pending | 0.52 | 1 | 0 |  | Saji A | Aardra | Komal
Step 1 | Task description 1 | 2026-10-05 | User 1
Step 2 | Task description 2 | 2026-10-05 | User 2
PoaRR-T08 | LOD 350 D35 Default [Modification for Dry Wall] | 2026-10-05 | Saji P | BoQ closure pending | 0.52 | 1 | 0 |  | Saji A | Komal | Aardra
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 Master Plan | 2026-12-22 | Saji P |  | 0.17 | 1 | 0 |  | Saji A | Vivek | Komal
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 Landscape | 2026-12-18 | Saji P |  | 0.03 | 1 | 0 |  | Saji A | Vivek | Komal
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 Site MEP | 2026-12-14 | Saji P |  | 0.03 | 1 | 0 |  | Saji A | Vivek | Komal
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 Site Development | 2026-12-23 | Saji P |  | 0.1 | 1 | 0 |  | Saji A | Vivek | Komal
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
Structural | Complete the project |  |  |  | 1.7 | 7 | 0 | 0
PoaRR-T08 | LOD 350 Penthouse Levels | 2026-10-06 | Prakash C |  | 0.2 | 1 | 0 |  | Prakash C | Lincy | Jayashankar | Subrahmanya | Darshan
Step 1 | Framing plan, Beams and slabs | 2026-10-15 | User 1 | issued
Step 2 | sleeves | 2026-10-30 | User 2 | awaiting arch and services details
PoaRR-T08 | LOD 350 Terrace Level | 2026-11-05 | Prakash C |  | 0.4 | 1 | 0 |  | Prakash C | Lincy | Jayashankar | Subrahmanya | Darshan
Step 1 | Framing plan, Beams and slabs | 2026-10-15 | User 1 | Received arch drawing. Services drawings awaited. Planned in Nov (resources)
Step 2 | sleeves | 2026-10-30 | User 2 | awaiting arch and services details
PoaRR-T08 | LOD 350 T08 - ISS - Foundations & Grade Slab | 2026-12-04 | Prakash C |  | 0.32 | 1 | 0 |  | Prakash C | Lincy | Nadeem | - | Darshan
Step 1 | Foundations and columns | 2026-10-15 | User 1 | issued
Step 2 | tank walls | 2026-10-30 | User 2 | 30th Sept
PoaRR-T08 | LOD 350 T08 - ISS - Podium Slab | 2026-11-05 | Prakash C |  | 0.32 | 1 | 0 |  | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan
Step 1 | Framing plan, Beams and slabs | 2026-10-15 | User 1
Step 2 | sleeves | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 T08 - ISS - Parking Level Subgrade | 2026-10-28 | Prakash C |  | 0.43 | 1 | 0 |  | Prakash C | Lincy | Nadeem | Subrahmanya | Karthik
Step 1 | Framing plan, Beams and slabs - Staff lounge | 2026-10-15 | User 1 | issued
Step 2 | Framing plan, Beams and slabs - STP -walkway slabs | 2026-10-30 | User 2 | issued
PoaRR-T08 | LOD 350 Site Development | 2026-12-25 | Prakash C |  | 0.02 | 1 | 0 |  | Prakash C | Lincy | Subrahmanya | - | Karthik
Step 1 | Boundary walls | 2026-10-15 | User 1
Step 2 | Infra gradings (roads, pavements, chambers, trenches) | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 Site MEP | 2026-12-16 | Prakash C |  | 0.01 | 1 | 0 |  | Prakash C | Lincy | Subrahmanya | - | Karthik
Step 1 | Electrical panel rooms, DG sync, transformer yard, etc - Electrical related | 2026-10-15 | User 1 | Awaiting details
Step 2 | Task description 2 | 2026-10-30 | User 2
MEP | Package Release [Complete the project] |  |  |  | 0.46574 | 6 | 0 | 0
PoaRR-T08 | LOD 350 Terrace Level | 2026-12-23 | Gagan |  | 0.08574 | 1 | 0 |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep
Step 1 | Terrace cordinated layout | 2026-11-15 | Hareesha /Praveen/ Rinu/Vallivel | Electrical layout & schedule awaited
Step 2 | Terrace individual services layouts | 2026-11-15 | Hareesha /Praveen/ Rinu/Vallivel | Electrical layout & schedule awaited
PoaRR-T08 | LOD 350 L20 Default and it's variants | 2026-10-05 | Gagan | GFC released | 0.06 | 1 | 0 |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep
Step 1 | Task description 1 | 2026-10-05 | User 1
Step 2 | Task description 2 | 2026-10-05 | User 2
PoaRR-T08 | LOD 350 D35 Default and it's variants | 2026-10-05 | Gagan | GFC released | 0.06 | 1 | 0 |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 Master Plan | 2026-12-17 | Gagan |  | 0.04 | 1 | 0 |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep
Step 1 | MEP coordinated master plan | 2026-10-15 | Hareesha /Praveen/ Rinu/Vallivel | Awaiting for updated master plan from architects
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 Site MEP | 2026-12-21 | Gagan |  | 0.12 | 1 | 0 |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep
Step 1 | Task description 1 | 2026-10-15 | Hareesha /Praveen/ Rinu/Vallivel | Awaiting for updated master plan from architects
Step 2 | Task description 2 | 2026-10-30 | User 2
PoaRR-T08 | LOD 350 L22 Default and It's Variants [Modification for Dry Wall] | 2026-10-30 | Gagan |  | 0.1 | 1 | 0 |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep
Step 1 | Coordinated cut out details | 2026-10-30 | Hareesha /Praveen/ Rinu/Vallivel
Step 2 | Task description 2 | 2026-10-30 | User 2
Landscape | Package Release [Complete the project] |  |  |  | 0.02 | 1 | 0 | 0
PoaRR-T08 | LOD 350 T08-Clubhouse—Interiors and Facilities | 2026-12-28 | Gagan |  | 0.02 | 1 | 0 |  | Gagan | Lajja | Apoorva
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2

## Pkgs Summary (Status)- Resi (hidden)
|  | 0059 ¦ Pursuit of a Radical Rhapsody ¦ Residential |  | AR | ST | MEP | LS | 1 | Completed
|  |  | Scope | 108 | 91 | 66 | 28 | -1 | Pending
|  |  | Actuals | 101 | 87 | 63 | 26 |  | NA
DESIGN CONCEPT
| 1 | 1 | Contract + Design Brief | 1
| 2 | 2 | Schematic Concept | 1 | 1 | 1 | 1
| 3 | 3 | Pre Construction Set | 1 | 1 | 1 | 1
| 4 | 4 | Approvals | 1 |  | 1 | 1
| 5 | 5 | Marketing and Sales | 1 |  |  | 1
CONSTRUCTION DOCUMENTS
| 4 | 1 | GFC ¦ Tower—01
| T01-01 | 1 | Foundation and Grade Slab | 1 | 1 | 1
| T01-02 | 2 | Parking Level-Sub grade | 1 | 1
| T01-03 | 3 | Building Envelope and Common Areas [Basement] | 1
| T01-04 | 4 | Habitable Level 01 | 1 | 1 | 1
| T01-05 | 5 | Habitable Level - Even | 1 | 1
| T01-06 | 6 | Habitable Level - Odd | 1 | 1
| T01-07 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  | 1 |  |  |  | `
| T01-08 | 8 | Penthouse Levels | 1 | 1 | 1
| T01-09 | 9 | Terrace Level | 1 | 1 | 1
| T01-10 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1
| 5 | 2 | GFC ¦ Tower—2V
| T2V-01 | 1 | Foundation and Grade Slab | 1 | 1 | 1
| T2V-02 | 2 | Parking Level-Sub grade | 1 | 1
| T2V-03 | 3 | Building Envelope and Common Areas [Basement] | 1
| T2V-04 | 4 | Habitable Level 01 | 1 | 1 | 1
| T2V-05 | 5 | Habitable Level - Even | 1 | 1
| T2V-06 | 6 | Habitable Level - Odd | 1 | 1
| T2V-07 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  | 1
| T2V-08 | 8 | Penthouse Levels | 1 | 1
| T2V-09 | 9 | Terrace Level | 1 | 1 | 1
| T2V-10 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1
| 6 | 3 | GFC ¦ Tower—2S
| T2S-01 | 1 | Foundation and Grade Slab | 1 | 1 | 1
| T2S-02 | 2 | Parking Level-Sub grade |  | 1
| T2S-03 | 3 | Building Envelope and Common Areas [Basement] | 1
| T2S-04 | 4 | Habitable Level 01 - 02 | 1 | 1 | 1
| T2S-05 | 5 | Habitable Level - 03 - 06 | 1 | 1
| T2S-06 | 6 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  | 1 | 1
| T2S-07 | 7 | Penthouse Levels | 1 | 1 | 1
| T2S-08 | 8 | Terrace Level | 1 | 1 | 1
| T2S-09 | 9 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1 |  |  | 1
| 7 | 4 | GFC ¦ Tower—3V-5V
| TXV-01 | 1 | Foundation and Grade Slab | 1 | 1 | 1
| TXV-02 | 2 | Parking Level-Sub grade | 1 | 1
| TXV-03 | 3 | Building Envelope and Common Areas [Basement] | 1
| TXV-04 | 4 | Habitable Level 01 | 1 | 1 | 1
| TXV-05 | 5 | Habitable Level - Even | 1 | 1
| TXV-06 | 6 | Habitable Level - Odd | 1 | 1
| TXV-07 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  | 1
| TXV-08 | 8 | Penthouse Levels | 1 | 1
| TXV-09 | 9 | Terrace Level | 1 | 1 | 1
| TXV-10 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1
| 8 | 5 | GFC ¦ Tower—3S-5S
| TXS-01 | 1 | Foundation and Grade Slab | 1 | 1 | 1
| TXS-02 | 2 | Parking Level-Sub grade |  | 1
| TXS-03 | 3 | Building Envelope and Common Areas [Basement] | 1
| TXS-04 | 4 | Habitable Level 01 - 02 | 1 | 1 | 1
| TXS-05 | 5 | Habitable Level - 03 - 06 | 1 | 1
| TXS-06 | 6 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  | 1 | 1
| TXS-07 | 7 | Penthouse Levels | 1 | 1 | 1
| TXS-08 | 8 | Terrace Level | 1 | 1 | 1
| TXS-09 | 9 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1 |  |  | 1
| 9 | 6 | GFC ¦ Tower—6V
| T6V-01 | 1 | Foundation and Grade Slab | 1 | 1 | 1
| T6V-02 | 2 | Parking Level-Sub grade | 1 | 1
| T6V-03 | 3 | Building Envelope and Common Areas [Basement] | 1
| T6V-04 | 4 | Habitable Level 01 | 1 | 1 | 1
| T6V-05 | 5 | Habitable Level - Even | 1 | 1
| T6V-06 | 6 | Habitable Level - Odd | 1 | 1
| T6V-07 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  | 1
| T6V-08 | 8 | Penthouse Levels | 1 | 1
| T6V-09 | 9 | Terrace Level | 1 | 1 | 1
| T6V-10 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1
| 10 | 7 | GFC ¦ Tower—6S
T06S - Foundation and Grade Slab | T6S-01 | 1 | Foundation and Grade Slab | 1 | 1 | 1
T06S - Parking Level-Sub grade | T6S-02 | 2 | Parking Level-Sub grade |  | 1
T06S - Building Envelope and Common Areas [Basement] | T6S-03 | 3 | Building Envelope and Common Areas [Basement] | 1
T06S - Habitable Level 01 - 02 | T6S-04 | 4 | Habitable Level 01 - 02 | 1 | 1 | 1
T06S - Habitable Level - 03 - 06 | T6S-05 | 5 | Habitable Level - 03 - 06 | 1 | 1
T06S - Building Envelope and Common Areas [Typical Tower Levels] | T6S-06 | 6 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  | 1 | 1
T06S - Penthouse Levels | T6S-07 | 7 | Penthouse Levels | 1 | 1 | 1
T06S - Terrace Level | T6S-08 | 8 | Terrace Level | 1 | 1 | 1
T06S - Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | T6S-09 | 9 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1 |  |  | 1
| 11 | 8 | GFC ¦ Tower—07
| T07-01 | 1 | Foundation and Grade Slab | 1 | 1 | 1
| T07-02 | 2 | Parking Level-Sub grade | 1 | 1
| T07-03 | 3 | Building Envelope and Common Areas [Basement] | 1
| T07-04 | 4 | Habitable Level 01 | 1 | 1 | 1
| T07-05 | 5 | Habitable Level - Even | 1 | 1
| T07-06 | 6 | Habitable Level - Odd | 1 | 1
| T07-07 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  | 1
| T07-08 | 8 | Penthouse Levels | 1 | 1 | 1
| T07-09 | 9 | Terrace Level | 1 | 1 | 1
| T07-10 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1
| 2 | 9 | GFC ¦ Independent Subgrade Structure [Tower 1-7]
| SS0-01 | 1 | Earthwork |  | 1
| SS0-02 | 2 | Foundations & Grade Slab | 1 |  | 1
| SS0-03 | 3 | Podium Slab | 1 |  | 1
| SS0-04 | 4 | Building Envelope and Common Areas | -1 |  | 1
| 2.1 | 2.1 | GFC ¦ Independent Subgrade Structure—Block 01
| SS1-01 | 1 | Foundations & Grade Slab |  | 100%
| SS1-02 | 2 | Podium Slab |  | 100%
| 2.2 | 2.2 | GFC ¦ Independent Subgrade Structure—Block 02
| SS1-01 | 1 | Foundations & Grade Slab |  | 100%
| SS1-02 | 2 | Podium Slab |  | 100%
| 2.3 | 2.3 | GFC ¦ Independent Subgrade Structure—Block 03
| SS1-01 | 1 | Foundations & Grade Slab |  | 100%
| SS1-02 | 2 | Podium Slab |  | 100%
| 2.4 | 2.4 | GFC ¦ Independent Subgrade Structure—Block 04
| SS4-02 | 1 | Foundations & Grade Slab |  | 100%
| SS4-04 | 2 | Podium Slab |  | 100%
| 2.5 | 2.5 | GFC ¦ Independent Subgrade Structure—Block 05
| SS1-01 | 1 | Foundations & Grade Slab |  | 100%
| SS1-02 | 2 | Podium Slab |  | 100%
| 2.6 | 2.6 | GFC ¦ Independent Subgrade Structure—Block 06
| SS1-01 | 1 | Foundations & Grade Slab |  | 100%
| SS1-02 | 2 | Podium Slab |  | 100%
| 2.7 | 2.7 | GFC ¦ Independent Subgrade Structure—Block 07
| SS1-01 | 1 | Foundations & Grade Slab |  | 100%
| SS1-02 | 2 | Podium Slab |  | 100%
| 2.8 | 2.8 | GFC ¦ Independent Subgrade Structure—Block 08
| SS1-01 | 1 | Foundations & Grade Slab |  | 100%
| SS1-02 | 2 | Podium Slab |  | 100%
| 2.9 | 2.9 | GFC ¦ Independent Subgrade Structure—Block 09
| SS9-02 | 1 | Foundations & Grade Slab |  | 100%
| SS9-04 | 2 | Podium Slab |  | 100%
| 2.1 | 2.1 | GFC ¦ Independent Subgrade Structure—Block 10
| SS1-01 | 1 | Foundations & Grade Slab |  | 100%
| SS1-02 | 2 | Podium Slab |  | 100%
| 2.1 | 2.11 | GFC ¦ Independent Subgrade Structure—Block 11
| SS1-01 | 1 | Foundations & Grade Slab |  | 100%
| SS1-02 | 2 | Podium Slab |  | 100%
| 2.1 | 2.11 | GFC ¦ Independent Subgrade Structure—Block 12 [6V EXT BSMNT]
| SS1-01 | 1 | Foundations & Grade Slab |  | 100%
| SS1-02 | 2 | Podium Slab |  | 100%
| 12 | 10 | GFC ¦ Villas—Cluster 1 & 2
| VC1-01 | 1 | Foundations and Sub-Grade | 1 | 100% | 100%
| VC1-02 | 2 | All Levels | 1 | 100% | 100%
| VC1-03 | 3 | Building Envelope and Common Areas | 1 |  | 100% | 100%
| 13 | 11 | GFC ¦ Villas—Cluster 3
| VC3-01 | 1 | Foundations and Sub-Grade | 1 | 100% | 100%
| VC3-02 | 2 | All Levels | -1 | 100% | 100%
| VC3-03 | 3 | Building Envelope and Common Areas | -1 |  | 100% | 100%
| 15 | 14 | GFC ¦ Individual Homes
| C20-01 | 1 | C20 Default and it's variants | 1 |  | 1 | 100%
| L30-01 | 2 | L30 Default and it's variants | 1 |  | 1 | 100%
| L45-01 | 3 | L45 Default and it's variants | 1 |  | 1 | 100%
| V50-01 | 4 | V50 Default and it's variants | 1 |  | 1 | 100%
| V40-01 | 5 | V40 Default and it's variants | -1 |  | 1 | 100%
| V50-01 | 6 | R11 Default and it's variants | 1 |  | 1 | 100%
| V40-01 | 7 | R22 Default and it's variants | 1 |  | 1 | 100%
| C20-01 | 8 | C20P Default and it's variants | 1 |  | 1 | 100%
| L30-01 | 9 | L30P Default and it's variants | 1 |  | 1 | 100%
| L45-01 | 10 | L45P Default and it's variants | 1 |  | 1 | 100%
| 16 | 15 | GFC ¦ Master Plan
| SDV-01 | 1 | Master Plan | 100% |  | 100% | 100%
| SDV-02 | 2 | Site Development | 100% | -100%
| SDV-03 | 3 | Site MEP | -100% | -100% | -100%
| SDV-04 | 4 | Landscaping | 100% |  |  | 100%
| 17 | 16 | GFC ¦ Amenities & Facilities
Amenities & Facilities - Clubhouse—Structure and Envelope | AMN-01 | 1 | Clubhouse—Structure and Envelope | 100% | 100% | 100%
Amenities & Facilities - Clubhouse—Interiors and Facilities | AMN-02 | 2 | Clubhouse—Interiors and Facilities | 100% |  | 100% | 100%
Amenities & Facilities - Clubhouse—Outdoor Spaces and Pool | AMN-03 | 3 | Clubhouse—Outdoor Spaces and Pool | 100% | 100% | 100% | 100%
Amenities & Facilities - Community spaces [Board Walk, Children play area] | AMN-04 | 4 | Community spaces [Board Walk, Children play area] | 100% | 100% |  | -100%
Amenities & Facilities - Sporting Facilities | AMN-05 | 5 | Sporting Facilities | -100% | -100% | -100%
POST-CONSTRUCTION
| 1 | 1 | Archives
| 1 | 1 | Complete set of "As-Built" drawings, final BoQ and project costs, | -100% | -100% | -100% | -100%
MAJOR REWORKS

## Pkgs Summary (Status) - T08 (hidden)
| 0059 ¦ Pursuit of a Radical Rhapsody ¦ Tower-08 |  | AR | ST | MEP | LS | 1 | Completed
|  | Scope | 36 | 17 | 25 | 19 | -1 | Pending
|  | Actuals | 12 | 10 | 11 | 6 |  | NA
DESIGN CONCEPT
1 | 1 | Contract + Design Brief | 1
2 | 2 | Schematic Concept | 1 | 1 | 1 | 1
3 | 3 | Pre Construction Set | 1 | 1 | 1 | 1
4 | 4 | Approvals | 1 |  | 1 | 1
5 | 5 | Experience Home + Project Experience | 1 | 1 | 1 | 1
6 | 6 | Marketing and Sales | 1 |  |  | 1
CONSTRUCTION DOCUMENTS
BB01 | 1 | GFC ¦ Tower—08
BB01-1 | 1 | Foundation and Grade Slab | 1 | 1 | 1
BB01-2 | 2 | Parking Level-Sub grade | 1 | 1
BB01-3 | 3 | Building Envelope and Common Areas [Basement] | 1
BB01-4 | 4 | Habitable Level 01 | -1 | 1 | 1
BB01-5 | 5 | Habitable Level - Even | 1 | 1
BB01-6 | 6 | Habitable Level - Odd | 1 | 1
BB01-7 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | -1 | [5 empty] | `
BB01-8 | 8 | Penthouse Levels | -1 | -1 | -1
BB01-9 | 9 | Terrace Level | -1 | -1 | -1
BB01-10 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | -1
BB02 | 2 | GFC ¦ Independent Subgrade Structure - Tower 8
BB02-1 | 1 | Earthwork |  | 1
BB02-2 | 2 | Foundations & Grade Slab | -1 | -1 | 1
BB02-3 | 3 | Parking level Subgrade | -1 | 1 | 1
BB02-4 | 4 | Podium Slab | -1 | -1 | 1
BB02-5 | 5 | Building Envelope and Common Areas | -1 |  | 1
PD | 3 | GFC ¦ Individual Homes
R25-1 | 1 | R25 Default and it's variants | 1 |  | 1 | 1
L20-1 | 2 | L20 Default and it's variants | -1 |  | -1 | -1
D35-1 | 3 | D35 Default and it's variants | -1 |  | -1 | -1
L22-1 | 4 | L22 Default and it's variants | -1 |  | -1 | -1
R25P-1 | 5 | R25 P Default and it's variants | -1 |  | -1 | -1
L20P-1 | 6 | L20 P Default and it's variants | -1 |  | -1 | -1
D35P-1 | 7 | D35 P Default and it's variants | -1 |  | -1 | -1
L22P-1 | 8 | L22 P Default and it's variants | -1 |  | -1 | -1
MP | 4 | GFC ¦ Master Plan
MP-1 | 1 | Master Plan | -1 |  | -1 | -1
MP-2 | 2 | Site Development | -1 | -1
MP-3 | 3 | Site MEP | -1 | -1 | -1
MP-4 | 4 | Landscaping | -1 |  |  | -1
AM | 5 | GFC ¦ Amenities & Facilities
AM-1 | 1 | Clubhouse—Structure and Envelope
AM-2 | 2 | Clubhouse—Interiors and Facilities | -1 |  | -1 | -1
AM-3 | 3 | Clubhouse—Outdoor Spaces and Pool | -1 |  | -1 | -1
AM-4 | 4 | Community spaces [Board Walk, Children play area] | -1 |  |  | -1
AM-5 | 5 | Sporting Facilities
POST-CONSTRUCTION
1 | 1 | Archives
1 | 1 | Complete set of "As-Built" drawings, final BoQ and project costs, | -100% | -100% | -100% | -100%
MAJOR REWORKS