## Goals FY 26-27Q3
FY 2026-27 Q3 ¦ Design Goals + Billing |  |  |  |  | 19.4359 | 30 | 0.18 | 1 | [10 empty] | 19.2559 | 29
Project | Description | Release date | Responsible | Remarks | Plan - Billing [Cr.] | Plan - Pkgs | Actuals - Billing [Cr.] | Actuals - Pkgs | Phase | Discipline | Design Lead | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | 0.9261% | 3.333%
ITQE |  |  |  |  | 2.4032 | 27 | 0.18 | 1
ITQE-Ph1 | Package Release |  |  |  | 0.023824 | 2 | 0 | 0 | Ph 1 |  |  |  |  | Aishwarya Hegde | Sheethal Prabhu | Anand Thoppil
Architecture | Complete the project |  |  |  | 0.023824 | 2 | 0 | 0 | Ph 1 | Structural
ITQE-Ph1 | Masterplan - Updated driveways & infrastructure [Rework package] | 2026-11-30 | Cijey M |  | 0.011912 | 1 | 0 |  | Ph 1 | Structural | Prakash C | Prakash C | Satish H | Raghavendra |  | Vinay
Step 1 | MEP coordinated layout | 2026-10-30 | Bhavya, Hareesha
Step 2 | ` | - | AUM | Revert to AUM for modifications to existing Infrastructure drawings
ITQE-Ph1 | DG/ Transformer yard | 2026-11-13 | Cijey M |  | 0.011912 | 1 | 0 |  | Ph 1 | Structural | Prakash C | Prakash C | Satish H | Raghavendra |  | Vinay
Step 1 | MEP coordination | 2026-10-13 | Hareesha
Step 2
Structure | Complete the project |  |  |  | 0.023824 | 2 | 0 | 0 | Ph 1 | Structural
ITQE-Ph1 | LoD 350 - Amenities & Facilities ¦ Clubhouse—Outdoor Spaces and Pool | 2026-09-30 | Prakash C |  | 0.011912 | 1 | 0 |  | Ph 1 | Structural | Prakash C | Prakash C | Satish H | Raghavendra |  | Vinay
Step 1 | Filtration Tank - sent for approval | 2026-09-30 | Satish, Raghavendra, Abhinav
Step 2 | Tennis court details | 2026-10-15 | Satish, Raghavendra
| Cafe portal Steel structure | 2026-10-30 | Satish, Alwin | Preliminary framing is shared on 28th July 26. Awaiting updated arch details. Require final arch drawings by 30th Sep.
ITQE-Ph1 | LoD 350 - Amenities & Facilities ¦ Community spaces | 2026-10-05 | Prakash C |  | 0.011912 | 1 | 0 |  | Ph 1 | Structural | Prakash C | Prakash C | Satish H | Raghavendra |  | Vinay
Step 1 | Pedestal for play equipement | 2026-09-30 | Satish, Raghavendra
ITQE-Ph1 | Masterplan - Updated driveways & infrastructure [Rework package] | 2026-12-31 | Prakash C |  | 0.011912 | 1 | 0 |  | Ph 1 | Structural | Prakash C | Prakash C | Satish H | Raghavendra |  | Vinay
Step 1 | Arch Drawings | 2026-09-30 | Akarsh
Landscape | Complete the project |  |  |  | 0.011912 | 1 | 0 |  | Ph 1 | Structural | Prakash C | Prakash C | Satish H | Raghavendra |  | Vinay
ITQE-Ph1 | Masterplan - Updated driveways & infrastructure [Rework package] | 2026-12-15 | Gagan
Step 1 | Masterplan - Updated driveways & infrastructure |  | Anisha/chetan | Awaiting the updated AR details
ITQE-Ph1 | Tree Avenue details, Play equipments | 2026-10-15 | Gagan |  | 0 | 0 | 0 | 0 | Ph 1 | Landscape
Step 1 | Tree Avenue details |  | Sanjana/Chetan | Awaiting the updated AR details for the changes in Road No. 02. | 0.011912 | 1 | 0 |  | Ph 1 | Structural | Prakash C | Prakash C | Satish H | Raghavendra |  | Vinay
Step 2 | Tree Avenue details |  | Sanjana/Chetan | Awaiting the updated Services details for the changes in Road No. 02.
MEP | Complete the project | [7 empty] | Ph 1 | Landscape | Gagan
ITQE-Ph1 | Masterplan - Updated driveways & infrastructure [Rework package] | 2026-10-30 | Gagan
Step 1 | Task description 1 |  | User 1
Step 2 | Task description 2 |  | User2 |  | 0.02 | 1 | 0 | 0 | Ph 2b | MEP
ITQE-Ph1 | DG/ Transformer yard | 2026-10-30 | Gagan |  | 0.02 | 1 | 0 | - | Ph 2b | MEP | Gagan | Gagan | Salomi | Antony |  | Harshitha |  | 0
Step 1
Step 2
ITQE-Ph2b | Package Release |  |  |  | 0.011912 | 1 | 0 |  | Ph 1 | Structural | Prakash C | Prakash C | Satish H | Raghavendra |  | Vinay
Architecture | Complete the project
ITQE-Ph2b | LoD 350 - Tower—05 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 2026-10-28 | Cijey M
Step 1 | Structural Framing Plans and Sections (Terrace, LMR , OHT) | 2026-10-09 | Satish, Raghavendra |  | 1.72 | 12 | 0.18 | 1 | Ph 2b
Step 2 | Task description 2 |  |  |  | 1.52 | 8 | 0 | 0 | Ph 2b | Architecture
ITQE-Ph2b | LoD 350 - Tower—06 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 2026-10-28 | Cijey M |  | 0.22 | 1 | 0 |  | Ph 2b | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty
Step 1 | Structural Framing Plans and Sections (Terrace, LMR , OHT) | 2026-10-09 | Satish, Raghavendra
Step 2 | Task description 2
ITQE-Ph2b | LoD 350 - Tower—07 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 2026-10-28 | Cijey M |  | 0.22 | 1 | 0 |  | Ph 2b | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty
Step 1 | Structural Framing Plans and Sections (Terrace, LMR , OHT) | 2026-10-09 | Satish, Raghavendra
Step 2 | Task description 2
ITQE-Ph2b | LoD 350 - Master Plan ¦ Master Plan | 2026-12-31 | Cijey M |  | 0.22 | 1 | 0 |  | Ph 2b | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty
Step 1 | MEP revised storm water Chamber & Earth pit locations | 2026-11-30 | Bhavya, Hareesha | To be updated as per latest property Line & Nala extent
Step 2 | Landscape revised Masterplan | 2026-11-30 | Lajja, Chetan | Updated Masterplan based on Modifications to properrty line , Nala extent , Driveways, Arch Finishes etc.
ITQE-Ph2b | LoD 350 - Master Plan ¦ Site Development | 2026-10-13 | Cijey M |  | 0.03 | 1 | 0 |  | Ph 2b | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty
Step 1 | Task description 1
Step 2 | Task description 2
ITQE-Ph2b | LoD 350 - Master Plan ¦ Site MEP | 2026-12-09 | Cijey M |  | 0.02 | 1 | 0 |  | Ph 2b | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty
Step 1 | OWC and Gas Bank | 2026-10-31 | Bhavya
Step 2 | Task description 2
ITQE-Ph2b | LoD 350 - ISS 5&6 ¦ Building Envelope and Common Areas | 2026-10-31 | Cijey M |  | 0.01 | 1 | 0 |  | Ph 2b | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty
Step 1 | Task description 1
Step 2 | Task description 2
ITQE-Ph2b | LoD 350 - ISS 7 ¦ Building Envelope and Common Areas | 2026-10-31 | Cijey M |  | 0.4 | 1 | 0 |  | Ph 2b | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty
Step 1 | Task description 1
Step 2 | Task description 2
Structure | Complete the project |  |  |  | 0.4 | 1 | 0 |  | Ph 2b | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty
ITQE-Ph2b | LoD 350 - Tower 05 ¦ Terrace Level | 2026-10-09 | Prakash C
Step 1 | Terrace level | 2026-10-10 | Satish, Raghavendra, Antony, Raghav gupta
Step 2 | OHT + LMR level | 2026-10-20 | Satish, Raghavendra, Antony, Raghav gupta |  | 0.18 | 3 | 0.18 | 1 | Ph 2b | Structural
ITQE-Ph2b | LoD 350 - Tower 06 ¦ Terrace Level | 2026-10-09 | Prakash C
Step 1 | Terrace level | 2026-11-10 | Satish, Raghavendra, Antony, Shiva
Step 2 | OHT + LMR level | 2026-11-20 | Satish, Raghavendra, Antony, Shiva
ITQE-Ph2b | LoD 350 - Tower 07 ¦ Terrace Level | 2026-10-09 | Prakash C
Step 1 | Terrace level | 2026-10-30 | Satish, Raghavendra, Shiva
Step 2 | OHT + LMR level | 2026-10-30 | Satish, Raghavendra, Shiva
ITQE-Ph2b | LoD 350 - ISS5&6 ¦Podium Slab | 2026-12-14 | Prakash C
Step 1 | Podium level | 2026-12-31 | Satish, Antony, Shahnawaz
Step 2 | Staircase Headroom | 2026-12-31 | Satish, Antony, Shahnawaz
Step 3 | STP | 2026-12-31 | Satish, Ajmal |  | 0.18 | 1 | 0.18 | 1 | Ph 2b | Structural | Prakash C | Prakash C | Satish H | Ajmal (after finishing ATR Site MEP works) & New resource hired, joining in July |  | Harshitha |  | 0
ITQE-Ph2b | LoD 350 - ISS7 ¦ Podium Slab | 2026-12-14 | Prakash C
Step 1 | Podium level | 2026-12-31 | Satish, Antony, Shahnawaz
Step 2 | Staircase Headroom | 2026-12-31 | Satish, Antony, Shahnawaz
ITQE-Ph2b | LoD 350 - Master Plan ¦ Site Development | 2026-11-13 | Prakash C
Step 1 | Task description 1 |  |  | Awaiting arch drawings
ITQE-Ph2b | LoD 350 - Master Plan ¦ Site MEP | 2026-11-30 | Prakash C |  | 0 | 1 | 0 |  | Ph 2b | Structural | Prakash C | Prakash C | Satish H | Ajmal (after finishing ATR Site MEP works) & New resource hired, joining in July |  | Harshitha |  | 0
Step 1 | OWC and Gas Bank arch drawings | 2026-12-09 | Akarsh | Awaiting arch drawings
MEP | Complete the project
ITQE-Ph2b | LoD 350 - Master Plan ¦ Site MEP | 2026-12-11 | Gagan |  | 0 | 1 | 0 |  | Ph 2b | Structural | Prakash C | Prakash C | Satish H | Ajmal (after finishing ATR Site MEP works) & New resource hired, joining in July |  | Harshitha |  | 0
Step 1 | Task description 1
Step 2 | Task description 2
ItQE-Ph2c [T9] | Package Release |  |  |  | 0.02 | 1 | 0 | 0 | Ph 2b | MEP
Architecture | LoD 350 - T09 [Foundation & Grade Slab, Parking Lvl Sub Grade], ISS09 [[Foundation & Grade Slab] |  |  |  | 0.02 | 1 | 0 | - | Ph 2b | MEP | Gagan | Gagan | Salomi | Antony |  | Harshitha |  | 0
ItQE-Ph2c [T9] | LoD 350 - Tower 9 ¦ Foundation and Grade Slab | 2026-10-15 | Cijey M
Step 1 | Task description 1
Step 2 | Task description 2 |  |  |  | 0.56787 | 6 | 0 | 0 | Ph 2c
ItQE-Ph2c [T9] | LoD 350 - Tower 9 ¦ Parking Level-Sub grade | 2026-12-31 | Cijey M |  | 0.30106 | 3 | 0 | 0 | Ph 2c | Architecture
Step 1 | SSL01 Framing Plan | 2026-10-15 |  |  | 0.1306 | 1 | 0 |  | Ph 2c | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkisani | Hruthika Mylar
Step 2 | Task description 2
ItQE-Ph2c [T9] | LoD 350 - ISS 9 ¦ Foundations & Grade Slab | 2026-12-31 | Cijey M | Requires rework on existing plans due to additional 12m road accessing Block 9, 10 & requirement of additional ramp
Step 1 | BBMP scrutiny of Block 4 Basement | 2026-09-30 | Jagadish | Require confirmation on scrutiny of approval drawings regarding number of Ramps | 0.078362 | 1 | 0 |  | Ph 2c | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkisani | Hruthika Mylar
Step 2 | MEP schematic & approval on the Arch layouts | 2026-11-30 | Bhavya, Hareesha | Requires MEP coordination to be completed to proceed with GFC
Structure | LoD 350 - T09 [Foundation & Grade Slab, Parking Lvl Sub Grade], ISS09 [[Foundation & Grade Slab]
ItQE-Ph2c [T9] | LoD 350 - Tower 9 ¦ Foundation and Grade Slab | 2026-12-15 | Prakash C |  | 0.092092 | 1 | 0 |  | Ph 2c | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkisani | Hruthika Mylar
Step 1 | T09 foundation |  |  | Awaiting closure of Soil consultant analysis results and initial pile load test results.
Step 2 | T09 column details upto SSL04
ItQE-Ph2c [T9] | LoD 350 - Tower 9 ¦ Parking Level-Sub grade | 2026-12-28 | Prakash C |  | 0.23599 | 2 | 0 | 0 | Ph 2c | Structural
Step 1 | SSL01 details |  |  |  | 0.118 | 1 | 0 |  | Ph 2c | Structural | Prakash C | Prakash C | Satish H | Raghavendra |  | Sahana |  | 0
Step 2 | SSL02 details
MEP | LoD 350 - T09 [Foundation & Grade Slab], ISS09 [[Foundation & Grade Slab]
ItQE-Ph2c [T9] | LoD 350 - Tower 9 ¦ Foundation and Grade Slab | 2026-12-08 | Gagan |  | 0.118 | 1 | 0 |  | Ph 2c | Structural | Prakash C | Prakash C | Satish H | Raghavendra |  | Sahana |  | 0
Step 1 | Task description 1
Step 2 | Task description 2
ItQE-Ph3a [T10-12 & 31 Villas] | Package Release |  |  |  | 0.030822 | 1 | 0 | 0 | Ph 2c | MEP
Architecture | LoD 300 [Marketing and Sales, Pre Construction Set], LoD 350 [Experience Home + Project Experience] |  |  |  | 0.030822 | 1 | 0 |  | Ph 2c | MEP | Gagan | Gagan | Salomi | Hareesha Bhavya | Byahattimath Matsarambabu Prem
ItQE-Ph3a [T10-12 & 31 Villas] | LoD 300 - Pre Construction Set | 2026-12-28 | Cijey M
Step 1 | Approvals (RERA number) | 2026-09-30 | Jagadish
Step 2 | Visualisations for Brochure | 2026-11-30 | Praveen |  | 4.3907 | 1 | 0 | 0 | Ph 3a
VADERAHALLI |  |  |  |  | 4.3907 | 1 | 0 | 0 | Ph 3a | Architecture
Architecture | LoD 100 [Contract + Design Brief] ,LoD 200 [Schematic Concept] |  |  |  | 4.3907 | 1 | 0 |  | Ph 3a | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkineni | Hruthika Mylar
Vaderahalli [Residential] | LoD 100 - Contract + Design Brief | 2026-11-30 | Cijey M
Step 1 | DP Scrutiny inputs | 2026-10-30 | Karthick, Jagadish | Requires confirmation on possible Road access, permissible FAR & combined DP feasibility
Step 2 | ADLR Map & Survey | 2026-10-30 | Karthick, Jagadish | Required to establish plot boundary with ADLR survey, PRR alignment for Bileshivale and assess feasibility | 12.6421 | 2 | 0 | 0 | Vdrhl
Vaderahalli [Residential] | LoD 200 - Schematic Concept | 2026-11-30 | Cijey M |  | 12.6421 | 2 | 0 | 0 | Vdrhl-Res | Architecture
Step 1 | ADLR Map & Survey | 2026-10-30 | Karthick, Jagadish | Required to establish plot boundary and assess feasibility | 6.321 | 1 | 0 |  | Vdrhl-Res | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Syed Musharaff
Step 2 | Task description 2
Vaderahalli [Commercial] | LoD 100 - Contract + Design Brief | 2026-10-15 | Naveen Y
Step 1 | Task description 1 |  |  |  | 6.321 | 1 | 0 |  | Vdrhl-Res | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Syed Musharaff
Step 2 | Task description 2
Vaderahalli [Commercial] | LoD 200 - Schematic Concept + Approvals |  | Naveen Y
Step 1 | New PRR Stitched sketch to be received |  | karthick,Chandan |  | 6.321 | 1 | 0 |  | Vdrhl-Res | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Syed Musharaff
Step 2 | Based on the sketch DBR to be finalised,and reapply DP |  | Swathi,Aswin
[5 empty] | 6.321 | 1 | 0 |  | Vdrhl-Res | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Akarsh Vagman | Syed Musharaff

## Pkgs Summary Phase 1(Status)
|  | 0063¦ In That Quite Earth -Phase1¦ Residential |  | AR |  | ST |  | MEP |  | LS | 1 | Completed
|  |  | Scope | 62 |  | 41 |  | 36 |  | 13 | -1 | Pending
|  |  | Actuals | 61 |  | 38 |  | 35 |  | 12 |  | NA
PHASE 1
DESIGN CONCEPT
| 1 | 1 | Contract + Design Brief | 1
| 2 | 2 | Schematic Concept | 1 |  | 1 |  | 1 |  | 1
| 3 | 3 | Pre Construction Set | 1 |  | 1 |  | 1 |  | 1
| 4 | 4 | Approvals | 1 |  |  |  | 1 |  | 1
| 5 | 5 | Marketing and Sales | 1 | [5 empty] | 1
CONSTRUCTION DOCUMENTS
GFC ¦ Independent Subgrade Structure -1
|  | 1 | Earthwork |  |  | 1
|  | 2 | Foundations & Sub-Grade | 1 |  | 1 |  | 1
|  | 3 | Structrural Slab 01 [Basement] | 1 |  | 1 |  | 1
|  | 4 | Podium Slab | 1 |  | 1 |  | 1
|  | 5 | Building Envelope and Common Areas | 1 |  |  |  | 1
GFC ¦ Independent Subgrade Structure -2
|  | 1 | Earthwork |  |  | 1
|  | 2 | Foundations & Sub-Grade | 1 |  | 1 |  | 1
|  | 3 | Structrural Slab 02 [Basement] | 1 |  | 1 |  | 1
|  | 4 | Podium Slab | 1 |  | 1 |  | 1
|  | 5 | Building Envelope and Common Areas | 1 |  |  |  | 1
| 4 | 1 | GFC ¦ Phase 1 ¦ Tower—1
| T01-00 | 1 | Foundation and Grade Slab | 1 |  | 1 |  | 1
| T01-01 | 2 | Parking Level-Sub grade | 1 |  | 1
| T01-02 | 3 | Building Envelope and Common Areas [Basement] | 1
| T01-03 | 4 | Habitable Level 01 | 1 |  | 1 |  | 1
| T01-04 | 5 | Habitable Level - Even | 1 |  | 1
| T01-05 | 6 | Habitable Level - Odd | 1 |  | 1
| T01-06 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  |  |  | 1 |  |  |  |  | `
| T01-08 | 9 | Terrace Level | 1 |  | 1 |  | 1
| T01-09 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1
| 5 | 2 | GFC ¦ Phase 1 ¦ Tower—2
| T2V-00 | 1 | Foundation and Grade Slab | 1 |  | 1 |  | 1
| T2V-01 | 2 | Parking Level-Sub grade | 1 |  | 1
| T2V-02 | 3 | Building Envelope and Common Areas [Basement] | 1
| T2V-03 | 4 | Habitable Level 01 | 1 |  | 1 |  | 1
| T2V-04 | 5 | Habitable Level - Even | 1 |  | 1
| T2V-05 | 6 | Habitable Level - Odd | 1 |  | 1
| T2V-06 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  |  |  | 1
| T2V-08 | 9 | Terrace Level | 1 |  | 1 |  | 1
| T2V-09 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1
| 6 | 3 | GFC ¦ Phase 1 ¦ Tower—3
| T2S-00 | 1 | Foundation and Grade Slab | 1 |  | 1 |  | 1
| T2S-01 | 2 | Parking Level-Sub grade | 1 |  | 1
| T2S-02 | 3 | Building Envelope and Common Areas [Basement] | 1
| T2S-03 | 4 | Habitable Level 01 | 1 |  | 1 |  | 1
| T2S-04 | 5 | Habitable Level - Even | 1 |  | 1
| T2S-05 | 6 | Habitable Level - Odd | 1 |  | 1
| T2S-06 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  |  |  | 1
| T2S-08 | 9 | Terrace Level | 1 |  | 1 |  | 1
| T2S-09 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1
| 7 | 4 | GFC ¦ Phase 1 ¦ Tower—4
| TXV-00 | 1 | Foundation and Grade Slab | 1 |  | 1 |  | 1
| TXV-01 | 2 | Parking Level-Sub grade | 1 |  | 1
| TXV-02 | 3 | Building Envelope and Common Areas [Basement] | 1
| TXV-03 | 4 | Habitable Level 01 | 1 |  | 1 |  | 1
| TXV-04 | 5 | Habitable Level - Even | 1 |  | 1
| TXV-05 | 6 | Habitable Level - Odd | 1 |  | 1
| TXV-06 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  |  |  | 1
| TXV-08 | 9 | Terrace Level | 1 |  | 1 |  | 1
| TXV-09 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 1
| 15 | 14 | GFC ¦ Individual Homes
| C20-01 | 1 | U10 Default and it's variants | 1 |  |  |  | 1 |  | 1
| L30-01 | 2 | U20 Default and it's variants | 1 |  |  |  | 1 |  | 1
| L45-01 | 3 | H20 Default and it's variants | 1 |  |  |  | 1 |  | 1
| 16 | 15 | GFC ¦ Master Plan
| AR-MP-1 | 1 | Master Plan | 1 |  |  |  | 1 |  | 1
| AR-MP-2 | 2 | Site Development | 1 |  | 1
| AR-MP-3 | 3 | Site MEP | 1 |  | 1 |  | 1
| AR-MP-4 | 4 | Landscaping | 1 | [5 empty] | 1
| 17 | 16 | GFC ¦ Amenities & Facilities
Amenities & Facilities - Clubhouse—Structure and Envelope | AMN-00 | 1 | Clubhouse—Structure and Envelope | 1 |  | 1 |  | 1
Amenities & Facilities - Clubhouse—Interiors and Facilities | AMN-1.1 | 2 | Clubhouse—Interiors and Facilities | 1 |  |  |  | 1 |  | 1
Amenities & Facilities - Clubhouse—Outdoor Spaces and Pool | AMN-1.2 | 3 | Clubhouse—Outdoor Spaces and Pool | 1 |  | -1 |  |  |  | 1
Amenities & Facilities - Community spaces [Board Walk, Children play area] | AMN-1.3 | 4 | Community spaces [Board Walk, Children play area] | 1 |  | -1 |  |  |  | 1
Amenities & Facilities - Sporting Facilities | AMN-1.4 | 5 | Sporting Facilities | 1 |  | 1 |  | 1
POST-CONSTRUCTION
| 1 | 1 | Archives
| 1 | 1 | Complete set of "As-Built" drawings, final BoQ and project costs, | -1 | - | -1 | - | -1 | - | -1
MAJOR REWORKS

## Pkgs Summary Phase 2B (Status)
| 0063¦ In That Quite Earth -Phase2b ¦ Residential |  | AR | ST | MEP | LS | 1 | Completed
|  | Scope | 47 | 31 | 28 | 9 | -1 | Pending
|  | Actuals | 38 | 22 | 26 | 8 |  | NA
PHASE 2B
DESIGN CONCEPT
1 | 1 | Contract + Design Brief | 1
2 | 2 | Schematic Concept | 1 | 1 | 1 | 1
3 | 3 | Pre Construction Set | 1 | 1 | 1 | 1
4 | 4 | Approvals | 1 |  | 1 | 1
5 | 5 | Marketing and Sales | 1 |  |  | 1
CONSTRUCTION DOCUMENTS
GFC ¦ Independent Subgrade Structure 5 & 6
AR-EB5-1 | 1 | Earthwork |  | 1
AR-EB5-2 | 2 | Foundations & Sub-Grade | 1 | 1 | 1
AR-EB5-3 | 3 | Structrural Slab 01 [Basement] | 1 | 1 | 1
AR-EB5-4 | 4 | Podium Slab | 1 | -1 | 1
AR-EB5-5 | 5 | Building Envelope and Common Areas | -1 |  | 1
GFC ¦ Independent Subgrade Structure -7
AR-EB7-1 | 1 | Earthwork |  | 1
AR-EB7-2 | 2 | Foundations & Sub-Grade | 1 | -1 | 1
AR-EB7-3 | 3 | Structrural Slab 02 [Basement] | 1 | 1 | 1
AR-EB7-4 | 4 | Podium Slab | 1 | -1 | 1
AR-EB7-5 | 5 | Building Envelope and Common Areas | -1 |  | 1
4 | 1 | GFC ¦ Phase 1 ¦ Tower—5
T05-1 | 1 | Foundation and Grade Slab | 1 | 1 | 1
T05-2 | 2 | Parking Level-Sub grade | 1 | 1
T05-3 | 3 | Building Envelope and Common Areas [Basement] | 1
T05-4 | 4 | Habitable Level 01 | 1 | 1 | 1
T05-5 | 5 | Habitable Level - Even | 1 | 1
T05-6 | 6 | Habitable Level - Odd | 1 | 1
T05-8 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  | 1 |  |  |  | `
T05-9 | 9 | Terrace Level | 1 | -1 | 1
T05-10 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | -1
5 | 2 | GFC ¦ Phase 1 ¦ Tower—6
T06-1 | 1 | Foundation and Grade Slab | 1 | 1 | 1
T06-2 | 2 | Parking Level-Sub grade | 1 | 1
T06-3 | 3 | Building Envelope and Common Areas [Basement] | 1
T06-4 | 4 | Habitable Level 01 | 1 | 1 | 1
T06-5 | 5 | Habitable Level - Even | 1 | 1
T06-6 | 6 | Habitable Level - Odd | 1 | 1
T06-8 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  | 1
T06-9 | 9 | Terrace Level | 1 | -1 | 1
T06-10 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | -1
6 | 3 | GFC ¦ Phase 1 ¦ Tower—7
T07-1 | 1 | Foundation and Grade Slab | 1 | 1 | 1
T07-2 | 2 | Parking Level-Sub grade | 1 | 1
T07-3 | 3 | Building Envelope and Common Areas [Basement] | 1
T07-4 | 4 | Habitable Level 01 | 1 | 1 | 1
T07-5 | 5 | Habitable Level - Even | 1 | 1
T07-6 | 6 | Habitable Level - Odd | 1 | 1
T07-8 | 7 | Building Envelope and Common Areas [Typical Tower Levels] | 1 |  | 1
T07-9 | 9 | Terrace Level | 1 | -1 | 1
T07-10 | 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | -1
15 | 14 | GFC ¦ Individual Homes
AR-L21-1 | 1 | L21 Default and it's variants | 1 |  | 1 | 1
AR-L25-2 | 2 | L25 Default and it's variants | 1 |  | 1 | 1
16 | 15 | GFC ¦ Master Plan
AR-MP-1 | 1 | Master Plan | -1 |  | 1 | 1
AR-MP-2 | 2 | Site Development | -1 | -1
AR-MP-3 | 3 | Site MEP | -1 | -1 | -1
AR-MP-4 | 4 | Landscaping | 1 |  |  | 1
POST-CONSTRUCTION
1 | 1 | Archives
1 | 1 | Complete set of "As-Built" drawings, final BoQ and project costs, | -1 | -1 | -1 | -1
MAJOR REWORKS
Note on D63: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 [Tasks] There is a task anchored to this comment that cannot be viewed in your client. Comment: @Annapoorna Bhat L21 workshop to be schedules Electrical layout approval

## Pkgs Summary Phase 2C (Status)
| 0063¦ In That Quite Earth -Phase 2c¦ Residential |  | AR | ST | MEP | LS | 1 | Completed
|  | Scope | 24 | 15 | 15 | 8 | -1 | Pending
|  | Actuals | 2 | 1 | 0 | 0 |  | NA
PHASE 2C
DESIGN CONCEPT
1 | 1 | Contract + Design Brief | 1
2 | 2 | Schematic Concept | 1 | 1 | -1 | -1
3 | 3 | Pre Construction Set | -1 | -1 | -1 | -1
4 | 4 | Approvals | -1 |  | -1 | -1
5 | 5 | Marketing and Sales | -1 |  |  | -1
CONSTRUCTION DOCUMENTS
GFC ¦ Independent Subgrade Structure T9
AR-EB5-1 | 1 | Earthwork |  | -1
AR-EB5-2 | 2 | Foundations & Sub-Grade | -1 | -1 | -1
AR-EB5-3 | 3 | Structrural Slab 01 [Basement] | -1 | -1 | -1
AR-EB5-4 | 4 | Podium Slab | -1 | -1 | -1
AR-EB5-5 | 5 | Building Envelope and Common Areas | -1 |  | -1
4 |  | GFC ¦ Phase 1 ¦ Tower—9
| 1 | Foundation and Grade Slab | -1 | -1 | -1
| 2 | Parking Level-Sub grade | -1 | -1
| 3 | Building Envelope and Common Areas [Basement] | -1
| 4 | Habitable Level 01 | -1 | -1 | -1
| 5 | Habitable Level - Even | -1 | -1
| 6 | Habitable Level - Odd | -1 | -1
| 7 | Building Envelope and Common Areas [Typical Tower Levels] | -1 |  | -1 |  |  |  | `
| 9 | Terrace Level | -1 | -1 | -1
| 10 | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | -1
15 |  | GFC ¦ Individual Homes
AR-L21-1 | 1 | L21 Default and it's variants | -1 |  | -1 | -1
16 |  | GFC ¦ Master Plan
AR-MP-1 | 1 | Master Plan | -1 |  | -1 | -1
AR-MP-2 | 2 | Site Development | -1 | -1
AR-MP-3 | 3 | Site MEP | -1 | -1 | -1
AR-MP-4 | 4 | Landscaping | -1 |  |  | -1
POST-CONSTRUCTION
1 | 1 | Archives
1 | 1 | Complete set of "As-Built" drawings, final BoQ and project costs, | -1 | -1 | -1 | -1
MAJOR REWORKS