## Goals FY 26-27Q3
FY 2026-27 Q3 ¦ Design Goals + Billing |  |  |  |  | 1.6889 | 11 | 0 | 0 | [10 empty] | 1.6889 | 11
Project | Description | Release date | Responsible | Remarks | Plan - Billing [Cr.] | Plan - Pkgs | Actuals - Billing [Cr.] | Actuals - Pkgs | Phase | Discipline | Design Lead | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | 0% | 0%
0082¦ OVER THE RAINBOW |  |  |  |  | 2.2508 | 16 | 0 | 0
OTR-Ph01 | Package Release |  |  |  | 0.32 | 5 | 0 | 0 | Ph 1
Architecture | Complete the project |  |  |  | 0.09 | 1 | 0 | 0 | Ph 1 | Architecture
OTR-Ph01 | LoD 350 - Master Plan ¦ Master Plan | 2026-10-16 | Cijey M |  | 0.09 | 1 | 0 |  | Ph 1 | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Niashinlulu | Akshara Rohit | Saurabh Bothra
Step 1 | Recieve Service yard 02 foundation details from Structural team | 2026-10-08 | Mohammed Mazharuddin
OTR-Ph01 | Villa 22 - Personalised customization unit | 2026-10-01 | Cijey M |  | 0.09 | 1 | 0 |  | Ph 1 | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Niashinlulu | Akshara Rohit | Saurabh Bothra
Step 1 | Task description 1
Step 2 | Task description 2
Structure | Complete the project |  |  |  | 0.1 | 2 | 0 | 0 | Ph 1 | Structural
OTR-Ph01 | LoD 350 - Master Plan ¦ Site MEP | 2026-12-31 | Prakash C |  | 0.03 | 1 | 0 |  | Ph 1 | Structural | Prakash C | Prakash C | Satish H | Mazhar |  | Samyukta |  | 0
Step 1 | STP and PMD | 2026-11-30
Step 2 | Electrical Panel room
Step 3 | DG yard and Transformer Yard
OTR-Ph01 | LoD 350 - LoD 350 - Amenities & Facilities ¦ Community spaces [Board Walk, Children play area] | 2026-11-05 | Prakash C |  | 0.07 | 1 | 0 |  | Ph 1 | Structural | Prakash C | Prakash C | Satish H | Mazhar |  | Samyukta |  | 0
Step 1 | Details yet to be received from Arch/Landscape | 2026-10-19 | Sukathirtha Apoorva
Step 2
MEP | Complete the project |  |  |  | 0.04 | 1 | 0 | 0 | Ph 1 | MEP
OTR-Ph01 | LoD 350 - Master Plan ¦ Site MEP | 2026-11-19 | Gagan |  | 0.04 | 1 | 0 |  | Ph 1 | MEP | Gagan | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar
Step 1 | Rain water Harwesting Tank ,Service yard-02 SWD drain layout shared with Architects | 2026-10-19 | Praveen /Rameshchandra | Awaiting approval from Architects
Step 2 | STP details | 2026-11-30 | Praveen | Awaiting details from STP Vendor
OTR-Ph02 | Package Release |  |  |  | 1.3689 | 6 | 0 | 0 | Ph 2
Architecture | LoD 200 - Schematic Concept & Approvals |  |  |  | 1.08 | 3 | 0 | 0 | Ph 2 | Architecture
OTR-Ph02 | LoD 100 - Contract + Design Brief | 2026-10-16 | Cijey M |  | 0.54 | 1 | 0 |  | Ph 2 | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra
Step 1 | Hudbust survey closure by Site operations team | 2026-09-30 | Sunil Biswal
Step 2 | V60 layout and area statement closure by FKH team | 2026-09-30 | FKH team
OTR-Ph02 | LoD 200 - Schematic Concept | 2026-11-09 | Cijey M |  | 0.43 | 1 | 0 |  | Ph 2 | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra
Step 1 | Hudbust survey closure by Site operations team | 2026-09-30 | Sunil Biswal
Step 2 | V60 layout and area statement closure by FKH team | 2026-09-30 | FKH team
OTR-Ph02 | LoD 200 - Schematic Concept - CH | 2026-12-10 | Om Prakash |  | 0.11 | 1 | 0 |  | Ph 2 | Architecture | Om Prakash | Om Prakash | Dinakar Venugopal | Niashinlulu | Saurabh Bothra
Step 1 | Task description 1
Step 2 | Task description 2
Structure | Complete Schematic concept |  |  |  | 0.17172 | 1 | 0 | 0 | Ph 2 | Structural
OTR-Ph02 | LoD 200 - Schematic Concept | 2026-12-09 | Prakash C |  | 0.17172 | 1 | 0 |  | Ph 2 | Structural | Prakash C | Prakash C | Satish | Mazhar ( If Villa concept is different new resource is required) |  | Samyukta |  | 0
Step 1 | Require product details from Arch. |  | Niashinlulu
Step 2 | Need soil testing report |  |  | Consultant not finalized
MEP | LoD 200 - Schematic Concept & Approvals |  |  |  | 0.06372 | 1 | 0 | 0 | Ph 2 | MEP
OTR-Ph02 | LoD 200 - Schematic Concept |  | Gagan |  | 0.06372 | 1 | 0 |  | Ph 2 | MEP | Gagan | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Deepu Mahadev
Step 1 | Task description 1 | 2026-12-18 |  | Awaiting the AR details
Step 2 | Task description 2 | 2026-12-18 |  | Awaiting the AR details
Landscape | LoD 200 - Schematic Concept & Approvals |  |  |  | 0.05346 | 1 | 0 | 0 | Ph 2 | Landscape
OTR-Ph02 | LoD 200 - Schematic Concept | 2026-12-09 | Gagan |  | 0.05346 | 1 | 0 |  | Ph 2 | Landscape | Gagan | Gagan | Lajja | Apoorva
Step 1 | Master plan |  | Nihareeka | Awaiting the AR details
OTR Museum | Package Release |  |  |  | 0.56189 | 5 | 0 | 0 | OTR Mus
Architecture | Complete Schematic concept |  |  |  | 0.43996 | 2 | 0 | 0 | OTR Mus | Architecture
OTR Museum | LoD 100 - Design Brief | 2026-10-08 | Cijey M |  | 0.17598 | 1 | 0 |  | OTR Mus | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra
Step 1 | 39G Kharab regularisation approval from Liasoning team | 2026-09-25 | Chandan KR
OTR Museum | LoD 200 - Schematic Concept | 2026-11-17 | Cijey M |  | 0.26398 | 1 | 0 |  | OTR Mus | Architecture | Cijey M | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra
Step 1 | 39G Kharab regularisation approval from Liasoning team | 2026-09-30 | Chandan KR
Structure | Complete Schematic concept |  |  |  | 0.08045 | 1 | 0 | 0 | OTR Mus | Structural
OTR Museum | LoD 200 - Schematic Concept | 2026-12-02 | Prakash C |  | 0.08045 | 1 | 0 |  | OTR Mus | Structural | Prakash C | Prakash C | Satish H | Mazhar
Step 1 | Need soil testing report |  |  | Consultant not finalized
Step 2
MEP | Complete Schematic concept |  |  |  | 0.022627 | 1 | 0 | 0 | OTR Mus | MEP
OTR Museum | LoD 200 - Schematic Concept |  | Gagan |  | 0.022627 | 1 | 0 |  | OTR Mus | MEP | Gagan | Gagan | Batches to be removed - Can be taken up once the architectural details are received.
Step 1 | Task description 1 | 2026-12-18 |  | Awaiting the AR details
Step 2 | Task description 2 | 2026-12-18 |  | Awaiting the AR details
Landscape | Complete Schematic concept |  |  |  | 0.018855 | 1 | 0 | 0 | OTR Mus | Landscape
OTR Museum | LoD 200 - Schematic Concept | 2026-11-30 | Gagan |  | 0.018855 | 1 | 0 |  | OTR Mus | Landscape | Gagan | Gagan | Batches to be removed - Can be taken up once the architectural details are received.
Step 1 | Master plan |  | Anisha | Awaiting the AR details
OTR Oota | Package Release | [7 empty] | OTR Mus
OTR Oota | Complete Schematic concept | [7 empty] | OTR Mus | Architecture
OTR Museum | LoD 100 - Design Brief |  | Manik | [5 empty] | OTR Mus | Architecture | Cijey M
Step 1 | Task description 1
Step 2 | Task description 2
OTR Museum | LoD 200 - Schematic Concept |  | Manik | [5 empty] | OTR Mus | Architecture | Cijey M
Step 1 | Task description 1
Step 2 | Task description 2

## Pkgs Summary OTR Phase1
|  | 0082¦ Over the rainbow -Phase1 ¦ Residential |  | AR | ST | MEP | LS | 1 | Completed
|  |  | Scope | 14 | 8 | 10 | 10 | -1 | Pending
|  |  | Actuals | 12 | 4 | 8 | 9 |  | NA
PHASE 1
DESIGN CONCEPT
|  | 1 | Contract + Design Brief | 1
|  | 2 | Schematic Concept | 1 | 1 | 1 | 1
|  | 3 | Pre Construction Set | 1 | 1 | 1 | 1
|  | 4 | Approvals | 1 |  | 1 | 1
|  | 5 | Marketing and Sales | 1 |  |  | 1
CONSTRUCTION DOCUMENTS
GFC ¦ Villa—Block
|  | 1 | Foundations & Sub-Grade | 1 | 1 | 1
|  | 2 | All levels | 1 | 1 | 1
|  | 3 | Building Envelope and Common Areas | 1 |  | 1 | 1
GFC ¦ Individual Homes
|  | 1 | V25 Default and variants | 1 |  | 1 | 1
GFC ¦ Master Plan
|  | 1 | Master Plan | -1 |  | 1 | 1
|  | 2 | Site Development | 1 | -1
|  | 3 | Site MEP | 1 | -1 | -1
|  | 4 | Landscaping | 1 |  |  | 1
GFC ¦ Amenities & Facilities
Amenities & Facilities - Children's play area |  | 1 | Children's play area |  | -1 |  | 1
POST-CONSTRUCTION
| 1 | 1 | Archives
| 1 | 1 | Complete set of "As-Built" drawings, final BoQ and project costs, | -1 | -1 | -1 | -1
MAJOR REWORKS

## Pkgs Summary OTR Phase2
|  | 0082¦ Over the rainbow -Phase2 ¦ Residential |  | AR | ST | MEP | LS | 1 | Completed
|  |  | Scope | 18 | 9 | 13 | 12 | -1 | Pending
|  |  | Actuals | 0 | 0 | 0 | 0 |  | NA
PHASE 2b
DESIGN CONCEPT
| 1 | 1 | Contract + Design Brief | -1
| 2 | 2 | Schematic Concept | -1 | -1 | -1 | -1
| 3 | 3 | Pre Construction Set | -1 | -1 | -1 | -1
| 4 | 4 | Approvals | -1 |  | -1 | -1
| 5 | 5 | Marketing and Sales | -1 |  |  | -1
CONSTRUCTION DOCUMENTS
GFC ¦ Villa—Block
|  | 1 | Foundations & Sub-Grade | -1 | -1 | -1
|  | 2 | All levels | -1 | -1 | -1
|  | 3 | Building Envelope and Common Areas | -1 |  | -1 | -1
GFC ¦ Individual Homes
|  | 1 | V25 Default | -1 |  | -1 | -1
|  | 2 | V60 Default | -1 |  | -1 | -1
GFC ¦ Master Plan
| AR-MP-1 | 1 | Master Plan | -1 |  | -1 | -1
| AR-MP-2 | 2 | Site Development | -1 | -1
| AR-MP-3 | 3 | Site MEP | -1 | -1 | -1
| AR-MP-4 | 4 | Landscaping | -1 |  |  | -1
|  | 16 | GFC ¦ Amenities & Facilities
Amenities & Facilities - Clubhouse—Structure and Envelope | AMN-00 | 1 | Clubhouse—Structure and Envelope | -1 | -1 | -1
Amenities & Facilities - Clubhouse—Interiors and Facilities | AMN-1.1 | 2 | Clubhouse—Interiors and Facilities | -1 |  | -1 | -1
Amenities & Facilities - Clubhouse—Outdoor Spaces and Pool | AMN-1.2 | 3 | Clubhouse—Outdoor Spaces and Pool | -1 | -1 |  | -1
Amenities & Facilities - Community spaces [Board Walk, Children play area] | AMN-1.3 | 4 | Community spaces [Board Walk, Children play area]
Amenities & Facilities - Sporting Facilities | AMN-1.4 | 5 | Sporting Facilities
POST-CONSTRUCTION
| 1 | 1 | Archives
| 1 | 1 | Complete set of "As-Built" drawings, final BoQ and project costs, | -1 | -1 | -1 | -1
MAJOR REWORKS

## Pkgs Summary OTR Museum
| 0082¦ Over the rainbow - Museum |  | AR | ST | MEP | LS | 1 | Completed
|  | Scope | 13 | 7 | 9 | 8 | -1 | Pending
|  | Actuals | 0 | 0 | 0 | 0 |  | NA
Theatre and Museum
DESIGN CONCEPT
1 | 1 | Contract + Design Brief | -1
2 | 2 | Schematic Concept | -1 | -1 | -1 | -1
3 | 3 | Pre Construction Set | -1 | -1 | -1 | -1
4 | 4 | Approvals | -1 |  | -1 | -1
5 | 5 | Marketing and Sales | -1 |  |  | -1
CONSTRUCTION DOCUMENTS
GFC ¦ Block 1
| 1 | Foundations & Structure | -1 | -1 | -1
| 2 | Building Envelope and Plot development | -1 | -1 | -1
| 3 | Interiors | -1 |  | -1 | -1
GFC ¦ Master Plan
AR-MP-1 | 1 | Master Plan | -1 |  | -1 | -1
AR-MP-2 | 2 | Site Development | -1 | -1
AR-MP-3 | 3 | Site MEP | -1 | -1 | -1
AR-MP-4 | 4 | Landscaping | -1 |  |  | -1
POST-CONSTRUCTION
1 | 1 | Archives
1 | 1 | Complete set of "As-Built" drawings, final BoQ and project costs, | -1 | -1 | -1 | -1
MAJOR REWORKS