## 0116MS Res,0131NHHS FY26Q3
0116 MS Res, 0131 NHHS ¦ Design package release FY26-27 Q3 |  |  |  |  | 1.6073 | 28 | 0.22284 | 3
Project | Description | Release date | Responsible | Remarks | Plan - Billing [Cr.] | Plan - Pkgs | Actuals - Billing [Cr.] | Actuals - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks
MeenaSai Res | Package Release |  |  |  | 0.4095 | 15 | 0 | 0
Architecture | Complete LoD 300, LoD 350 [except Interiors] |  |  |  | 0.252 | 4 | 0 | 0
MeenaSai Res | LoD 200 - Schematic Concept | 2026-10-15 | Cijey M |  | 0.063 | 1 | 0 |  | Cijey M | Niashinlulu | Syed Musharaff
Step 1 | Confirmation on Layout by Shibanee ma'am | 2026-09-24 | User 1
Step 2 | Structural framing closure | 2026-10-02 | User 2
MeenaSai Res | LoD 300 - Pre Construction set | 2026-11-20 | Cijey M |  | 0.042 | 1 | 0 |  | Cijey M | Niashinlulu | Syed Musharaff
Step 1 | Confirmation on Layout by Shibanee ma'am | 2026-09-24 | User 1
Step 2 | Structural framing closure | 2026-10-02 | Subrahmanya
Step 3 | PHE, Electrical and HVAC coordination closure | 2026-10-20 | Praveen
MeenaSai Res | LoD 350 - Foundation and Structure | 2026-12-10 | Cijey M |  | 0.084 | 1 | 0 |  | Cijey M | Niashinlulu | Syed Musharaff
Step 1 | Task description 1 | 2026-10-01 | User 1
Step 2 | Task description 2 | 2026-10-05 | User 2
MeenaSai Res | LoD 350 - Building Envelope + Plot Development | 2026-12-24 | Cijey M |  | 0.063 | 1 | 0 |  | Cijey M | Niashinlulu | Syed Musharaff
Step 1 | Task description 1 | 2026-10-01 | User 1
Step 2 | Task description 2 | 2026-10-05 | User 2
Structural | Complete LoD 300, LoD 350 Foundation and Structure, Building Envelope + Plot development |  |  |  | 0.0912 | 4 | 0 | 0
MeenaSai Res | LoD 200 - Schematic Concept | 2026-10-22 | Prakash C |  | 0.0192 | 1 | 0 |  | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan
Step 1 | Column locations, framing plans with details of beams, levels and sections (wherever requried) | 2026-10-01 | User 1 | completed
Step 2 | Updated structural model with tentative foundation sizes (based on geotechnical report) | 2026-10-05 | User 2 | completed
MeenaSai Res | LoD 300 - Pre Construction set | 2026-11-20 | Prakash C | LoD 200 completion - confirmation awaited | 0.0192 | 1 | 0 |  | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan
Step 1 | Updated framing plan with sleeve details and services requriements incorporated | 2026-10-01 | User 1 | Details pending from arch and MEP ( 5 days)
Step 2 | Signed off drawings with finalised member sizes | 2026-10-05 | User 2 | After completion of step 1 ( 2 days)
MeenaSai Res | LoD 350 - Foundation and Structure | 2026-12-09 | Prakash C | After LoD 300 | 0.048 | 1 | 0 |  | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan
Step 1 | Task description 1 | 2026-10-01 | User 1
Step 2 | Task description 2 | 2026-10-05 | User 2
MeenaSai Res | LoD 350 - Building Envelope + Plot Development | 2026-12-24 | Prakash C |  | 0.0048 | 1 | 0 |  | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan
Step 1 | Task description 1 | 2026-10-01 | User 1
Step 2 | Task description 2 | 2026-10-05 | User 2
MEP | Complete LoD 300, LoD 350 [except Interiors] |  |  |  | 0.0378 | 4 | 0 | 0
MeenaSai Res | LoD 200 - Schematic Concept | 2026-10-22 | Gagan | Awaiting updated layouts from Architects | 0.0054 | 1 | 0 |  | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sampath Mahadev
Step 1 | Task description 1 | 2026-10-01 | Eranna/Praveen/Rinu/Shekar
Step 2 | Task description 2 | 2026-10-05 | User 2
MeenaSai Res | LoD 300 - Pre Construction set | 2026-11-20 | Gagan | Awaiting updated layouts from Architects | 0.0054 | 1 | 0 |  | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sampath Mahadev
Step 1 | Task description 1 | 2026-10-01 | Eranna/Praveen/Rinu/Shekar
Step 2 | Task description 2 | 2026-10-05 | User 2
MeenaSai Res | LoD 350 - Foundation and Structure | 2026-12-16 | Gagan | Awating updated layout from architect / structural | 0.0189 | 1 | 0 |  | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sampath Mahadev
Step 1 | Task description 1 | 2026-10-01 | Eranna/Praveen/Rinu/Shekar
Step 2 | Task description 2 | 2026-10-05 | User 2
MeenaSai Res | LoD 350 - Building Envelope + Plot Development | 2026-12-31 | Gagan | Awating updated layout from architect / structural | 0.0081 | 1 | 0 |  | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sampath Mahadev
Step 1 | Task description 1 | 2026-10-01 | Eranna/Praveen/Rinu/Shekar
Step 2 | Task description 2 | 2026-10-05 | User 2
Landscape | Complete LoD 300, LoD 350 Building Envelope + Plot development |  |  |  | 0.0285 | 3 | 0 | 0
MeenaSai Res | LoD 200 - Schematic Concept | 2026-10-22 | Gagan |  | 0.006 | 1 | 0 |  | Gagan | Lajja | Anisha
Step 1 | Task description 1 | 2026-10-01 | User 1
Step 2 | Task description 2 | 2026-10-05 | User 2
MeenaSai Res | LoD 300 - Pre Construction set | 2026-11-20 | Gagan |  | 0.006 | 1 | 0 |  | Gagan | Lajja | Anisha
Step 1 | Task description 1 | 2026-10-01 | User 1
Step 2 | Task description 2 | 2026-10-05 | User 2
MeenaSai Res | LoD 350 - Building Envelope + Plot Development | 2026-12-28 | Gagan |  | 0.0165 | 1 | 0 |  | Gagan | Lajja | Anisha
Step 1 | Task description 1 | 2026-10-01 | User 1
Step 2 | Task description 2 | 2026-10-05 | User 2
NH Homestay | Package Release |  |  |  | 1.1978 | 13 | 0.22284 | 3
Architecture | Complete the project |  |  |  | 0.77994 | 4 | 0 | 0
NH Homestay | LoD 300 - Pre Construction set | 2026-10-01 | Cijey M | DBR pending | 0.12999 | 1 | 0 |  | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
NH Homestay | LoD 350 - Foundation and Structure | 2026-10-05 | Cijey M |  | 0.25998 | 1 | 0 |  | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira
Step 1 | Task description 1 | 2026-09-15 | User 1
Step 2 | Task description 2 | 2026-09-30 | User 2
NH Homestay | LoD 350 - Building Envelope + Plot Development | 2026-10-30 | Cijey M |  | 0.19498 | 1 | 0 |  | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
NH Homestay | LoD 350 - Interiors | 2026-12-02 | Cijey M |  | 0.19498 | 1 | 0 |  | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
Structural | All STR Deliverables completed by Aug'26 |  |  |  | 0.22284 | 3 | 0.22284 | 3
NH Homestay | LoD 300 - Pre Construction set | 2026-08-20 | Prakash C | Completed | 0.059424 | 1 | 0.059424 | 1 | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan
NH Homestay | LoD 350 - Foundation and Structure | 2026-08-18 | Prakash C | Completed | 0.14856 | 1 | 0.14856 | 1 | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan
NH Homestay | LoD 350 - Building Envelope + Plot Development | 2026-08-24 | Prakash C | Completed | 0.014856 | 1 | 0.014856 | 1 | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan
MEP | Complete the project |  |  |  | 0.12535 | 4 | 0 | 0
NH Homestay | LoD 300 - Pre Construction set | 2026-10-01 | Gagan | DBR pending | 0.016713 | 1 | 0 |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
NH Homestay | LoD 350 - Foundation and Structure | 2026-10-05 | Gagan | GRMS Consultant onboarding | 0.058495 | 1 | 0 |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu
Step 1 | Task description 1 | 2026-09-15 | User 1
Step 2 | Task description 2 | 2026-09-30 | User 2
NH Homestay | LoD 350 - Building Envelope + Plot Development | 2026-10-22 | Gagan |  | 0.025069 | 1 | 0 |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
NH Homestay | LoD 350 - Interiors | 2026-12-01 | Gagan |  | 0.025069 | 1 | 0 |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
Landscape | Complete the project |  |  |  | 0.069638 | 2 | 0 | 0
NH Homestay | LoD 300 - Pre Construction set | 2026-10-01 | Gagan | DBR pending | 0.01857 | 1 | 0 |  | Gagan | Lajja | Anisha | Chetan
Step 1 | Task description 1 | 2026-10-15 | User 1
Step 2 | Task description 2 | 2026-10-30 | User 2
NH Homestay | LoD 350 - Building Envelope + Plot Development | 2026-10-05 | Gagan |  | 0.051068 | 1 | 0 |  | Gagan | Lajja | Anisha | Chetan
Step 1 | Task description 1 | 2026-09-15 | User 1
Step 2 | Task description 2 | 2026-09-30 | User 2

## 0116 MSRes Pkgs Smmy (Status)
| 0116 ¦ Meena and KrishnaSai residence |  | AR | ST | MEP | LS | 1 | Completed
|  | Scope | 8 | 5 | 7 | 4 | -1 | Pending
|  | Actuals | 2 | 0 | 0 | 0 |  | NA
DESIGN CONCEPT
1 | 1 | Contract + Design Brief | 1
2 | 2 | Schematic Concept | -1 | -1 | -1 | -1
3 | 3 | Pre Construction Set | -1 | -1 | -1 | -1
4 | 4 | Approvals | 1 |  | -1
CONSTRUCTION DOCUMENTS
4 | 1 | GFC ¦ Block—01
T01-01 | 1 | Foundation and Grade Slab | -1 | -1 | -1
T01-02 | 2 | Building Envelope and Plot development | -1 | -1 | -1 | -1
T01-03 | 3 | Interiors | -1 |  | -1
POST-CONSTRUCTION
1 | 1 | Archives
1 | 1 | Complete set of "As-Built" drawings, final BoQ and project costs, | -1 | -1 | -1 | -1

## 0131 NHHS Pkgs Smmy (Status)
| 0131 ¦ Homestay at Sultanpete |  | AR | ST | MEP | LS |  | 1 | Completed
|  | Scope | 8 | 5 | 7 | 4 |  | -1 | Pending
|  | Actuals | 3 | 4 | 1 | 1 |  |  | NA
DESIGN CONCEPT
1 | 1 | Contract + Design Brief | 1
2 | 2 | Schematic Concept | 1 | 1 | 1 | 1
3 | 3 | Pre Construction Set | -1 | 1 | -1 | -1 | DBRs pending
4 | 4 | Approvals | 1 |  | -1
CONSTRUCTION DOCUMENTS
4 | 1 | GFC ¦ Block—01
T01-01 | 1 | Foundation and Grade Slab | -1 | 1 | -1
T01-02 | 2 | Building Envelope and Plot development | -1 | 1 | -1 | -1
T01-03 | 3 | Interiors | -1 |  | -1
POST-CONSTRUCTION
1 | 1 | Archives
1 | 1 | Complete set of "As-Built" drawings, final BoQ and project costs, | -1 | -1 | -1 | -1

## Goals FY 26-27Q2 (hidden)
FY 2026-27 Q2 ¦ Design Goals + Billing |  |  |  |  | 1.49 | 6 | 0 | 0 | [7 empty] | 1.49 | 6
Project | Description | Release date | Responsible | Remarks | Plan - Billing [Cr.] | Plan - Pkgs | Actuals - Billing [Cr.] | Actuals - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | 0% | 0%
Imagine Campus | Package Release |  |  |  | 1.49 | 6 | 0 | 0
Architecture | Package Release [Complete LoD 100, 200] |  |  |  | 1.15 | 2 | 0 | 0
Imagine Campus | LoD 200 - Schematic Concept |  | Naveen Y |  | 0.69 | 1 | 0 |  | Naveen Y | Akhila G | Fathima S
Imagine Campus | Approvals |  | Naveen Y |  | 0.46 | 1 | 0 |  | Naveen Y | Akhila G | Fathima S
Structural | Package Release [Complete LoD 200] |  |  |  | 0.19 | 1 | 0 | 0
Imagine Campus | LoD 200 - Schematic Concept |  | Prakash C |  | 0.19 | 1 | 0 |  | Prakash C | Lincy | Charan | - | Karthik |  | 0
MEP | Package Release [Complete LoD 200] |  |  |  | 0.1 | 2 | 0 | 0
Imagine Campus | LoD 200 - Schematic Concept |  | Gagan |  | 0.05 | 1 | 0 |  | Gagan | Salomi | Hareesha Bhavya | Byahattimath Shreedhar Viresh
Imagine Campus | Approvals |  | Gagan |  | 0.05 | 1 | 0 |  | Gagan | Salomi | Hareesha Bhavya | Byahattimath Shreedhar Viresh
Landscape | Package Release [Complete LoD 200] |  |  |  | 0.05 | 1 | 0 | 0
Imagine Campus | Approvals |  | Gagan |  | 0.05 | 1 | 0 |  | Gagan | Lajja | Aproova