## 26Q1 Actuals Smry (hidden)
Design Lead | Design Packages | 26Q1 Fee | Actuals | Actual Fees | Remarks
|  | 112.683 | 55 | 3.5167
Saji | PoaRR [T8-GFC except Penthouse products, T1-7-GFC] [Pkgs 26] | 10.4
Saji | AtR [1,2a,2b,2c-GFC, P3 Structure] [Pkgs 19] | 2.2 |  |  | LoD 350 - Clubhouse + Amenities - Clubhouse—Interiors and Facilities
Cijey | itQE [P2a GFC, 2b-Basements, 2c-Foundations/ Parking, P3-Approvals & Exp Homes][Pkgs 12] | 11.71 |  |  | Ph2a -LoD 350 - Master Plan ¦ Site Development, LoD 350 -Experience Home + Project Experience [ V35 ], Ph2b - LoD 350 - L25 Default and it's variants, LoD 350 - ISS 5&6 ¦ Structural Slab 01 [Basement] LoD 350 - ISS 7 ¦ Structrural Slab 01 [Basement], Ph 2c - I20, I25 Experience Homes
Cijey | OtR [P1-GFC, Museum-LOD 200][Pkgs 7] | 1.4 |  |  | Ph1 - LoD 350 - Individual Homes ¦ V25 Default & its Variant, LoD 350 - Villa Block ¦ Building Envelope + Plot Development, Museum - Lod 100 - Design Brief
Cijey | Homestay NH GFC [Pkgs 4] | 0.78
Cijey | Sarjapur Road [LOD 200, Approval, Experience Homes] [Pkgs 4] | 13.81 |  |  | LoD 100 - Contract + Design Brief
Cijey | Meena Sai [LOD 200, Approvals] [Pkgs 2] | 0.11
Cijey | OtR P2 [LOD 200, Approval] [Pkgs 3] | 1.18 |  |  | LoD 100 - Contract + Design Brief
Naveen | AtR Commercial [Complete GFCs] [Pkgs 3] | 0.36
Naveen | TMFT P3 [LOD 200, Approvals] [Pkgs 3] | 0.62
Naveen | Sarjapur C [LOD 200, Approvals] [Pkgs 19] | 14.74 |  |  | LoD 100 - Contract + Design Brief
Naveen | OtF [LOD 300, Approvals, Marketing and Proj Exp] [Pkgs 6] | 2.75 |  |  | LoD 100 - Contract + Design Brief [Commercial]; LoD 200 - Schematic Concept
Naveen | Imagine [LOD 200, Approvals] [Pkgs 3] | 1.61
OP | DbtW [Complete GFCs-except Clubhouse Interiors and Community spaces] [Pkgs 10] | 5.88 |  |  | LoD 350 - ISS - Podium Slab, Home Products - I20 and I25 Default and it's variants, Master Plan - Site Development
OP | SftW [Complete GFCs-except Clubhouse Interiors and Community spaces] [Pkgs 09] | 0.85
OP | TuiG [Clubhouse Outdoor and Community Spaces] [Pkgs 3] | 0.33 |  |  | LoD 350 - Clubhouse structure & envelope, Sporting facility
OP | LGCE [LOD 200] [Pkgs 2] | 0.38
OP | OtR P2 [Clubhouse LOD 200 and Approvals] [Pkgs 2] | 0.17
OP | Violet Hill [Clubhouse LOD 200] [Pkgs 1] | 0.06 |  |  | LoD 200 - Schematic Concept
OP | OtF [Clubhouse LOD 200 and Approvals] [Pkgs 3] | 0.29 |  |  | LoD 200 - Schematic Concept - CH
OP | Sarjapur Rd [Clubhouse LOD 200 and Approvals] [Pkgs 2] | 0.51
Manik | Indiranagar Resi GFCs [Pkgs 4] | 0.004
Manik | MT Plano [LOD 200 and Approvals] [Pkgs 8] | 0.7
Manik | Ooty Resi [LOD 200 and Approvals] [Pkgs 26] [ON HOLD]
Manik | OtR-Oota [LOD 200 and Approvals] [Pkgs 3] | 0.15
Atul L | Total Packages [11 Pkgs] | 0
Atul P | TuiG FKH [V20, V30 and V40] [Pkgs 3] |  |  |  | LoD 350 - V20, V30 and V40
Atul P | Harohalli FKH [V30, V40 and V50] [Pkgs 3] |  |  |  | LoD 350 - V30, V40
Atul P | Violet Hill FKH [P-1 D & P-2 U][Pkgs 2] |  |  |  | LoD 100 - Concept to be finalized for product brochure & walkthrough
Atul P | Shreegaon FKH [V50 C] [Pkgs 1]
Atul P | OTF FKH V50 C and V50 D [Pkgs 2]
Prakash C | AtR Ph 1, 2a, 2b [LOD 350] [Pkgs 1] | 0.01
Prakash C | AtR Ph 2c [LOD 350] [Pkgs 2] | 0.02
Prakash C | AtR Ph 3 [LOD 350] except Villa block 33[Pkgs 15] | 0.36 | 2 | 0.01
Prakash C | AtR - C [LOD 350] [Pkgs 4] | 0.41 | 1 | 0.13
Prakash C | PoaRR-Res [LOD 350] [Pkgs 3] | 0.36
Prakash C | PoaRR-T08 [LOD 350] [Pkgs 8] | 2.1
Prakash C | ITQE-Ph1 [LOD 350] [Pkgs 3] | 0.08 |  |  | LoD 350 - Master Plan ¦ Site Development, LoD 350 - Amenities & Facilities ¦ Community spaces
Prakash C | ITQE-Ph2a [LOD 350] [Pkgs 3] | 0.17 |  |  | LoD 350 -Experience Home + Project Experience [ V35 ], LoD 350 - Master Plan ¦ Site Development, LoD 350 - Master Plan ¦ Site MEP
Prakash C | ITQE-Ph2b [LOD 350] except terrace level [Pkgs 11] | 1.12 | 2 | 0.14 | LoD 350 - Tower 06 ¦ Habitable Level - Even, LoD 350 - Tower 06 ¦ Habitable Level - Odd, LoD 350 - Tower 07 ¦ Habitable Level - Even, LoD 350 - Tower 07 ¦ Habitable Level - Odd, LoD 350 - ISS5&6 ¦ Structrural Slab 01 [Basement], LoD 350 - ISS 7 ¦ Structrural Slab 01 [Basement]
Prakash C | ItQE-Ph2c [LOD 350] [T9] Till Parking level subgrade [Pkgs 4] | 0.28
Prakash C | ItQE-Ph3a [T10-12 & 31 Villas] [LOD 350] [Pkgs 2] | 3.26
Prakash C | OTR-Ph01 [LOD 350] [Pkgs 5] | 0.38 |  |  | LoD 350 - LoD 350 -Experience Home + Project Experience [ V35 ], LoD 350 - Villa Block ¦ Super Structure
Prakash C | TuiG [LOD 350] [Pkgs 4] | 0.8 | 1 | 0.061982
Prakash C | TMFT-Ph 2 [LOD 350] [Pkgs 1] | 0.03 |  |  | LoD 350 - Master Plan - Site Development
Prakash C | DBTW [LOD 350] except odd level ,Terrace [Pkgs 15] | 3.64 | 1 | 2.25 | LoD 300 - Pre Construction Set [Podium], LoD 350 - Tower-2-Habitable Level 01
Prakash C | SftW [LOD 350] except community spaces[Pkgs 6] | 0.35
Prakash C | LGCE Campus [Pkgs 0] | 0
Prakash C | Ooty Res [Pkgs 0] | 0
Prakash C | MeenaSai Res [LOD 200] [Pkgs 1] | 0.02
Prakash C | NH Homestay [LOD 350] [Pkgs 3] | 0.22
Prakash C | OTR Museum [LOD 350] [Pkgs 0] | 0
Prakash C | KIADB - Mys [LOD 350] [Pkgs 1] | 0
Prakash C | Imagine Campus [LOD 200] [Pkgs 1] | 0.19
Prakash C | OTR-Ph02 [LOD 200] [Pkgs 1] | 0.17
Prakash C | TMFT-Ph 3 [LOD 200] [Pkgs 1] | 0.08
Prakash C | Srjp - Res [LOD 200], experience home [Pkgs 2] | 2.02
Prakash C | Srjp - C - SB [LOD 200] [Pkgs 1] | 1.56
Prakash C | Srjp - C - NB [LOD 200][Pkgs 1] | 0.52
Prakash C | OTF [LOD 300] [Pkgs 3] | 0.57
Prakash C | Harohalli [Plotted] [LOD 200] [Pkgs 2] | 0.73
Prakash C | Shreegaon [70a] [LOD 200] [Pkgs 1] | 0.2
Prakash C | Violet hill [LOD 300][Pkgs 4] | 0.57 |  |  | LoD 350 - Infra Grading LoD 350 - Infra MEP LoD 350 - BOQ & Tech Specs
Prakash C | Ambegaon [Pkgs 0] | 0
Prakash C | Mall of Asia [Pkgs 0] | 0
Prakash C | TR Mills [Pkgs 0] | 0
Prakash C | Indiranagar Res [LOD 350] [Pkgs 1] | 0 |  |  | [LOD 350] - Building Envelope + Common area - Gym Spiral staircase
Prakash C | OTR OOTA [LOD 200] [Pkgs 1] | 0.02
Gaganjit S | AtR Ph 2c [LOD 350] - Site MEP [Pkgs 1] | 0.014337 |  |  | LoD 350 - Site MEP
Gaganjit S | AtR Ph 3 [LOD 350] except villa block 33, VAT Default [Pkgs 12] | 0.36573 |  |  | LoD 350 - Foundations and Sub-Grade Structure [Block 31, 32, 34]
Gaganjit S | AtR - Com [LOD 350] [Pkgs 2] | 0.16751
Gaganjit S | PoaRR-Res [LOD 350] [Pkgs 4] | 0.40327
Gaganjit S | PoaRR-T08 [LOD 350] except penthouse products [Pkgs 3] | 0.14
Gaganjit S | ITQE-Ph2b [LOD 350] - ISS 5,6,7 [Pkgs 2] | 0.031656 |  |  | LoD 350 - ISS -5 & 6 ¦ Structrural Slab 01 [Basement], LoD 350 - ISS -7 ¦ Structrural Slab 01 [Basement]
Gaganjit S | ItQE-Ph2c [T9] [LOD 350 -ISS 9, T9 Foundation and grade slab] [Pkgs 3] | 0.047123
Gaganjit S | ItQE-Ph3a [T10-12 & 31 Villas] [LOD 300], experience home [Pkgs 8] | 2.1646
Gaganjit S | OTR-Ph01 [LOD 350] Site MEP [Pkgs 1] | 0.04
Gaganjit S | TuiG [LOD 350] , Clubhouse except interiors[Pkgs 7] | 0.32 | 1 | 0.02 | LoD 350 - CH structure & envelope [MEP ] , CH interior & facilities [MEP+LS]
Gaganjit S | DBTW [LOD 350] Master plan [Pkgs 3] | 0.036853
Gaganjit S | SftW [LOD 350] Site MEP , Sporting facilities [Pkgs 4] | 0.021398
Gaganjit S | LGCE Campus [Pkgs 0] | 0
Gaganjit S | Ooty Res [Pkgs 0] | 0.0033
Gaganjit S | MeenaSai Res [LOD 200][Pkgs 2] | 0.0168
Gaganjit S | NH Homestay [LOD 350] [Pkgs 7] | 0.23027 | 1 | 0.02 | LoD 200-LS Schm Dsgn completed.
Gaganjit S | Indiranagar Res [LOD 350] [Pkgs 1] | 0.000113 |  |  | LOD 350- LS Building envelope + Common area
Gaganjit S | OTR Museum [Pkgs 0] | 0
Gaganjit S | KIADB - Mys [LOD 200] , Approvals[Pkgs 2] | 0 |  |  | LoD 100 - Design concept
Gaganjit S | Imagine Campus [LOD 200], Approvals [Pkgs 3] | 0.15
Gaganjit S | OTR-Ph02 [LOD 200], Approvals [Pkgs 4] | 0.16686
Gaganjit S | TMFT-Ph 3 [LOD 200], Approvals [Pkgs 4] | 0.07641
Gaganjit S | Srjp - Res [LOD 200], Approvals, experience home [Pkgs 5] | 1.7571
Gaganjit S | Srjp - C - SB [LOD 200], Approvals [Pkgs 2] | 0.86951
Gaganjit S | Srjp - C - NB [LOD 200], Approvals[Pkgs 2] | 0.28984
Gaganjit S | OTF [LOD 300], experience home [Pkgs 7] | 0.32805
Gaganjit S | Harohalli [Plotted] [LOD 200], Approvals [Pkgs 10] | 5.2621 |  |  | LoD 100 - Design concept
Gaganjit S | Shreegaon [70a] [LOD 200], Approvals [Pkgs 7] | 2.5074
Gaganjit S | Violet hill [LOD 300] [Pkgs 16] - MEP | 2.7928 |  |  | LoD 350 - Infra MEP LoD 350 - BOQ & Tech Specs
Gaganjit S | Violet hill [LOD 300] [Pkgs 16] - LS | 0 |  |  | LoD 350 - Infra MEP LoD 350 - BOQ & Tech Specs
Gaganjit S | Mall of Asia [Pkgs 0] | 0
Gaganjit S | TR Mills [Pkgs 0] | 0
Gaganjit S | OTR OOTA [Pkgs 4]
Design Lead | Design Packages | 26Q1 Fee | Actuals | Actual Fees
Navneet K | Home product launch [ItQE L25 - 632, OtR V25 - 525] | 0.9256 |  | 0.4392
Navneet K | Interior Design GFCs [149 Nos] | 1.1602 | 46 | 0.44551
Navneet K | Personalised [10 Nos] | 0.66198 | 2 | 0.20408
Navneet K | E-Build, E-Design, Online [107 Nos] | 0.4982 | 39 | 0.24143
Navneet K | Default [32 Nos] | 0 | 5
Note on C111: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: L25 Options - 600 ¦ V25 Options - 900

## Goal Summary 25Q4 (hidden)
|  |  |  | 353 | 0 | 0 | 0 | 157.0698 | 0 | 0 | 0
| Design Goals 2026 |  |  | Design Packages | Design Packages | Design Packages | Design Packages | Design Fees | Design Fees | Design Fees | Design Fees
| Project Design |  |  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
|  |  |  | 582 | 0 | 0 | 0 | 157.0698 | 0 | 0 | 0
| Atul | Design [FKH, Units] | Architecture | 16 |  |  |  | 0.45
| FKH | [Experience Homes] |  | 10 |  |  |  | 0
| Saji | TuiG | Architecture | 3
| Saji | Harohalli | Architecture | 2
|  | Violet Hill | Architecture | 1
|  | Shreegaon | Architecture | 2
|  | One Tiny Flower | Architecture | 2
| Individual Units GFC |  |  | 6 |  |  |  | 0.45
|  | Units - Personalised | Architecture | 6 |  |  |  | 0.45
| Cijey | Design [ITQE ¦ Srjp ¦ NH ¦ OTR] | Architecture | 65 |  |  |  | 51.6977
| ITQE |  |  | 29 |  |  |  | 7.6
|  | ITQE Ph 1 | Architecture | Amenities & Facilities ¦ Clubhouse—Interiors and Facilities |  |  |  | 0.26
|  | ITQE Ph 2a | Architecture | Master Plan ¦ Site Development |  |  |  | 0.07
|  | ITQE Ph 2a | Architecture | Experience Home + Project Experience [ V35 ] |  |  |  | 0.18
|  | ITQE Ph 2b | Architecture | Tower—05 ¦ Habitable Level 01 |  |  |  | 0.13
|  | ITQE Ph 2b | Architecture | Tower—06 ¦ Habitable Level 01 |  |  |  | 0.13
|  | ITQE Ph 2b | Architecture | Tower—07 ¦ Habitable Level 01 |  |  |  | 0.13
|  | ITQE Ph 2b | Architecture | Tower—05 ¦ Terrace Level |  |  |  | 0.08
|  | ITQE Ph 2b | Architecture | Tower—05 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] |  |  |  | 0.22
|  | ITQE Ph 2b | Architecture | Tower—06 ¦ Terrace Level |  |  |  | 0.08
|  | ITQE Ph 2b | Architecture | Tower—06 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] |  |  |  | 0.22
|  | ITQE Ph 2b | Architecture | Tower—07 ¦ Terrace Level |  |  |  | 0.08
|  | ITQE Ph 2b | Architecture | Tower—07 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] |  |  |  | 0.22
|  | ITQE Ph 2b | Architecture | ISS 5&6 ¦ Foundations & Sub-Grade |  |  |  | 0.2
|  | ITQE Ph 2b | Architecture | ISS 7 ¦ Foundations & Sub-Grade |  |  |  | 0.2
|  | ITQE Ph 2b | Architecture | ISS 5&6 ¦ Structural Slab 01 [Basement] |  |  |  | 0.3
|  | ITQE Ph 2b | Architecture | ISS 7 ¦ Structrural Slab 01 [Basement] |  |  |  | 0.3
|  | ITQE Ph 2b | Architecture | Master Plan ¦ Master Plan |  |  |  | 0.03
|  | ITQE Ph 2b | Architecture | ISS 5&6 ¦ Podium Slab |  |  |  | 0.1
|  | ITQE Ph 2b | Architecture | ISS 7 ¦ Podium Slab |  |  |  | 0.1
|  | ITQE Ph 2b | Architecture | ISS 5&6 ¦ Building Envelope and Common Areas |  |  |  | 0.4
|  | ITQE Ph 2b | Architecture | ISS 7 ¦ Building Envelope and Common Areas |  |  |  | 0.4
|  | ITQE Ph 2b | Architecture | Master Plan ¦ Site Development |  |  |  | 0.02
|  | ITQE Ph 2b | Architecture | Master Plan ¦ Site MEP |  |  |  | 0.01
|  | ITQE Ph 2b | Architecture | Master Plan ¦ Landscaping |  |  |  | 0.01
|  | ITQE Ph 2c | Architecture | Marketing and Sales |  |  |  | 0.88
|  | ITQE Ph 2c | Architecture | Pre Construction Set |  |  |  | 1.76
|  | ITQE Ph 2c | Architecture | Experience Home + Project Experience [I20,I25] |  |  |  | 0.88
|  | ITQE Ph 2c | Architecture | Tower 9¦Foundations & Sub-Grade |  |  |  | 0.11
|  | ITQE Ph 2c | Architecture | ISS 9¦Foundations & Sub-Grade |  |  |  | 0.1
| Sarjapur [Inspira] |  |  | 6 |  |  |  | 36.0668
|  | Sarjapur | Architecture | Contract + Design Brief |  |  |  | 8.2202
|  | Sarjapur | Architecture | Schematic Concept |  |  |  | 7.8096
|  | Sarjapur | Architecture | Preconstruction Set |  |  |  | 7.8096
|  | Sarjapur | Architecture | Approvals |  |  |  | 4.0074
|  | Sarjapur | Architecture | Experience Home + Project Experience |  |  |  | 4.1101
|  | Sarjapur | Architecture | Marketing and Sales |  |  |  | 4.1101
| 37a Nandi Hiils [V] Hoysala |  |  | 1 |  |  |  | 1.2875
|  | NH37a [V] | Architecture | Contract + Design Brief |  |  |  | 1.2875
| 36a Nandi Hills [V] Madukosanahalli |  |  | 2 |  |  |  | 3.0034
|  | NH36a [V] | Architecture | Contract + Design Brief |  |  |  | 1.5181
|  | NH36a [V] | Architecture | Schematic Concept |  |  |  | 1.4854
| OtR |  |  | 12 |  |  |  | 2.43
|  | OtR Ph1 | Architecture | Pre Construction Set |  |  |  | 0.31
|  | OtR Ph1 | Architecture | Individual Homes ¦ V25 Default & its Variant |  |  |  | 0.3
|  | OtR Ph1 | Architecture | Villa Block ¦ Super Structure |  |  |  | 0.3
|  | OtR Ph1 | Architecture | Villa Block ¦ Building Envelope + Plot Development |  |  |  | 0.14
|  | OtR Ph1 | Architecture | Master Plan |  |  |  | 0.09
|  | OtR Ph1 | Architecture | Site Development |  |  |  | 0.03
|  | OtR Ph1 | Architecture | Site MEP |  |  |  | 0.03
|  | OtR Ph1 | Architecture | Landscaping |  |  |  | 0.15
|  | OtR Ph2 | Architecture | Contract + Design Brief |  |  |  | 0.31
|  | OtR Ph2 | Architecture | Schematic Concept |  |  |  | 0.31
|  | OtR Ph2 | Architecture | Approvals |  |  |  | 0.31
|  | OtR Ph2 | Architecture | Marketing and Sales |  |  |  | 0.15
| Meena & Krishnasai Residence |  |  | 4 |  |  |  | 0.27
|  | MeenaSai Res | Architecture | Design Brief |  |  |  | 0.27
|  | MeenaSai Res | Architecture | Schematic Concept
|  | MeenaSai Res | Architecture | Pre Construction Set
|  | MeenaSai Res | Architecture | Approvals
| 10a Nandi Hills [V] Sltnpt | [6 empty] | 0
|  | NH10a [V] | Architecture
| NH Homestay |  |  | 5 |  |  |  | 0.995
|  | NH Homestay | Architecture | Schematic Concept |  |  |  | 0.19
|  | NH Homestay | Architecture | Preconstruction |  |  |  | 0.19
|  | NH Homestay | Architecture | Foundation + Subgrade |  |  |  | 0.246
|  | NH Homestay | Architecture | Building envelope + Plot development |  |  |  | 0.246
|  | NH Homestay | Architecture | Interiors |  |  |  | 0.123
| OtR -Museum |  |  | 2 |  |  |  | 0
|  | OtR -Museum | Architecture | Contract + Design Brief
|  | OtR -Museum | Architecture | Schematic Concept
| Vaderahalli |  |  | 3 |  |  |  | 0
|  | Vaderahalli | Architecture | Contract + Design Brief
|  | Vaderahalli | Architecture | Schematic Concept
|  | Vaderahalli | Architecture | Approvals
| Individual Units GFC |  |  | 1 |  |  |  | 0.045
|  | Units | Architecture | OtR ¦ Villa -22- Personalised design |  |  |  | 0.045
| OP | Design [TMFT ¦ SFTW ¦ DBTW ¦ TUIG] | Architecture | 67 |  |  |  | 13.6236
| TMFT - Ph3 |  |  | 2 |  |  |  | 0
| OP | TMFT - Ph3 | Architecture | Contract + Design Brief
| OP | TMFT - Ph3 | Architecture | Schematic Concept
| SFTW |  |  | 10 |  |  |  | 0.90157
| OP | SFTW | Architecture | ISS 01 - Podium Slab |  |  |  | 0.25575
| OP | SFTW | Architecture | Clubhouse—Structure and Envelope |  |  |  | 0.081564
| OP | SFTW | Architecture | Master Plan |  |  |  | 0.18697
|  | SFTW | Architecture | Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.027188
|  | SFTW | Architecture | Master Plan - Site Development |  |  |  | 0.11218
|  | SFTW | Architecture | Master Plan - Site MEP |  |  |  | 0.037394
|  | SFTW | Architecture | Master Plan - Landscaping |  |  |  | 0.037394
|  | SFTW | Architecture | Clubhouse—Interiors and Facilities |  |  |  | 0.10875
|  | SFTW | Architecture | Clubhouse + Amenities - Community spaces [Board Walk, Children play area] |  |  |  | 0.027188
|  | SFTW | Architecture | Clubhouse + Amenities - Sporting Facilities |  |  |  | 0.027188
| DBTW |  |  | 35 |  |  |  | 9.88
| OP | DBTW | Architecture | Master Plan - Site MEP |  |  |  | 0.07
| OP | DBTW | Architecture | Master Plan - Landscaping |  |  |  | 0.07
| OP | DBTW | Architecture | Clubhouse—Interiors and Facilities |  |  |  | 0.15
|  | DBTW | Architecture | Community spaces [Board Walk, Children play area,OAT] |  |  |  | 0.04
|  | DBTW | Architecture | Sporting Facilities |  |  |  | 0.04
|  | DBTW | Architecture | Tower 06 - Foundation and Grade Slab |  |  |  | 0.06
|  | DBTW | Architecture | Tower 06 -Parking Level-Sub grade |  |  |  | 0.03
|  | DBTW | Architecture | Tower 06 - Building Envelope and Common Areas [Basement] |  |  |  | 0.06
| OP | DBTW | Architecture | Tower 06 - Habitable Level 01 |  |  |  | 0.06
|  | DBTW | Architecture | Tower 06 - Habitable Level - Even |  |  |  | 0.03
|  | DBTW | Architecture | Tower 06 -Habitable Level - Odd |  |  |  | 0.03
|  | DBTW | Architecture | Tower 06 -Building Envelope and Common Areas [Typical Tower Levels] |  |  |  | 0.13
|  | DBTW | Architecture | Tower 06- Terrace Level |  |  |  | 0.1
|  | DBTW | Architecture | Tower 06 - Building Envelope and Common Areas [Terrace Level] |  |  |  | 0.13
|  | DBTW | Architecture | ISS 01 - Foundations & Grade Slab |  |  |  | 0.27
|  | DBTW | Architecture | ISS 02 - Foundations & Grade Slab |  |  |  | 0.27
|  | DBTW | Architecture | ISS 01 - Podium Slab |  |  |  | 0.14
|  | DBTW | Architecture | ISS 02 - Podium Slab |  |  |  | 0.14
|  | DBTW | Architecture | ISS 01 - Building Envelope and Common Areas |  |  |  | 0.55
|  | DBTW | Architecture | ISS 02 - Building Envelope and Common Areas |  |  |  | 0.55
|  | DBTW | Architecture | Home Products - I20 Default and it's variants |  |  |  | 2.24
|  | DBTW | Architecture | Home Products - I25 Default and it's variants |  |  |  | 2.24
|  | DBTW | Architecture | Tower 1 - Terrace Level |  |  |  | 0.1
|  | DBTW | Architecture | Tower 1 - Building Envelope and Common Areas [Terrace Level] |  |  |  | 0.13
|  | DBTW | Architecture | Tower 2 - Terrace Level |  |  |  | 0.2
|  | DBTW | Architecture | Tower 2 - Building Envelope and Common Areas [Terrace Level] |  |  |  | 0.27
|  | DBTW | Architecture | Tower 3 - Terrace Level |  |  |  | 0.2
|  | DBTW | Architecture | Tower 3 - Building Envelope and Common Areas [Terrace Level] |  |  |  | 0.27
|  | DBTW | Architecture | Tower 4 - Terrace Level |  |  |  | 0.2
|  | DBTW | Architecture | Tower 4 - Building Envelope and Common Areas [Terrace Level] |  |  |  | 0.27
|  | DBTW | Architecture | Tower 5 - Terrace Level |  |  |  | 0.2
|  | DBTW | Architecture | Tower 5 - Building Envelope and Common Areas [Terrace Level] |  |  |  | 0.27
|  | DBTW | Architecture | Master Plan - Site Development |  |  |  | 0.22
|  | DBTW | Architecture | Clubhouse—Structure and Envelope |  |  |  | 0.11
|  | DBTW | Architecture | Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.04
| TUIG |  |  | 7 |  |  |  | 1.6448
|  | TUIG | Architecture | Pre-construction set - CH |  |  |  | 0.11
|  | TUIG | Architecture | Approvals
|  | TUIG | Architecture | Clubhouse—Structure and Envelope |  |  |  | 0.46
|  | TUIG | Architecture | Clubhouse—Interiors and Facilities |  |  |  | 0.62
|  | TUIG | Architecture | Community spaces [Board Walk, Children play area] |  |  |  | 0.15478
|  | TUIG | Architecture | Sporting Facilities |  |  |  | 0.15
|  | TUIG | Architecture | Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.15
| Poinciana |  |  | 0
| Ambegaon |  |  | 0
| Savakanhli |  |  | 0
| Harohalli |  |  | 2 |  |  |  | 0.3525
|  | Harohalli | Architecture | Schematic concept - CH |  |  |  | 0.235
|  | Harohalli | Architecture | Project Experience - Entrance portal |  |  |  | 0.1175
| 37a Nandi Hills [V] Hoysala |  |  | 0
| Sarjapur [Inspira] |  |  | 2 |  |  |  | 0.51325
|  | Sarjapur | Architecture | Schematic Concept - CH |  |  |  | 0.4106
|  | Sarjapur | Architecture | Approvals-CH |  |  |  | 0.10265
| 36a Nandi Hills [V] Madukosanahalli |  |  | 0 | [7 empty] | 0
|  | NH36a [V] | Architecture
| Shreegaon |  |  | 1 |  |  |  | 0.09
|  | Shreegaon | Architecture | Schematic Concept - CH |  |  |  | 0.09
| Violet Hill |  |  | 2 |  |  |  | 0.050686
|  | Violet Hill | Architecture | Schematic Concept - CH |  |  |  | 0.025343
|  | Violet Hill | Architecture | Approvals |  |  |  | 0.025343
| OTF [Suntikoppa] |  |  | 1 |  |  |  | 0.1233
|  | OTF [Suntikoppa] | Architecture | Schematic Concept - CH |  |  |  | 0.1233
| Vijayapura |  |  | 0 |  |  |  | 0
|  | Vijayapura | Architecture
|  | Vijayapura | Architecture
|  | Vijayapura | Architecture
|  | Vijayapura | Architecture
| Vaderahalli | [6 empty] | 0
|  | Vaderahalli | Architecture | Project Experience - Entrance Portal
|  | Vaderahalli | Architecture | Schematic Concept - CH
| 10a Nandi Hiils [V] Sltnpt |  |  | 0 |  |  |  | 0
|  | NH10a [V] | Architecture
|  | NH10a [V] | Architecture
| LGCE |  |  | 4 |  |  |  | 0
|  | LGCE | Architecture | Contract + Design brief
|  | LGCE | Architecture | Schematic concept
|  | LGCE | Architecture | Pre-construction set
|  | LGCE | Architecture | Approvals
3
Aundh 3a
Sarjapur [P]
CSR- Auditorium Malleshwaram
| Individual Units GFC |  |  | 1 |  |  |  | 0.06747
|  | Units | Architecture | TMFT 3284 - Personalised |  |  |  | 0.06747
| Saji | Design [AtR ¦ PoaRR] | Architecture | 67 |  |  |  | 13.1281
| ATR | [Complete Ph 1 - 2c] |  | 5 |  |  |  | 1.2252
| Saji | AtR Ph 1, 2a, 2b | Architecture | AR ¦ Master Plan - Site Development (Rework)
|  | AtR Ph 1, 2a, 2b | Architecture | AR ¦ Clubhouse + Amenities - Clubhouse—Interiors and Facilities |  |  |  | 0.22689
|  | AtR Ph 1, 2a, 2b | Architecture | AR ¦ Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] |  |  |  | 0.045377
|  | AtR Ph 2c | Architecture | AR ¦ Master Plan - Site MEP |  |  |  | 0.039416
|  | AtR Ph 2c | Architecture | AR ¦ Clubhouse + Amenities - Sporting Facilities |  |  |  | 0.91353
| ATR - 3 | [Dsgn Brf, Schm Cncpt, Pre-Con, V45, Villa blocks 29 - 34, Masterplan] |  | 19 |  |  |  | 1.9114
|  | AtR-3 | Architecture | Contract + Design brief |  |  |  | 0.27398
|  | AtR-3 | Architecture | AR ¦ Schematic Concept |  |  |  | 0.27398
|  | AtR-3 | Architecture | Approvals |  |  |  | 0.13699
|  | AtR-3 | Architecture | AR ¦ Pre Construction Set |  |  |  | 0.27398
|  | AtR-3 | Architecture | AR ¦ Home Products - V30 Default and it's variants |  |  |  | 0.07
|  | AtR-3 | Architecture | AR ¦ Home Products - V50 Default and it's variants |  |  |  | 0.07
|  | AtR-3 | Architecture | AR ¦ Home Products - V45 Default and it's variants |  |  |  | 0.29
|  | AtR-3 | Architecture | AR ¦ Master Plan - Master Plan |  |  |  | 0.037476
|  | AtR-3 | Architecture | AR ¦ Villa Block 29 - Foundations and Sub-Grade Structure |  |  |  | 0.07
|  | AtR-3 | Architecture | AR ¦ Villa Block 30 - Foundations and Sub-Grade Structure |  |  |  | 0.07
|  | AtR-3 | Architecture | AR ¦ Villa Block 34 - Foundations and Sub-Grade Structure |  |  |  | 0.04
|  | AtR-3 | Architecture | AR ¦ Villa Block 29 - Building Envelope + Plot Development |  |  |  | 0.07
|  | AtR-3 | Architecture | AR ¦ Villa Block 30 - Building Envelope + Plot Development |  |  |  | 0.07
|  | AtR-3 | Architecture | AR ¦ Villa Block 31 - Building Envelope + Plot Development |  |  |  | 0.01
|  | AtR-3 | Architecture | AR ¦ Villa Block 32 - Building Envelope + Plot Development |  |  |  | 0.03
|  | AtR-3 | Architecture | AR ¦ Villa Block 34 - Building Envelope + Plot Development |  |  |  | 0.04
|  | AtR-3 | Architecture | Master Plan - Site Development |  |  |  | 0.024984
|  | AtR-3 | Architecture | Master Plan - Site MEP |  |  |  | 0.04
|  | AtR-3 | Architecture | Master Plan - Landscaping |  |  |  | 0.02
| PoaRR | [Complete the project] |  | 7 |  |  |  | 2.32
| Saji | PoaRR Res | Architecture | Villa Cluster 3 - All Levels |  |  |  | 0.17
| Saji | PoaRR Res | Architecture | Villa Cluster 3 - Building Envelope and Common Areas |  |  |  | 0.17
| Saji | PoaRR Res | Architecture | V40 Default and it's variants |  |  |  | 1.18
| Saji | PoaRR Res | Architecture | Residential - Site Development |  |  |  | 0.45
| Saji | PoaRR Res | Architecture | Masterplan - Site MEP |  |  |  | 0.15
| Saji | PoaRR Res | Architecture | Masterplan - Landscaping |  |  |  | 0.15
| Saji | PoaRR Res | Architecture | Amenities & Facilities - Sporting Facilities |  |  |  | 0.05
| PoaRR T08 |  |  | 19 |  |  |  | 6.38
| Saji | PoaRR T08 | Architecture | T08 - ISS - Foundations & Grade Slab |  |  |  | 0.2
| Saji | PoaRR T08 | Architecture | T08 - ISS - Parking Level Subgrade |  |  |  | 0.41
| Saji | PoaRR T08 | Architecture | T08 - ISS - Podium Slab |  |  |  | 0.61
| Saji | PoaRR T08 | Architecture | T08 - ISS - Building Envelope and Common Areas |  |  |  | 0.48
| Saji | PoaRR T08 | Architecture | T08 - Habitable Level 01 |  |  |  | 0.24
| Saji | PoaRR T08 | Architecture | T08 - Building Envelope and Common Areas [Typical Tower Levels] |  |  |  | 0.82
| Saji | PoaRR T08 | Architecture | L22 Default and it's variants |  |  |  | 0.52
| Saji | PoaRR T08 | Architecture | L20 Default and it's variants |  |  |  | 0.52
| Saji | PoaRR T08 | Architecture | D35 Default and it's variants |  |  |  | 0.52
| Saji | PoaRR T08 | Architecture | T08 - Master Plan |  |  |  | 0.17
| Saji | PoaRR T08 | Architecture | T08 - Penthouse Levels |  |  |  | 0.48
| Saji | PoaRR T08 | Architecture | T08 - Terrace Level |  |  |  | 0.24
|  | PoaRR T08 | Architecture | T08 - Building Envelope and Common Areas [Penthouse Levels And Terrace Level] |  |  |  | 0.96
| Saji | PoaRR T08 | Architecture | T08 - Clubhouse—Interiors and Facilities |  |  |  | 0.02
| Saji | PoaRR T08 | Architecture | T08 - Landscape |  |  |  | 0.03
| Saji | PoaRR T08 | Architecture | T08 - Site MEP |  |  |  | 0.03
| Saji | PoaRR T08 | Architecture | T08 - Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.015
| Saji | PoaRR T08 | Architecture | T08 - Community spaces [Board Walk, Children play area] |  |  |  | 0.015
| Saji | PoaRR T08 | Architecture | T08 - Site Development |  |  |  | 0.1
| POARR Workcations |  |  | 2 |  |  |  | 0
|  | POARR Workcations | Architecture | Lvl 23 - Staff dining [Construction GFC]—Whole floor
|  | POARR Workcations | Architecture | Mezzanine Floor
CSR-Padmashree Campus
|  | CSR - PDC | Architecture | Design Brief
|  | CSR - PDC | Architecture | Schematic Concept
|  | CSR - PDC | Architecture | Pre-construction set
|  | CSR - PDC | Architecture | GFC ¦ Block
| Individual Units GFC |  |  | 15 |  |  |  | 1.2915
|  | Units | Architecture | 15 |  |  |  | 1.2915
| Naveen | Design [AtR-C, Srjp-C, OtF, DP] | Architecture | 27 |  |  |  | 27.1467
| AtR Com |  |  | 3 |  |  |  | 0.37
| Naveen | AtR Com | Architecture | Master Plan - Site Development |  |  |  | 0.14
| Naveen | AtR Com | Architecture | Master Plan - Site MEP |  |  |  | 0.18
| Naveen | AtR Com | Architecture | Master Plan - Landscaping |  |  |  | 0.05
| DonaPaula |  |  | 4 |  |  |  | 4.085
|  | DonaPaula | Architecture | Schematic Concept .v7 [Rework] |  |  |  | 1.3617
|  | DonaPaula | Architecture | Preconstruction |  |  |  | 1.3617
|  | DonaPaula | Architecture | Experience home |  |  |  | 0.68084
|  | DonaPaula | Architecture | Approvals ¦ v7 |  |  |  | 0.68084
| OtF [Suntikoppa] |  |  | 6 |  |  |  | 7.7968
|  | OtF [Suntikoppa] | Architecture | Contract + Design Brief [Commercial] |  |  |  | 2.2805
|  | OtF [Suntikoppa] | Architecture | Approvals |  |  |  | 1.1403
|  | OtF [Suntikoppa] | Architecture | Pre Construction Set |  |  |  | 2.1572
|  | OtF [Suntikoppa] | Architecture | Marketing and Sales |  |  |  | 1.1403
|  | OtF [Suntikoppa] | Architecture | Experience Home + Project Experience |  |  |  | 1.0786
|  | OtF [Suntikoppa] | Architecture | Schematic Concept v2
Fee | PoaRR - T9 (Commercial Fit-outs) |  |  | 3 |  |  |  | 0.15736
|  | POARR Workcations | Architecture | T9-05 Nudge ¦ GFC Batch 3 |  |  |  | 0.096
|  | POARR Workcations | Architecture | T9-14 Sequel ¦ GFC Batch 3 |  |  |  | 0.061358
|  | POARR Workcations | Architecture | T9-15 to 20 Clayworks, TE - GFCs
| Sarjapur [Commercial] |  |  | 3 |  |  |  | 14.7375
|  | Sarjapur-C | Architecture | Contract + Design Brief |  |  |  | 4.9125
|  | Sarjapur-C | Architecture | Schematic Concept |  |  |  | 4.9125
|  | Sarjapur-C | Architecture | Approvals |  |  |  | 4.9125
Fee | KIADB - Machinecraft |  |  | 3 |  |  |  | 0
|  | KIADB-MC | Architecture | Contract + Design Brief
|  | KIADB-MC | Architecture | Schematic concept
|  | KIADB-MC | Architecture | Approvals
Fee | Imagine |  |  | 3 |  |  |  | 0
|  | IMGN | Architecture | Contract + Design Brief
|  | IMGN | Architecture | Schematic concept
|  | IMGN | Architecture | Approvals
|  | IMGN | Architecture
Fee | Vaderahalli [Commercial] |  |  | 2 |  |  |  | 0
|  | Vaderahalli | Architecture | Contract + Design Brief
|  | Vaderahalli | Architecture | Schematic Concept-Commercial
| Manik | Design [Independent Residence + tFS-2] | Architecture | 45 |  |  |  | 0.61038
Foundation School-2
|  | TFS2 | Architecture | GFC ¦ Block A & C: Lvl 3, 4 |  |  |  | 0.12878
| Indiranagar Residence |  |  | 7 |  |  |  | 0
|  | Indranagar Res | Architecture | B1 - MEP Coordination - Electrical, Plumbing, Home Automation
|  | Indranagar Res | Architecture | B1 - Interior Client Closure
|  | Indranagar Res | Architecture | B2 - MEP Coordination - Electrical, Plumbing, Home Automation
|  | Indranagar Res | Architecture | B2 - Interior Client Closure
|  | Indranagar Res | Architecture | B3 - Interior Client Closure
|  | Indranagar Res | Architecture | Boundary Wall, Security Cabin & Site MEP
|  | Indranagar Res | Architecture | Courtyard & Swimming Pool
Swiss Town Residence
|  | Swisstown Res | Architecture | Interiors |  |  |  | 0.0035
| Windmills Hyd |  |  | 2 |  |  |  | 0.61038
|  | Windmills Hyd | Architecture | Signage Drawings |  |  |  | 0.61038
|  | Windmills Hyd | Architecture | Handover Furnishing
| Windmills & Brewery @ SftW, Pune |  |  | 2 |  |  |  | 0
|  | Windmills at Sftw | Architecture | Contract + Design Brief
|  | Windmills at Sftw | Architecture | Schematic Concept
| TEHPL @ OTR |  |  | 2 |  |  |  | 0
|  | TEHPL @ OTR | Architecture | Contract + Design Brief
|  | TEHPL @ OTR | Architecture | Schematic Concept
| OB 2 Furniture Store |  |  | 1 |  |  |  | 0
|  | OB2 FS | Architecture | Order for Production
| Ooty Residence |  |  | 2 |  |  |  | 0
|  | Ooty Res | Architecture | Design Brief
|  | Ooty Res | Architecture | Schematic Concept
| Madison Trail, Plano |  |  | 5 |  |  |  | 0
|  | MT, Plano | Architecture | Default Unit Development
|  | MT, Plano | Architecture | Villa #03 : Kush's Residence - Dsgn Brf
|  | MT, Plano | Architecture | Villa #03 : Kush's Residence - LOD 200
|  | MT, Plano | Architecture | Villa #03 : Kush's Residence - Approvals
|  | MT, Plano | Architecture | Villa #03 : Kush's Residence - Preconstruction set
| Tapestry |  |  | 24 |  |  |  | 0
|  | Villa #01 : V50-EH v3 | Architecture | 1
|  | Villa #02 & 11 : V40D Spec Homes [Interiors] | Architecture | 1
|  | Villa #12 : Client - Prabhash | Architecture | 1
|  | Villa #10 : Client - Raj | Architecture | 5
|  | Villa #09 : V50-EH v3 [Spec version] | Architecture | 3
|  | Villa #00 : V40 Guclu - Concept Sign-off | Architecture | 1
|  | Villa #30-31 : V40D Spec Homes - Permit Set | Architecture | 2
|  | V25-EH [4 out of 5 Packages] | Architecture | 4
|  | V50-Dv4 Drawings | Architecture | 1
|  | V40-Dv4 Drawings | Architecture | 1
|  | V25-Dv1 Drawings | Architecture | 1
|  | ClubHouse & Play area Concept closure | Architecture | 2
|  | Standard Details v4 | Architecture | 1
|  | V25 LGSF Structural/Masonry Coordination | Architecture | 0
| Gagan | Design [MP+MEP+LS] | [MP+MEP+LS] | 137 |  |  |  | 20.3251
| AtR Ph 1, 2a, 2b, 2c |  |  | 1 |  |  |  | 0.014337
| Gagan | AtR Ph 2c | MEP | MEP ¦ Master Plan - Site MEP |  |  |  | 0.014337
| AtR-3 |  |  | 15 |  |  |  | 0.37326
|  | AtR-III | MEP | Schematic Concept [V80] |  |  |  | 0.02
|  | AtR-III | MEP | PreConstruction Set [V45] |  |  |  | 0.02
|  | AtR-III | MEP | MEP ¦ Villa Block 29 - Foundations and Sub-Grade Structure |  |  |  | 0.004
|  | AtR-III | MEP | MEP ¦ Villa Block 30 - Foundations and Sub-Grade Structure |  |  |  | 0.004
|  | AtR-III | MEP | MEP ¦ Villa Block 31 - Foundations and Sub-Grade Structure |  |  |  | 0.00025671
|  | AtR-III | MEP | MEP ¦ Villa Block 32 - Foundations and Sub-Grade Structure |  |  |  | 0.002
|  | AtR-III | MEP | MEP ¦ Villa Block 34 - Foundations and Sub-Grade Structure |  |  |  | 0.003
|  | AtR-III | MEP | MEP ¦ Home Products - V45 Default and it's variants |  |  |  | 0.1
|  | AtR-III | MEP | MEP ¦ Master Plan - Master Plan |  |  |  | 0.01
|  | AtR-III | MEP | MEP ¦ Master Plan - Site MEP |  |  |  | 0.03
|  | AtR-III | LS | Schematic Concept |  |  |  | 0.05
|  | AtR-III | LS | LS ¦ Preconstruction Set |  |  |  | 0.05
|  | AtR-III | LS | LS ¦ Home Products - V45 Default and it's variants |  |  |  | 0.05
|  | AtR-III | LS | LS ¦ Master Plan - Master Plan |  |  |  | 0.01
|  | AtR-III | LS | LS ¦ Master Plan - Landscaping |  |  |  | 0.02
| AtR Com |  |  | 5 |  |  |  | 0.31
| Gagan | AtR Com | MEP | MEP ¦ Tower-[Commercial] - Building Envelope and Common Areas [Basement] |  |  |  | 0.05
| Gagan | AtR Com | MEP | MEP ¦ Tower-[Commercial] - Habitable Level 6-10 |  |  |  | 0.05
| Gagan | AtR Com | MEP | MEP ¦ Tower-[Commercial] - Terrace Level |  |  |  | 0.04
| Gagan | AtR Com | MEP | MEP ¦ Master Plan - Master Plan |  |  |  | 0.04
| Gagan | AtR Com | MEP | MEP ¦ Master Plan - Site MEP |  |  |  | 0.13
| TMFT - Ph3 |  |  | 1 |  |  |  | 0
| Gagan | TMFT - Ph3 | MEP | Schematic Concept
| Gagan | TMFT - Ph3 | LS
| SFTW |  |  | 3 |  |  |  | 0.022509
| Gagan | SFTW | MEP | MEP ¦ Master Plan - Site MEP |  |  |  | 0.020843
| Gagan | SFTW | MEP | MEP ¦ Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.0011107
| Gagan | SFTW | MEP | MEP ¦ Clubhouse—Sporting Facilities |  |  |  | 0.00055534
| PoaRR |  |  | 17 |  |  |  | 0.9164
| Gagan | PoaRR Res | MEP | MEP ¦ Master Archives - Res |  |  |  | 0.24
| Gagan | PoaRR Res | MEP | Sporting Facilities |  |  |  | 0.001
| Gagan | PoaRR T08 | MEP | T08 - Habitable Level 01 |  |  |  | 0.11
| Gagan | PoaRR T08 | MEP | T08 - Building Envelope and Common Areas [Typical Tower Levels] |  |  |  | 0.09
| Gagan | PoaRR T08 | MEP | T08 - ISS - Foundation and Gradeslab |  |  |  | 0.02
| Gagan | PoaRR T08 | MEP | T08 - L20 Default and it's variants |  |  |  | 0.06
| Gagan | PoaRR T08 | MEP | T08 - D35 Default and it's variants |  |  |  | 0.06
| Gagan | PoaRR T08 | MEP | T08 - Clubhouse—Interiors and Facilities |  |  |  | 0.004
| Gagan | PoaRR T08 | MEP | T08 - Master Plan |  |  |  | 0.04
| Gagan | PoaRR T08 | MEP | T08 - Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.0014
| Gagan | PoaRR T08 | MEP | T08 - Site MEP |  |  |  | 0.12
| Gagan | PoaRR | LS | Amenities & Facilities - Community spaces [Sporting Facilities] |  |  |  | 0.04
| Gagan | PoaRR-T08 | LS | T08-Clubhouse—Interiors and Facilities |  |  |  | 0.02
| Gagan | PoaRR-T08 | LS | T08 Pre Construction |  |  |  | 0.02
| Gagan | PoaRR-T08 | LS | T08-Master Plan |  |  |  | 0.02
| Gagan | PoaRR-T08 | LS | T08-Landscaping |  |  |  | 0.02
| Gagan | PoaRR-T08 | LS | T08-Community spaces [Board Walk, Children play area] |  |  |  | 0.05
| ITQE |  |  | 15 |  |  |  | 0.52189
|  | ITQE Ph 2b | MEP | ISS -5 & 6 ¦ Structrural Slab 01 [Basement] |  |  |  | 0.015828
|  | ITQE Ph 2b | MEP | ISS -7 ¦ Structrural Slab 01 [Basement] |  |  |  | 0.015828
|  | ITQE Ph 2b | MEP | Tower—05 ¦ Terrace Level |  |  |  | 0.037611
|  | ITQE Ph 2b | MEP | Tower—06 ¦ Terrace Level |  |  |  | 0.037611
|  | ITQE Ph 2b | MEP | Tower—07 ¦ Terrace Level |  |  |  | 0.037611
|  | ITQE Ph 2b | MEP | Masterplan ¦ Master Plan |  |  |  | 0.0054604
|  | ITQE Ph 2b | MEP | ISS -5 & 6 ¦ Podium Slab |  |  |  | 0.011871
|  | ITQE Ph 2b | MEP | ISS -7 ¦ Podium Slab |  |  |  | 0.011871
|  | ITQE Ph 2b | MEP | Masterplan ¦ Site MEP |  |  |  | 0.018201
|  | ITQE Ph 2c | MEP | Schematic Concept |  |  |  | 0.06
|  | ITQE Ph 2c | MEP | Experience Home + Project Experience |  |  |  | 0.06
|  | ITQE Ph 2c | MEP | PreConstruction Set |  |  |  | 0.13
|  | ITQE Ph 2c | LS | Schematic Concept |  |  |  | 0.05
|  | ITQE Ph 2c | LS | Marketing and Sales |  |  |  | 0.02
|  | ITQE Ph 2c | LS | PreConstruction Set |  |  |  | 0.01
| Foundation school -2 |  |  | 0 |  |  |  | 0
|  | TFS2 | MEP
| Indiranagar Residence |  |  | 2 |  |  |  | 0
|  | Indranagar Res | MEP | GFC ¦ Block [Gym + Swimming pool]
|  | Indranagar Res | LS | GFC ¦ Block [Gym + Swimming pool]
| Karnataka Public School, Basavanagudi | [6 empty] | 0
|  | KPS Basavangudi | MEP
|  | KPS Basavangudi | LS
| Auditorium [Malleswaram] | [6 empty] | 0
|  | CSR - Auditorium | MEP
|  | CSR - Auditorium | LS
| Padmashree Diagnostic center |  |  | 0 |  |  |  | 0
|  | CSR - PDC | MEP
| DBTW |  |  | 19 |  |  |  | 1.3942
|  | DBTW | MEP | Home Products - I20 Default and it's variants |  |  |  | 0.30995
|  | DBTW | MEP | Home Products - I25 Default and it's variants |  |  |  | 0.29586
|  | DBTW | MEP | Tower 1 - Terrace Level |  |  |  | 0.02
|  | DBTW | MEP | Tower 2 - Terrace Level |  |  |  | 0.05
|  | DBTW | MEP | Tower 3 - Terrace Level |  |  |  | 0.05
|  | DBTW | MEP | Tower 4 - Terrace Level |  |  |  | 0.05
|  | DBTW | MEP | Tower 5 - Terrace Level |  |  |  | 0.05
|  | DBTW | MEP | Master Plan- Master Plan |  |  |  | 0.04
|  | DBTW | MEP | Clubhouse—Structure and Envelope |  |  |  | 0.02
|  | DBTW | MEP | Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.01
|  | DBTW | MEP | Master Plan - Site MEP |  |  |  | 0.12284
|  | DBTW | MEP | Clubhouse—Interiors and Facilities |  |  |  | 0.0081296
|  | DBTW | MEP | Sporting Facilities |  |  |  | 0.0027099
|  | DBTW | MEP | Tower 06- Terrace Level |  |  |  | 0.023284
|  | DBTW | LS | Master Plan - Master Plan |  |  |  | 0.1027
|  | DBTW | LS | Master Plan - Landscaping |  |  |  | 0.12324
|  | DBTW | LS | Clubhouse—Interiors and Facilities |  |  |  | 0.021
|  | DBTW | LS | Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.042
|  | DBTW | LS | Community spaces [Board Walk, Children play area,OAT] |  |  |  | 0.0525
| TUIG |  |  | 10 |  |  |  | 1.8335
|  | TUIG | MEP | PreConstruction Set [Clubhouse] |  |  |  | 0.14
|  | TUIG | MEP | Clubhouse—Structure and Envelope |  |  |  | 0.17351
|  | TUIG | MEP | Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.05
|  | TUIG | MEP | Clubhouse—Interiors and Facilities |  |  |  | 0.07
|  | TUIG | MEP | Sporting Facilities |  |  |  | 0.02
|  | TUIG | MP | Master Plan - Site MEP |  |  |  | 0.3
|  | TUIG | MP | Master Plan - Site Development |  |  |  | 0.91
|  | TUIG | LS | Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.06
|  | TUIG | LS | Clubhouse—Interiors and Facilities |  |  |  | 0.03
|  | TUIG | LS | Community spaces [Board Walk, Children play area] |  |  |  | 0.08
| Sarjapur [Inspira] |  |  | 9 |  |  |  | 5.6307
|  | Sarjapur | MEP | Schematic Concept |  |  |  | 0.97
|  | Sarjapur | MEP | Preconstruction Set |  |  |  | 0.97
|  | Sarjapur | MEP | Approvals |  |  |  | 0.48
|  | Sarjapur | MEP | Experience Home + Project Experience |  |  |  | 0.48
|  | Sarjapur Commercial | MEP | Schematic Concept |  |  |  | 0.57968
|  | Sarjapur Commercial | MEP | Approvals |  |  |  | 0.57968
|  | Sarjapur | LS | Schematic Concept |  |  |  | 0.81379
|  | Sarjapur | LS | Experience Home + Project Experience |  |  |  | 0.27126
|  | Sarjapur Commercial | LS | Schematic Concept |  |  |  | 0.48634
36a Nandi Hills[V]
Poinciana
| Ambegaon |  |  | 3 |  |  |  | 3.065
|  | Ambegaon | LS
|  | Ambegaon | LS
|  | Ambegaon | MEP
|  | Ambegaon | MEP
|  | Ambegaon | MP | Contract + Design Brief |  |  |  | 1.02
|  | Ambegaon | MP | Schematic Concept |  |  |  | 1.0225
|  | Ambegaon | MP | Approvals |  |  |  | 1.0225
| Savakanhli |  |  | 0 |  |  |  | 0
|  | Savakanhli | MP
| Harohalli |  |  | 6 |  |  |  | 2.6167
|  | Harohalli | MEP | Schematic Concept |  |  |  | 0.028907
|  | Harohalli | MEP | Approvals |  |  |  | 0.057814
|  | Harohalli | MEP
|  | Harohalli | LS
|  | Harohalli | LS
|  | Harohalli | LS
|  | Harohalli | MP | Contract + Design Brief |  |  |  | 0.24 |  |  |  |  | 0
|  | Harohalli | MP | Schematic Concept |  |  |  | 1.0225
|  | Harohalli | MP | Approvals |  |  |  | 1.0225
|  | Harohalli | MP | Project Experience & Entrance Gate |  |  |  | 0.24497
| 37a Nandi Hills [V] |  |  | 0 |  |  |  | 0
| 10a Nandi Hiils [V] Sltnpt |  |  | 0 |  |  |  | 0
|  | NH10a [V] | MEP
|  | NH10a [V] | LS
| DonaPaula |  |  | 0 |  |  |  | 0
|  | DonaPaula | MEP
|  | DonaPaula | MEP
|  | DonaPaula | LS
|  | DonaPaula | LS
| OTF [Suntikoppa] |  |  | 5 |  |  |  | 0.59609
|  | OTF [Suntikoppa] | MEP | Schematic Concept |  |  |  | 0.13436
|  | OTF [Suntikoppa] | MEP | Approvals |  |  |  | 0.067178
|  | OTF [Suntikoppa] | MEP | Pre Construction Set |  |  |  | 0.13436
|  | OTF [Suntikoppa] | MEP | Experience Home + Project Experience |  |  |  | 0.067178
|  | OTF [Suntikoppa] | LS | Schematic Concept |  |  |  | 0.19302
| OtR |  |  | 1 |  |  |  | 0.074219
|  | OtR Ph1 | MEP | Site MEP |  |  |  | 0.074219
|  | OtR Ph2 | MEP
|  | OtR Ph2 | MEP
|  | OtR Ph2 | LS
|  | OtR Ph2 | LS
|  | OtR Ph2 | LS
| PoaRR - T9 (Commercial Fit-outs) |  |  | 0 |  |  |  | 0
| Imagine Campus |  |  | 3 |  |  |  | 0
|  | Imagine | MEP | Schematic Concept
|  | Imagine | MEP
|  | Imagine | MEP | Approvals
|  | Imagine | LS | Approvals
|  | Imagine | LS
| KIADB - Machinecraft |  |  | 0 |  |  |  | 0
|  | KIADB-MC | MEP
|  | KIADB-MC | MEP
|  | KIADB-MC | MP
|  | KIADB-MC | MP
|  | KIADB-MC | LS
|  | KIADB-MC | LS
| Meena & Krishnasai Residence |  |  | 0 |  |  |  | 0
|  | MeenaSai Res | MEP
|  | MeenaSai Res | MEP
|  | MeenaSai Res | MEP
|  | MeenaSai Res | LS
|  | MeenaSai Res | LS
|  | MeenaSai Res | LS
| Ooty Residence |  |  | 0 |  |  |  | 0
|  | Ooty Res | MEP
|  | Ooty Res | LS
| OTR Museum |  |  | 0 |  |  |  | 0
|  | OTR Museum | MEP
|  | OTR Museum | LS
| NH-Homestay |  |  | 8 |  |  |  | 0.024698
|  | NH-Homestay | MEP | Schematic Concept |  |  |  | 0.015877
|  | NH-Homestay | MEP | Approvals
|  | NH-Homestay | MEP | Pre-construction set
|  | NH-Homestay | MEP | Constrcution GFC
|  | NH-Homestay | LS | Schematic Concept |  |  |  | 0.0088208
|  | NH-Homestay | LS | Approvals
|  | NH-Homestay | LS | Pre-construction set
|  | NH-Homestay | LS | Constrcution GFC
| MT, Plano [Uma & Kush] |  |  | 0 |  |  |  | 0
|  | MT, Plano | MEP
|  | MT, Plano | MEP
|  | MT, Plano | MEP
|  | MT, Plano | LS
|  | MT, Plano | LS
|  | MT, Plano | LS
| LGCE Campus |  |  | 3 |  |  |  | 0
|  | LGCE Campus | MEP | Schematic Concept
|  | LGCE Campus | MEP | Approvals
|  | LGCE Campus | MEP | Pre-construction set
|  | LGCE Campus | LS
|  | LGCE Campus | LS
|  | LGCE Campus | LS
| Shreegaon |  |  | 4 |  |  |  | 2.495
|  | Shreegaon | MP | Contract + Design Brief |  |  |  | 0.47
|  | Shreegaon | MP | Schematic Concept |  |  |  | 0.85
|  | Shreegaon | MP | Approvals |  |  |  | 0.94
|  | Shreegaon | MP | Project Experience & Entrance Gate |  |  |  | 0.235
|  | Shreegaon | MEP
|  | Shreegaon | MEP
|  | Shreegaon | MEP
|  | Shreegaon | LS
|  | Shreegaon | LS
|  | Shreegaon | LS
| Violet Hill |  |  | 4 |  |  |  | 0.43655
|  | Violet Hill | MP | Infra - Grading |  |  |  | 0.1216
|  | Violet Hill | MP | Infra - MEP |  |  |  | 0.24321
|  | Violet Hill | MEP | Infra - MEP |  |  |  | 0.057396
|  | Violet Hill | LS | Infra - MEP |  |  |  | 0.014349
| Sarjapur [P] |  |  | 0 |  |  |  | 0
|  | Sarjapur [P] | MP
|  | Sarjapur [P] | MP
|  | Sarjapur [P] | MP
|  | Sarjapur [P] | MEP
|  | Sarjapur [P] | MEP
|  | Sarjapur [P] | MEP
|  | Sarjapur [P] | LS
|  | Sarjapur [P] | LS
|  | Sarjapur [P] | LS
|  | Sarjapur [P] | LS
| Vijayapura | [6 empty] | 0
|  | Vijayapura | MP
| Tumkur | [6 empty] | 0
|  | Tumkur | MP
Tumkur
Tumkur
| Yadgarpalle | [6 empty] | 0
|  | Yadgarpalle | MP
| Varthur 52a | [6 empty] | 0
|  | Varthur 52a | MP
| Chamarajpet | [6 empty] | 0
|  | Chamarajpet | MP
| Aundh 3a |  |  | 0 |  |  |  | 0
|  | Aundh 3a | MP
Aundh 3a
Aundh 3a
| Lonavala | [6 empty] | 0
|  | Lonavala | MP
| Vaderahalli | [6 empty] | 0
|  | Vaderahalli | MP
|  | Vaderahalli | MEP
|  | Vaderahalli | MEP
|  | Vaderahalli | LS
|  | Vaderahalli | LS
| Product Launch |  |  | 3 |  |  |  | 0
| ITQE | L25 | Interior design | L25
| PoaRR | R25 | Interior design | R25
| OTR | V25 | Interior design | V25
| Individual Units GFC |  |  | 0 |  |  |  | 0
|  | Units | MEP
|  | Units | LS
| Prakash | Design [Structural] | Structural | 158 |  |  |  | 30.0882
| AtR Ph 1, 2a, 2b, 2c |  |  | 3 |  |  |  | 0.03
|  | AtR Ph 1, 2a, 2b | Structural | ST ¦ Clubhouse + Amenities - Community spaces [Board Walk, Children play area] |  |  |  | 0.01
|  | AtR Ph 2c | Structural | ST ¦ Master Plan - Site MEP |  |  |  | 0.01
|  | AtR Ph 2c | Structural | ST ¦ Clubhouse + Amenities - Sporting Facilities |  |  |  | 0.01
| AtR-3 |  |  | 19 |  |  |  | 0.44496
|  | AtR-3 | Structural | ST ¦ Schematic Concept |  |  |  | 0.084427
|  | AtR-3 | Structural | ST ¦ Pre Construction Set |  |  |  | 0.084427
|  | AtR-3 | Structural | ST ¦ Villa Block 29 - Foundations and Sub-Grade Structure |  |  |  | 0.021107
|  | AtR-3 | Structural | ST ¦ Villa Block 29 - Super Structure |  |  |  | 0.03166
|  | AtR-3 | Structural | ST ¦ Villa Block 29 - Building Envelope + Plot Development |  |  |  | 0.0052767
|  | AtR-3 | Structural | ST ¦ Villa Block 30 - Foundations and Sub-Grade Structure |  |  |  | 0.021107
|  | AtR-3 | Structural | ST ¦ Villa Block 30 - Super Structure |  |  |  | 0.03166
|  | AtR-3 | Structural | ST ¦ Villa Block 30 - Building Envelope + Plot Development |  |  |  | 0.0052767
|  | AtR-3 | Structural | ST ¦ Villa Block 31 - Foundations and Sub-Grade Structure |  |  |  | 0.021107
|  | AtR-3 | Structural | ST ¦ Villa Block 31 - Super Structure |  |  |  | 0.03166
|  | AtR-3 | Structural | ST ¦ Villa Block 31 - Building Envelope + Plot Development |  |  |  | 0.0052767
|  | AtR-3 | Structural | ST ¦ Villa Block 32 - Foundations and Sub-Grade Structure |  |  |  | 0.0093808
|  | AtR-3 | Structural | ST ¦ Villa Block 32 - Super Structure |  |  |  | 0.014071
|  | AtR-3 | Structural | ST ¦ Villa Block 32 - Building Envelope + Plot Development |  |  |  | 0.0023452
|  | AtR-3 | Structural | ST ¦ Villa Block 34 - Foundations and Sub-Grade Structure |  |  |  | 0.014071
|  | AtR-3 | Structural | ST ¦ Villa Block 34 - Super Structure |  |  |  | 0.021107
|  | AtR-3 | Structural | ST ¦ Villa Block 34 - Building Envelope + Plot Development |  |  |  | 0.0035178
|  | AtR-3 | Structural | ST ¦ Master Plan - Site Development |  |  |  | 0.020441
|  | AtR-3 | Structural | ST ¦ Master Plan - Site MEP |  |  |  | 0.017034
| AtR Com |  |  | 5 |  |  |  | 0.67
|  | AtR Com | Structural | ST ¦ Tower-[Commercial] - Habitable Level 1-2 |  |  |  | 0.13
|  | AtR Com | Structural | ST ¦ Tower-[Commercial] - Habitable Level 3-5 |  |  |  | 0.26
|  | AtR Com | Structural | ST ¦ Tower-[Commercial] - Habitable Level 6-10 [till 7th Lvl] |  |  |  | 0.26
|  | AtR Com | Structural | ST ¦ Master Plan - Site Development |  |  |  | 0.01
|  | AtR Com | Structural | ST ¦ Master Plan - Site MEP |  |  |  | 0.01
| PoaRR |  |  | 10 |  |  |  | 2.06
|  | PoaRR | Structural | Site Development |  |  |  | 0.19
|  | PoaRR | Structural | Site MEP |  |  |  | 0.16
|  | PoaRR | Structural | Sporting Facilities |  |  |  | 0.01
|  | PoaRR T08 | Structural | Penthouse Levels |  |  |  | 0.2
|  | PoaRR T08 | Structural | Terrace Level |  |  |  | 0.4
|  | PoaRR T08 | Structural | T08 - ISS - Foundations & Grade Slab |  |  |  | 0.32
|  | PoaRR T08 | Structural | T08 - ISS - Podium Slab |  |  |  | 0.32
|  | PoaRR T08 | Structural | T08 - ISS - Parking Level Subgrade |  |  |  | 0.43
|  | PoaRR T08 | Structural | Site Development |  |  |  | 0.02
|  | PoaRR T08 | Structural | Site MEP |  |  |  | 0.01
| TMFT |  |  | 1 |  |  |  | 0.02873
|  | TMFT -2 | Structural | Master Plan - Site Development |  |  |  | 0.02873
| TMFT - Ph3 |  |  | 1 |  |  |  | 0
|  | TMFT - Ph3 | Structural | Schematic Concept
| SFTW |  |  | 7 |  |  |  | 0.34917
|  | SFTW | Structural | Tower 2 - Terrace Level |  |  |  | 0.20116
|  | SFTW | Structural | Master Plan - Site Development |  |  |  | 0.058457
|  | SFTW | Structural | Master Plan - Site MEP |  |  |  | 0.048714
|  | SFTW | Structural | Clubhouse—Structure and Envelope |  |  |  | 0.025989
|  | SFTW | Structural | Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.0037128
|  | SFTW | Structural | Clubhouse - Community spaces [Board Walk, Children play area,OAT] |  |  |  | 0.0037128
|  | SFTW | Structural | Clubhouse—Sporting Facilities |  |  |  | 0.0074255
| ITQE |  |  | 28 |  |  |  | 3.4647
|  | ITQE Ph 1 | Structural | Master Plan ¦ Site Development |  |  |  | 0.060249
|  | ITQE Ph 1 | Structural | Amenities & Facilities ¦ Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.011912
|  | ITQE Ph 1 | Structural | Amenities & Facilities ¦ Community spaces |  |  |  | 0.011912
|  | ITQE Ph 2a | Structural | Master Plan ¦ Site Development |  |  |  | 0.054104
|  | ITQE Ph 2a | Structural | Master Plan ¦ Site MEP |  |  |  | 0.045086
|  | ITQE Ph 2a | Structural | Experience Home + Project Experience [ V35 ] |  |  |  | 0.067724
|  | ITQE Ph 2b | Structural | Tower 05 - Habitable Level - Even |  |  |  | 0.065484
|  | ITQE Ph 2b | Structural | Tower 05 - Habitable Level - Odd |  |  |  | 0.065484
|  | ITQE Ph 2b | Structural | Tower 06 - Habitable Level - Even |  |  |  | 0.065484
|  | ITQE Ph 2b | Structural | Tower 06 - Habitable Level - Odd |  |  |  | 0.065484
|  | ITQE Ph 2b | Structural | Tower 07 - Habitable Level - Even |  |  |  | 0.065484
|  | ITQE Ph 2b | Structural | Tower 07 - Habitable Level - Odd |  |  |  | 0.065484
|  | ITQE Ph 2b | Structural | ISS5&6 - Structrural Slab 01 [Basement] |  |  |  | 0.13355
|  | ITQE Ph 2b | Structural | ISS 7 - Foundations & Sub-Grade |  |  |  | 0.17806
|  | ITQE Ph 2b | Structural | ISS 7 - Structrural Slab 01 [Basement] - |  |  |  | 0.13355
|  | ITQE Ph 2b | Structural | Tower 05 - Terrace Level |  |  |  | 0.087312
|  | ITQE Ph 2b | Structural | Tower 06 - Terrace Level |  |  |  | 0.087312
|  | ITQE Ph 2b | Structural | Tower 07 - Terrace Level |  |  |  | 0.087312
|  | ITQE Ph 2b | Structural | ISS5&6 Podium Slab |  |  |  | 0.13355
|  | ITQE Ph 2b | Structural | ISS 7 - Podium Slab |  |  |  | 0.13355
|  | ITQE Ph 2b | Structural | Master Plan ¦ Site Development |  |  |  | 0.0036135
|  | ITQE Ph 2b | Structural | Master Plan ¦ Site MEP |  |  |  | 0.0030113
|  | ITQE Ph 2c | Structural | Schematic Concept |  |  |  | 0.41
|  | ITQE Ph 2c | Structural | PreConstruction Set |  |  |  | 0.82
|  | ITQE Ph 2c | Structural | Experience Home + Project Experience [ I20, I25 ] |  |  |  | 0.41
|  | ITQE Ph 2c | Structural | ISS 9 - Earthwork |  |  |  | 0.02
|  | ITQE Ph 2c | Structural | Tower 09 - Foundations & Sub-Grade |  |  |  | 0.09
|  | ITQE Ph 2c | Structural | ISS 9¦Foundations & Sub-Grade |  |  |  | 0.09
| Foundation School-2 |  |  | 1 |  |  |  | 0
|  | TFS2 | Structural | GFC ¦ Block [ Multipurpose Hall ]
| Indiranagar Residence |  |  | 1 |  |  |  | 0.01
|  | Indranagar Res | Structural | GFC ¦ Block [Gym + Swimming pool & boundary wall] |  |  |  | 0.01
CSR-Auditorium [Malleswaram]
| CSR-Padmashree Diagnostic center |  |  | 1 |  |  |  | 0
|  | CSR - PDC | Structural | GFC ¦ Block
| DBTW |  |  | 38 |  |  |  | 7.2881
|  | DBTW | Structural | Pre Construction Set [Podium] |  |  |  | 2.25
|  | DBTW | Structural | Foundations & Grade Slab |  |  |  | 0.26479
|  | DBTW | Structural | Structrural Slab 01 [Basement] |  |  |  | 0.19859
|  | DBTW | Structural | Podium Slab |  |  |  | 0.19859
|  | DBTW | Structural | Foundations & Grade Slab |  |  |  | 0.26479
|  | DBTW | Structural | Structrural Slab 01 [Basement] |  |  |  | 0.19859
|  | DBTW | Structural | Podium Slab |  |  |  | 0.19859
|  | DBTW | Structural | Tower-1-Habitable Level - Even |  |  |  | 0.025613
|  | DBTW | Structural | Tower-1-Terrace Level |  |  |  | 0.025613
|  | DBTW | Structural | Tower-1-Terrace Level |  |  |  | 0.076838
|  | DBTW | Structural | Tower-2-Habitable Level 01 |  |  |  | 0.10834
|  | DBTW | Structural | Tower-2-Habitable Level - Even |  |  |  | 0.05417
|  | DBTW | Structural | Tower-2-Terrace Level |  |  |  | 0.05417
|  | DBTW | Structural | Tower-2-Habitable Level - Odd |  |  |  | 0.16251
|  | DBTW | Structural | Tower-3-Habitable Level 01 |  |  |  | 0.10834
|  | DBTW | Structural | Tower-3-Habitable Level - Even |  |  |  | 0.05417
|  | DBTW | Structural | Tower-3-Terrace Level |  |  |  | 0.05417
|  | DBTW | Structural | Tower-3-Habitable Level - Odd |  |  |  | 0.16251
|  | DBTW | Structural | Tower-4-Habitable Level 01 |  |  |  | 0.10834
|  | DBTW | Structural | Tower-4-Habitable Level - Even |  |  |  | 0.05417
|  | DBTW | Structural | Tower-4-Terrace Level |  |  |  | 0.05417
|  | DBTW | Structural | Tower-4-Habitable Level - Odd |  |  |  | 0.16251
|  | DBTW | Structural | Tower-5-Habitable Level 01 |  |  |  | 0.10834
|  | DBTW | Structural | Tower-5-Habitable Level - Even |  |  |  | 0.05417
|  | DBTW | Structural | Tower-5-Terrace Level |  |  |  | 0.05417
|  | DBTW | Structural | Tower-5-Habitable Level - Odd |  |  |  | 0.16251
|  | DBTW | Structural | Tower 06-Foundation and Grade Slab |  |  |  | 0.051226
|  | DBTW | Structural | Tower 06-Parking Level-Sub grade |  |  |  | 0.051226
|  | DBTW | Structural | Tower 06-Habitable Level 01 |  |  |  | 0.051226
|  | DBTW | Structural | Tower 06-Habitable Level - Even |  |  |  | 0.025613
|  | DBTW | Structural | Tower 06-Habitable Level - Odd |  |  |  | 0.025613
|  | DBTW | Structural | Tower 06-Terrace Level |  |  |  | 0.076838
|  | DBTW | Structural | Site Development |  |  |  | 0.65004
|  | DBTW | Structural | Site MEP |  |  |  | 0.5417
|  | DBTW | Structural | Clubhouse—Structure and Envelope |  |  |  | 0.37919
|  | DBTW | Structural | Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.05417
|  | DBTW | Structural | Community spaces [Board Walk, Children play area,OAT] |  |  |  | 0.05417
|  | DBTW | Structural | Sporting Facilities |  |  |  | 0.10834
| TUIG |  |  | 6 |  |  |  | 1.08
|  | TUIG | Structural | Site MEP |  |  |  | 0.34
|  | TUIG | Structural | Site Development |  |  |  | 0.4
|  | TUIG | Structural | Clubhouse—Structure and Envelope |  |  |  | 0.22
|  | TUIG | Structural | Clubhouse—Outdoor Spaces and Pool |  |  |  | 0.03
|  | TUIG | Structural | Community spaces [Board Walk, Children play area] |  |  |  | 0.03
|  | TUIG | Structural | Sporting Facilities |  |  |  | 0.06
| Sarjapur [Inspira] |  |  | 6 |  |  |  | 8.9665
|  | Sarjapur Resi | Structural | Schematic Concept |  |  |  | 2.527
|  | Sarjapur Resi | Structural | Preconstruction Set |  |  |  | 3.3983
|  | Sarjapur Resi | Structural | Experience Home + Project Experience |  |  |  | 0.87134
|  | Sarjapur Resi | Structural | Clubhouse—Schematic Concept |  |  |  | 0.087047
|  | Sarjapur Commercial (North) | Structural | Schematic Concept |  |  |  | 0.49045
|  | Sarjapur Commercial (South) | Structural | Schematic Concept |  |  |  | 1.5925
37a Nandi Hills [V]
10a Nandi Hiils [V] Sltnpt
Poinciana
| Ambegaon |  |  | 1 |  |  |  | 0.43354
|  | Ambegaon | Structural | Schematic Concept |  |  |  | 0.43354
Savakanhli
| Harohalli |  |  | 2 |  |  |  | 0.20774
|  | Harohalli | Structural | Schematic Concept |  |  |  | 0.10387
|  | Harohalli | Structural | Experience Home + Project Experience |  |  |  | 0.10387
| 36a Nandi Hills [V] |  |  | 1 |  |  |  | 0.64365
|  | NH36a [V] | Structural | Schematic Concept |  |  |  | 0.64365
| OTR |  |  | 6 |  |  |  | 0.31
|  | OtR Ph1 | Structural | Experience Home + Project Experience |  |  |  | 0.08
|  | OtR Ph1 | Structural | Villa Block ¦ Super Structure |  |  |  | 0.11
|  | OtR Ph1 | Structural | Site Development |  |  |  | 0.03
|  | OtR Ph1 | Structural | Site MEP |  |  |  | 0.03
|  | OtR Ph1 | Structural | Community spaces [Board Walk, Children play area] |  |  |  | 0.02
|  | OtR Ph2 | Structural | Schematic Concept |  |  |  | 0.04
Villa block - Foundation and Sub-grade structure
| DonaPaula |  |  | 1 |  |  |  | 0.26985
|  | DonaPaula | Structural | Schematic Concept |  |  |  | 0.26985
| OTF [Suntikoppa] |  |  | 2 |  |  |  | 2.9578
|  | OTF [Suntikoppa] | Structural | Schematic Concept |  |  |  | 2.0525
|  | OTF [Suntikoppa] | Structural | Pre Construction Set |  |  |  | 0.90532
KIADB - Machinecraft
| Meena & Krishnasai Residence |  |  | 2 |  |  |  | 0.0576
|  | MeenaSai Res | Structural | Schematic Concept |  |  |  | 0.024
|  | MeenaSai Res | Structural | Pre-construction set |  |  |  | 0.0336
| Shreegaon |  |  | 2 |  |  |  | 0.39928
|  | Shreegaon | Structural | Schematic Concept |  |  |  | 0.2
|  | Shreegaon | Structural | Project Experience |  |  |  | 0.19928
| Violet hill |  |  | 3 |  |  |  | 0.13427
|  | Talashet | Structural | Schematic Concept |  |  |  | 0.056932
|  | Talashet | Structural | Infra - Grading |  |  |  | 0.02578
|  | Talashet | Structural | Infra - MEP |  |  |  | 0.05156
| Vijayapura |  |  | 0 |  |  |  | 0
|  | Vijayapura | Structural
|  | Vijayapura | Structural
|  | Vijayapura | Structural
| OTR - Museum |  |  | 1 |  |  |  | 0
|  | OTR - Museum | Structural | Schematic Concept
| Ooty Residence |  |  | 1 |  |  |  | 0
|  | Ooty Residence | Structural | Schematic Concept
| MT Plano |  |  | 2 |  |  |  | 0
|  | MT Plano | Structural | Schematic Concept
|  | MT Plano | Structural | Preconstruction
| LGCE Campus |  |  | 2 |  |  |  | 0
|  | LGCE Campus | Structural | Schematic Concept
|  | LGCE Campus | Structural | Pre-construction set
| NH - Homestay |  |  | 3 |  |  |  | 0.28226
|  | NH - Homestay | Structural | Schematic Concept
|  | NH - Homestay | Structural | Pre-construction set
|  | NH - Homestay | Structural | GFC - Block
| Imagine campus |  |  | 1 |  |  |  | 0
|  | Imagine campus | Structural | Schematic concept
|  | Imagine campus | Structural
Vaderahalli
| FKH |  |  | 1 |  |  |  | 0
|  | FKH | Structural | Full Kit Homes - M30,40
| Interior Design |  |  | Q1 |  |  |  | Q4
|  |  |  | 13 |  |  |  | 1.038
| Navneet | Design [ID GFC + Product launch] | Interior design | 3 |  |  |  | 0.94
| ID GFC Release |  |  | 0 |  |  |  | 0
| ATR |  | Interior design
| LTF |  | Interior design
| ITQE |  | Interior design
| PoaRR |  | Interior design
| TMD |  | Interior design
| TMFT |  | Interior design
| SFTW |  | Interior design
| WoYM |  | Interior design
| Personalised / Assisted Customization |  |  | 0 |  |  |  | 0
| ATR |  | Interior design
| LTF |  | Interior design
| ITQE |  | Interior design
| PoaRR |  | Interior design
| TMD |  | Interior design
| TMFT |  | Interior design
| SFTW |  | Interior design
| WoYM |  | Interior design
| Product Launch |  |  | 3 |  |  |  | 0.48
| ITQE | L25 | Interior design | L25 |  |  |  | 0.16
| OTR | V25 | Interior design | V25 |  |  |  | 0.16
| PoaRR | R25 | Interior design | R25 |  |  |  | 0.16
| Shweta Varma | Personalised customisations + Experience Homes | Interior design | 10 |  |  |  | 0.09801
| Experience Homes |  |  | 10 |  |  |  | 0.09801
| DbtW |  |  | DbtW I20 |  |  |  | 0.00747
| DbtW |  |  | DbtW I25 |  |  |  | 0.00972
| OTR |  |  | OTR V25 |  |  |  | 0.009
| ItqE |  |  | ItqE V35 |  |  |  | 0.01026
| ItQE Ph 2c |  |  | ItQE Ph 2c - I20 |  |  |  | 0.01026
| ItQE Ph 2c |  |  | ItQE Ph 2c - I20 |  |  |  | 0.01026
| Sarj |  |  | Sarj I20 |  |  |  | 0.01026
| Sarj |  |  | Sarj I25 |  |  |  | 0.01026
| Sarj |  |  | Sarj L21 |  |  |  | 0.01026
| Sarj |  |  | Sarj D35 |  |  |  | 0.01026
Note on H20: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: POARR51 POARR56 POARR58 POARR60 POARR62 POARR66

## Data sheet (hidden)
Project | Phase | Leader | Discipline | Package | Billing value | Plan | Actual | Status
ATR | 1 | Saji | Architecture | Site MEP | 1 | 2025-03-01 | 2025-06-01 | Actual
NH Homestay | 1 | Cijey | Architecture | GFC | 1 | 2025-06-01 | 2025-06-01 | Plan
NH Homestay | 1 | Cijey | Architecture | Archives | 2 | 2025-09-01 | 2025-12-01 | Plan

## Sheet1 (hidden)
Suresh goals
| Approved [Plan Sanction + RERA] | Designer assigned |  |  | Types | Imagine Campus | 5.6 | 0.2 | SD
1 | Vaderahalli[63.5A] | Cijey | Apt +V+C |  |  | The Magic Faraway Tree | 11 | 1.22 | JD | 841 | Apt
| Dona Paula, Goa [12A] | Naveen Y | Apt+C |  |  | The Meadow Dance | 20 | 0.49 | JD | 326 | V
| After the Rain Phase 3 [7.83A] | Saji | V |  |  | Songs from the Wood | 5.14 | 0.81 | JD | 618 | Apt
| Ambegaon Phase 1 [60A] | Gagan | P |  |  | Pursuit of a Radical Rhapsody | 37 | 4.88 | SD | 5083 | Apt +V
| Sarjapura [Iinspira] [18.92A] | Cijey | Apt +V+C | Srjp-C [NY] |  | A Saucerful of Secrets | 20 | 0.25 | SD | 300
| Harohalli - Phase 1 Plotted [40 A] | Gagan | P |  |  | In That Quiet Earth | 75.5 | 7.29 | SD | 7939 | Apt +V
1 | Harohalli - Phase 2 Villas [42 A] | Saji |  |  |  | Learning to Fly | 3.77 | 0.73 | SD | 870 | Apt
| Vijayapura - Phase 1 [40 A] | Gagan | P |  |  | After the Rain | 49.4 | 1.12 | SD | 1372 | V
| Alibagh [70 A] | Gagan | P |  |  | Campus @ KIADB Mysore | 176 | 1.5 | SD | -
| Talshet [30A] | Gagan | P |  |  | Over the Rainbow | 24 | 0.3 | DM | 232 | V
1 | Acharlahalli, Nandi Hills Phase 1 [Hoysala -12A] | Cijey | V |  |  | Down by the Water | 18 | 1.94 | JD | 2181 | Apt
1 | In That Quiet Earth Phase 3 [38.3A] | Cijey | Apt +V |  |  | Sunticoppa | 72.7 | 0.54 | JD | 819 | V
| Suntikoppa - Phase 1 [33A] | Naveen Y | V |  |  | Sarjpr Rd Iinspira | 24 | 3.62 | DM | 1088 | Apt +V+C
| Suntikoppa - Phase 2 [39 A] | Naveen Y | V |  |  | Acharahalli, Nandi Hills | 37 | 0.89 | JD | 961 | V
| Poinciana Phase1 [20.575A] | Gagan | P |  |  | Harohalli | 40 | 4.21 | SD | 6819 | Apt
| Poinciana Phase 2 [42A] | Gagan | P |  |  | Vaderahalli | 63.5 | 4.67 | JD | 6923 | Apt +V+C
1 | Mysore - KIADB Phase 1[130.55A] | Naveen Y |  |  |  | Sultanpet | 10 | 0.23 | DM | 27 | Apt
1 | Over the Rainbow Phase 2 [16.575 A] | Cijey | V |  |  | Dona Paula | 11.64 | 2.14 | JD | 2038 | Apt+C
1 | Sultanpet, Nandi Hills [10A] | Cijey | Apt |  |  | Madakuhosanahalli, Nandi Hills | 35 | 0.42 | JD | 819 | V
[6 empty] | Kashmir Projects | 36.8 | 0.69 | JD | 1313 | Apt+V
[6 empty] | Chikkajala | 40 | 4.7 | JD | 5544 | Apt+V
[6 empty] | Thubarahalli [Varthur Lake] | 45 | 6.13 | JD | 9170 | Apt+V
[6 empty] | ECR Chennai | 400 | 8.98 | JD | 4332 | Apt+C
[6 empty] | Pallavaram | 80 | 12.15 | DM | 3007 | Apt+V+C
[6 empty] | Ooty | 46 | 0.32 | JD | 587 | V
[6 empty] | Yadgarpalle | 60 | 1.57 | JD | 2007 | V
[6 empty] | Financial disrtict, Gachibowli | 15 | 4.5 | SD | 6084
[6 empty] | Dabolim | 12.5 | 0.26 | JD | 479 | V
[6 empty] | Panvel, Mumbai | 192 | 7.96 | JD | 9140 | Apt +V+C
[6 empty] | Worli, Mumbai | 1.42 | 0.33 | DM | 539 | Apt
[6 empty] | Naya Raipur | 20 | 0.74 | DM | 144 | V
[6 empty] | Aronda | 200 | 2.74 | DM | 659 | V
[6 empty] | Poinciana | 93 | 2.22 | SD | 665 | P
[6 empty] | Tangled up in Green | 120 | 2.64 | DM | 209 | P
[6 empty] | Coimbatore | 60 | 6.53 | DM | 1529
[6 empty] | Alibaug | 70 | 1.68 | JD | 688 | P
[6 empty] | Talshet | 30 | 0.72 | JD | 295 | P
[6 empty] | Ambegaon | 150 | 3.59 | JD | 1405 | P
[6 empty] | Savakanahalli | 120 | 2.87 | JD | 1869 | P
[6 empty] | Vijayapura | 100 | 2.4 | JD | 1497 | P
[6 empty] | Sarjapur [Koothaganahalli] | 300 | 7.19 | SD | 5750 | P
[6 empty] | Yadgarpalle | 185 | 4.43 | JD | 1551 | P
[6 empty] | Harohalli | 40 | 0.96 | SD | 575 | P
[6 empty] | Naya Raipur [Plots] | 40 | 0.96 | DM | 77 | P
[6 empty] | Aronda | 200 | 4.79 | DM | 383 | P

## Breakup-MP+MEP+LS (hidden)
|  |  | Pkgs | Design Packages |  |  |  | Fees | Design Fees
|  |  | 539 | 146 | 158 | 123 | 112 | 136.9464 | 26.6392 | 45.0683 | 31.8842 | 33.3547
| Marathon 2025 |  | 2025 | Q1 | Q2 | Q3 | Q4 | 2025 | Q1 | Q2 | Q3 | Q4
| Gagan | Design [MP+MEP+LS] | 539 | 146 | 158 | 123 | 112 | 136.9464 | 26.6392 | 45.0683 | 31.8842 | 33.3547
| Masterplanning | MP | 81 | 20 | 23 | 21 | 17 | 86.5836 | 17.0199 | 26.5261 | 21.4816 | 21.556
1 | TUIG |  | 2 | 2 | 0 | 0 | 0 | 1.21 | 1.21 | 0 | 0 | 0
|  |  | MP | Site MEP |  |  |  | MP | 0.3
|  |  |  | Site Development |  |  |  | MP | 0.91
1 | Sarjapur |  | 2 | 0 | 1 | 1 | 0 | 1.6 | 0 | 0.79999 | 0.79999 | 0
|  |  | MP |  | Schematic Concept | Pre-construction set |  | MP |  | 0.79999 | 0.79999
1 | 36a Nandi Hills[V] |  | 6 | 1 | 2 | 2 | 1 | 6.0675 | 1.365 | 2.0175 | 2.0175 | 0.6675
|  |  | MP | Contract + Design Brief | Schematic Concept | Pre-construction set | Experience Home + Project Experience | MP | 1.365 | 1.335 | 1.335 | 0.6675
|  |  | MP |  | Approvals | Marketing and Sales |  | MP |  | 0.6825 | 0.6825
1 | Poinciana |  | 8 | 4 | 2 | 1 | 1 | 4.5576 | 1.6699 | 1.6687 | 0.9142 | 0.30473
|  |  | MP | Schematic Concept | Pre-construction set | Site Development | Site MEP | MP | 0.45101 | 0.44976 | 0.9142 | 0.30473
|  |  | MP | Approvals | Master Plan |  |  | MP | 0.60947 | 1.2189
|  |  | MP | Project Experience+ Entrance portal |  |  |  | MP | 0.30473
|  |  | MP | Marketing and Sales |  |  |  | MP | 0.30473
1 | Ambegn |  | 6 | 1 | 2 | 2 | 1 | 6.4563 | 1.0225 | 2.045 | 1.5338 | 1.855
|  |  | MP | Contract + Design Brief | Schematic Concept | Experience Home + Project Experience | Pre-construction set | MP | 1.0225 | 1.0225 | 0.51125 | 1.855
|  |  | MP |  | Approvals | Marketing and Sales |  | MP |  | 1.0225 | 1.0225
|  |  | MP |  |  |  |  | MP
1 | Savakanhli |  | 6 | 1 | 2 | 2 | 1 | 6.3088 | 0.7775 | 2.96 | 2.1825 | 0.38875
|  |  | MP | Contract + Design Brief | Schematic Concept | Pre-construction set | Experience Home + Project Experience | MP | 0.7775 | 1.405 | 1.405 | 0.38875
|  |  | MP |  | Approvals | Marketing and Sales |  | MP |  | 1.555 | 0.7775
1 | Harohalli |  | 6 | 1 | 2 | 2 | 1 | 2.2048 | 0.24497 | 0.9799 | 0.73493 | 0.24497
|  |  | MP | Contract + Design Brief | Schematic Concept | Pre-construction set | Experience Home + Project Experience | MP | 0.24497 | 0.48995 | 0.48995 | 0.24497
[5 empty] | Approvals | Marketing and Sales |  |  |  | 0.48995 | 0.24497
1 | 37a Nandi Hills [V] |  | 2 | 0 | 0 | 1 | 1 | 0.8 | 0 | 0 | 0.4 | 0.4
|  |  | MP |  |  | Schematic Concept | Pre Construction Set | MP |  |  | 0.4 | 0.4
MP
1 | Alibaug |  | 6 | 2 | 2 | 1 | 1 | 3.815 | 1.32 | 1.41 | 0.85 | 0.235
|  |  | MP | Contract + Design Brief | Marketing and Sales | Pre Construction Set | Project Experience | MP | 0.47 | 0.47 | 0.85 | 0.235
|  |  | MP | Schematic Concept | Approvals |  |  | MP | 0.85 | 0.94
1 | Talashet |  | 6 | 2 | 2 | 1 | 1 | 1.63 | 0.565 | 0.6 | 0.365 | 0.1
|  |  | MP | Contract + Design Brief | Marketing and Sales | Pre Construction Set | Project Experience | MP | 0.2 | 0.2 | 0.365 | 0.1
|  |  | MP | Schematic Concept | Approvals |  |  | MP | 0.365 | 0.4
1 | Sarjpr [P] |  | 5 | 0 | 1 | 2 | 2 | 15.84 | 0 | 3.52 | 5.28 | 7.04
|  |  | MP |  | Contract + Design Brief | Schematic Concept | Pre Construction Set |  |  | 3.52 | 3.52 | 3.52
[6 empty] | Approvals | Marketing and Sales |  |  |  | 1.76 | 1.76
|  |  | MP |  |  |  | Project Experience |  |  |  |  | 1.76
1 | Vijayapura |  | 7 | 2 | 2 | 2 | 1 | 6.4013 | 1.42 | 1.57 | 1.1613 | 2.25
|  |  | MP | Contract + Design Brief | Marketing and Sales | Pre Construction Set | Master Plan | MP | 0.52 | 0.52 | 0.9 | 2.25
|  |  | MP | Schematic Concept | Approvals | Project Experience |  | MP | 0.9 | 1.05 | 0.26125
1 | Lal Bazar |  | 4 | 1 | 1 | 1 | 1 | 3.78 | 1.08 | 1.08 | 0.54 | 1.08
|  |  | MP | Contract + Design Brief | Schematic Concept | Approvals | Pre Construction Set | MP | 1.08 | 1.08 | 0.54 | 1.08
1 | Dani Hama |  | 4 | 1 | 1 | 1 | 1 | 6.9825 | 1.995 | 1.995 | 0.9975 | 1.995
|  |  | MP | Contract + Design Brief | Schematic Concept | Approvals | Pre Construction Set | MP | 1.995 | 1.995 | 0.9975 | 1.995
1 | Bellandur |  | 6 | 1 | 2 | 1 | 2 | 13.77 | 3.06 | 4.59 | 3.06 | 3.06
|  |  | MP | Contract + Design Brief | Schematic Concept | Pre Construction Set | Marketing and Sales | MP | 3.06 | 3.06 | 3.06 | 1.53
|  |  | MP |  | Approvals |  | Experience Home + Project Experience |  |  | 1.53 |  | 1.53
1 | Vaderahalli |  | 5 | 1 | 1 | 1 | 2 | 5.16 | 1.29 | 1.29 | 0.645 | 1.935
|  |  | MP | Contract+Design Brief | Schematic Concept | Project Experience | Pre Construction Set | MP | 1.29 | 1.29 | 0.645 | 1.29
[7 empty] | Marketing and Sales |  |  |  |  | 0.645
| MEP Services | MEP | 287 | 87 | 79 | 62 | 59 | 32.0183 | 7.1261 | 10.9351 | 6.8101 | 7.147
1 | AtR Ph 1, 2a, 2b, 2c |  | 4 | 3 | 1 | 0 | 0 | 0.07807 | 0.072082 | 0.0059878 | 0 | 0
| Gagan | AtR Ph 1, 2a, 2b | MEP | MEP ¦ Master Archives |  |  |  | MEP | 0.055696
| Gagan | AtR Ph 2c | MEP | MEP ¦ Clubhouse + Amenities - Sporting Facilities | MEP ¦ Master Archives |  |  | MEP | 0.0020496 | 0.0059878
| Gagan | AtR Ph 2c | MEP | MEP ¦ Master Plan - Site MEP |  |  |  | MEP | 0.014337
1 | AtR Com |  | 9 | 8 | 1 | 0 | 0 | 0.55873 | 0.48264 | 0.076094 | 0 | 0
| Gagan | AtR Com | MEP | Preconstruction set [Loading signoff] | MEP ¦ Master Archives |  |  | MEP | 0.076094 | 0.076094
| Gagan | AtR Com | MEP | MEP ¦ Tower-[Commercial] - Building Envelope and Common Areas [Basement] |  |  |  | MEP | 0.050323
| Gagan | AtR Com | MEP | MEP ¦ Tower-[Commercial] - Habitable Level 1-2 |  |  |  | MEP | 0.050323
| Gagan | AtR Com | MEP | MEP ¦ Tower-[Commercial] - Habitable Level 3-5 |  |  |  | MEP | 0.050323
| Gagan | AtR Com | MEP | MEP ¦ Tower-[Commercial] - Habitable Level 6-10 |  |  |  | MEP | 0.050323
| Gagan | AtR Com | MEP | MEP ¦ Tower-[Commercial] - Terrace Level |  |  |  | MEP | 0.037743
| Gagan | AtR Com | MEP | MEP ¦ Master Plan - Master Plan |  |  |  | MEP | 0.038655
|  | AtR Com | MEP | MEP ¦ Master Plan - Site MEP |  |  |  | MEP | 0.12885
1 | TMFT -2 |  | 1 | 1 | 0 | 0 | 0 | 0.059954 | 0.059954 | 0 | 0 | 0
| Gagan | TMFT -2 | MEP | MEP ¦ Master Archives |  |  |  | MEP | 0.059954
| SFTW |  | 6 | 3 | 3 | 0 | 0 | 0.14475 | 0.0365 | 0.10824 | 0 | 0
| Gagan | SFTW | MEP | MEP ¦ ISS 01 - Foundations & Grade Slab | MEP ¦ Clubhouse—Interiors and Facilities |  |  | MEP | 0.0020341 | 0.001666
| Gagan | SFTW | MEP | MEP ¦ Master Plan - Site MEP | MEP ¦ Clubhouse—Sporting Facilities |  |  | MEP | 0.0023731 | 0.00055534
| Gagan | SFTW | MEP |  | MEP ¦ Master Archives |  |  | MEP | 0.0062528 | 0.10602
| Gagan | SFTW | MEP | MEP ¦ Clubhouse—Outdoor Spaces and Pool |  |  |  | MEP | 0.020843
| Gagan | SFTW | [5 empty] | MEP | 0.0038873
[8 empty] | MEP | 0.0011107
| PoaRR |  | 31 | 23 | 7 | 1 | 0 | 2.3154 | 1.874 | 0.3614 | 0.08 | 0
| Gagan | PoaRR Res | MEP | ISS [Tower 1-7] - Podium Slab |  |  |  | MEP | 0.06
| Gagan | PoaRR Res | MEP | Individual Homes - R11 Default and it's variants |  |  |  | MEP | 0.16
| Gagan | PoaRR Res | MEP | Individual Homes - R22 Default and it's variants |  |  |  | MEP | 0.16
| Gagan | PoaRR Res | MEP | Residential - Master Plan |  |  |  | MEP | 0.11
| Gagan | PoaRR Res | MEP | MEP ¦ Master Archives - Res |  |  |  | MEP | 0.24
| Gagan | PoaRR Res | MEP |  |  |  |  | MEP
| Gagan | PoaRR Res | MEP | Villa Cluster 3 - All Levels |  |  |  | MEP | 0.004
| Gagan | PoaRR Res | MEP | Villa Cluster 3 - Building Envelope and Common Areas |  |  |  | MEP | 0.003
| Gagan | PoaRR Res | MEP | V40 Default and it's variants |  |  |  | MEP | 0.16
| Gagan | PoaRR Res | MEP |  |  |  |  | MEP
| Gagan | PoaRR Res | MEP |  |  |  |  | MEP
|  | PoaRR Res | MEP |  |  |  |  | MEP
|  | PoaRR Res | MEP | Residential - Site MEP |  |  |  | MEP | 0.36
|  | PoaRR Res | MEP | Clubhouse—Outdoor Spaces and Pool |  |  |  | MEP | 0.002
|  | PoaRR Res | MEP | Sporting Facilities |  |  |  | MEP | 0.001
| Gagan | PoaRR T08 | MEP | T08 - Foundation and Grade Slab | T08 - R25 P Default and it's variants | MEP ¦ Master Archives - T08 |  | MEP | 0.09 | 0.06 | 0.08
| Gagan | PoaRR T08 | MEP | T08 - Habitable Level 01 | T08 - L20 P Default and it's variants |  |  | MEP | 0.11 | 0.06
| Gagan | PoaRR T08 | MEP | T08 - Penthouse Levels | T08 - D35 P Default and it's variants |  |  | MEP | 0.09 | 0.06
| Gagan | PoaRR T08 | MEP | T08 - Terrace Level | T08 - L22 P Default and it's variants |  |  | MEP | 0.09 | 0.06
| Gagan | PoaRR T08 | MEP | T08 - ISS - Foundations & Grade Slab | T08 - Sporting Facilities |  |  | MEP | 0.01 | 0.0004
| Gagan | PoaRR T08 | MEP | T08 - ISS - Podium Slab | T08 - Clubhouse—Outdoor Spaces and Pool |  |  | MEP | 0.01 | 0.001
| Gagan | PoaRR T08 | MEP | T08 - ISS - Parking Level Subgrade | T08 - Site MEP |  |  | MEP | 0.03 | 0.12
| Gagan | PoaRR T08 | MEP | T08 - ISS - Building Envelope and Common Areas |  |  |  | MEP | 0.02
| Gagan | PoaRR T08 | MEP | T08 - L20 Default and it's variants |  |  |  | MEP | 0.06
| Gagan | PoaRR T08 | MEP | T08 - D35 Default and it's variants |  |  |  | MEP | 0.06
| Gagan | PoaRR T08 | MEP | T08 - Clubhouse—Interiors and Facilities |  |  |  | MEP | 0.004
| Gagan | PoaRR T08 | MEP | T08 - Master Plan |  |  |  | MEP | 0.04
| TMD |  | 2 | 2 | 0 | 0 | 0 | 0.021893 | 0.021893 | 0 | 0 | 0
| Gagan | TMD - II | MEP | Master Archives |  |  |  | MEP | 0.010947
| Gagan | TMD - I | MEP | Master Archives |  |  |  | MEP | 0.010947
| ITQE |  | 61 | 11 | 19 | 15 | 16 | 3.172 | 0.98732 | 0.2421 | 0.25945 | 1.6831
|  | ITQE Ph 1 | MEP |  | Master Archives |  |  | MEP | 0.0014559 | 0.083476
|  | ITQE Ph 2a | MEP | Experience Home + Project Experience [ V35 ] | Master Archives |  |  | MEP | 0.016149 | 0.016149
|  | ITQE Ph 2a | MEP |  |  |  |  | MEP
|  | ITQE Ph 2b | MEP | ISS -5 & 6 ¦ Structrural Slab 01 [Basement] | ISS -5 & 6 ¦ Building Envelope and Common Areas | Masterplan ¦ Site MEP |  | MEP | 0.011871 | 0.011871 | 0.018201
|  | ITQE Ph 2b | MEP | ISS -7 ¦ Structrural Slab 01 [Basement] | ISS -7 ¦ Building Envelope and Common Areas | Master Archives |  | MEP | 0.015828 | 0.011871 | 0.06273
|  | ITQE Ph 2b | MEP | Tower—05 ¦ Terrace Level | ISS -5 & 6 ¦ Podium Slab |  |  | MEP | 0.011871 | 0.011871
|  | ITQE Ph 2b | MEP | Tower—06 ¦ Terrace Level | ISS -7 ¦ Podium Slab |  |  | MEP | 0.015828 | 0.011871
|  | ITQE Ph 2b | MEP | Tower—07 ¦ Terrace Level | Amenities & Facilities ¦ Sporting Facilities |  |  | MEP | 0.037611 | 0.0014559
|  | ITQE Ph 2b | MEP | Masterplan ¦ Master Plan |  |  |  | MEP | 0.037611
|  | ITQE Ph 2b | MEP |  |  |  |  | MEP | 0.037611
|  | ITQE Ph 2b | MEP |  |  |  |  | MEP | 0.0054604
|  | ITQE Ph 2b | MEP |  |  |  |  | MEP
|  | ITQE Ph 2b | MEP |  |  |  |  | MEP
|  | ITQE Ph 2b | MEP |  |  |  |  | MEP
|  | ITQE Ph 2b | MEP |  |  |  |  | MEP
|  | ITQE Ph 2b | MEP |  |  |  |  | MEP
|  | ITQE Ph 2b | MEP |  |  |  |  | MEP
|  | ITQE Ph 2c / 3 | MEP | Schematic Concept | Pre Construction Set | ISS 9¦Podium Slab | Tower 9¦Building Envelope and Common Areas [Typical Tower Levels] | MEP | 0.06273 | 0.018806 | 0.0059355 | 0.018806
|  | ITQE Ph 2c / 3 | MEP | Approvals | ISS -10 ¦ Foundations & Sub-Grade | ISS 10¦Podium Slab | Tower 10¦Building Envelope and Common Areas [Typical Tower Levels] | MEP | 0.12546 | 0.018806 | 0.0059355 | 0.018806
|  | ITQE Ph 2c / 3 | MEP | Tower—09 ¦ Foundations & Sub-Grade | ISS 11¦Foundations & Sub-Grade | ISS 11¦Podium Slab | Tower 11¦Building Envelope and Common Areas [Typical Tower Levels] | MEP | 0.43983 | 0.018806 | 0.0059355 | 0.018806
|  | ITQE Ph 2c / 3 | MEP | ISS -9 ¦ Foundations & Sub-Grade | ISS 12¦Foundations & Sub-Grade | ISS 12¦Podium Slab | Tower 12¦Building Envelope and Common Areas [Typical Tower Levels] | MEP | 0.12546 | 0.007914 | 0.0059355 | 0.018806
|  | ITQE Ph 2c / 3 | MEP |  | Tower 10¦Foundations & Sub-Grade | ISS 9¦Building Envelope and Common Areas | I20 Default and it's variants | MEP | 0.018806 | 0.007914 | 0.0059355 | 0.43983
|  | ITQE Ph 2c / 3 | MEP |  | Tower 11¦Foundations & Sub-Grade | ISS 10¦Building Envelope and Common Areas | I25 Default and it's variants | MEP | 0.0059355 | 0.007914 | 0.0059355 | 0.43983
|  | ITQE Ph 2c / 3 | MEP |  | Tower 12¦Foundations & Sub-Grade | ISS 11¦Building Envelope and Common Areas | D35 Default and it's variants | MEP | 0.0059355 | 0.007914 | 0.0059355 | 0.43983
|  | ITQE Ph 2c / 3 | MEP |  | ISS 9¦Structrural Slab 01 [Basement] | ISS 12¦Building Envelope and Common Areas | Tower 9¦Terrace Level | MEP | 0.0059355 | 0.0054604 | 0.0059355 | 0.028208
|  | ITQE Ph 2c / 3 | MEP |  | ISS 10¦Structrural Slab 01 [Basement] | Tower 9¦Habitable Level 01 | Tower 10¦Terrace Level | MEP | 0.0059355 |  | 0.028208 | 0.028208
|  | ITQE Ph 2c / 3 | MEP |  | ISS 11¦Structrural Slab 01 [Basement] | Tower 10¦Habitable Level 01 | Tower 11¦Terrace Level | MEP |  |  | 0.028208 | 0.028208
|  | ITQE Ph 2c / 3 | MEP |  | ISS 12¦Structrural Slab 01 [Basement] | Tower 11¦Habitable Level 01 | Tower 12¦Terrace Level | MEP |  |  | 0.028208 | 0.028208
|  | ITQE Ph 2c / 3 | MEP |  | Masterplan ¦ Masterplan | Tower 12¦Habitable Level 01 | Master Archives | MEP |  |  | 0.028208 | 0.06273
|  | ITQE Ph 2c / 3 | MEP |  |  | Masterplan ¦ Site MEP | Tower 9¦Penthouse Levels | MEP |  |  | 0.018201 | 0.028208
|  | ITQE Ph 2c / 3 | MEP |  |  |  | Tower 10¦Penthouse Levels | MEP |  |  |  | 0.028208
|  | ITQE Ph 2c / 3 | MEP |  |  |  | Tower11¦Penthouse Levels | MEP |  |  |  | 0.028208
|  | ITQE Ph 2c / 3 | MEP |  |  |  | Tower 12¦Penthouse Levels | MEP |  |  |  | 0.028208
|  | ITQE Ph 2c / 3 | MEP |  |  |  |  | MEP
|  | ITQE Ph 2c / 3 | MEP |  |  |  |  | MEP
|  | ITQE Ph 2c / 3 | MEP |  |  |  |  | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
|  | ITQE Ph 2c / 3 | MEP
| Foundation school -2 |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | MEP | GFC ¦ BLOCK [ Multipurpose Hall]
| Indiranagar Residence |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | MEP | GFC ¦ Block [Gym + Swimming pool]
| Karnataka Public School, Basavanagudi |  | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | MEP | GFC¦ Block
| Auditorium [Malleswaram] |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | MEP | GFC ¦ Block
| Padmashree Diagnostic center |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | MEP | GFC ¦ Block [Electrical layout [ All levels]]
| AtR-3 |  | 19 | 1 | 1 | 5 | 12 | 0.2945 | 0.018202 | 0.018202 | 0.25337 | 0.0047277
|  | AtR-III | MEP | MEP ¦ Schematic Concept | MEP ¦ Pre Construction Set | MEP ¦ Home Products - V30 Default and it's variants | MEP ¦ Villa Block 29 - Foundations and Sub-Grade Structure |  | 0.018202 | 0.018202 | 0.056304 | 0.00051342
|  | AtR-III | MEP |  |  | MEP ¦ Home Products - V50 Default and it's variants | MEP ¦ Villa Block 29 - Super Structure |  |  |  | 0.065688 | 0.00034228
|  | AtR-III | MEP |  |  | MEP ¦ Home Products - V80 Default and it's variants | MEP ¦ Villa Block 29 - Building Envelope + Plot Development |  |  |  | 0.065688 | 0.00025671
|  | AtR-III | MEP |  |  | MEP ¦ Home Products - V45 Default and it's variants | MEP ¦ Villa Block 30 - Foundations and Sub-Grade Structure |  |  |  | 0.065688 | 0.00051342
|  | AtR-III | MEP |  |  | MEP ¦ Master Plan - Master Plan | MEP ¦ Villa Block 30 - Super Structure |  |  |  | 1.2684e-09 | 0.00034228
|  | AtR-III | MEP |  |  |  | MEP ¦ Villa Block 30 - Building Envelope + Plot Development |  |  |  |  | 0.00025671
|  | AtR-III | MEP |  |  |  | MEP ¦ Villa Block 31 - Foundations and Sub-Grade Structure |  |  |  |  | 0.00025671
|  | AtR-III | MEP |  |  |  | MEP ¦ Villa Block 31 - Super Structure |  |  |  |  | 0.00017114
|  | AtR-III | MEP |  |  |  | MEP ¦ Villa Block 31 - Building Envelope + Plot Development |  |  |  |  | 0.00012835
|  | AtR-III | MEP |  |  |  | MEP ¦ Villa Block 32 - Foundations and Sub-Grade Structure |  |  |  |  | 0.00089848
|  | AtR-III | MEP |  |  |  | MEP ¦ Villa Block 32 - Super Structure |  |  |  |  | 0.00059899
|  | AtR-III | MEP |  |  |  | MEP ¦ Villa Block 32 - Building Envelope + Plot Development |  |  |  |  | 0.00044924
| DBTW |  | 42 | 9 | 13 | 13 | 7 | 2.0127 | 0.38239 | 1.0912 | 0.35493 | 0.18413
|  |  | MEP | Pre Construction Set | Tower 05 - Foundation and Grade Slab | Tower 1 - Building Envelope and Common Areas [Typical Tower Levels] | Master Plan - Site MEP | MEP | 0.26835 | 0.016415 | 0.0077615 | 0.12284
|  |  | MEP | Tower 01 - Foundation and Grade Slab | Tower 01 - Habitable Level 01 | Tower 1 - Terrace Level | Clubhouse—Interiors and Facilities | MEP | 0.0077615 | 0.011642 | 0.023284 | 0.0081296
|  |  | MEP | Tower 02 - Foundation and Grade Slab | Tower 02 - Habitable Level 01 | Tower 2 - Building Envelope and Common Areas [Typical Tower Levels] | Sporting Facilities | MEP | 0.016415 | 0.024623 | 0.016415 | 0.0027099
|  |  | MEP | Tower 03 - Foundation and Grade Slab | Tower 03 - Habitable Level 01 | Tower 2 - Terrace Level | Tower 06 - Foundation and Grade Slab | MEP | 0.016415 | 0.024623 | 0.049245 | 0.0077615
|  |  | MEP | Tower 04 - Foundation and Grade Slab | Tower 04 - Habitable Level 01 | Tower 3 -Building Envelope and Common Areas [Typical Tower Levels] | Tower 06 - Habitable Level 01 | MEP | 0.016415 | 0.024623 | 0.016415 | 0.011642
|  |  | MEP | ISS 01 - Foundations & Grade Slab | Tower 05 - Habitable Level 01 | Tower 3 - Terrace Level | Tower 06 -Building Envelope and Common Areas [Typical Tower Levels] | MEP | 0.012221 | 0.024623 | 0.049245 | 0.0077615
|  |  | MEP | ISS 02 - Foundations & Grade Slab | ISS 01 - Podium Slab | Tower 4 -Building Envelope and Common Areas [Typical Tower Levels] | Tower 06- Terrace Level | MEP | 0.012221 | 0.012221 | 0.016415 | 0.023284
|  |  | MEP | ISS 01 - Parking Level Grade-Slab | ISS 02 - Podium Slab | Tower 4 - Terrace Level |  | MEP | 0.016295 | 0.012221 | 0.049245
|  |  | MEP | ISS 02 - Parking Level Grade-Slab | ISS 01 - Building Envelope and Common Areas | Tower 5 -Building Envelope and Common Areas [Typical Tower Levels] |  | MEP | 0.016295 | 0.012221 | 0.016415
|  |  | MEP |  | ISS 02 - Building Envelope and Common Areas | Tower 5 - Terrace Level |  | MEP |  | 0.012221 | 0.049245
|  |  | MEP |  | Home Products - I20 Default and it's variants | Master Plan- Master Plan |  | MEP |  | 0.30995 | 0.036853
|  |  | MEP |  | Home Products - I25 Default and it's variants | Clubhouse—Structure and Envelope |  | MEP |  | 0.30995 | 0.018969
|  |  | MEP |  | Home Products - L21 Default and it's variants | Clubhouse—Outdoor Spaces and Pool |  | MEP |  | 0.29586 | 0.0054198
| TUIG |  | 5 | 3 | 2 | 0 | 0 | 0.93 | 0.84 | 0.09 | 0 | 0
|  |  | MEP | Pre Construction Set - CH | Clubhouse—Interiors and Facilities |  |  | MEP | 0.14 | 0.07
|  |  |  | Clubhouse—Structure and Envelope | Sporting Facilities |  |  | MEP | 0.48 | 0.02
|  |  |  | Clubhouse—Outdoor Spaces and Pool |  |  |  | MEP | 0.17
[8 empty] | MEP | 0.05
| Sarj |  | 4 | 0 | 2 | 2 | 0 | 4.2498 | 0 | 2.1249 | 2.1249 | 0
|  |  | MEP |  | Schematic Concept | Pre-construction set |  | MEP |  | 0.7083 | 1.4166
[5 empty] | Approvals | Experience Home + Project Experience |  |  |  | 1.4166 | 0.7083
| 36a Nandi Hills[V] |  | 4 | 0 | 2 | 1 | 1 | 0.48321 | 0 | 0.32214 | 0.16107 | 0
|  |  | MEP |  | Schematic Concept | Pre-construction set | Experience Home + Project Experience | MEP |  | 0.16107 | 0.16107
|  |  | MEP |  | Approvals |  |  | MEP |  | 0.16107
| Poinciana |  | 9 | 3 | 2 | 1 | 3 | 1.3492 | 0.28926 | 0.28721 | 0.17351 | 0.5992
|  |  | MEP | Schematic Concept | Pre-construction set | Clubhouse—Structure and Envelope | Clubhouse—Interiors and Facilities | MEP | 0.072314 | 0.14463 | 0.17351 | 0.074361
|  |  | MEP | Approvals | Master Plan |  | Clubhouse—Outdoor Spaces and Pool | MEP | 0.14463 | 0.14258 |  | 0.049574
|  |  | MEP | Experience Home + Project Experience |  |  | Site MEP | MEP | 0.072314 |  |  | 0.47527
| Ambegn |  | 4 | 0 | 2 | 1 | 1 | 0.59354 | 0 | 0.36197 | 0.12066 | 0.11092
|  |  | MEP |  | Schematic Concept | Experience Home + Project Experience | Pre-construction set | MEP |  | 0.12066 | 0.12066 | 0.11092
|  |  | MEP |  | Approvals |  |  | MEP |  | 0.24131
| Savakanhli |  | 4 | 0 | 2 | 1 | 1 | 0.4779 | 0 | 0.27524 | 0.11092 | 0.091745
|  |  | MEP |  | Schematic Concept | Pre-construction set | Experience Home + Project Experience | MEP |  | 0.091745 | 0.11092 | 0.091745
|  |  | MEP |  | Approvals |  |  | MEP |  | 0.18349
| Harohalli |  | 4 | 0 | 2 | 1 | 1 | 0.22655 | 0 | 0.086721 | 0.11092 | 0.028907
|  |  | MEP |  | Schematic Concept | Pre-construction set | Experience Home + Project Experience | MEP |  | 0.028907 | 0.11092 | 0.028907
[5 empty] | Approvals |  |  |  |  | 0.057814
| 37a Nandi Hills [V] |  | 4 | 0 | 0 | 2 | 2 | 0.93456 | 0 | 0 | 0.62304 | 0.31152
|  |  | MEP |  |  | Schematic Concept | Pre Construction Set | MEP |  |  | 0.31152 | 0.31152
|  |  | MEP |  |  | Approvals | Project Experience | MEP |  |  | 0.31152
| DP |  | 5 | 2 | 1 | 1 | 1 | 1.9621 | 1.2307 | 0.61537 | 0 | 0.11599
|  |  | MEP | Schematic Concept | Pre Construction Set | Experience Home + Project Experience | Foundation and Grade Slab | MEP | 0.61537 | 0.61537 |  | 0.11599
|  |  | MEP | Approvals |  |  |  | MEP | 0.61537
| Suntikoppa |  | 7 | 2 | 1 | 1 | 3 | 1.6964 | 0.46014 | 0.23007 | 0 | 1.0061
|  |  | MEP | Schematic Concept | Pre Construction Set | Experience Home + Project Experience | Foundations and Sub-Grade structure |  | 0.23007 | 0.23007 |  | 0.46437
|  |  | MEP | Approvals |  |  | Super Structure |  | 0.23007 |  |  | 0.30958
|  |  | MEP |  |  |  | Building Envelope + Plot Development |  |  |  |  | 0.23219
| OtR |  | 7 | 5 | 2 | 0 | 0 | 0.27415 | 0.23194 | 0.042217 | 0 | 0
|  |  | MEP | Site MEP | Master Archives |  |  |  | 0.074219 | 0.012341
|  |  | LS | Pre Construction Set | Master Archives |  |  |  | 0.029875
|  |  | LS | Master Plan |  |  |  |  | 0.044985 | 0.029875
|  |  | LS | Landscaping |  |  |  |  | 0.053982
|  |  | LS | Community spaces [Board Walk, Children play area] |  |  |  |  | 0.028875
| PoaRR - T9 (Commercial Fit-outs) |  | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | MEP | T9-14 Sequel ¦ GFC Batch 01 | T9-06 TE Office ¦ Master Archives
|  |  | MEP | T9-05 Nudge ¦ GFC Batch 01 | T9-14 Sequel ¦ Master Archives
|  |  | MEP | T9-06 TE Office ¦ GFC Batch 01 | T9-05 Nudge ¦ Master Archives
| Inspira Corp Ofc |  | 2 | 0 | 1 | 1 | 0 |  | 0 | 0.037125 | 0.037125 | 0
|  |  | MEP |  | Schematic concept | Pre-construction |  |  |  | 0.037125 | 0.037125
| Meena & Krishnasai Residence |  | 4 | 0 | 1 | 2 | 1 | 0.0432 | 0 | 0.0054 | 0.0216 | 0.0162
|  |  | MEP |  | Schematic Concept | Pre-construction set | Construction GFC |  |  | 0.0054 | 0.0162 | 0.0162
|  |  | MEP |  |  | Approvals |  |  |  |  | 0.0054
| Kavita & Dr. LS Family Residences |  | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | MEP |  | Schematic Concept | Pre-construction set | Construction GFC
|  |  | MEP |  |  | Approvals
| Sudha & Arun Residence Extension |  | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | MEP |  | Schematic Concept | Pre-construction set | Construction GFC
|  |  | MEP |  |  | Approvals
| Alibaug |  | 4 | 1 | 1 | 1 | 1 | 0.33276 | 0.05546 | 0.11092 | 0.11092 | 0.05546
|  |  | MEP | Schematic Concept |  | Pre Construction Set | Project Experience | MEP | 0.05546 |  | 0.11092 | 0.05546
|  |  | MEP |  | Approvals |  |  | MEP |  | 0.11092
| Talashet |  | 4 | 1 | 1 | 1 | 1 | 0.20532 | 0.0236 | 0.0472 | 0.11092 | 0.0236
|  |  | MEP | Schematic Concept |  | Pre Construction Set | Project Experience | MEP | 0.0236 |  | 0.11092 | 0.0236
|  |  | MEP |  | Approvals |  |  | MEP |  | 0.0472
1 | Sarjpr [P] |  | 4 | 0 | 0 | 2 | 2 | 1.3664 | 0 | 0 | 0.79709 | 0.56935
|  |  | MEP |  |  | Schematic Concept | Pre Construction Set |  |  |  | 0.34161 | 0.45548
|  |  | MEP |  |  | Approvals | Project Experience |  |  |  | 0.45548 | 0.11387
| Vijayapura |  | 5 | 1 | 1 | 2 | 1 | 0.52 | 0.06 | 0.12 | 0.18 | 0.16
|  |  | MEP | Schematic Concept |  | Pre Construction Set | Master Plan | MEP | 0.06 |  | 0.12 | 0.16
|  |  | MEP |  | Approvals | Project Experience |  | MEP |  | 0.12 | 0.06
| Lal Bazar |  | 3 | 0 | 1 | 1 | 1 | 0.38232 | 0 | 0.12744 | 0.12744 | 0.12744
|  |  | MEP |  | Schematic Concept | Approvals | Pre Construction Set | MEP |  | 0.12744 | 0.12744 | 0.12744
| Dani Hama |  | 3 | 0 | 1 | 1 | 1 | 0.70623 | 0 | 0.23541 | 0.23541 | 0.23541
|  |  | MEP |  | Schematic Concept | Approvals | Pre Construction Set | MEP |  | 0.23541 | 0.23541 | 0.23541
| Bellandur |  | 3 | 0 | 2 | 1 | 0 | 1.0832 | 0 | 0.72216 | 0.36108 | 0
|  |  | MEP |  | Schematic Concept | Pre Construction Set |  | MEP |  | 0.36108 | 0.36108
|  |  | MEP |  | Approvals |  |  | MEP |  | 0.36108
1 | Vaderahalli |  | 4 | 0 | 2 | 1 | 1 | 5.4693 | 0 | 3.1904 | 0.45577 | 1.8231
|  |  | MEP |  | Schematic Concept | Project Experience | Pre Construction Set |  |  | 1.3673 | 0.45577 | 1.8231
|  |  | MEP |  | Approvals |  |  |  |  | 1.8231
| Landscape | LS | 171 | 39 | 56 | 40 | 36 | 18.3445 | 2.4932 | 7.6071 | 3.5925 | 4.6518
1 | AtR Ph 1, 2a, 2b, 2c |  | 3 | 2 | 1 | 0 | 0 | 0.14738 | 0.13513 | 0.01225 | 0 | 0
| Gagan | AtR Ph 1, 2a, 2b | LS | LS ¦ Clubhouse + Amenities - Community spaces [Board Walk, Children play area] |  |  |  | LS | 0.042474
| Gagan | AtR Ph 1, 2a, 2b | LS | LS ¦ Master Archives |  |  |  | LS | 0.092658
| Gagan | AtR Ph 2c | LS |  | LS ¦ Master Archives |  |  | LS |  | 0.01225
1 | AtR Com |  | 4 | 3 | 1 | 0 | 0 | 0.19812 | 0.13621 | 0.061912 | 0 | 0
| Gagan | AtR Com | LS | LS ¦ Master Plan - Master Plan | LS ¦ Master Archives |  |  | LS | 0.030733 | 0.061912
| Gagan | AtR Com | LS | LS ¦ Master Plan - Landscaping |  |  |  | LS | 0.025611
| Gagan | AtR Com | LS | LS ¦ Tower-[Commercial] - Building Envelope and Common Areas [All Levels] |  |  |  | LS | 0.079861
1 | TMFT -2 |  | 1 | 1 | 0 | 0 | 0 | 0.032487 | 0.032487 | 0 | 0 | 0
| Gagan | TMFT -2 | LS | LS ¦ Master Archives |  |  |  | LS | 0.032487
1 | SFTW |  | 6 | 3 | 3 | 0 | 0 | 0.16323 | 0.088957 | 0.074274 | 0 | 0
|  | SFTW | LS | LS ¦ Master Plan | LS ¦ Clubhouse—Interiors and Facilities |  |  | LS | 0.024769 | 0.017232
|  | SFTW | LS | LS ¦ Master Plan-Landscaping | LS ¦ Clubhouse - Community spaces [Board Walk, Children play area,OAT] |  |  | LS | 0.029723 | 0.043081
|  | SFTW | LS | LS ¦ Clubhouse—Outdoor Spaces and Pool | LS ¦ Master Archives |  |  | LS | 0.034465 | 0.013961
| PoaRR |  | 11 | 3 | 7 | 1 | 0 | 0.234 | 0.08 | 0.144 | 0.01 | 0
| Gagan | PoaRR | LS | Res - Community spaces [Board Walk, Children play area] | Res ¦ Master Archives |  |  | LS | 0.04 | 0.07
| Gagan | PoaRR-T08 | LS |  | R25 P Default and it's variants | T08 ¦ Master Archives |  | LS |  | 0.001 | 0.01
| Gagan | PoaRR-T08 | LS |  | L20 P Default and it's variants |  |  | LS |  | 0.001
| Gagan | PoaRR-T08 | LS |  | D35 P Default and it's variants |  |  | LS |  | 0.001
| Gagan | PoaRR-T08 | LS | T08-Clubhouse—Interiors and Facilities | L22 P Default and it's variants |  |  | LS | 0.02 | 0.001
| Gagan | PoaRR-T08 | LS | T08-Master Plan | T08-Landscaping |  |  | LS | 0.02 | 0.02
| Gagan | PoaRR-T08 | LS |  | T08-Community spaces [Board Walk, Children play area] |  |  | LS |  | 0.05
| TMD |  | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Gagan | TMD - II | LS | Master Archives |  |  |  | LS
| Gagan | TMD - I | LS | Master Archives |  |  |  | LS
| ITQE |  | 14 | 4 | 3 | 2 | 5 | 0.64269 | 0.24835 | 0.08212 | 0.030443 | 0.28177
|  | ITQE Ph 1 | LS |  | Master Archives |  |  | LS |  | 0.053077
|  | ITQE Ph 2a | LS |  | Master Archives |  |  | LS |  | 0.022485
|  | ITQE Ph 2b | LS | Masterplan ¦ Master Plan |  | Masterplan ¦ Landscaping |  | LS | 0.0065579 |  | 0.0078694
|  | ITQE Ph 2b | LS |  |  | LS ¦ Master Archives |  | LS |  |  | 0.022574
|  | ITQE Ph 2c / 3 | LS | Schematic Concept | Pre Construction Set |  | I20 Default and it's variants | LS | 0.045148 | 0.0065579 |  | 0.083777
|  | ITQE Ph 2c / 3 | LS | Approvals |  |  | I25 Default and it's variants | LS | 0.067721 |  |  | 0.083777
|  | ITQE Ph 2c / 3 | LS | Marketing and Sales |  |  | D35 Default and it's variants | LS | 0.022574 |  |  | 0.083777
|  | ITQE Ph 2c / 3 | LS |  |  |  | Masterplan ¦ Landscaping | LS | 0.083777 |  |  | 0.0078694
|  | ITQE Ph 2c / 3 | LS |  |  |  | Master Archives | LS | 0.022574 |  |  | 0.022574
| Indiranagar Residence |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
0 |  |  | LS | GFC ¦ Block [Gym + Swimming pool]
| Karnataka Public School, Basavanagudi |  | 1 | 1 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | LS | GFC ¦ Block
| Auditorium [Malleswaram] |  | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | LS | GFC ¦ Block
| AtR-3 |  | 12 | 0 | 3 | 5 | 4 | 0.15556 | 0 | 0.072075 | 0.078241 | 0.0052457
|  | AtR-III |  |  | LS ¦ Pre Construction Set | LS ¦ Home Products - V30 Default and it's variants | LS ¦ Villa Block 29 - Building Envelope + Plot Development |  |  | 0.043245 | 0.017009 | 0.0012343
|  | AtR-III |  |  | LS ¦ Approvals | LS ¦ Home Products - V50 Default and it's variants | LS ¦ Villa Block 30 - Building Envelope + Plot Development |  |  | 0.014415 | 0.020411 | 0.0012343
|  | AtR-III |  |  | LS ¦ Marketing and Sales | LS ¦ Home Products - V80 Default and it's variants | LS ¦ Villa Block 31 - Building Envelope + Plot Development |  |  | 0.014415 | 0.020411 | 0.00061714
|  | AtR-III |  |  |  | LS ¦ Home Products - V45 Default and it's variants | LS ¦ Villa Block 32 - Building Envelope + Plot Development |  |  |  | 0.020411 | 0.00216
|  | AtR-III |  |  |  | LS ¦ Master Plan - Master Plan |  |  |  |  | 1.7034e-10
| DBTW |  | 10 | 2 | 3 | 2 | 3 | 0.7048 | 0.13212 | 0.23124 | 0.1447 | 0.19674
|  |  | LS | Pre Construction Set | Home Products - I20 Default and it's variants | Master Plan - Master Plan | Master Plan - Landscaping | LS | 0.066062 | 0.079883 | 0.1027 | 0.12324
|  |  | LS | Experience Homes + Project Experience | Home Products - I25 Default and it's variants | Clubhouse—Outdoor Spaces and Pool | Clubhouse—Interiors and Facilities | LS | 0.066062 | 0.075679 | 0.042 | 0.021
|  |  | LS |  | Home Products - L21 Default and it's variants |  | Community spaces [Board Walk, Children play area,OAT] | LS |  | 0.075679 |  | 0.0525
| TUIG |  | 3 | 1 | 2 | 0 | 0 | 0.17 | 0.06 | 0.11 | 0 | 0
|  |  | LS | Clubhouse—Outdoor Spaces and Pool | Clubhouse—Interiors and Facilities |  |  | LS | 0.06 | 0.03
[5 empty] | Community spaces [Board Walk, Children play area] |  |  | LS |  | 0.08
| Sarjapur |  | 5 | 0 | 2 | 2 | 1 | 3.1693 | 0 | 1.9808 | 0.79233 | 0.39617
|  |  | LS |  | Schematic Concept | Pre-construction set | Marketing and Sales | LS |  | 0.79233 | 0.39617 | 0.39617
[5 empty] | Approvals | Experience Home + Project Experience |  |  |  | 1.1885 | 0.39617
| 36a Nandi Hills[V] |  | 4 | 0 | 2 | 1 | 1 | 0.36036 | 0 | 0.18018 | 0.13514 | 0.045045
|  |  | LS |  | Schematic Concept | Pre-construction set | Experience Home + Project Experience | LS |  | 0.13514 | 0.13514 | 0.045045
|  |  | LS |  | Approvals |  |  | LS |  | 0.045045
| Poinciana |  | 8 | 4 | 2 | 0 | 2 | 0.6068 | 0.318 | 0.19145 | 0 | 0.097354
|  |  | LS | Schematic Concept | Pre-construction set |  | Clubhouse—Interiors and Facilities | LS | 0.090858 | 0.045429 |  | 0.032451
|  |  | LS | Approvals | Master Plan |  | Clubhouse—Outdoor Spaces and Pool | LS | 0.13629 | 0.14602 |  | 0.064902
|  |  | LS | Marketing and Sales |  |  |  | LS | 0.045429
|  |  | LS | Experience Home + Project Experience |  |  |  | LS | 0.045429
| Ambegn |  | 5 | 0 | 2 | 2 | 1 | 0.53988 | 0 | 0.33742 | 0.13497 | 0.067485
|  |  | LS |  | Schematic Concept | Experience Home + Project Experience | Pre-construction set | LS |  | 0.13497 | 0.067485 | 0.067485
|  |  | LS |  | Approvals | Marketing and Sales |  | LS |  | 0.20245 | 0.067485
| Savakanhli |  | 5 | 0 | 2 | 2 | 1 | 0.41052 | 0 | 0.25657 | 0.10263 | 0.051315
|  |  | LS |  | Schematic Concept | Pre-construction set | Experience Home + Project Experience | LS |  | 0.10263 | 0.051315 | 0.051315
|  |  | LS |  | Approvals | Marketing and Sales |  | LS |  | 0.15394 | 0.051315
| Harohalli |  | 5 | 0 | 2 | 2 | 1 | 0.12935 | 0 | 0.080842 | 0.032337 | 0.016168
|  |  | LS |  | Schematic Concept | Pre-construction set | Experience Home + Project Experience | LS |  | 0.032337 | 0.016168 | 0.016168
[5 empty] | Approvals | Marketing and Sales |  |  |  | 0.048505 | 0.016168
| 37a Nandi Hills [V] |  | 4 | 0 | 0 | 2 | 2 | 0.69696 | 0 | 0 | 0.34848 | 0.34848
|  |  | LS |  |  | Schematic Concept | Pre Construction Set | LS |  |  | 0.26136 | 0.26136
|  |  | LS |  |  | Approvals | Project Experience | LS |  |  | 0.08712 | 0.08712
| DP |  | 4 | 2 | 1 | 1 | 0 | 1.3768 | 0.68838 | 0.51628 | 0.17209 | 0
|  |  | LS | Schematic Concept | Pre Construction Set | Experience Home + Project Experience |  | LS | 0.51628 | 0.51628 | 0.17209
|  |  | LS | Approvals |  |  |  | LS | 0.17209
| Suntikoppa |  | 5 | 2 | 1 | 1 | 1 | 0.99091 | 0.25737 | 0.19302 | 0.064341 | 0.47618
|  |  | LS | Schematic Concept | Pre Construction Set | Experience Home + Project Experience | Building Envelope + Plot Development |  | 0.19302 | 0.19302 | 0.064341 | 0.47618
|  |  | LS | Approvals |  |  |  |  | 0.064341
| OtR |  | 5 | 4 | 1 | 0 | 0 | 0.18759 | 0.15772 | 0.029875 | 0 | 0
|  |  | LS | Pre Construction Set | Master Archives |  |  |  | 0.029875
|  |  | LS | Master Plan |  |  |  |  | 0.044985 | 0.029875
|  |  | LS | Landscaping |  |  |  |  | 0.053982
|  |  | LS | Community spaces [Board Walk, Children play area] |  |  |  |  | 0.028875
0 | PoaRR - T9 (Commercial Fit-outs) |  | 3 | 0 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0
|  |  | LS |  | T9-06 TE Office ¦ Master Archives
|  |  | LS |  | T9-14 Sequel ¦ Master Archives
|  |  | LS |  | T9-05 Nudge ¦ Master Archives
1 | Inspira Corp Ofc |  | 3 | 0 | 1 | 1 | 1 |  | 0 | 0.020625 | 0.00825 | 0.020625
|  |  | LS |  | Schematic concept | Approvals | PreConstruction |  |  | 0.020625 | 0.00825 | 0.020625
1 | Meena & Krishnasai Residence |  | 4 | 0 | 1 | 2 | 1 | 0.0285 | 0 | 0.0075 | 0.0105 | 0.0105
|  |  | LS |  | Schematic Concept | Pre-construction set | Construction GFC |  |  | 0.0075 | 0.0075 | 0.0105
|  |  | LS |  |  | Approvals |  |  |  |  | 0.003
0 | Kavita & Dr. LS Family Residences |  | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | LS |  | Schematic Concept | Pre-construction set | Construction GFC
|  |  | LS |  |  | Approvals
0 | Sudha & Arun Residence Extension |  | 4 | 0 | 1 | 2 | 1 | 0 | 0 | 0 | 0 | 0
|  |  | LS |  | Schematic Concept | Pre-construction set | Construction GFC
|  |  | LS |  |  | Approvals
| Alibaug |  | 5 | 1 | 2 | 1 | 1 | 0.24816 | 0.06204 | 0.12408 | 0.03102 | 0.03102
|  |  | LS | Schematic Concept | Marketing and Sales | Pre Construction Set |  | LS | 0.06204 | 0.03102 | 0.03102
|  |  | LS |  | Approvals |  | Project Experience | LS |  | 0.09306 |  | 0.03102
| Talashet |  | 5 | 1 | 2 | 1 | 1 | 0.1056 | 0.0264 | 0.0528 | 0.0132 | 0.0132
|  |  | LS | Schematic Concept | Marketing and Sales | Pre Construction Set |  | LS | 0.0264 | 0.0132 | 0.0132
|  |  | LS |  | Approvals |  | Project Experience | LS |  | 0.0396 |  | 0.0132
1 | Sarjpr [P] |  | 4 | 0 | 0 | 2 | 2 | 1.019 | 0 | 0 | 0.50952 | 0.50952
|  |  | LS |  |  | Schematic Concept | Pre Construction Set |  |  |  | 0.38214 | 0.38214
|  |  | LS |  |  | Approvals | Marketing and Sales |  |  |  | 0.12738 | 0.12738
| Vijayapura |  | 5 | 1 | 1 | 2 | 1 | 0.38 | 0.07 | 0.1 | 0.06 | 0.15
|  |  | LS | Schematic Concept |  | Pre Construction Set | Master Plan | LS | 0.07 |  | 0.03 | 0.15
|  |  | LS |  | Approvals | Project Experience |  | LS |  | 0.1 | 0.03
| Lal Bazar |  | 3 | 0 | 1 | 1 | 1 | 0.24948 | 0 | 0.10692 | 0.03564 | 0.10692
|  |  | LS |  | Schematic Concept | Approvals | Pre Construction Set | LS |  | 0.10692 | 0.03564 | 0.10692
| Dani Hama |  | 3 | 0 | 1 | 1 | 1 | 0.46085 | 0 | 0.1975 | 0.065835 | 0.1975
|  |  | LS |  | Schematic Concept | Approvals | Pre Construction Set | LS |  | 0.1975 | 0.065835 | 0.1975
| Bellandur |  | 4 | 0 | 2 | 1 | 1 | 0.80784 | 0 | 0.40392 | 0.30294 | 0.10098
|  |  | LS |  | Schematic Concept | Pre Construction Set | Experience Home + Project Experience | LS |  | 0.30294 | 0.30294 | 0.10098
|  |  | LS |  | Approvals |  |  | LS |  | 0.10098
1 | Vaderahalli |  | 5 | 0 | 2 | 1 | 2 | 4.0788 | 0 | 2.0394 | 0.50985 | 1.5295
|  |  | LS |  | Schematic Concept | Project Experience | Pre Construction Set |  |  | 1.5295 | 0.50985 | 1.5295
|  |  | LS |  | Approvals |  | Marketing and Sales |  |  | 0.50985
Note on N171: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can be moved to next quarter
Note on N172: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can be moved to next quarter
Note on N173: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can be moved to next quarter
Note on N174: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can be moved to next quarter
Note on N175: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Can be moved to next quarter
Note on N176: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NA
Note on N177: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NA
Note on N178: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NA
Note on N179: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: NA
Note on V376: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Children play area equipment selection

## Prj List (hidden)
| 62 | 53
Ongoing | AtR | 1
| AtR - 03 | 1
| AtR - C | 1
| PoaRR-Res | 1
| PoaRR-T08 | 1
PoaRR-T09
| PoaRR-Workcations | 1
| ITQE-Ph1 | 1
| ITQE-Ph2a | 1
| ITQE-Ph2b | 1
| ITQE-Ph2c | 1
| OTR-Ph01 | 1
| OTR-Ph02 | 1
| TMFT | 1
| DBTW | 1
| TMD | 1
| LTF | 1
| SftW | 1
| 22a Sarjapur | 1
DonaPaula
OtF
KIADB - MC
New Prj | Vaderahalli | 1
| NH37a - Acharalahalli | 1
NH 30a - Madakuhosahalli
NH 10a
| TuiG | 1
| Poinciana | 1 | On Hold
| Harohalli | 1
| Violet hill | 1
| Vijayapura | 1
| Ambegaon | 1
| Savakanahalli | 1
| Aundh 3a | 1
| Shreegaon | 1
| Yadgarpalle | 1
Varthur 52a
| TR Mills Chamarajpet | 1
| Lonavala | 1
| Jhanjh Lake [Mayfair] | 1
| Tumkur 33a | 1
| Sarjapur - Plotted | 1
| Mall of Asia | 1
DsgnBld | MeenaSai Res | 1
| NH Homestay | 1
| OTR Museum | 1
| Indiranagar Res | 1
| Swisstown | 1 | On Hold
| Imagine | 1
| LGCE | 1
| Ooty Res | 1
| MT Plano | 1
| Saideep reddy Res,Hyd | 1 |  | New
| 5a GTC Indrngr | 1 |  | New
HPL | Tapestry
| Windmils, Hyd | 1
Windmils, Sftw
| TEHPL-OTR | 1
CSR | Aud-Malleswaram | 1
| tFS-2 | 1
| PDC | 1
| KPS-Mall | 1

## Sheet2 (hidden)
Tracking mechanism for small scale design revision [eg. Partition mesh between Villas]
Harohalli include package

## Prj Crtcl rqrmnt (hidden)
Project | Critical Requirement
Ongoing Projects | Packages
AtR Ph 1,2a,2b,2c | LoD 350 - Clubhouse + Amenities [Auditoruim Drawings + BOQ] [Tennis Court Structural drawings] LoD 350 - Master Plan - Site MEP [DG Panel Room drawings ] - Ph2c
AtR Ph 3 | LoD 350 - Foundations and Sub-Grade Structure - Villa Block 29 [V45 Structural Drawings]; Villa Block 30, 34 [V30, V50 Structural Drawings] LoD 350 - Home Products - V45 Default and it's variants LoD 300 - Pre Construction Set [V80]
AtR - C | LoD 350 - Master Plan - Site Development [Compound wall Details, Entry/Exit Gate Details and Security Room] LoD 350 - Master Plan - Site MEP [OWC, Transformer yard, STP, UGT, Stormwater Trench Details] LoD 350 - Tower-[Commercial] - Habitable Level 3-5 [ Slab and Sleeve details for SSL 7&8]
PoaRR-Res | Sports Complex [Structural drawings], West Boundary Wall Detail - 03, V40 Building Envelope Drawings
PoaRR-T08 | Podium/ISS - Foundations & Grade Slab [Setting out drawings, Wall details], R25, D35, L20, L22 Default closure.
ITQE-Ph1 | ST - Clubhouse drawings [Storm water tank, Sewage tank]; Tree avenue details, Play equipment details.
ITQE-Ph2b | Podium Slab - Structural details
ItQE-Ph2c [T9] | Tower column, ramp, staircase, lift core wall structural details
OTR-Ph01 | Service yard 2 structural details [STP, Storm water tank]
TuiG | LoD 350 - Clubhouse—Concept finalization & Structural drawings revision, Amphitheatre & swimming pool dwgs
DBTW | Tower 1-5 All structural drawings All Podium/Extended Basement Structural Drawings Home Products - I20 and I25, L21 Default and it's variants
SftW | Service Block - All drawings Master Plan - AR- Site Development [Boundary Wall, Entrance Gate, Security Cabin and Access Road Details] Site MEP [Transformer Yard, DG Yard]
LGCE Campus | LoD 100 Concept finalisation
MT Plano | -
MeenaSai Res | LoD 300 Pre Construction
NH Homestay | LoD 350 [SSL-3,4,5] Structural drawings, LoD 350 MEP [Electrical layouts - All levels]
Indiranagar Res | LoD 350 - Building Envelope + Plot Development, Interiors. [On-Site works on hold]
OTR Museum | LoD 100 - Concept finalisation with client
Fullkit Homes | Tuig [V20, V30, V40, Site plan and Sales office], Harohalli [V60], OTF [V25] | Tuig [V20, V30, V40], Harohalli [V20, V30, V50H], Violet hill - P1,P2, Shreegaon [V50H], OTF [V60, V25H] | V40 - PoaRR 51, 66
New Projects
OTR-Ph02 | LoD 200 Schematic concept, Approvals
TMFT-Ph 3 | LoD 200 Schematic concept
ItQE-Ph3a [T10-12 & 31 Villas] | Experience Home + Project Experience; LoD 300 - Pre Construction Set; LoD 300 - Marketing and Sales
Sarjapur Road [South Block-Resi] | LoD 300 Pre Construction, Approvals, Experience home and Sales lounge
Sarjapur - C (South Block) | LoD 300 Pre Construction, Approvals
Sarjapur - C (North Block) | LoD 300 Pre Construction, Approvals
OTF | LoD 200 by Jul'26. LoD 350 - Project Entrance by Jul'26. Approvals by Aug'26
Harohalli [Plotted] | LoD 200 Schematic concept finalization [Master plan]
Shreegaon [61.6a] | LoD 200 Schematic concept
Violet Hill [21.76a] | LoD 350 - Structures - Security Cabin and Entrance
Violet Hill [21.76a] | LoD 350 - Project Experience [Sales Lounge, Model Road]
Violet Hill [27.08a] | LoD 350 - BOQ & Technical Specifications
Byatarayanpura [behind Mall of Asia] | LoD 100 Concept finalisation
TR Mills Chamarajpet | LoD 100 Concept finalisation
KIADB - Mys | LoD 100 Concept finalisation, LoD 200 Schematic concept, Approvals
Imagine Campus | LoD 100 Concept finalisation, Approvals
OtR OOTA | LoD 100 Concept finalisation
Blue in Green | LoD 200 Schematic concept
Varthur 52a | LoD 100 Concept finalisation
Vaderahalli | LoD 100 Concept finalisation
Nava Raipur | LoD 300 Pre Construction, Approvals

## Goals FY 26-27Q3
Poinciana ¦ Design package release FY26-27 Q3 |  |  |  |  | 5.8118 | 16 | 0 | 0
Project | Description | Release date | Responsible | Remarks | Plan - Billing [Cr.] | Plan - Pkgs | Actuals - Billing [Cr.] | Actuals - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson
Poinciana | Package Release |  |  |  | 5.8118 | 16 | 0 | 0
Master Planning | Package Release [Lod 200 -Schematic Concept & Approvals] |  | Gagan |  | 1.7117 | 2 | 0 | 0
Poinciana | LoD 200 - Schematic Concept | 2026-10-22 | Gagan |  | 0.85586 | 1 | 0 |  | Gagan | Utpal | Manali
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Poinciana | Approvals | 2026-10-27 | Gagan |  | 0.85586 | 1 | 0 |  | Gagan | Utpal | Manali
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Poinciana | LoD 300 - Pre Construction | 2026-11-23 | Gagan |  | 0.85586 | 1 | 0 |  | Gagan | Utpal | Manali
Architecture | Package Release [LoD 200 - Schematic Concept] |  | Om Prakash |  | 1.89 | 2 | 0 | 0
Poinciana | LoD 200 - Schematic Concept | 2027-02-16 | Om Prakash |  | 0.945 | 1 | 0 |  | Om Prakash | Aparna Sahu
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Poinciana | LoD 300 - Pre Construction Set | 2025-05-18 | Om Prakash |  | 0.945 | 1 | 0 |  | Om Prakash | Aparna Sahu
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Step 1 | Task description 1
Step 2 | Task description 2
Structural | Package Release [ LoD 200 - Schematic Concept] |  | Prakash C |  | 0.80136 | 3 | 0 | 0
Poinciana | LoD 200 - Schematic Concept | 2026-10-22 | Prakash C |  | 0.20034 | 1 | 0 |  | Prakash C | Satish | Alwin | Raghav | Prasad
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Poinciana | LoD 300 - Pre Construction Set | 2026-12-21 | Prakash C |  | 0.40068 | 1 | 0 |  | Prakash C | Satish | Alwin | Raghav | Prasad
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Poinciana | Project Experience | 2026-12-24 | Prakash C |  | 0.20034 | 1 | 0 |  | Gagan | satish | Alwin
Step 1 | Task description 1
Step 2 | Task description 2
MEP | Package Release [till LoD 300 - Pre Construction Set] |  | Gagan |  | 0.33453 | 4 | 0 | 0
Poinciana | LoD 200 - Schematic Concept | 2026-10-26 | Gagan |  | 0.055755 | 1 | 0 |  | Gagan | Salomi
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Poinciana | Approvals | 2026-10-27 | Gagan |  | 0.11151 | 1 | 0 |  | Gagan | Salomi | Eranna Bhavya
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Poinciana | LoD 300 - Pre Construction Set | 2026-12-21 | Gagan |  | 0.11151 | 1 | 0 |  | Gagan | Salomi | Eranna Bhavya
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Poinciana | Project Experience | 2026-12-24 | Gagan |  | 0.055755 | 1 | 0 |  | Gagan | Salomi | Eranna Bhavya
Step 1 | Task description 1
Step 2 | Task description 2
Landscape | Package Release [till LoD 300 - Pre Construction Set] |  | Gagan |  | 0.21829 | 4 | 0 | 0
Poinciana | LoD 200 - Schematic Concept | 2027-01-15 | Gagan |  | 0.06237 | 1 | 0 |  | Gagan | Lajja | Apoorva Gouri
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Poinciana | Approvals | 2026-10-27 | Gagan |  | 0.093555 | 1 | 0 |  | Gagan | Lajja | Apoorva Gouri
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Poinciana | LoD 300 - Pre Construction Set | 2026-11-23 | Gagan |  | 0.031185 | 1 | 0 |  | Gagan | Lajja | Apoorva Gouri
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Step 1 | Task description 1 | 1900-01-13
Step 2 | Task description 2 | 1900-01-13
Poinciana | Project Experience | 2026-10-27 | Gagan |  | 0.031185 | 1 | 0 |  | Gagan | Lajja | Apoorva Gouri
Step 1 | Task description 1
Step 2 | Task description 2

## Pkgs Summary
| 0117 ¦ Poinciana |  | AR | ST | MEP | LS | 1 | Completed
|  | Scope | 23 | 18 | 19 | 20 | -1 | Pending
|  | Actuals | 1 | 0 | 0 | 0 |  | NA
DESIGN CONCEPT
1 | 1 | Contract + Design Brief | 1
2 | 2 | Schematic Concept | -1 | -1 | -1 | -1
3 | 3 | Approvals | -1 |  | -1 | -1
4 | 4 | Pre Construction Set | -1 | -1 | -1 | -1
5 | 5 | Project Experience | -1 | -1 | -1 | -1
6 | 6 | Marketing and Sales | -1 |  |  | -1
CONSTRUCTION DOCUMENTS
7 | 1 | Master Plan - MP
MP-01 | 1 | Infra - Grading | -1 | -1
MP-02 | 2 | Infra - MEP | -1 | -1 | -1 | -1
MP-03 | 3 | BOQ & Technical Specifications | -1 |  | -1 | -1
MP-04 | 4 | Infra - Coordinated |  |  | -1 | -1
MP-05 | 5 | Structures - Security Cabin and Entrance | -1 | -1 | -1 | -1
MP-06 | 6 | Infra - Plot Boundary & Enclosures | -1 | -1 |  | -1
MP-07 | 7 | Infra - Signage & Street Lighting | -1 | -1 | -1 | -1
MP-08 | 8 | Structures - Electrical Room & Toilet Block | -1 | -1 | -1 | -1
MP-09 | 9 | Structures - UGT | -1 | -1 | -1 | -1
MP-10 | 10 | Structures - OHT | -1 | -1 | -1 | -1
MP-11 | 11 | Structures - STP | -1 | -1 | -1 | -1
MP-12 | 12 | Structures - OWC & other structure | -1 | -1 | -1 | -1
8 | 2 | Clubhouse + Amenities - AMN
AMN-01 | 1 | Clubhouse—Structure and Envelope | -1 | -1 | -1
AMN-02 | 2 | Clubhouse—Interiors and Facilities | -1 |  | -1 | -1
AMN-03 | 3 | Clubhouse—Outdoor Spaces and pool | -1 | -1 | -1 | -1
AMN-04 | 4 | Community spaces [Children play area, Open Park space] | -1 | -1 |  | -1
AMN-05 | 5 | Sporting Facilities | -1 | -1 | -1
POST-CONSTRUCTION
9 | 1 | Master Archives | -1 | -1 | -1 | -1

## FY 26-27 Q2 Pivot (hidden)
|  |  | ID Units | FY26-27 Q2
Row Labels | Sum of Plan - Billing [Cr.] | Count of Plan - Pkgs |  | Jul-Sept BL0 | Billing | Area | ID revenue
Atul P | 0.3493 | 26 | Atul [Personalised] | 4 | 0.3493 | 18744 | 2.47
Architecture |  | 25 | Saji [Personalised] | 18 | 2.2044 | 122463 | 12.25
Harohalli |  | 6 | Navneet [Total] | 99 | 1.0917
OTF |  | 4 | Personalised | 7 | 0.53307 | 29117 | 3.36
Shreegaon |  | 1 | E-Design | 86 | 0.5586 | - | 27.93
TuiG |  | 8 | Default | 6 | 0 | - | 0
Violet Hill |  | 6
Interior Design | 0.3493 | 1
Personalised Customisation | 0.3493 | 1
Cijey M | 50.3353 | 40
Architecture | 50.3353 | 40
ITQE-Ph2b | 1.91 | 11
ItQE-Ph2c [T9] | 0.30106 | 3
ItQE-Ph3a [T10-12 & 31 Villas] | 8.7814 | 3
MeenaSai Res | 0.189 | 3
NH Homestay | 0.77994 | 4
OTR Museum | 0.43996 | 2
OTR-Ph01 | 0.39 | 2
OTR-Ph02 | 1.18 | 3
Srjp - Res | 20.5619 | 6
Vaderahalli | 15.8021 | 3
Gagan | 39.5624 | 156
Landscape | 5.9086 | 56
AtR | 0.14067 | 3
Blue in Green | 0.79096 | 3
Harohalli [Plotted] | 0.28215 | 2
Imagine Campus | 0.05 | 1
Indiranagar Res | 0.000113 | 1
ITQE-Ph1
KIADB - Mys |  | 2
LGCE Campus | 0.015065 | 1
MeenaSai Res | 0.012 | 2
NH Homestay | 0.069638 | 2
OTF | 0.0891 | 3
OTR Museum | 0.018855 | 1
OtR OOTA | 0.0093954 | 2
OTR-Ph02 | 0.07128 | 2
PoaRR-Res | 0.04 | 1
PoaRR-T08 | 0.20896 | 4
Shreegaon [61.6a] | 0.24948 | 5
Srjp - C - NB | 0.24317 | 2
Srjp - C - SB | 0.72951 | 2
Srjp - Res | 1.1029 | 3
TMFT-Ph 3 | 0.034481 | 2
Vaderahalli | 1.6716 | 2
Violet Hill [21.76a] | 0.057017 | 7
Violet Hill [27.08a] | 0.022209 | 1
Nava Raipur |  | 2
Master Planning | 22.6765 | 18
Harohalli [Plotted] | 3.665 | 3
KIADB - Mys |  | 3
Shreegaon [61.6a] | 2.1842 | 3
Vaderahalli | 15.8021 | 3
Violet Hill [21.76a] | 0.52044 | 4
Violet Hill [27.08a] | 0.50475 | 2
MEP | 10.9774 | 82
AtR | 0.29138 | 7
AtR - C | 0.16751 | 2
Blue in Green | 1.0047 | 3
DBTW | 0.036853 | 1
Harohalli [Plotted] | 0.30267 | 2
Imagine Campus | 0.1 | 2
ITQE-Ph2b | 0.02 | 1
ItQE-Ph2c [T9] | 0.067123 | 3
ItQE-Ph3a [T10-12 & 31 Villas] | 1.2953 | 3
KIADB - Mys |  | 2
LGCE Campus | 0.017956 | 1
MeenaSai Res | 0.0297 | 3
NH Homestay | 0.12535 | 4
OTF | 0.1593 | 3
OTR Museum | 0.022627 | 1
OtR OOTA | 0.011275 | 2
OTR-Ph01 | 0.04 | 1
OTR-Ph02 | 0.09558 | 2
PoaRR-Res | 0.36109 | 2
PoaRR-T08 | 0.65548 | 9
SftW | 0.021398 | 2
Shreegaon [61.6a] | 0.33453 | 4
Srjp - C - NB | 0.43476 | 3
Srjp - C - SB | 1.3043 | 3
Srjp - Res | 1.6902 | 4
TMFT-Ph 3 | 0.039179 | 2
Vaderahalli | 2.2418 | 2
Violet Hill [21.76a] | 0.08759 | 5
Violet Hill [27.08a] | 0.019854 | 1
Nava Raipur |  | 2
Manik G | 1.4243 | 20
Architecture | 1.1731 | 12
Indiranagar Res | 0.004 | 4
MT Plano | 1.0157 | 5
OtR OOTA | 0.15346 | 3
Landscape | 0.047993 | 3
MT Plano | 0.047993 | 3
MEP | 0.060271 | 3
MT Plano | 0.060271 | 3
Structural | 0.14286 | 2
MT Plano | 0.14286 | 2
Naveen Y | 40.8495 | 31
Architecture | 37.517 | 24
AtR - C | 0.36421 | 3
Blue in Green | 8.2775 | 3
Imagine Campus | 1.15 | 2
KIADB - Mys |  | 3
Srjp - C - NB | 5.5266 | 5
Srjp - C - SB | 16.5797 | 5
Vaderahalli | 5.619 | 3
Master Planning | 3.3325 | 7
OTF | 3.3325 | 7
Om Prakash | 15.9324 | 49
Architecture | 15.9324 | 49
Blue in Green | 0.25713 | 3
Byatarayanpura [behind Mall of Asia] | 1.6141 | 1
DBTW | 5.7306 | 11
Harohalli [Plotted] | 0.305 | 1
LGCE Campus | 0.38042 | 2
OTF | 0.285 | 3
OTR-Ph02 | 0.17 | 2
SftW | 0.72824 | 7
Shreegaon [61.6a] | 2.835 | 4
Srjp - Res | 0.92385 | 3
TMFT-Ph 3 | 0.6182 | 3
TuiG | 1.5478 | 4
Violet Hill [21.76a] | 0.5371 | 2
Nava Raipur |  | 3
Prakash C | 29.5652 | 125
Structural | 29.5652 | 125
AtR | 0.36098 | 19
AtR - C | 0.80124 | 5
Blue in Green | 2.5364 | 2
DBTW | 2.1218 | 19
Harohalli [Plotted] | 0.36252 | 1
Imagine Campus | 0.19 | 1
Indiranagar Res | 0.0008 | 1
ITQE-Ph1 | 0.023824 | 2
ITQE-Ph2b | 0.71 | 8
ItQE-Ph2c [T9] | 0.2848 | 4
ItQE-Ph3a [T10-12 & 31 Villas] | 3.2579 | 2
ITQE-T05 | 0.04 | 1
KIADB - Mys |  | 1
LGCE Campus | 0.064519 | 1
MeenaSai Res | 0.0864 | 3
NH Homestay | 0.22284 | 3
OTF | 0.6324 | 4
OTR Museum | 0.08045 | 1
OtR OOTA | 0.020044 | 1
OTR-Ph01 | 0.3 | 4
OTR-Ph02 | 0.17172 | 1
PoaRR-Res | 0.36 | 3
PoaRR-T08 | 2.1 | 8
SftW | 0.34546 | 6
Shreegaon [61.6a] | 0.80136 | 3
Srjp - C - NB | 1.0415 | 2
Srjp - C - SB | 3.1244 | 2
Srjp - Res | 4.0489 | 3
TMFT-Ph 3 | 0.078635 | 1
TuiG | 1.0053 | 4
Vaderahalli | 4.0202 | 1
Violet Hill [21.76a] | 0.2997 | 6
Violet Hill [27.08a] | 0.071339 | 1
Nava Raipur |  | 1
Saji A | 37.7999 | 46
Architecture | 35.5955 | 45
AtR | 1.9207 | 18
PoaRR-Res | 3.3659 | 8
PoaRR-T08 | 5.9438 | 17
TR Mills | 5.965 | 1
Varthur 52a | 18.4 | 1
Interior Design | 2.2044 | 1
Personalised Customisation | 2.2044 | 1
Shweta V |  | 12
Interior Design |  | 12
Personalised Customisation |  | 1
Experience Homes |  | 7
Product Development |  | 3
Fabric Craft |  | 1
Navneet K | 1.0931 | 7
Interior Design | 1.0931 | 7
Product Launch |  | 4
Personalised Customisation | 0.53307 | 1
Edesign | 0.56 | 1
Default | 0 | 1
Grand Total | 216.9113 | 512

## Goals FY 26-27Q2 Cijey (hidden)
FY 2026-27 Q2 ¦ Design Goals + Billing ¦ Cijey M |  |  |  |  | 50.3353 | 40 | [7 empty] | 0 | 0 | 50.3353 | 40
Project | Phase | Discipline | Design Lead | Description | Plan - Billing [Cr.] | Plan - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | Actuals - Billing [Cr.] | Actuals - Pkgs | 0% | 0%
Ongoing Projects |  |  |  |  | 4.01 | 25 | [7 empty] | 0 | 0
ITQE-Ph2b | Ph 2b |  |  | Package Release | 1.91 | 11 | [7 empty] | 0 | 0
ITQE-Ph2b | Ph 2b | Architecture |  | Complete the project | 1.91 | 11 | [7 empty] | 0 | 0
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Tower—05 ¦ Habitable Level 01 | 0.13 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Tower—06 ¦ Habitable Level 01 | 0.13 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Tower—07 ¦ Habitable Level 01 | 0.13 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Tower—05 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 0.22 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Tower—06 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 0.22 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Tower—07 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 0.22 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Master Plan ¦ Master Plan | 0.03 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Master Plan ¦ Site Development | 0.02 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Master Plan ¦ Site MEP | 0.01 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - ISS 5&6 ¦ Building Envelope and Common Areas | 0.4 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - ISS 7 ¦ Building Envelope and Common Areas | 0.4 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
ItQE-Ph2c [T9] | Ph 2c |  |  | Package Release | 0.30106 | 3 | [7 empty] | 0 | 0
ItQE-Ph2c [T9] | Ph 2c | Architecture |  | LoD 350 - T09 [Foundation & Grade Slab, Parking Lvl Sub Grade], ISS09 [[Foundation & Grade Slab] | 0.30106 | 3 | [7 empty] | 0 | 0
ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | LoD 350 - Tower 9 ¦ Foundation and Grade Slab | 0.1306 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkisani | Hruthika Mylar |  |  | 0
ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | LoD 350 - Tower 9 ¦ Parking Level-Sub grade | 0.078362 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkisani | Hruthika Mylar |  |  | 0
ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | LoD 350 - ISS 9 ¦ Foundations & Grade Slab | 0.092092 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkisani | Hruthika Mylar |  |  | 0
OTR-Ph01 | Ph 1 |  |  | Package Release | 0.39 | 2 | [7 empty] | 0 | 0
OTR-Ph01 | Ph 1 | Architecture |  | Complete the project | 0.39 | 2 | [7 empty] | 0 | 0
OTR-Ph01 | Ph 1 | Architecture | Cijey M | LoD 350 - Villa Block ¦ Building Envelope + Plot Development | 0.3 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Akshara Rohit | Saurabh Bothra |  |  | 0
OTR-Ph01 | Ph 1 | Architecture | Cijey M | LoD 350 - Master Plan ¦ Master Plan | 0.09 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Akshara Rohit | Saurabh Bothra |  |  | 0
MeenaSai Res | MS Res |  |  | Package Release | 0.189 | 3 | [7 empty] | 0 | 0
MeenaSai Res | MS Res | Architecture |  | Complete LoD 300, LoD 350 Foundation and Structure | 0.189 | 2 | [7 empty] | 0 | 0
MeenaSai Res | MS Res | Architecture | Cijey M | LoD 200 - Schematic Concept | 0.063 | 1 | Cijey M | Niashinlulu | Syed Musharaff |  |  |  |  | 0
MeenaSai Res | MS Res | Architecture | Cijey M | LoD 300 - Pre Construction set | 0.042 | 1 | Cijey M | Niashinlulu | Syed Musharaff |  |  |  |  | 0
MeenaSai Res | MS Res | Architecture | Cijey M | LoD 350 - Foundation and Structure | 0.084 | 1 | Cijey M | Niashinlulu | Syed Musharaff |  |  |  |  | 0
NH Homestay | NH HS |  |  | Package Release | 0.77994 | 4 | [7 empty] | 0 | 0
NH Homestay | NH HS | Architecture |  | Complete the project | 0.77994 | 4 | [7 empty] | 0 | 0
NH Homestay | NH HS | Architecture | Cijey M | LoD 300 - Pre Construction set | 0.12999 | 1 | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira |  |  |  | 0
NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Foundation and Structure | 0.25998 | 1 | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira |  |  |  | 0
NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Building Envelope + Plot Development | 0.19498 | 1 | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira |  |  |  | 0
NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Interiors | 0.19498 | 1 | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira |  |  |  | 0
OTR Museum | OTR Mus |  |  | Package Release | 0.43996 | 2 | [7 empty] | 0 | 0
OTR Museum | OTR Mus | Architecture |  | Complete Schematic concept | 0.43996 | 2 | [7 empty] | 0 | 0
OTR Museum | OTR Mus | Architecture | Cijey M | LoD 100 - Design Brief | 0.17598 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
OTR Museum | OTR Mus | Architecture | Cijey M | LoD 200 - Schematic Concept | 0.26398 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
New Projects |  |  |  |  | 46.3253 | 15 | [7 empty] | 0 | 0
OTR-Ph02 | Ph 2 |  |  | Package Release | 1.18 | 3 | [7 empty] | 0 | 0
OTR-Ph02 | Ph 2 | Architecture |  | LoD 200 - Schematic Concept & Approvals | 1.18 | 3 | [7 empty] | 0 | 0
OTR-Ph02 | Ph 2 | Architecture | Cijey M | LoD 100 - Contract + Design Brief | 0.54 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
OTR-Ph02 | Ph 2 | Architecture | Cijey M | LoD 200 - Schematic Concept | 0.43 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
OTR-Ph02 | Ph 2 | Architecture | Cijey M | Approvals | 0.21 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a |  |  | Package Release | 8.7814 | 3 | [7 empty] | 0 | 0
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture |  | LoD 300 [Marketing and Sales, Pre Construction Set], LoD 350 [Experience Home + Project Experience] | 8.7814 | 3 | [7 empty] | 0 | 0
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | LoD 300 - Pre Construction Set | 4.3907 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkineni | Hruthika Mylar |  |  | 0
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | LoD 350 - Experience Home + Project Experience | 2.1953 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkineni | Hruthika Mylar |  |  | 0
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | LoD 300 - Marketing and Sales | 2.1953 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkineni | Hruthika Mylar |  |  | 0
Sarjapur Road [South Block-Resi] | Srjp - Res |  |  | Package Release | 20.5619 | 6 | [7 empty] | 0 | 0
Srjp - Res | Srjp - Res | Architecture |  | Complete LoD 300, Approvals & Experience Homes | 20.5619 | 6 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
Srjp - Res | Srjp - Res | Architecture | Cijey M | LoD 100 - Contract + Design Brief | 4.7746 | 1 | Cijey M | Theodora Rodrigues | Vidhi Kapadia | Nikita Potadar |  |  |  | 0
Srjp - Res | Srjp - Res | Architecture | Cijey M | LoD 200 - Schematic Concept | 4.364 | 1 | Cijey M | Theodora Rodrigues | Vidhi Kapadia | Nikita Potadar |  |  |  | 0
Srjp - Res | Srjp - Res | Architecture | Cijey M | LoD 200 - Approvals | 2.2847 | 1 | Cijey M | Theodora Rodrigues | Vidhi Kapadia | Nikita Potadar |  |  |  | 0
Srjp - Res | Srjp - Res | Architecture | Cijey M | LoD 200 - Marketing and Sales | 2.3873 | 1 | Cijey M | Theodora Rodrigues | Vidhi Kapadia | Nikita Potadar |  |  |  | 0
Srjp - Res | Srjp - Res | Architecture | Cijey M | LoD 350 - Experience Home + Project Experience | 2.3873 | 1 | Cijey M | Theodora Rodrigues | Vidhi Kapadia | Nikita Potadar |  |  |  | 0
Srjp - Res | Srjp - Res | Architecture | Cijey M | LoD 300 - Preconstruction | 4.364 | 1 | Cijey M | Theodora Rodrigues | Vidhi Kapadia | Nikita Potadar |  |  |  | 0
Vaderahalli | Vdrhl |  |  | Package Release | 15.8021 | 3 | [7 empty] | 0 | 0
Vaderahalli | Vdrhl-Res | Architecture |  | LoD 200 - Schematic Concept | 15.8021 | 3 | [7 empty] | 0 | 0
Vaderahalli | Vdrhl-Res | Architecture | Cijey M | LoD 100 - Contract + Design Brief | 6.321 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Syed Musharaff |  |  |  | 0
Vaderahalli | Vdrhl-Res | Architecture | Cijey M | LoD 200 - Schematic Concept | 6.321 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Syed Musharaff |  |  |  | 0
Vaderahalli | Vdrhl-Res | Architecture | Cijey M | Approvals | 3.16 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Syed Musharaff |  |  |  | 0

## Goals FY 26-27Q2 Saji (hidden)
FY 2026-27 Q2 ¦ Design Goals + Billing ¦ Saji A |  |  |  |  | 37.7999 | 63 | [7 empty] | 0 | 0 | 37.7999 | 63
Project | Phase | Discipline | Design Lead | Description | Plan - Billing [Cr.] | Plan - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | Actuals - Billing [Cr.] | Actuals - Pkgs | 0% | 0%
Ongoing Projects |  |  |  |  | 11.2305 | 43 | [7 empty] | 0 | 0
AtR | Ph 1, 2a, 2b, 2c |  |  | Package Release | 0.35762 | 3 | [7 empty] | 0 | 0
AtR | Ph 1, 2a, 2b, 2c | Architecture |  | Package Release [Complete LoD 350 ] | 0.35762 | 3 | [7 empty] | 0 | 0
AtR | Ph 1, 2a, 2b | Architecture | Saji A | LoD 350 - Clubhouse + Amenities - Clubhouse—Interiors and Facilities | 0.27 | 1 | Saji A | Ayesha | Shreelekha |  |  |  |  | 0
AtR | Ph 1, 2a, 2b | Architecture | Saji A | LoD 350 - Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] | 0.045377 | 1 | Saji A | Shreenivasa | Kishore |  |  |  |  | 0
AtR | Ph 2c | Architecture | Saji A | LoD 350 - Master Plan - Site MEP | 0.042238 | 1 | Saji A | Shreenivasa | Kishore |  |  |  |  | 0
AtR | Ph 3 |  |  | Package Release | 1.5631 | 15 | [7 empty] | 0 | 0
AtR | Ph 3 | Architecture |  | Package Release [Complete LoD 350] | 1.5631 | 15 | [7 empty] | 0 | 0
AtR | Ph 3 | Architecture | Saji A | LoD 300 - Pre Construction Set | 0.27398 | 1 | Saji A | Ayesha | Guruprasad | Kishore |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Home Products - V45 Default and it's variants | 0.36 | 1 | Saji A | Ayesha | Guruprasad | Aaron |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Home Products - V80 Default and it's variants | 0.36 | 1 | Saji A | Ayesha | Guruprasad | Aaron |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 33 - Foundations and Sub-Grade Structure | 0.043983 | 1 | Saji A | Ayesha | Kishore |  |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 34 - Foundations and Sub-Grade Structure | 0.043983 | 1 | Saji A | Ayesha | Shreelekha |  |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 29 - Foundations and Sub-Grade Structure | 0.065974 | 1 | Saji A | Ayesha | Guruprasad |  |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 29 - Building Envelope + Plot Development | 0.065974 | 1 | Saji A | Ayesha | Guruprasad |  |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 30 - Foundations and Sub-Grade Structure | 0.065974 | 1 | Saji A | Ayesha | Guruprasad |  |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 30 - Building Envelope + Plot Development | 0.065974 | 1 | Saji A | Ayesha | Guruprasad |  |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 31 - Building Envelope + Plot Development | 0.014661 | 1 | Saji A | Ayesha | Guruprasad |  |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 32 - Building Envelope + Plot Development | 0.029322 | 1 | Saji A | Ayesha | Shreelekha |  |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 33 - Building Envelope + Plot Development | 0.029322 | 1 | Saji A | Ayesha | Shreelekha |  |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 34 - Building Envelope + Plot Development | 0.043983 | 1 | Saji A | Ayesha | Shreelekha |  |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Master Plan - Master Plan | 0.05 | 1 | Saji A | Shreenivasa | Kishore |  |  |  |  | 0
AtR | Ph 3 | Architecture | Saji A | LoD 350 - Site Development - 02 Road Works | 0.05 | 1 | Saji A | Shreenivasa | Kishore |  |  |  |  | 0
PoaRR-Res | Res |  |  | Package Release | 3.3659 | 8 | [7 empty] | 0 | 0
PoaRR-Res | Res | Architecture |  | Complete the project | 3.3659 | 8 | [7 empty] | 0 | 0
PoaRR-Res | Res | Architecture | Saji A | LOD 350 Villa Cluster 3 - All Levels | 0.17 | 1 | Saji A | Gokul | Krishnapriya |  |  |  |  | 0
PoaRR-Res | Res | Architecture | Saji A | LOD 350 Villa Cluster 3 - Building Envelope and Common Areas | 0.17 | 1 | Saji A | Gokul | Krishnapriya |  |  |  |  | 0
PoaRR-Res | Res | Architecture | Saji A | LOD 350 V40 Default and it's variants | 1.18 | 1 | Saji A | Nirupama | [5 empty] | 0
PoaRR-Res | Res | Architecture | Saji A | LOD 350 ISS Building Envelope and Common Areas | 1.0659 | 1 | Saji A | Arshad | Latha |  |  |  |  | 0
PoaRR-Res | Res | Architecture | Saji A | LOD 350 Residential - Site Development | 0.45 | 1 | Saji A | Sathwik | [5 empty] | 0
PoaRR-Res | Res | Architecture | Saji A | LOD 350 Masterplan - Site MEP | 0.15 | 1 | Saji A | Sathwik | [5 empty] | 0
PoaRR-Res | Res | Architecture | Saji A | LOD 350 Masterplan - Landscaping | 0.15 | 1 | Saji A | Sathwik | [5 empty] | 0
PoaRR-Res | Res | Architecture | Saji A | LOD 350 Amenities & Facilities - Sporting Facilities | 0.03 | 1 | Saji A | Sathwik | Abdul |  |  |  |  | 0
PoaRR-T08 | T08 |  |  | Package Release | 5.9438 | 17 | [7 empty] | 0 | 0
PoaRR-T08 | T08 | Architecture |  | Package Release [Complete the project] | 5.9438 | 17 | [7 empty] | 0 | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 ISS - Foundations & Grade Slab | 0.2 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 ISS - Parking Level Subgrade | 0.41 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 ISS - Podium Slab | 0.61 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 ISS - Building Envelope and Common Areas | 0.82 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Habitable Level 01 | 0.48 | 1 | Saji A | Komal | Mononita |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Building Envelope and Common Areas [Typical Tower Levels] | 0.96385 | 1 | Saji A | Komal | Mononita |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 L22 Default and variants | 0.52 | 1 | Saji A | Mononita | Shahbazz |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 R25 Default [Modification for Dry Wall] | 0.52 | 1 | Saji A | Aardra
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 L20 Default [Modification for Dry Wall] | 0.52 | 1 | Saji A | Aardra | Komal |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 D35 Default [Modification for Dry Wall] | 0.52 | 1 | Saji A | Komal | Aardra |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Master Plan | 0.17 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Clubhouse—Interiors and Facilities | 0.02 | 1 | Saji A | Komal | Mononita |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Landscape | 0.03 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Site MEP | 0.03 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Clubhouse—Outdoor Spaces and Pool | 0.015 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Community spaces [Board Walk, Children play area] | 0.015 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Site Development | 0.1 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
New Projects |  |  |  |  | 24.365 | 2 | [7 empty] | 0 | 0
TR Mills | TR Mills | Architecture |  | LoD 100 - Contract + Design Brief | 5.965 | 1 | [7 empty] | 0 | 0
TR Mills | TR Mills | Architecture | Saji A | LoD 100 - Contract + Design Brief | 5.965 | 1 | Saji A | Simran | Arshad |  |  |  |  | 0
Varthur 52a | Varthur 52a |  |  | Package Release | 18.4 | 1 | [7 empty] | 0 | 0
Varthur 52a | Varthur 52a | Architecture |  | LoD 100 - Contract + Design Brief | 18.4 | 1 | [7 empty] | 0 | 0
Varthur 52a | Varthur 52a | Architecture | Saji A | LoD 100 - Contract + Design Brief | 18.4 | 1 | Saji A | Ayesha | [5 empty] | 0
Interior Design + Product Development |  |  |  |  | 2.2044 | 18 | [7 empty] | 0 | 0
Interior Design | ID |  |  | Package Release | 2.2044 | 18 | [7 empty] | 0 | 0
Personalised Customisation | PID | Interior Design |  |  | 2.2044 | 18 | [7 empty] | 0 | 0
Personalised Customisation | PID | Interior Design | Saji A | ATR , POARR | 2.2044 | 18 | [7 empty] | 0

## Goals FY 26-27Q2 OP (hidden)
| FY 2026-27 Q2 ¦ Design Goals + Billing ¦ Om Prakash |  |  |  |  | 15.9324 | 49 | [7 empty] | 0 | 0 | 15.9324 | 49
| Project | Phase | Discipline | Design Lead | Description | Plan - Billing [Cr.] | Plan - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | Actuals - Billing [Cr.] | Actuals - Pkgs | 0% | 0%
| Ongoing Projects |  |  |  |  | 8.387 | 24 | [7 empty] | 0 | 0
| TuiG | TuiG |  |  | Package Release | 1.5478 | 4 | [7 empty] | 0 | 0
| TuiG | TuiG | Architecture |  | Package Release [LoD 350 - CH structure & envelope, Interiors] | 1.5478 | 4 | [7 empty] | 0 | 0
| TuiG | TuiG | Architecture | Om Prakash | LoD 350 - Clubhouse—Structure and Envelope | 0.6191 | 1 | Om Prakash | Veeresh N | Ankita Macha | Lavanya |  |  |  | 0
| TuiG | TuiG | Architecture | Om Prakash | LoD 350 - Clubhouse—Interiors and Facilities | 0.6191 | 1 | Om Prakash | Veeresh N | Ankita Macha | Lavanya |  |  |  | 0
| TuiG | TuiG | Architecture | Om Prakash | LoD 350 - Sporting Facilities | 0.15478 | 1 | Om Prakash | Veeresh N | Ankita Macha | Lavanya |  |  |  | 0
| TuiG | TuiG | Architecture | Om Prakash | Clubhouse—Outdoor Spaces and Pool | 0.15478 | 1 | Om Prakash | Veeresh N | Ankita Macha | Lavanya |  |  |  | 0
| DBTW | DBTW |  |  | Package Release | 5.7306 | 11 | [7 empty] | 0 | 0
| DBTW | DBTW | Architecture |  | Complete the project | 5.7306 | 11 | [7 empty] | 0 | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site Development | 0.073717 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
` | DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site MEP | 0.073717 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Landscaping | 0.073717 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Tower 06 - Foundation and Grade Slab | 0.064032 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Foundations & Grade Slab | 0.54995 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Podium Slab | 0.27497 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I20 Default and it's variants | 2.2352 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I25 Default and it's variants | 2.2352 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - L21 Default and it's variants |  | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Structure and Envelope | 0.1125 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Outdoor Spaces and Pool | 0.0375 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| SftW | SftW |  |  | Package Release | 0.72824 | 7 | [7 empty] | 0 | 0
| SftW | SftW | Architecture |  | Complete LoD 350 [Podium, Clubhouse & Masterplan] by 26'Q2 | 0.72824 | 7 | [7 empty] | 0 | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - ISS 01 - Podium Slab | 0.25575 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Clubhouse: Structure and Envelope | 0.081564 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Master Plan: Master Plan | 0.18697 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Clubhouse: Outdoor Spaces and Pool | 0.027188 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Master Plan: Site Development | 0.11218 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Master Plan: Site MEP | 0.037394 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Master Plan: Landscaping |  |  | Om Prakash
| SftW | SftW | Architecture | Om Prakash | LoD 350: Clubhouse + Amenities - Sporting Facilities | 0.027188 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Tower 02: Terrace Level |  |  | Om Prakash
| LGCE Campus | LGCE Campus |  |  | Package Release | 0.38042 | 2 | [7 empty] | 0 | 0
| LGCE Campus | LGCE Campus | Architecture |  | Complete LoD 200 by 26'Q2 | 0.38042 | 2 | [7 empty] | 0 | 0
| LGCE Campus | LGCE Campus | Architecture | Om Prakash | LoD 100 - Design Brief | 0.15217 | 1 | Om Prakash | Veeresh N | Ankita Macha |  |  |  |  | 0
| LGCE Campus | LGCE Campus | Architecture | Om Prakash | LoD 200 - Schematic Concept | 0.22825 | 1 | Om Prakash | Veeresh N | Ankita Macha |  |  |  |  | 0
| New Projects |  |  |  |  | 7.5454 | 22 | [7 empty] | 0 | 0
| Nava Raipur | Nava Raipur |  |  | Package Release | 0 | 3 | [7 empty] | 0 | 0
| Nava Raipur | Nava Raipur | Architecture |  | LoD 200 - Schematic Concept & Approvals | 0 | 3 | [7 empty] | 0 | 0
| Nava Raipur | Nava Raipur | Architecture | Om Prakash | LoD 100 - Contract + Design Brief |  | 1 | Om Prakash | Sreeja P | [5 empty] | 0
| Nava Raipur | Nava Raipur | Architecture | Om Prakash | LoD 200 - Schematic Concept |  | 1 | Om Prakash | Sreeja P | [5 empty] | 0
| Nava Raipur | Nava Raipur | Architecture | Om Prakash | LoD 300 - Pre Construction |  |  | Om Prakash | Sreeja P
| Nava Raipur | Nava Raipur | Architecture | Om Prakash | Approvals |  | 1 | Om Prakash | Sreeja P | [5 empty] | 0
| OTR-Ph02 | Ph 2 |  |  | Package Release | 0.17 | 2 | [7 empty] | 0 | 0
| OTR-Ph02 | Ph 2 | Architecture |  | LoD 200 - Schematic Concept & Approvals | 0.17 | 2 | [7 empty] | 0 | 0
| OTR-Ph02 | Ph 2 | Architecture | Om Prakash | LoD 200 - Schematic Concept - CH | 0.11 | 1 | Om Prakash | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Approvals - CH | 0.06 | 1 | Om Prakash | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
| TMFT-Ph 3 | Ph 3 |  |  | Package Release | 0.6182 | 3 | [7 empty] | 0 | 0
| TMFT-Ph 3 | Ph 3 | Architecture |  | LoD 200 - Schematic Concept, Approvals | 0.6182 | 3 | [7 empty] | 0 | 0
| TMFT-Ph 3 | Ph 3 | Architecture | Om Prakash | LoD 100 - Contract + Design Brief | 0.24728 | 1 | Om Prakash | Aparna | [5 empty] | 0
| TMFT-Ph 3 | Ph 3 | Architecture | Om Prakash | LoD 200 - Schematic Concept | 0.24728 | 1 | Om Prakash | Aparna | [5 empty] | 0
| TMFT-Ph 3 | Ph 3 | Architecture | Om Prakash | Approvals | 0.12364 | 1 | Om Prakash | Aparna | [5 empty] | 0
| Sarjapur Road [South Block-Resi] | Srjp - Res |  |  | Package Release | 0.92385 | 3 | [7 empty] | 0 | 0
| Srjp - Res | Srjp - Res | Architecture |  | Complete LoD 300, Approvals & Experience Homes | 0.92385 | 3 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
| Srjp - Res | Srjp - Res | Architecture | Om Prakash | LoD 200 - CH: Schematic Concept | 0.4106 | 1 | Om Prakash | [6 empty] | 0
| Srjp - Res | Srjp - Res | Architecture | Om Prakash | LoD 200 - CH: Approvals | 0.10265 | 1 | Om Prakash | [6 empty] | 0
| Srjp - Res | Srjp - Res | Architecture | Om Prakash | LoD 300 - CH: Preconstruction | 0.4106 | 1 | Om Prakash | [6 empty] | 0
| OTF | OTF |  |  | Package Release | 0.285 | 3 | [7 empty] | 0 | 0
| OTF | OTF | Architecture |  | LoD 300 - Pre Construction set - CH | 0.285 | 3 | [7 empty] | 0 | 0
| OTF | OTF | Architecture | Om Prakash | LoD 200 - Schematic Concept - CH | 0.095 | 1 | Om Prakash | Aparna S | [5 empty] | 0
| OTF | OTF | Architecture | Om Prakash | Approvals - CH | 0.095 | 1 | Om Prakash | Aparna S | [5 empty] | 0
| OTF | OTF | Architecture | Om Prakash | LoD 300 - Pre Construction set - CH | 0.095 | 1 | Om Prakash | Aparna S | [5 empty] | 0
| Harohalli [Plotted] | Harohalli |  |  | Package Release | 0.305 | 1 | [7 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | Architecture |  | [LOD 200 - Schematic] | 0.305 | 1 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | Architecture | Om Prakash | LoD 200 - Schematic Concept | 0.305 | 1 | Om Prakash | [6 empty] | 0
| Shreegaon [61.6a] | Ph 1 |  |  | Package Release | 2.835 | 4 | [7 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Architecture |  | Package Release [LoD 200 - Schematic Concept] | 2.835 | 4 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Architecture | Om Prakash | LoD 200 - Schematic Concept | 0.945 | 1 | Om Prakash | [6 empty] | 0
| Shreegaon [61.6a] | Ph 1 | Architecture | Om Prakash | LoD 300 - Pre Construction Set | 0.945 | 1 | Om Prakash | [5 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Architecture | Om Prakash | Project Experience | 0.4725 | 1 | Om Prakash | [5 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Architecture | Om Prakash | Marketing and Sales | 0.4725 | 1 | Om Prakash | [5 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 |  |  | Package Release | 0.5371 | 2 | [7 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Architecture |  | Package Release [till LoD 200 - Approvals] | 0.5371 | 2 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Architecture | Om Prakash | LoD 200 - Schematic Concept | 0.26855 | 1 | Om Prakash | [6 empty] | 0
| Violet Hill [21.76a] | Ph 1 | Architecture | Om Prakash | LoD 200 - Approvals | 0.26855 | 1 | Om Prakash | [6 empty] | 0
| Byatarayanpura [behind Mall of Asia] | Byatarayanpura |  |  | Package Release | 1.6141 | 1 | [7 empty] | 0 | 0
| Byatarayanpura [behind Mall of Asia] | Byatarayanpura | Architecture |  | LoD 100 - Contract + Design Brief | 1.6141 | 1 | [7 empty] | 0 | 0
| Byatarayanpura [behind Mall of Asia] | Byatarayanpura | Architecture | Om Prakash | LoD 100 - Contract + Design Brief | 1.6141 | 1 | Om Prakash | Om Prakash | Sreeja | Sinchana |  |  |  | 0
| Blue in Green | BiG |  |  | Package Release | 0.25713 | 3 | [7 empty] | 0 | 0
| Blue in Green | BiG | Architecture |  | LoD 300 - Pre Construction Set | 0.25713 | 3 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
| Blue in Green | BiG | Architecture | Om Prakash | LoD 200 - Schematic Concept - CH | 0.10475 | 1 | Om Prakash | [6 empty] | 0
| Blue in Green | BiG | Architecture | Om Prakash | Approvals - CH | 0.052375 | 1 | Om Prakash | [6 empty] | 0
| Blue in Green | BiG | Architecture | Om Prakash | LoD 300 - Pre Construction set - CH | 0.1 | 1 | Om Prakash | [6 empty] | 0

## Goals FY 26-27Q2 Naveen Y (hidden)
FY 2026-27 Q2 ¦ Design Goals + Billing ¦ Naveen Y |  |  |  |  | 40.8495 | 31 | [7 empty] | 0 | 0 | 40.8495 | 31
Project | Phase | Discipline | Design Lead | Description | Plan - Billing [Cr.] | Plan - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | Actuals - Billing [Cr.] | Actuals - Pkgs | 0% | 0%
Ongoing Projects |  |  |  |  | 0.36421 | 3 | [7 empty] | 0 | 0
AtR - C | Com |  |  | Package Release | 0.36421 | 3 | [7 empty] | 0 | 0
AtR - C | Com | Architecture |  | Package Release [Complete LoD 350 ] | 0.36421 | 3 | [7 empty] | 0 | 0
AtR - C | Com | Architecture | Naveen Y | LoD 350 - Master Plan - Site Development | 0.13658 | 1 | Naveen Y | Naveen KL | Vasudha C |  |  |  |  | 0
AtR - C | Com | Architecture | Naveen Y | LoD 350 - Master Plan - Site MEP | 0.18211 | 1 | Naveen Y | Naveen KL | Sathvika D |  |  |  |  | 0
AtR - C | Com | Architecture | Naveen Y | LoD 350 - Master Plan - Landscaping | 0.045527 | 1 | Naveen Y | Naveen KL | Arshad |  |  |  |  | 0
New Projects |  |  |  |  | 40.4853 | 28 | [7 empty] | 0 | 0
Sarjapur - C (South Block) | Srjp - C - SB |  |  | Package Release | 16.5797 | 5 | [7 empty] | 0 | 0
Srjp - C - SB | Srjp - C - SB | Architecture |  | Complete LoD 300, Approvals, Marketing & Sales | 16.5797 | 5 | [7 empty] | 0 | 0
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | LoD 100 - Contract + Design Brief | 3.6844 | 1 | Naveen Y | Naveen Y | Swathi S |  |  |  |  | 0
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | LoD 200 - Schematic Concept | 3.6844 | 1 | Naveen Y | Naveen Y | Swathi S |  |  |  |  | 0
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | LoD 200 - Approvals | 3.6844 | 1 | Naveen Y | Akhila G | Swathi S | Shadha |  |  |  | 0
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | LoD 200 - Marketing and Sales | 1.8422 | 1 | Naveen Y | Akhila G | Swathi S | Shadha |  |  |  | 0
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | LoD 300 - Preconstruction | 3.6844 | 1 | Naveen Y | Naveen Y | Swathi S |  |  |  |  | 0
Sarjapur - C (North Block) | Srjp - C - NB |  |  | Package Release | 5.5266 | 5 | [7 empty] | 0 | 0
Srjp - C - NB | Srjp - C - NB | Architecture |  | Complete LoD 300, Approvals, Marketing & Sales | 5.5266 | 5 | [7 empty] | 0 | 0
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | LoD 100 - Contract + Design Brief | 1.2281 | 1 | Naveen Y | Naveen Y | Fathima S |  |  |  |  | 0
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | LoD 200 - Schematic Concept | 1.2281 | 1 | Naveen Y | Naveen Y | Fathima S |  |  |  |  | 0
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | LoD 200 - Approvals | 1.2281 | 1 | Naveen Y | Akhila G | Fathima S | Nanditha S |  |  |  | 0
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | LoD 200 - Marketing and Sales | 0.61406 | 1 | Naveen Y | Akhila G | Fathima S | Nanditha S |  |  |  | 0
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | LoD 300 - Preconstruction | 1.2281 | 1 | Naveen Y | Naveen Y | Fathima S |  |  |  |  | 0
OTF | OTF |  |  | Package Release | 3.3325 | 7 | [7 empty] | 0 | 0
OTF | OTF | Master Planning |  | LOD 350 - MP Pkg 1, Project Entrance | 3.3325 | 7 | [7 empty] | 0 | 0
OTF | OTF | Master Planning | Naveen Y | LoD 100 - Contract + Design Brief [Commercial] | 0.3375 | 1 | Naveen Y | Naveen Y | Aswin J |  |  |  |  | 0
OTF | OTF | Master Planning | Naveen Y | LoD 200 - Schematic Concept | 0.58 | 1 | Naveen Y | Naveen Y | Aswin J |  |  |  |  | 0
OTF | OTF | Master Planning | Naveen Y | Approvals | 0.58 | 1 | Naveen Y | Aswin J | Mithoon |  |  |  |  | 0
OTF | OTF | Master Planning | Naveen Y | LoD 300 - Pre Construction Set | 0.58 | 1 | Naveen Y | Aswin J | Mithoon |  |  |  |  | 0
OTF | OTF | Master Planning | Naveen Y | LoD 200 - Marketing and Sales | 0.3375 | 1 | Naveen Y | Aswin J | Mithoon |  |  |  |  | 0
OTF | OTF | Master Planning | Naveen Y | LoD 350 - Project Entrance | 0.3375 | 1 | Naveen Y | Aswin J | Mithoon |  |  |  |  | 0
OTF | OTF | Master Planning | Naveen Y | LoD 350 - Infra - Grading | 0.58 | 1 | Naveen Y | Aswin J | [5 empty] | 0
KIADB - Mys | KIADB - Mys |  |  | Package Release | 0 | 3 | [7 empty] | 0 | 0
KIADB - Mys | KIADB - Mys | Master Planning |  | Complete the project by Q4 | 0 | 3 | [7 empty] | 0 | 0
KIADB - Mys | KIADB - Mys | Architecture | Naveen Y | LoD 100 - Contract + Design Brief |  | 1 | Naveen Y | Swathi | Manali
KIADB - Mys | KIADB - Mys | Architecture | Naveen Y | LoD 200 - Schematic Concept |  | 1 | Naveen Y | Swathi | Manali
KIADB - Mys | KIADB - Mys | Architecture | Naveen Y | Approvals |  | 1 | Naveen Y | Swathi | Manali
Imagine Campus | Imgn |  |  | Package Release | 1.15 | 2 | [7 empty] | 0 | 0
Imagine Campus | Imgn | Architecture |  | Package Release [Complete LoD 100, 200] | 1.15 | 2 | [7 empty] | 0 | 0
Imagine Campus | Imgn | Architecture | Naveen Y | LoD 200 - Schematic Concept | 0.69 | 1 | Naveen Y | Akhila G | Fathima S |  |  |  |  | 0
Imagine Campus | Imgn | Architecture | Naveen Y | Approvals | 0.46 | 1 | Naveen Y | Akhila G | Fathima S |  |  |  |  | 0
Blue in Green | BiG |  |  | Package Release | 8.2775 | 3 | [7 empty] | 0 | 0
Blue in Green | BiG | Architecture |  | LoD 300 - Pre Construction Set | 8.2775 | 3 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
Blue in Green | BiG | Architecture | Naveen Y | LoD 200 - Schematic Concept .v7 [Rework] | 3.3117 | 1 | Naveen Y | Naveen KL | Aswin J |  |  |  |  | 0
Blue in Green | BiG | Architecture | Naveen Y | Approvals | 1.6558 | 1 | Naveen Y | Naveen KL | Aswin J |  |  |  |  | 0
Blue in Green | BiG | Architecture | Naveen Y | LoD 300 - Pre Construction Set | 3.31 | 1 | Naveen Y | Naveen KL | Aswin J |  |  |  |  | 0
Vaderahalli | Vdrhl |  |  | Package Release | 5.619 | 3 | [7 empty] | 0 | 0
Vaderahalli | Vdrhl-Cmrcl | Architecture |  | LoD 200 - Schematic Concept | 5.619 | 3 | [7 empty] | 0 | 0
Vaderahalli | Vdrhl-Cmrcl | Architecture | Naveen Y | LoD 100 - Contract + Design Brief | 1.4045 | 1 | Naveen Y | [6 empty] | 0
Vaderahalli | Vdrhl-Cmrcl | Architecture | Naveen Y | LoD 200 - Schematic Concept | 1.4045 | 1 | Naveen Y | [6 empty] | 0
Vaderahalli | Vdrhl-Cmrcl | Architecture | Naveen Y | Approvals | 2.81 | 1 | Naveen Y | [6 empty] | 0

## Goals FY 26-27Q2 Manik (hidden)
FY 2026-27 Q2 ¦ Design Goals + Billing ¦ Manik G |  |  |  |  | 1.4243 | 20 | [7 empty] | 0 | 0 | 1.4243 | 20
Project | Phase | Discipline | Design Lead | Description | Plan - Billing [Cr.] | Plan - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | Actuals - Billing [Cr.] | Actuals - Pkgs | 0% | 0%
Ongoing Projects |  |  |  |  | 1.2708 | 17 | [7 empty] | 0 | 0
MT Plano | MT Plano |  |  | Package Release | 1.2668 | 13 | [7 empty] | 0 | 0
MT Plano | MT Plano | Architecture |  | Complete LoD 350 - Foundation and Structure by 26'Q2 | 1.0157 | 5 | [7 empty] | 0 | 0
MT Plano | MT Plano | Architecture | Manik G | LoD 100 - Design Brief | 0.15626 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | Architecture | Manik G | LoD 200 - Schematic Concept | 0.23439 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | Architecture | Manik G | LoD 200 - Approvals | 0.15626 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | Architecture | Manik G | LoD 300 - Pre Construction set | 0.15626 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | Architecture | Manik G | LoD 350 - Foundation and Structure | 0.31251 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | Structural |  | Complete LoD 300 by 26'Q2 | 0.14286 | 2 | [7 empty] | 0 | 0
MT Plano | MT Plano | Structural | Manik G | LoD 200 - Schematic Concept | 0.071432 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | Structural | Manik G | LoD 300 - Pre Construction set | 0.071432 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | MEP |  | Complete LoD 300 by 26'Q2 | 0.060271 | 3 | [7 empty] | 0 | 0
MT Plano | MT Plano | MEP | Manik G | LoD 200 - Schematic Concept | 0.02009 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | MEP | Manik G | LoD 200 - Approvals | 0.02009 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | MEP | Manik G | LoD 300 - Pre Construction set | 0.02009 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | Landscape |  | Complete LoD 300 by 26'Q2 | 0.047993 | 3 | [7 empty] | 0 | 0
MT Plano | MT Plano | Landscape | Manik G | LoD 200 - Schematic Concept | 0.016742 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | Landscape | Manik G | LoD 200 - Approvals | 0.02009 | 1 | Manik G | [6 empty] | 0
MT Plano | MT Plano | Landscape | Manik G | LoD 300 - Pre Construction set | 0.011161 | 1 | Manik G | [6 empty] | 0
Indiranagar Res | Indrng Res |  |  | Package Release | 0.004 | 4 | [7 empty] | 0 | 0
Indiranagar Res | Indrng Res | Architecture |  | Complete the project [Complete LoD 350 ] | 0.004 | 4 | [7 empty] | 0 | 0
Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block A - Interiors | 0.0021 | 1 | Manik G | [6 empty] | 0
Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block B - Interiors | 0.000875 | 1 | Manik G | [6 empty] | 0
Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block C - Interiors | 0.000525 | 1 | Manik G | [6 empty] | 0
Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 -Block C - Building Envelope + Plot Development | 0.0005 | 1 | Manik G | [6 empty] | 0
New Projects |  |  |  |  | 0.15346 | 3 | [7 empty] | 0 | 0
OtR OOTA | OTR OOTA |  |  | Package Release | 0.15346 | 3 | [7 empty] | 0 | 0
OTR OOTA | OTR OOTA | Architecture |  | Complete Approvals | 0.15346 | 3 | [7 empty] | 0 | 0
OTR OOTA | OTR OOTA | Architecture | Manik G | Lod100 - Design Brief | 0.043845 | 1 | Manik G | [6 empty] | 0
OTR OOTA | OTR OOTA | Architecture | Manik G | LoD 200 - Schematic Concept | 0.065768 | 1 | Manik G | [6 empty] | 0
OTR OOTA | OTR OOTA | Architecture | Manik G | Approvals | 0.043845 | 1 | Manik G | [6 empty] | 0

## Goals FY 26-27Q2 Gagan (hidden)
| FY 2026-27 Q2 ¦ Design Goals + Billing ¦ Gaganjit S |  |  |  |  | 23.7604 | 153 | [7 empty] | 0 | 0 | 23.7604 | 153
| Project | Phase | Discipline | Design Lead | Description | Plan - Billing [Cr.] | Plan - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | Actuals - Billing [Cr.] | Actuals - Pkgs | 0% | 0%
| Ongoing Projects |  |  |  |  | 2.3618 | 52 | [7 empty] | 0 | 0
| AtR | Ph 1, 2a, 2b, 2c |  |  | Package Release | 0.014337 | 1 | [7 empty] | 0 | 0
| AtR | Ph 1, 2a, 2b, 2c | MEP |  | Package Release [Complete LoD 350 ] | 0.014337 | 1 | [7 empty] | 0 | 0
| AtR | Ph 2c | MEP | Gagan | LoD 350 - Master Plan - Site MEP | 0.014337 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Deepu Shreedhar Mahadev |  |  |  | 0
| AtR | Ph 3 |  |  | Package Release | 0.37131 | 8 | [7 empty] | 0 | 0
| AtR | Ph 3 | MEP |  | Package Release [Complete LoD 350 ] | 0.27705 | 6 | [7 empty] | 0 | 0
| AtR | Ph 3 | MEP | Gagan | LoD 300 - Preconstruction Set | 0.0215 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| AtR | Ph 3 | MEP | Gagan | LoD 350 - Villa Block 33 - Foundations and Sub-Grade Structure | 0.0028274 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| AtR | Ph 3 | MEP | Gagan | LoD 350 - Villa Block 34 - Foundations and Sub-Grade Structure | 0.0028274 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| AtR | Ph 3 | MEP | Gagan | LoD 350 - Home Products - V45 Default and it's variants | 0.10495 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| AtR | Ph 3 | MEP | Gagan | LoD 350 - Home Products - V80 Default and it's variants | 0.10495 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| AtR | Ph 3 | MEP | Gagan | LoD 350 - Master Plan - Master Plan | 0.04 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| AtR | Ph 3 | Landscape |  | Package Release [Complete LoD 350 ] | 0.094268 | 2 | [7 empty] | 0 | 0
| AtR | Ph 3 | Landscape | Gagan | LoD 300 - Preconstruction Set | 0.047864 | 1 | Gagan | Lajja | Anisha | Chetan Anupa |  |  |  | 0
| AtR | Ph 3 | Landscape | Gagan | LoD 350 - Home Products - V45 Default | 0.046405 | 1 | Gagan | Lajja | Anisha | Chetan Anupa |  |  |  | 0
| AtR | Ph 3 | Landscape | Gagan | LoD 350 - Home Products - V80 Default and it's variants | 0.046405 | 1 | Gagan | Lajja | Anisha | Chetan Anupa |  |  |  | 0
| AtR - C | Com |  |  | Package Release | 0.16751 | 2 | [7 empty] | 0 | 0
| AtR - C | Com | MEP |  | Package Release [Complete LoD 350 ] | 0.16751 | 2 | [7 empty] | 0 | 0
| AtR - C | Com | MEP | Gagan | LoD 350 - Master Plan - Master Plan | 0.038655 | 1 | Gagan | Salomi | Eranna Praveen | Avinash Deepu |  |  |  | 0
| AtR - C | Com | MEP | Gagan | LoD 350 - Master Plan - Site MEP | 0.12885 | 1 | Gagan | Salomi | Eranna Praveen | Avinash Deepu |  |  |  | 0
| TMD Ph2 | Ph 2 |  |  | Package Release | 0 | 0 | [7 empty] | 0 | 0
| TMD Ph2 | Ph 2 |  |  | LoD 350 - Childern play area | 0 | 0 | [7 empty] | 0 | 0
Play equipment selection pending
| PoaRR-Res | Res |  |  | Package Release | 0.40109 | 3 | [7 empty] | 0 | 0
| PoaRR-Res | Res | MEP |  | Complete the project | 0.36109 | 2 | [7 empty] | 0 | 0
| PoaRR-Res | Res | MEP | Gagan | LOD 350 Site MEP | 0.36 | 1 | Gagan | Salomi | Hareesha Praveen | Byahattimath Shreedhar Mahadev Deepu Ajay |  |  |  | 0
| PoaRR-Res | Res | MEP | Gagan | LOD 350 Sporting Facilities | 0.0010915 | 1 | Gagan | Salomi | Hareesha Praveen | Byahattimath Shreedhar Mahadev Deepu Ajay |  |  |  | 0
| PoaRR-Res | Res | Landscape |  | Complete the project | 0.04 | 1 | [7 empty] | 0 | 0
| PoaRR-Res | Res | Landscape | Gagan | LOD 350 Amenities & Facilities - Community spaces [Sporting Facilities] | 0.04 | 1 | Gagan | Lajja | Apoorva |  |  |  |  | 0
| PoaRR-T08 | T08 |  |  | Package Release | 0.86444 | 13 | [7 empty] | 0 | 0
| PoaRR-T08 | T08 | MEP |  | Package Release [Complete the project] | 0.65548 | 9 | [7 empty] | 0 | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 Penthouse Levels | 0.08574 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 Terrace Level | 0.08574 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 L20 Default and it's variants | 0.06 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 D35 Default and it's variants | 0.06 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 Clubhouse—Interiors and Facilities | 0.004 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 Master Plan | 0.04 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 Site MEP | 0.12 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 L22 Default and It's Variants | 0.1 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 R25P Default and It's Variants | 0.1 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | Landscape |  | Package Release [Complete the project] | 0.20896 | 4 | [7 empty] | 0 | 0
| PoaRR-T08 | T08 | Landscape | Gagan | LOD 350 T08-Clubhouse—Interiors and Facilities | 0.02 | 1 | Gagan | Lajja | Apoorva |  |  |  |  | 0
| PoaRR-T08 | T08 | Landscape | Gagan | LOD 350 T08-Clubhouse—Outdoor Spaces and Pool | 0.03896 | 1 | Gagan | Lajja | [5 empty] | 0
| PoaRR-T08 | T08 | Landscape | Gagan | LOD 350 T08-Community spaces [Board Walk, Children play area] | 0.05 | 1 | Gagan | Lajja | [5 empty] | 0
| PoaRR-T08 | T08 | Landscape | Gagan | LOD 350 R25P Default and It's Variants | 0.1 | 1 | Gagan | Lajja | Apoorva |  |  |  |  | 0
| ITQE-Ph1 | Ph 1 |  |  | Package Release | 0 | 0 |  |  | Aishwarya Hegde | Sheethal Prabhu | Anand Thoppil |  |  | 0 | 0
| ITQE-Ph1 | Ph 1 | Landscape |  |  | 0 | 0 | [7 empty] | 0 | 0
| ITQE-Ph1 | Ph 1 | Landscape | Gagan | Tree Avenue details, Play equipment selection pending
| ITQE-Ph2b | Ph 2b |  |  | Package Release | 0.02 | 1 | [7 empty] | 0 | 0
| ITQE-Ph2b | Ph 2b | MEP |  | Complete the project | 0.02 | 1 | [7 empty] | 0 | 0
| ITQE-Ph2b | Ph 2b | MEP | Gagan | LoD 350 - Master Plan ¦ Site MEP | 0.02 | 1 | Gagan | Salomi | Antony |  | Harshitha |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c |  |  | Package Release | 0.067123 | 3 | [7 empty] | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP |  | LoD 350 - T09 [Foundation & Grade Slab], ISS09 [[Foundation & Grade Slab] | 0.067123 | 3 | [7 empty] | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP | Gagan | LoD 350 - Tower 9 ¦ Foundation and Grade Slab | 0.030822 | 1 | Gagan | Salomi | Hareesha Bhavya | Byahattimath Matsarambabu Prem |  |  |  | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP | Gagan | LoD 350 - Tower 9 ¦ Parking Level-Sub grade | 0.02 | 1 | Gagan | Salomi | Hareesha Bhavya | Byahattimath Matsarambabu Prem |  |  |  | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP | Gagan | LoD 350 - ISS 9 ¦ Foundations & Grade Slab | 0.0163 | 1 | Gagan | Salomi | Hareesha Bhavya | Byahattimath Matsarambabu Prem |  |  |  | 0
| OTR-Ph01 | Ph 1 |  |  | Package Release | 0.04 | 1 | [7 empty] | 0 | 0
| OTR-Ph01 | Ph 1 | MEP |  | Complete the project | 0.04 | 1 | [7 empty] | 0 | 0
| OTR-Ph01 | Ph 1 | MEP | Gagan | LoD 350 - Master Plan ¦ Site MEP | 0.04 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| DBTW | DBTW | MEP |  | Complete the project | 0.036853 | 1 | [7 empty] | 0 | 0
| DBTW | DBTW | MEP | Gagan | LoD 350 - Master Plan- Master Plan | 0.036853 | 1 | Gagan | Salomi | Bhavya Hareesha | Viresh Matsarambabu Byahattimath Hanumanthraya |  |  |  | 0
| SftW | SftW |  |  | Package Release | 0.021398 | 2 | [7 empty] | 0 | 0
| SftW | SftW | MEP |  | Complete LoD 350 [Clubhouse & Masterplan] by 26'Q2 | 0.021398 | 2 | [7 empty] | 0 | 0
| SftW | SftW | MEP | Gagan | LoD 350 - Master Plan: Site MEP | 0.020843 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Antoney Shreedhar |  |  |  | 0
| SftW | SftW | MEP | Gagan | LoD 350: Clubhouse + Amenities - Sporting Facilities | 0.00055534 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Antoney Shreedhar |  |  |  | 0
| LGCE Campus | LGCE Campus |  |  | Package Release | 0.03302 | 2 | [7 empty] | 0 | 0
| LGCE Campus | LGCE Campus | MEP |  | Complete LoD 200 by 26'Q2 | 0.017956 | 1 | [7 empty] | 0 | 0
| LGCE Campus | LGCE Campus | MEP | Gagan | LoD 200 - Schematic Concept | 0.017956 | 1 | Gagan | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0
| LGCE Campus | LGCE Campus | Landscape |  | Complete LoD 200 by 26'Q2 | 0.015065 | 1 | [7 empty] | 0 | 0
| LGCE Campus | LGCE Campus | Landscape | Gagan | LoD 200 - Schematic Concept | 0.015065 | 1 | Gagan | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0
| MeenaSai Res | MS Res |  |  | Package Release | 0.0417 | 5 | [7 empty] | 0 | 0
| MeenaSai Res | MS Res | MEP |  | Complete LoD 300, LoD 350 Foundation and Structure | 0.0297 | 2 | [7 empty] | 0 | 0
| MeenaSai Res | MS Res | MEP | Gagan | LoD 200 - Schematic Concept | 0.0054 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sampath Mahadev |  |  |  | 0
| MeenaSai Res | MS Res | MEP | Gagan | LoD 300 - Pre Construction set | 0.0054 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sampath Mahadev |  |  |  | 0
| MeenaSai Res | MS Res | MEP | Gagan | LoD 350 - Foundation and Structure | 0.0189 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sampath Mahadev |  |  |  | 0
| MeenaSai Res | MS Res | Landscape |  | Complete LoD 300 | 0.012 | 2 | [7 empty] | 0 | 0
| MeenaSai Res | MS Res | Landscape | Gagan | LoD 200 - Schematic Concept | 0.006 | 1 | Gagan | Lajja | Anisha |  |  |  |  | 0
| MeenaSai Res | MS Res | Landscape | Gagan | LoD 300 - Pre Construction set | 0.006 | 1 | Gagan | Lajja | Anisha |  |  |  |  | 0
| NH Homestay | NH HS |  |  | Package Release | 0.19499 | 6 | [7 empty] | 0 | 0
| NH Homestay | NH HS | MEP |  | Complete the project | 0.12535 | 4 | [7 empty] | 0 | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 300 - Pre Construction set | 0.016713 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu |  |  |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Foundation and Structure | 0.058495 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu |  |  |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Building Envelope + Plot Development | 0.025069 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu |  |  |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Interiors | 0.025069 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu |  |  |  | 0
| NH Homestay | NH HS | Landscape |  | Complete the project | 0.069638 | 2 | [7 empty] | 0 | 0
| NH Homestay | NH HS | Landscape | Gagan | LoD 300 - Pre Construction set | 0.01857 | 1 | Gagan | Lajja | Anisha | Chetan |  |  |  | 0
| NH Homestay | NH HS | Landscape | Gagan | LoD 350 - Building Envelope + Plot Development | 0.051068 | 1 | Gagan | Lajja | Anisha | Chetan |  |  |  | 0
| Indiranagar Res | Indrng Res |  |  | Package Release | 0.000113 | 1 | [7 empty] | 0 | 0
| Indiranagar Res | Indrng Res | Landscape |  | Complete the project [Complete LoD 350 ] | 0.000113 | 1 | [7 empty] | 0 | 0
| Indiranagar Res | Indrng Res | Landscape | Gagan | LoD 350 - Block C- Building Envelope + Plot Development | 0.000113 | 1 | Gagan | Lajja | Chetan |  |  |  |  | 0
| OTR Museum | OTR Mus |  |  | Package Release | 0.041482 | 2 | [7 empty] | 0 | 0
| OTR Museum | OTR Mus | MEP |  | Complete Schematic concept | 0.022627 | 1 | [7 empty] | 0 | 0
| OTR Museum | OTR Mus | MEP | Gagan | LoD 200 - Schematic Concept | 0.022627 | 1 | Gagan | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0
| OTR Museum | OTR Mus | Landscape |  | Complete Schematic concept | 0.018855 | 1 | [7 empty] | 0 | 0
| OTR Museum | OTR Mus | Landscape | Gagan | LoD 200 - Schematic Concept | 0.018855 | 1 | Gagan | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0
| New Projects |  |  |  |  | 21.3986 | 97 | [7 empty] | 0 | 0
| Nava Raipur | Nava Raipur |  |  | Package Release | 0 | 3 | [7 empty] | 0 | 0
| Nava Raipur | Nava Raipur | MEP |  | LoD 200 - Schematic Concept & Approvals | 0 | 2 | [7 empty] | 0 | 0
| Nava Raipur | Nava Raipur | MEP | Gagan | LoD 200 - Schematic Concept |  | 1 | Gagan | Salomi | [5 empty] | 0
| Nava Raipur | Nava Raipur | MEP | Gagan | LoD 300 - Pre Construction |  |  | Gagan | Salomi
| Nava Raipur | Nava Raipur | MEP | Gagan | Approvals |  | 1 | Gagan | Salomi | [5 empty] | 0
| Nava Raipur | Nava Raipur | Landscape |  | LoD 200 - Schematic Concept & Approvals | 0 | 2 | [7 empty] | 0 | 0
| Nava Raipur | Nava Raipur | Landscape | Gagan | LoD 200 - Schematic Concept |  | 1 | Gagan | Lajja | [5 empty] | 0
| Nava Raipur | Nava Raipur | Landscape | Gagan | LoD 300 - Pre Construction |  |  | Gagan | Lajja
| Nava Raipur | Nava Raipur | Landscape | Gagan | Approvals |  | 1 | Gagan | Lajja | [5 empty] | 0
| OTR-Ph02 | Ph 2 |  |  | Package Release | 0.16686 | 4 | [7 empty] | 0 | 0
| OTR-Ph02 | Ph 2 | MEP |  | LoD 200 - Schematic Concept & Approvals | 0.09558 | 2 | [7 empty] | 0 | 0
| OTR-Ph02 | Ph 2 | MEP | Gagan | LoD 200 - Schematic Concept | 0.06372 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Deepu Mahadev |  |  |  | 0
| OTR-Ph02 | Ph 2 | MEP | Gagan | Approvals | 0.03186 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Deepu Mahadev |  |  |  | 0
| OTR-Ph02 | Ph 2 | Landscape |  | LoD 200 - Schematic Concept & Approvals | 0.07128 | 2 | [7 empty] | 0 | 0
| OTR-Ph02 | Ph 2 | Landscape | Gagan | LoD 200 - Schematic Concept | 0.05346 | 1 | Gagan | Lajja | Apoorva |  |  |  |  | 0
| OTR-Ph02 | Ph 2 | Landscape | Gagan | Approvals | 0.01782 | 1 | Gagan | Lajja | Apoorva |  |  |  |  | 0
| TMFT-Ph 3 | Ph 3 |  |  | Package Release | 0.07366 | 4 | [7 empty] | 0 | 0
| TMFT-Ph 3 | Ph 3 | MEP |  | LoD 200 - Schematic Concept, Approvals | 0.039179 | 2 | [7 empty] | 0 | 0
| TMFT-Ph 3 | Ph 3 | MEP | Gagan | LoD 200 - Schematic Concept | 0.029179 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Subash Shreedhar |  |  |  | 0
| TMFT-Ph 3 | Ph 3 | MEP | Gagan | Approvals | 0.01 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Subash Shreedhar |  |  |  | 0
| TMFT-Ph 3 | Ph 3 | Landscape |  | LoD 200 - Schematic Concept, Approvals | 0.034481 | 2 | [7 empty] | 0 | 0
| TMFT-Ph 3 | Ph 3 | Landscape | Gagan | LoD 200 - Schematic Concept | 0.024481 | 1 | Gagan | Lajja | Chetan |  |  |  |  | 0
| TMFT-Ph 3 | Ph 3 | Landscape | Gagan | Approvals | 0.01 | 1 | Gagan | Lajja | Chetan |  |  |  |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a |  |  | Package Release | 1.2953 | 3 | [7 empty] | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP |  | LoD 200 [Schematic Concept], LoD 300 [Pre Construction Set], LoD 350 [Experience Home + Project Experience] | 1.2953 | 3 | [7 empty] | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | LoD 200 - Schematic Concept | 0.5181 | 1 | Gagan | Salomi | Bhavya Hareesha | Prem Matsarambabu Byahattimath |  |  |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | LoD 300 - Pre Construction Set | 0.5181 | 1 | Gagan | Salomi | Bhavya Hareesha | Prem Matsarambabu Byahattimath |  |  |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | LoD 350 - Experience Home + Project Experience | 0.25905 | 1 | Gagan | Salomi | Bhavya Hareesha | Prem Matsarambabu Byahattimath |  |  |  | 0
| Sarjapur Road [South Block-Resi] | Srjp - Res |  |  | Package Release | 2.3205 | 6 | [7 empty] | 0 | 0
| Srjp - Res | Srjp - Res | MEP |  | Complete LoD 300, Approvals & Experience Homes | 1.6902 | 4 | [7 empty] | 0 | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | LoD 200 - Schematic Concept | 0.5634 | 1 | Gagan | Salomi | Praveen Hareesha | Ajay Hanumanthraya Byahattimath Matsarambabu Shreedhar |  |  |  | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | LoD 200 - Approvals | 0.2817 | 1 | Gagan | Salomi | Praveen Hareesha | Ajay Hanumanthraya Byahattimath Matsarambabu Shreedhar |  |  |  | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | LoD 350 - Experience Home + Project Experience | 0.2817 | 1 | Gagan | Salomi | Praveen Hareesha | Ajay Hanumanthraya Byahattimath Matsarambabu Shreedhar |  |  |  | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | LoD 300 - Preconstruction | 0.5634 | 1 | Gagan | Salomi | Praveen Hareesha | Ajay Hanumanthraya Byahattimath Matsarambabu Shreedhar |  |  |  | 0
2 | Srjp - Res | Srjp - Res | Landscape |  | Complete LoD 300 & Experience Homes | 1.1029 | 3 | [7 empty] | 0 | 0
| Srjp - Res | Srjp - Res | Landscape | Gagan | LoD 200 - Schematic Concept | 0.47269 | 1 | Gagan | Lajja | Apoorva | Chetan |  |  |  | 0
| Srjp - Res | Srjp - Res | Landscape | Gagan | LoD 350 - Experience Home + Project Experience | 0.15756 | 1 | Gagan | Lajja | Apoorva | Chetan |  |  |  | 0
| Srjp - Res | Srjp - Res | Landscape | Gagan | LoD 300 - Preconstruction | 0.47269 | 1 | Gagan | Lajja | Apoorva | Chetan |  |  |  | 0
| Sarjapur - C (South Block) | Srjp - C - SB |  |  | Package Release | 2.0338 | 5 | [7 empty] | 0 | 0
| Srjp - C - SB | Srjp - C - SB | MEP |  | Complete LoD 300 & Approvals | 1.3043 | 3 | [7 empty] | 0 | 0
| Srjp - C - SB | Srjp - C - SB | MEP | Gagan | LoD 200 - Schematic Concept | 0.43476 | 1 | Gagan | Salomi | Praveen Hareesha | Deepu Shreedhar Byahattimath |  |  |  | 0
| Srjp - C - SB | Srjp - C - SB | MEP | Gagan | LoD 200 - Approvals | 0.43476 | 1 | Gagan | Salomi | Praveen Hareesha | Deepu Shreedhar Byahattimath |  |  |  | 0
| Srjp - C - SB | Srjp - C - SB | MEP | Gagan | LoD 300 - Preconstruction | 0.43476 | 1 | Gagan | Salomi | Praveen Hareesha | Deepu Shreedhar Byahattimath |  |  |  | 0
| Srjp - C - SB | Srjp - C - SB | Landscape |  | Complete LoD 300 | 0.72951 | 2 | [7 empty] | 0 | 0
| Srjp - C - SB | Srjp - C - SB | Landscape | Gagan | LoD 200 - Schematic Concept | 0.36475 | 1 | Gagan | [6 empty] | 0
| Srjp - C - SB | Srjp - C - SB | Landscape | Gagan | LoD 300 - Preconstruction | 0.36475 | 1 | Gagan | [6 empty] | 0
| Sarjapur - C (North Block) | Srjp - C - NB |  |  | Package Release | 0.67793 | 5 | [7 empty] | 0 | 0
| Srjp - C - NB | Srjp - C - NB | MEP |  | Complete LoD 300 & Approvals | 0.43476 | 3 | [7 empty] | 0 | 0
| Srjp - C - NB | Srjp - C - NB | MEP | Gagan | LoD 200 - Schematic Concept | 0.14492 | 1 | Gagan | Salomi | Praveen Hareesha | Deepu Byahattimath Matsarambabu |  |  |  | 0
| Srjp - C - NB | Srjp - C - NB | MEP | Gagan | LoD 200 - Approvals | 0.14492 | 1 | Gagan | Salomi | Praveen Hareesha | Deepu Byahattimath Matsarambabu |  |  |  | 0
| Srjp - C - NB | Srjp - C - NB | MEP | Gagan | LoD 300 - Preconstruction | 0.14492 | 1 | Gagan | Salomi | Praveen Hareesha | Deepu Byahattimath Matsarambabu |  |  |  | 0
| Srjp - C - NB | Srjp - C - NB | Landscape |  | Complete LoD 300 | 0.24317 | 2 | [7 empty] | 0 | 0
| Srjp - C - NB | Srjp - C - NB | Landscape | Gagan | LoD 200 - Schematic Concept | 0.12158 | 1 | Gagan | [6 empty] | 0
| Srjp - C - NB | Srjp - C - NB | Landscape | Gagan | LoD 300 - Preconstruction | 0.12158 | 1 | Gagan | [6 empty] | 0
| OTF | OTF |  |  | Package Release | 0.2484 | 6 | [7 empty] | 0 | 0
| OTF | OTF | MEP |  | LoD 350 - Project Entrance | 0.1593 | 3 | [7 empty] | 0 | 0
| OTF | OTF | MEP | Gagan | LoD 200 - Schematic Concept | 0.039825 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Prem Matsarambabu |  |  |  | 0
| OTF | OTF | MEP | Gagan | LoD 300 - Pre Construction Set | 0.07965 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Prem Matsarambabu |  |  |  | 0
| OTF | OTF | MEP | Gagan | LoD 350 - Project Entrance | 0.039825 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Prem Matsarambabu |  |  |  | 0
| OTF | OTF | Landscape |  | LoD 350 - Project Entrance | 0.0891 | 3 | [7 empty] | 0 | 0
| OTF | OTF | Landscape | Gagan | LoD 200 - Schematic Concept | 0.04455 | 1 | Gagan | Lajja | Aproova | Chetan |  |  |  | 0
| OTF | OTF | Landscape | Gagan | LoD 300 - Pre Construction Set | 0.022275 | 1 | Gagan | Lajja | Aproova | Chetan |  |  |  | 0
| OTF | OTF | Landscape | Gagan | LoD 350 - Project Entrance | 0.022275 | 1 | Gagan | Lajja | Aproova | Chetan |  |  |  | 0
| Harohalli [Plotted] | Harohalli |  |  | Package Release | 4.2498 | 7 | [7 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | Master Planning |  | [Dsgn Brf, LOD 200 - Schematic, Approvals] | 3.665 | 3 | [7 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | LoD 100 - Contract + Design Brief | 0.855 | 1 | Gagan | Utpal | Megha |  |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | LoD 200 - Schematic Concept | 1.405 | 1 | Gagan | Utpal | Megha |  |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Approvals | 1.405 | 1 | Gagan | Utpal | Megha |  |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | MEP |  | [LOD 200 - Schematic, Approvals] | 0.30267 | 2 | [7 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | MEP | Gagan | LoD 200 - Schematic Concept | 0.10089 | 1 | Gagan | Salomi | Eranna Praveen | Avinash Prateesha Deepu |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | MEP | Gagan | Approvals | 0.20178 | 1 | Gagan | Salomi | Eranna Praveen | Avinash Prateesha Deepu |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | Landscape |  | [LOD 200 - Schematic, Approvals] | 0.28215 | 2 | [7 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | Landscape | Gagan | LoD 200 - Schematic Concept | 0.11286 | 1 | Gagan | Lajja | Anisha |  |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Approvals | 0.16929 | 1 | Gagan | Lajja | Anisha |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 |  |  | Package Release | 2.7682 | 12 | [7 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Master Planning |  | Package Release [Lod 200 -Schematic Concept & Approvals] | 2.1842 | 3 | [7 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Master Planning | Gagan | LoD 100 - Contract + Design Brief | 0.4725 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Master Planning | Gagan | LoD 200 - Schematic Concept | 0.85586 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Master Planning | Gagan | Approvals | 0.85586 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | MEP |  | Package Release [till LoD 300 - Pre Construction Set] | 0.33453 | 4 | [7 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | MEP | Gagan | LoD 200 - Schematic Concept | 0.055755 | 1 | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | MEP | Gagan | LoD 200 - Approvals | 0.11151 | 1 | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | MEP | Gagan | LoD 300 - Pre Construction Set | 0.11151 | 1 | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | MEP | Gagan | Project Experience | 0.055755 | 1 | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Landscape |  | Package Release [till LoD 300 - Pre Construction Set] | 0.24948 | 5 | [7 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Landscape | Gagan | LoD 200 - Schematic Concept | 0.06237 | 1 | Gagan | Lajja | Anisha |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Landscape | Gagan | LoD 200 - Approvals | 0.093555 | 1 | Gagan | Lajja | Anisha |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Landscape | Gagan | LoD 300 - Pre Construction Set | 0.031185 | 1 | Gagan | Lajja | Anisha |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Landscape | Gagan | Marketing and Sales | 0.031185 | 1 | Gagan | Lajja | Anisha |  |  |  | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Landscape | Gagan | Project Experience | 0.031185 | 1 | Gagan | Lajja | Anisha |  |  |  | 0 | 0
| Violet Hill [21.76a] | Ph 1 |  |  | Package Release | 0.649 | 14 | [7 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Master Planning |  | Package Release [till LoD 350 - Infra - Signage & Street Lighting] | 0.52044 | 4 | [7 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Master Planning | Gagan | LoD 350 - Project Experience [Sales Lounge, Model Road] | 0.13427 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Master Planning | Gagan | LoD 350 - BOQ & Technical Specifications | 0.24321 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Master Planning | Gagan | LoD 350 - Structures - Security Cabin and Entrance [Rework] | 0.072962 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Master Planning | Gagan | Lod 350 - Infra - Signage & Street Lighting | 0.07 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | MEP |  | Package Release [till LoD 350 - Infra - Signage & Street Lighting] | 0.08759 | 5 | [7 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | MEP | Gagan | LoD 350 - Project Experience [Sales Lounge, Model Road] | 0.015844 | 1 | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | MEP | Gagan | LoD 350 - BOQ & Technical Specifications | 0.014349 | 1 | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | MEP | Gagan | LoD 350 - Infra - Coordinated | 0.028698 | 1 | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | MEP | Gagan | LoD 350 - Structures - Security Cabin and Entrance [Rework] | 0.014349 | 1 | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | MEP | Gagan | Lod 350 - Infra - Signage & Street Lighting | 0.014349 | 1 | Gagan | Salomi | [5 empty] | 0
| Violet Hill [21.76a] | Ph 1 | Landscape |  | Package Release [till LoD 350 - Infra - Signage & Street Lighting] | 0.057017 | 7 | [7 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | LoD 350 - Project Experience [Sales Lounge, Model Road] | 0.0088621 | 1 | Gagan | Lajja | Apoorva Gouri |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | LoD 350 - Infra - MEP | 0.0080258 | 1 | Gagan | Lajja | Apoorva Gouri |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | LoD 350 - BOQ & Technical Specifications | 0.0080258 | 1 | Gagan | Lajja | Apoorva Gouri |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | LoD 350 - Infra - Coordinated | 0.0080258 | 1 | Gagan | Lajja | Apoorva Gouri |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | LoD 350 - Structures - Security Cabin and Entrance | 0.0080258 | 1 | Gagan | Lajja | Apoorva Gouri |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | Lod 350 - Infra - Signage & Street Lighting | 0.0080258 | 1 | Gagan | Lajja | [5 empty] | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | LoD 350 - Structures - Security Cabin and Entrance [Rework] | 0.0080258 | 1 | Gagan | Lajja | Manali |  |  |  |  | 0
| Violet Hill [27.08a] | Ph 2 |  |  | Package Release | 0.54682 | 4 | [7 empty] | 0 | 0
| Violet Hill [27.08a] | Ph 2 | Master Planning |  | Package Release [till LoD 300 - Pre Construction Set] | 0.50475 | 2 | [7 empty] | 0 | 0
| Violet Hill [27.08a] | Ph 2 | Master Planning | Gagan | LoD 100 - Contract + Design Brief | 0.16825 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [27.08a] | Ph 2 | Master Planning | Gagan | LoD 200 - Schematic Concept | 0.3365 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [27.08a] | Ph 2 | MEP |  | Package Release [till LoD 300 - Pre Construction Set] | 0.019854 | 1 | [7 empty] | 0 | 0
| Violet Hill [27.08a] | Ph 2 | MEP | Gagan | LoD 200 - Schematic Concept | 0.019854 | 1 | Gagan | [6 empty] | 0
| Violet Hill [27.08a] | Ph 2 | Landscape |  | Package Release [till LoD 300 - Pre Construction Set] | 0.022209 | 1 | [7 empty] | 0 | 0
| Violet Hill [27.08a] | Ph 2 | Landscape | Gagan | LoD 200 - Schematic Concept | 0.022209 | 1 | Gagan | [6 empty] | 0
| KIADB - Mys | KIADB - Mys |  |  | Package Release | 0 | 7 | [7 empty] | 0 | 0
| KIADB - Mys | KIADB - Mys | Master Planning |  | Complete the project by Q4 | 0 | 3 | [7 empty] | 0 | 0
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | LoD 100 - Contract + Design Brief |  | 1 | Gagan | Utpal | Manali
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | LoD 200 - Schematic Concept |  | 1 | Gagan | Utpal | Manali
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | Approvals |  | 1 | Gagan | Utpal | Manali
| KIADB - Mys | KIADB - Mys | MEP |  | Complete the project by Q4 | 0 | 2 | [7 empty] | 0 | 0
| KIADB - Mys | KIADB - Mys | MEP | Gagan | LoD 200 - Schematic Concept |  | 1 | Gagan | Salomi | Eranna Praveen
| KIADB - Mys | KIADB - Mys | MEP | Gagan | Approvals |  | 1 | Gagan | Salomi | Eranna Praveen
| KIADB - Mys | KIADB - Mys | Landscape |  | Complete the project by Q4 | 0 | 2 | [7 empty] | 0 | 0
| KIADB - Mys | KIADB - Mys | Landscape | Gagan | LoD 200 - Schematic Concept |  | 1 | Gagan | Lajja | Anisha
| KIADB - Mys | KIADB - Mys | Landscape | Gagan | Approvals |  | 1 | Gagan | Lajja | Anisha
| Imagine Campus | Imgn |  |  | Package Release | 0.15 | 3 | [7 empty] | 0 | 0
| Imagine Campus | Imgn | MEP |  | Package Release [Complete LoD 200] | 0.1 | 2 | [7 empty] | 0 | 0
| Imagine Campus | Imgn | MEP | Gagan | LoD 200 - Schematic Concept | 0.05 | 1 | Gagan | Salomi | Hareesha Bhavya | Byahattimath Shreedhar Viresh |  |  |  | 0
| Imagine Campus | Imgn | MEP | Gagan | Approvals | 0.05 | 1 | Gagan | Salomi | Hareesha Bhavya | Byahattimath Shreedhar Viresh |  |  |  | 0
| Imagine Campus | Imgn | Landscape |  | Package Release [Complete LoD 200] | 0.05 | 1 | [7 empty] | 0 | 0
| Imagine Campus | Imgn | Landscape | Gagan | Approvals | 0.05 | 1 | Gagan | Lajja | Aproova |  |  |  |  | 0
| OtR OOTA | OTR OOTA |  |  | Package Release | 0.02067 | 4 | [7 empty] | 0 | 0
| OTR OOTA | OTR OOTA | MEP |  | Complete Approvals | 0.011275 | 2 | [7 empty] | 0 | 0
| OTR OOTA | OTR OOTA | MEP | Gagan | LoD 200 - Schematic Concept | 0.0056373 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| OTR OOTA | OTR OOTA | MEP | Gagan | Approvals | 0.0056373 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| OTR OOTA | OTR OOTA | Landscape |  | Complete Approvals | 0.0093954 | 2 | [7 empty] | 0 | 0
| OTR OOTA | OTR OOTA | Landscape | Gagan | LoD 200 - Schematic Concept | 0.0046977 | 1 | Gagan | Lajja | Anisha |  |  |  |  | 0
| OTR OOTA | OTR OOTA | Landscape | Gagan | Approvals | 0.0046977 | 1 | Gagan | Lajja | Anisha |  |  |  |  | 0
| Blue in Green | BiG |  |  | Package Release | 1.7957 | 6 | [7 empty] | 0 | 0
| Blue in Green | BiG | MEP |  | LoD 300 - Pre Construction Set | 1.0047 | 3 | [7 empty] | 0 | 0
| Blue in Green | BiG | MEP | Gagan | LoD 200 - Schematic Concept | 0.40314 | 1 | Gagan | [6 empty] | 0
| Blue in Green | BiG | MEP | Gagan | Approvals | 0.20157 | 1 | Gagan | [6 empty] | 0
| Blue in Green | BiG | MEP | Gagan | LoD 300 - Pre Construction Set | 0.4 | 1 | Gagan | [6 empty] | 0
| Blue in Green | BiG | Landscape |  | LoD 300 - Pre Construction Set, Approvals | 0.79096 | 3 | [7 empty] | 0 | 0
| Blue in Green | BiG | Landscape | Gagan | LoD 200 - Schematic Concept | 0.33822 | 1 | Gagan | [6 empty] | 0
| Blue in Green | BiG | Landscape | Gagan | Approvals | 0.11274 | 1 | Gagan | [6 empty] | 0
| Blue in Green | BiG | Landscape | Gagan | LoD 300 - Pre Construction Set | 0.34 | 1 | Gagan | [6 empty] | 0
| Vaderahalli | Vdrhl |  |  | Package Release | 3.9133 | 4 | [7 empty] | 0 | 0
| Vaderahalli | Vdrhl | MEP |  | LoD 200 - Schematic Concept | 2.2418 | 2 | [7 empty] | 0 | 0
| Vaderahalli | Vdrhl | MEP | Gagan | LoD 200 - Schematic Concept | 1.4918 | 1 | Gagan | [6 empty] | 0
| Vaderahalli | Vdrhl | MEP | Gagan | Approvals | 0.75 | 1 | Gagan | [6 empty] | 0
| Vaderahalli | Vdrhl | Landscape |  | LoD 200 - Schematic Concept | 1.6716 | 2 | [7 empty] | 0 | 0
| Vaderahalli | Vdrhl | Landscape | Gagan | LoD 200 - Schematic Concept | 1.2516 | 1 | Gagan | [6 empty] | 0
| Vaderahalli | Vdrhl | Landscape | Gagan | Approvals | 0.42 | 1 | Gagan | [6 empty] | 0
Note on G28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on H28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on V28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on W28: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on V53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on W53: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed

## Goals FY 26-27Q2 Navneet (hidden)
FY 2026-27 Q2 ¦ Design Goals + Billing ¦ Navneet K |  |  |  |  | 1.0931 | 107 | [7 empty] | 0 | 0 | 1.0931 | 107
Project | Phase | Discipline | Design Lead | Description | Plan - Billing [Cr.] | Plan - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | Actuals - Billing [Cr.] | Actuals - Pkgs | 0% | 0%
Interior Design + Product Development |  |  |  |  | 1.0931 | 107 | [7 empty] | 0 | 0
Interior Design | ID |  |  | Package Release | 1.0931 | 107 | [7 empty] | 0 | 0
Product Launch | PD Launch | Interior Design |  |  | 0 | 8 | [7 empty] | 0 | 0
Product Launch | PD Launch | Interior Design | Navneet K | ITQE [L25] - Pending Variants |  | 1 | [7 empty] | 0
Product Launch | PD Launch | Interior Design | Navneet K | OTR [V25] |  | 1 | [7 empty] | 0
Product Launch | PD Launch | Interior Design | Navneet K | POARR [R25, D35, L20] |  | 3 | [7 empty] | 0
Product Launch | PD Launch | Interior Design | Navneet K | DBTW [I20, I25, L21] |  | 3 | [7 empty] | 0
Personalised Customisation | PID | Interior Design |  |  | 0.53307 | 7 | [7 empty] | 0 | 0
Personalised Customisation | PID | Interior Design | Navneet K | TMD, POARR, SFTW | 0.53307 | 7 | [7 empty] | 0
Edesign | PID | Interior Design |  |  | 0.56 | 86 | [7 empty] | 0 | #REF!
Edesign | PID | Interior Design | Navneet K | ATR, POARR, ITQE, TMFT, SFTW, TMD | 0.56 | 86 | [7 empty] | 0
Default | PID | Interior Design |  |  | 0 | 6 | [7 empty] | 0 | #REF!
Default | PID | Interior Design | Navneet K | SFTW | 0 | 6 | [7 empty] | 0

## Goals FY 26-27Q2 Shweta V (hidden)
FY 2026-27 Q2 ¦ Design Goals + Billing ¦ Shweta V |  |  |  |  | 0 | 12 | [7 empty] | 0 | 0 | 0 | 12
Project | Phase | Discipline | Design Lead | Description | Plan - Billing [Cr.] | Plan - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | Actuals - Billing [Cr.] | Actuals - Pkgs | #DIV/0! | 0%
Interior Design + Product Development |  |  |  |  | 0 | 12 | [7 empty] | 0 | 0
IDPD | IDPD | Interior Design |  | Package Release | 0 | 12 | [7 empty] | 0 | 0
Experience Homes | Exp Homes | Interior Design |  |  | 0 | 7 | [7 empty] | 0 | 0
Experience Homes | itqE | Interior Design | Shweta V | itqE i20- Experience Home Furniture and Furnishing |  | 1 | [7 empty] | 0
Experience Homes | itqE | Interior Design | Shweta V | itqE i25- Experience Home Furniture and Furnishing |  | 1 | [7 empty] | 0
Experience Homes | ItqE | Interior Design | Shweta V | ItqE V35-Experience Home Furniture and Furnishing |  | 1 | [7 empty] | 0
Experience Homes | Srjp | Interior Design | Shweta V | Srjp i20- Experience Home Furniture and Furnishing |  | 1 | [7 empty] | 0
Experience Homes | Srjp | Interior Design | Shweta V | Srjp i25- Experience Home Furniture and Furnishing |  | 1 | [7 empty] | 0
Experience Homes | Srjp | Interior Design | Shweta V | Srjp D35- Experience Home Furniture and Furnishing |  | 1 | [7 empty] | 0
Experience Homes | Srjp | Interior Design | Shweta V | Srjp L21- Experience Home Furniture and Furnishing |  | 1 | [7 empty] | 0
Product Development | PD | Interior Design |  |  | 0 | 3 | [7 empty] | 0 | 0
Product Development | PD | Interior Design | Shweta V | (i) Based on Shibanee's designs-2 themes due. 1 theme namely "Open Tennon theme" WIP (Viveka) |  | 1 | [7 empty] | 0
Product Development | PD | Interior Design | Shweta V | (ii) Cabinetry : Sectional sofas, Dressers, Puja Units, Bar unit, Utility, consoles, Dining, woven frames furniture theme (Viveka) |  | 1 | [7 empty] | 0
Product Development | PD | Interior Design | Shweta V | Project Entrance gate (Sushan) |  | 1 | [7 empty] | 0
Fabric Craft | PD | Interior Design |  |  | 0 | 1 | [7 empty] | 0 | 0
Fabric Craft | PD | Interior Design | Shweta V | Soft furnishing for all experience homes except V35 |  | 1 | [7 empty] | 0
Personalised Customisation | PID | Interior Design |  |  | 0 | 1 | [7 empty] | 0 | 0
Personalised Customisation | PoaRR | Interior Design | Shweta V | Villa 18 - Store selections |  | 1 | [7 empty] | 0

## Goals FY 26-27Q2 Prakash C (hidden)
FY 2026-27 Q2 ¦ Design Goals + Billing ¦ Prakash C |  |  |  |  | 29.5652 | 125 | [7 empty] | 0 | 0 | 29.5652 | 125
Project | Phase | Discipline | Design Lead | Description | Plan - Billing [Cr.] | Plan - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | Actuals - Billing [Cr.] | Actuals - Pkgs | 0% | 0%
Ongoing Projects |  |  |  |  | 8.9083 | 92 | [7 empty] | 0 | 0
AtR | Ph 1, 2a, 2b, 2c |  |  | Package Release | 0.021351 | 3 | [7 empty] | 0 | 0
AtR | Ph 1, 2a, 2b, 2c | Structural |  | Package Release [Complete LoD 350 ] | 0.021351 | 3 | [7 empty] | 0 | 0
AtR | Ph 1, 2a, 2b | Structural | Prakash C | LoD 350 - Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] | 0.0052867 | 1 | Prakash C | Satish H | Alwin | Aniket P | Ambika |  |  | 0
AtR | Ph 2c | Structural | Prakash C | LoD 350 - Master Plan - Site MEP | 0.010861 | 1 | Prakash C | Satish H | Ajmal/Shahnawaz | Atharv | Prasad |  |  | 0
AtR | Ph 2c | Structural | Prakash C | LoD 350 - Clubhouse + Amenities - Sporting Facilities | 0.0052029 | 1 | Prakash C | Satish H | Alwin | Aniket P | Prasad |  |  | 0
AtR | Ph 3 |  |  | Package Release | 0.33963 | 16 | [7 empty] | 0 | 0
AtR | Ph 3 | Structural |  | Package Release [Complete LoD 350 ] | 0.33963 | 16 | [7 empty] | 0 | 0
AtR | Ph 3 | Structural | Prakash C | LoD 300 - Preconstruction Set | 0.093422 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 29 - Foundations and Sub-Grade Structure | 0.021107 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 29 - Super Structure | 0.03166 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 29 - Building Envelope + Plot Development | 0.0052767 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 30 - Foundations and Sub-Grade Structure | 0.021107 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 30 - Super Structure | 0.03166 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 30 - Building Envelope + Plot Development | 0.0052767 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 31 - Building Envelope + Plot Development | 0.001 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 32 - Building Envelope + Plot Development | 0.0023452 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 33 - Foundations and Sub-Grade Structure | 0.014071 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 33 - Super Structure | 0.03166 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 33 - Building Envelope + Plot Development | 0.0023452 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 34 - Foundations and Sub-Grade Structure | 0.014071 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 34 - Super Structure | 0.021107 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 34 - Building Envelope + Plot Development | 0.0035178 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR | Ph 3 | Structural | Prakash C | LoD 350 - Site Development - 02 Road Works | 0.04 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
AtR - C | Com |  |  | Package Release | 0.80124 | 5 | [7 empty] | 0 | 0
AtR - C | Com | Structural |  | Package Release [Complete LoD 350 except Habitable Level 6-10 and Terrace Level ] | 0.80124 | 5 | [7 empty] | 0 | 0
AtR - C | Com | Structural | Prakash C | LoD 350 - Tower-[Commercial] - Habitable Level 3-5 | 0.25823 | 1 | Prakash C | Vineetha | Sagar+ Shrishail | Rajath |  |  |  | 0
AtR - C | Com | Structural | Prakash C | LoD 350 - Tower-[Commercial] - Habitable Level 6-10 | 0.25823 | 1 | Prakash C | Vineetha | Sagar+ Shrishail | Rajath |  |  |  | 0
AtR - C | Com | Structural | Prakash C | LoD 350 - Tower-[Commercial] - Terrace Level | 0.25823 | 1 | Prakash C | Vineetha | Sagar+ Shrishail | Rajath |  |  |  | 0
AtR - C | Com | Structural | Prakash C | LoD 350 - Master Plan - Site Development | 0.014486 | 1 | Prakash C | Vineetha | Dhirender+ Shrishail | Rohit |  |  |  | 0
AtR - C | Com | Structural | Prakash C | LoD 350 - Master Plan - Site MEP | 0.012072 | 1 | Prakash C | Vineetha | Sagar+Rajath | Namrath |  |  |  | 0
PoaRR-Res | Res |  |  | Package Release | 0.36 | 3 | [7 empty] | 0 | 0
PoaRR-Res | Res | Structural |  | Complete the project | 0.36 | 3 | [7 empty] | 0 | 0
PoaRR-Res | Res | Structural | Prakash C | LOD 350 Site Development | 0.19 | 1 | Prakash C | Lincy | Subrahmanya |  | Darshan |  |  | 0
PoaRR-Res | Res | Structural | Prakash C | LOD 350 Site MEP | 0.16 | 1 | Prakash C | Lincy | Subrahmanya |  | Darshan |  |  | 0
PoaRR-Res | Res | Structural | Prakash C | LOD 350 Sporting Facilities | 0.01 | 1 | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan |  |  | 0
PoaRR-T08 | T08 |  |  | Package Release | 1.7 | 7 | [7 empty] | 0 | 0
PoaRR-T08 | T08 | Structural |  | Complete the project | 1.7 | 7 | [7 empty] | 0 | 0
PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 Penthouse Levels | 0.2 | 1 | Prakash C | Lincy | Jayashankar | Subrahmanya | Darshan |  |  | 0
PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 Terrace Level | 0.4 | 1 | Prakash C | Lincy | Jayashankar | Subrahmanya | Darshan |  |  | 0
PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 T08 - ISS - Foundations & Grade Slab | 0.32 | 1 | Prakash C | Lincy | Nadeem | - | Darshan |  |  | 0
PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 T08 - ISS - Podium Slab | 0.32 | 1 | Prakash C | Lincy | Nadeem | - | Darshan |  |  | 0
PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 T08 - ISS - Parking Level Subgrade | 0.43 | 1 | Prakash C | Lincy | Nadeem | Subrahmanya | Karthik |  |  | 0
PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 Site Development | 0.02 | 1 | Prakash C | Lincy | Subrahmanya | - | Karthik |  |  | 0
PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 Site MEP | 0.01 | 1 | Prakash C | Lincy | Subrahmanya | - | Karthik |  |  | 0
ITQE-Ph1 | Ph 1 |  |  | Package Release | 0.023824 | 2 |  |  | Aishwarya Hegde | Sheethal Prabhu | Anand Thoppil |  |  | 0 | 0
ITQE-Ph1 | Ph 1 | Structural |  | Complete the project | 0.023824 | 2 | [7 empty] | 0 | 0
ITQE-Ph1 | Ph 1 | Structural | Prakash C | LoD 350 - Amenities & Facilities ¦ Clubhouse—Outdoor Spaces and Pool | 0.011912 | 1 | Prakash C | Satish H | Raghavendra |  | Vinay |  |  | 0
ITQE-Ph1 | Ph 1 | Structural | Prakash C | LoD 350 - Amenities & Facilities ¦ Community spaces | 0.011912 | 1 | Prakash C | Satish H | Raghavendra |  | Vinay |  |  | 0
ITQE-Ph2b | Ph 2b |  |  | Package Release | 0.71 | 8 | [7 empty] | 0 | 0
ITQE-Ph2b | Ph 2b | Structural |  | Complete the project | 0.71 | 8 | [7 empty] | 0 | 0
ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Tower 05 ¦ Terrace Level | 0.09 | 1 | Prakash C | Satish H | Antony |  | Harshitha |  | 0 | 0
ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Tower 06 ¦ Terrace Level | 0.09 | 1 | Prakash C | Satish H | Antony |  | Harshitha |  | 0 | 0
ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Tower 07 ¦ Terrace Level | 0.09 | 1 | Prakash C | Satish H | Antony |  | Harshitha |  | 0 | 0
ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - ISS5&6 ¦Foundations & Grade Slab | 0.18 | 1 | Prakash C | Satish H | Ajmal (after finishing ATR Site MEP works) & New resource hired, joining in July |  | Harshitha |  | 0 | 0
ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - ISS7 ¦ Podium Slab | 0.13 | 1 | Prakash C | Satish H | Ajmal (after finishing ATR Site MEP works) & New resource hired, joining in July |  | Harshitha |  | 0 | 0
ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - ISS 7 ¦ Podium Slab | 0.13 | 1 | Prakash C | Satish H | Ajmal (after finishing ATR Site MEP works) & New resource hired, joining in July |  | Harshitha |  | 0 | 0
ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Master Plan ¦ Site Development | 0 | 1 | Prakash C | Satish H | Ajmal (after finishing ATR Site MEP works) & New resource hired, joining in July |  | Harshitha |  | 0 | 0
ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Master Plan ¦ Site MEP | 0 | 1 | Prakash C | Satish H | Ajmal (after finishing ATR Site MEP works) & New resource hired, joining in July |  | Harshitha |  | 0 | 0
ItQE-Ph2c [T9] | Ph 2c |  |  | Package Release | 0.2848 | 4 | [7 empty] | 0 | 0
ItQE-Ph2c [T9] | Ph 2c | Structural |  | LoD 350 - T09 [Foundation & Grade Slab, Parking Lvl Sub Grade], ISS09 [[Foundation & Grade Slab] | 0.2848 | 4 | [7 empty] | 0 | 0
ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | LoD 350 - Tower 9 ¦ Foundation and Grade Slab | 0.118 | 1 | Prakash C | Satish H | Raghavendra |  | Sahana |  | 0 | 0
ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | LoD 350 - Tower 9 ¦ Parking Level-Sub grade | 0.118 | 1 | Prakash C | Satish H | Raghavendra |  | Sahana |  | 0 | 0
ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | LoD 350 - ISS 9 ¦ Earthwork | 0.0097618 | 1 | Prakash C |  | Outsourced |  |  |  | 0 | 0
ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | LoD 350 - ISS 9 ¦ Foundations & Grade Slab | 0.039047 | 1 | Prakash C |  | Outsourced |  |  |  | 0 | 0
OTR-Ph01 | Ph 1 |  |  | Package Release | 0.3 | 4 | [7 empty] | 0 | 0
OTR-Ph01 | Ph 1 | Structural |  | Complete the project | 0.3 | 4 | [7 empty] | 0 | 0
OTR-Ph01 | Ph 1 | Structural | Prakash C | LoD 350 - Villa Block ¦ Super Structure | 0.17 | 1 | Prakash C | Satish H | Mazhar |  | Samyukta |  | 0 | 0
OTR-Ph01 | Ph 1 | Structural | Prakash C | LoD 350 - Master Plan ¦ Site Development | 0.03 | 1 | Prakash C | Satish H | Mazhar |  | Samyukta |  | 0 | 0
OTR-Ph01 | Ph 1 | Structural | Prakash C | LoD 350 - Master Plan ¦ Site MEP | 0.03 | 1 | Prakash C | Satish H | Mazhar |  | Samyukta |  | 0 | 0
OTR-Ph01 | Ph 1 | Structural | Prakash C | LoD 350 - LoD 350 - Amenities & Facilities ¦ Community spaces [Board Walk, Children play area] | 0.07 | 1 | Prakash C | Satish H | Mazhar |  | Samyukta |  | 0 | 0
TuiG | TuiG |  |  | Package Release | 1.0053 | 4 | [7 empty] | 0 | 0
TuiG | TuiG | Structural |  | Package Release [LoD 350 - Site dev, Site MEP, CH structure & Envelope] | 1.0053 | 4 | [7 empty] | 0 | 0
TuiG | TuiG | Structural | Prakash C | LoD 350 - Site Development | 0.40295 | 1 | Prakash C | Satish H | Alwin |  | Shivaraj |  | 0 | 0
TuiG | TuiG | Structural | Prakash C | LoD 350 - Site MEP | 0.33579 | 1 | Prakash C | Satish H | Alwin |  | Shivaraj |  | 0 | 0
TuiG | TuiG | Structural | Prakash C | LoD 350 - Clubhouse—Structure and Envelope | 0.21694 | 1 | Prakash C | Satish H | Saurav |  | Shivaraj |  | 0 | 0
TuiG | TuiG | Structural | Prakash C | LoD 350 - Clubhouse—Outdoor Spaces and Pool | 0.049574 | 1 | Prakash C | Satish H | Saurav |  | Shivaraj |  | 0 | 0
DBTW | DBTW |  |  | Package Release | 2.1218 | 19 | [7 empty] | 0 | 0
DBTW | DBTW | Structural |  | Complete the project | 2.1218 | 19 | [7 empty] | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - ISS - Foundations & Grade Slab | 0.52958 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - ISS -Parking Level Slab - Sub grade | 0.39719 | 1 | Prakash C | Satish H | [5 empty] | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - ISS - Podium Slab | 0.39719 | 1 | Prakash C | Satish H | [5 empty] | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-1-Habitable Level - Even | 0.025613 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-1-Habitable Level - Odd | 0.025613 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level - Even | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level - Odd | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level - Even | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level - Odd | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level - Even | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level - Odd | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 05-Foundation and Grade Slab | 0.10834 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level - Even | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level - Odd | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Foundation and Grade Slab | 0.051226 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Parking Level-Sub grade | 0.051226 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level 01 | 0.051226 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level - Even | 0.025613 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level - Odd | 0.025613 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
SftW | SftW |  |  | Package Release | 0.34546 | 6 | [7 empty] | 0 | 0
SftW | SftW | Structural |  | Complete LoD 350 [Clubhouse & Masterplan] by 26'Q2 | 0.34546 | 6 | [7 empty] | 0 | 0
SftW | SftW | Structural | Prakash C | LoD 350 - Tower 2: Terrace Level | 0.20116 | 1 | Prakash C | Vineetha | Shrishail | Rohit | Arun |  | 0 | 0
SftW | SftW | Structural | Prakash C | LoD 350 - Master Plan: Site Development | 0.058457 | 1 | Prakash C | Satish H | New resource to be Hired |  | Arun |  | 0 | 0
SftW | SftW | Structural | Prakash C | LoD 350 - Master Plan: Site MEP | 0.048714 | 1 | Prakash C | Satish H | New resource to be Hired |  | Arun |  | 0 | 0
SftW | SftW | Structural | Prakash C | LoD 350 - Clubhouse: Structure and Envelope | 0.025989 | 1 | Prakash C | Satish H | Shubham |  | Vinay |  | 0 | 0
SftW | SftW | Structural | Prakash C | LoD 350 - Clubhouse: Outdoor Spaces and Pool | 0.0037128 | 1 | Prakash C | Satish H | Raghavendra |  | Vinay |  | 0 | 0
SftW | SftW | Structural | Prakash C | LoD 350: Clubhouse + Amenities - Sporting Facilities | 0.0074255 | 1 | Prakash C | Satish H | Shubam(after finishing clubhouse) |  | Vinay |  | 0 | 0
LGCE Campus | LGCE Campus |  |  | Package Release | 0.064519 | 1 | [7 empty] | 0 | 0
LGCE Campus | LGCE Campus | Structural |  | Complete LoD 200 by 26'Q2 | 0.064519 | 1 | [7 empty] | 0 | 0
LGCE Campus | LGCE Campus | Structural | Prakash C | LoD 200 - Schematic Concept | 0.064519 | 1 | Prakash C | Vineetha | Sagar | Rohit | karthik |  | 0 | 0
MeenaSai Res | MS Res |  |  | Package Release | 0.0864 | 3 | [7 empty] | 0 | 0
MeenaSai Res | MS Res | Structural |  | Complete LoD 300, LoD 350 Foundation and Structure | 0.0864 | 2 | [7 empty] | 0 | 0
MeenaSai Res | MS Res | Structural | Prakash C | LoD 200 - Schematic Concept | 0.0192 | 1 | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan |  | 0 | 0
MeenaSai Res | MS Res | Structural | Prakash C | LoD 300 - Pre Construction set | 0.0192 | 1 | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan |  | 0 | 0
MeenaSai Res | MS Res | Structural | Prakash C | LoD 350 - Foundation and Structure | 0.048 | 1 | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan |  | 0 | 0
NH Homestay | NH HS |  |  | Package Release | 0.22284 | 3 | [7 empty] | 0 | 0
NH Homestay | NH HS | Structural |  | Complete the project | 0.22284 | 3 | [7 empty] | 0 | 0
NH Homestay | NH HS | Structural | Prakash C | LoD 300 - Pre Construction set | 0.059424 | 1 | Prakash C | Lincy | Abhishek | Subrahmanya | Darshan |  | 0 | 0
NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Foundation and Structure | 0.14856 | 1 | Prakash C | Lincy | Abhishek | Subrahmanya | Darshan |  | 0 | 0
NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Building Envelope + Plot Development | 0.014856 | 1 | Prakash C | Lincy | Abhishek | Subrahmanya | Darshan |  | 0 | 0
Indiranagar Res | Indrng Res |  |  | Package Release | 0.0008 | 1 | [7 empty] | 0 | 0
Indiranagar Res | Indrng Res | Structural |  | Complete the project [Complete LoD 350 ] | 0.0008 | 1 | [7 empty] | 0 | 0
Indiranagar Res | Indrng Res | Structural | Prakash C | LoD 350 -Block C - Building Envelope + Plot Development | 0.0008 | 1 | Prakash C | Theja |  | 0 | Vinay |  | 0 | 0
OTR Museum | OTR Mus |  |  | Package Release | 0.08045 | 1 | [7 empty] | 0 | 0
OTR Museum | OTR Mus | Structural |  | Complete Schematic concept | 0.08045 | 1 | [7 empty] | 0 | 0
OTR Museum | OTR Mus | Structural | Prakash C | LoD 200 - Schematic Concept | 0.08045 | 1 | Prakash C | Satish H | Mazhar |  |  |  |  | 0
Rework Pkgs | Rwrk |  |  |  | 0.44 | 2 | [7 empty] | 0 | 0
PoaRR-T08 | T08 | Structural | Prakash C | STR Package Release [LoD 350 - Parking level subgrade] | 0.4 | 1 | Prakash C | Lincy | Charan |  | Darshan |  |  | 0
ITQE-T05 | T05 | Structural | Prakash C | STR Package Release [LoD 350 - Habitable Level 01] | 0.04 | 1 | Prakash C | Satish | Antony |  | Shivaraj |  |  | 0
New Projects |  |  |  |  | 20.6569 | 32 | [7 empty] | 0 | 0
Nava Raipur | Nava Raipur |  |  | Package Release | 0 | 1 | [7 empty] | 0 | 0
Nava Raipur | Nava Raipur | Structural |  | LoD 200 - Schematic Concept | 0 | 1 | [7 empty] | 0 | 0
Nava Raipur | Nava Raipur | Structural | Prakash C | LoD 200 - Schematic Concept |  | 1 | Prakash C | Lincy R |  |  |  |  | 0 | 0
Nava Raipur | Nava Raipur | Structural | Prakash C | LoD 300 - Pre Construction |  |  | Prakash C | Lincy R |  |  |  |  | 0
OTR-Ph02 | Ph 2 |  |  | Package Release | 0.17172 | 1 | [7 empty] | 0 | 0
OTR-Ph02 | Ph 2 | Structural |  | Complete Schematic concept | 0.17172 | 1 | [7 empty] | 0 | 0
OTR-Ph02 | Ph 2 | Structural | Prakash C | LoD 200 - Schematic Concept | 0.17172 | 1 | Prakash C | Satish | Mazhar ( If Villa concept is different new resource is required) |  | Samyukta |  | 0 | 0
TMFT-Ph 3 | Ph 3 |  |  | Package Release | 0.078635 | 1 | [7 empty] | 0 | 0
TMFT-Ph 3 | Ph 3 | Structural |  | LoD 200 - Schematic Concept | 0.078635 | 1 | [7 empty] | 0 | 0
TMFT-Ph 3 | Ph 3 | Structural | Prakash C | LoD 200 - Schematic Concept | 0.078635 | 1 | Prakash C | Vineetha | Dhirender | Rajath | Arpitha |  | 0 | 0
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a |  |  | Package Release | 3.2579 | 2 | [7 empty] | 0 | 0
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural |  | LoD 200 [Schematic Concept], LoD 300 [Pre Construction Set] | 3.2579 | 2 | [7 empty] | 0 | 0
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | LoD 200 - Schematic Concept | 1.3962 | 1 | Prakash C | Satish | Raghavendra & New Resource |  | Vinay |  | 0 | 0
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | LoD 300 - Pre Construction Set | 1.8617 | 1 | Prakash C | Satish | Raghavendra & New Resource |  | Vinay |  | 0 | 0
Sarjapur Road [South Block-Resi] | Srjp - Res |  |  | Package Release | 4.0489 | 3 | [7 empty] | 0 | 0
Srjp - Res | Srjp - Res | Structural |  | Complete LoD 300 & Experience Homes | 4.0489 | 3 | [7 empty] | 0 | 0
Srjp - Res | Srjp - Res | Structural | Prakash C | LoD 200 - Schematic Concept | 1.5183 | 1 | Prakash C | Lincy | Jayashankar | Charan | Darshan |  | 0 | 0
Srjp - Res | Srjp - Res | Structural | Prakash C | LoD 350 - Experience Home + Project Experience | 0.50611 | 1 | Prakash C | Lincy | Jayashankar | Charan | Darshan |  | 0 | 0
Srjp - Res | Srjp - Res | Structural | Prakash C | LoD 300 - Preconstruction | 2.0244 | 1 | Prakash C | Lincy | Jayashankar | Charan | Darshan |  | 0 | 0
Sarjapur - C (South Block) | Srjp - C - SB |  |  | Package Release | 3.1244 | 2 | [7 empty] | 0 | 0
Srjp - C - SB | Srjp - C - SB | Structural |  | Complete LoD 300 | 3.1244 | 2 | [7 empty] | 0 | 0
Srjp - C - SB | Srjp - C - SB | Structural | Prakash C | LoD 200 - Schematic Concept | 1.5622 | 1 | Prakash C | Lincy | - | - | Darshan |  | 0 | 0
Srjp - C - SB | Srjp - C - SB | Structural | Prakash C | LoD 300 - Preconstruction | 1.5622 | 1 | Prakash C | Lincy | - | - | Darshan |  | 0 | 0
Sarjapur - C (North Block) | Srjp - C - NB |  |  | Package Release | 1.0415 | 2 | [7 empty] | 0 | 0
Srjp - C - NB | Srjp - C - NB | Structural |  | Complete LoD 300 | 1.0415 | 2 | [7 empty] | 0 | 0
Srjp - C - NB | Srjp - C - NB | Structural | Prakash C | LoD 200 - Schematic Concept | 0.52073 | 1 | Prakash C | Lincy | Suganthan | - | Darshan |  | 0 | 0
Srjp - C - NB | Srjp - C - NB | Structural | Prakash C | LoD 300 - Preconstruction | 0.52073 | 1 | Prakash C | Lincy | Suganthan | - | Darshan |  | 0 | 0
OTF | OTF |  |  | Package Release | 0.6324 | 4 | [7 empty] | 0 | 0
OTF | OTF | Structural |  | LOD 350 - MP Pkg 1, Project Entrance | 0.5724 | 3 | [7 empty] | 0 | 0
OTF | OTF | Structural | Prakash C | LoD 200 - Schematic Concept | 0.1431 | 1 | Prakash C | Satish | Alwin | Raghav | Darshan |  | 0 | 0
OTF | OTF | Structural | Prakash C | LoD 300 - Pre Construction Set | 0.2862 | 1 | Prakash C | Satish | Alwin | Raghav | Darshan |  | 0 | 0
OTF | OTF | Structural | Prakash C | LoD 350 - Project Entrance | 0.1431 | 1 | Prakash C | Satish | Alwin | Raghav | Darshan |  | 0 | 0
OTF | OTF | Structural | Prakash C | LoD 350 - Infra - Grading | 0.06 | 1 | Prakash C | Satish | Alwin | Raghav | Darshan |  |  | 0
Harohalli [Plotted] | Harohalli |  |  | Package Release | 0.36252 | 1 | [7 empty] | 0 | 0
Harohalli [Plotted] | Ph 1 | Structural |  | [LOD 200 - Schematic] | 0.36252 | 1 | [7 empty] | 0 | 0
Harohalli [Plotted] | Ph 1 | Structural | Prakash C | LoD 200 - Schematic Concept | 0.36252 | 1 | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
Shreegaon [61.6a] | Ph 1 |  |  | Package Release | 0.80136 | 3 | [7 empty] | 0 | 0
Shreegaon [61.6a] | Ph 1 | Structural |  | Package Release [ LoD 200 - Schematic Concept] | 0.80136 | 3 | [7 empty] | 0 | 0
Shreegaon [61.6a] | Ph 1 | Structural | Prakash C | LoD 200 - Schematic Concept | 0.20034 | 1 | Prakash C | Satish | Alwin | Raghav | Harshitha |  | 0 | 0
Shreegaon [61.6a] | Ph 1 | Structural | Prakash C | LoD 300 - Pre Construction Set | 0.40068 | 1 | Prakash C | Satish | Alwin | Raghav | Harshitha |  | 0 | 0
Shreegaon [61.6a] | Ph 1 | Structural | Prakash C | Project Experience | 0.20034 | 1 | Prakash C | Satish | Alwin | Raghav | Harshitha |  | 0 | 0
Violet Hill [21.76a] | Ph 1 |  |  | Package Release | 0.2997 | 6 | [7 empty] | 0 | 0
Violet Hill [21.76a] | Ph 1 | Structural |  | Package Release [till LoD 350 - Infra - Signage & Street Lighting] | 0.2997 | 6 | [7 empty] | 0 | 0
Violet Hill [21.76a] | Ph 1 | Structural | Prakash C | LoD 300 - Pre Construction Set | 0.11386 | 1 | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
Violet Hill [21.76a] | Ph 1 | Structural | Prakash C | LoD 350 - Project Experience [Sales Lounge, Model Road] | 0.056932 | 1 | Prakash C | Satish/Lincy | Alwin/Subramanya | Raghav | Prasad |  | 0 | 0
Violet Hill [21.76a] | Ph 1 | Structural | Prakash C | LoD 350 - Infra - Grading | 0.02578 | 1 | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
Violet Hill [21.76a] | Ph 1 | Structural | Prakash C | LoD 350 - Infra - MEP | 0.05156 | 1 | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
Violet Hill [21.76a] | Ph 1 | Structural | Prakash C | LoD 350 - Structures - Security Cabin and Entrance [Rework] | 0.02578 | 1 | Prakash C | Lincy | Subrahmanya | - | Prasad |  | 0 | 0
Violet Hill [21.76a] | Ph1 | Structural | Prakash C | Lod 350 - Infra - Signage & Street Lighting | 0.02578 | 1 | Gagan | satish | [5 empty] | 0
Violet Hill [27.08a] | Ph 2 |  |  | Package Release | 0.071339 | 1 | [7 empty] | 0 | 0
Violet Hill [27.08a] | Ph 2 | Structural |  | Package Release [till LoD 300 - Pre Construction Set] | 0.071339 | 1 | [7 empty] | 0 | 0
Violet Hill [27.08a] | Ph 2 | Structural | Prakash C | LoD 200 - Schematic Concept | 0.071339 | 1 | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
KIADB - Mys | KIADB - Mys |  |  | Package Release | 0 | 1 | [7 empty] | 0 | 0
KIADB - Mys | KIADB - Mys | Structural |  | Complete the project by Q4 | 0 | 1 | [7 empty] | 0 | 0
KIADB - Mys | KIADB - Mys | Structural | Prakash C | LoD 200 - Schematic Concept |  | 1 | Prakash C | Satish | Alwin | Raghav | Vinay |  | 0
Imagine Campus | Imgn |  |  | Package Release | 0.19 | 1 | [7 empty] | 0 | 0
Imagine Campus | Imgn | Structural |  | Package Release [Complete LoD 200] | 0.19 | 1 | [7 empty] | 0 | 0
Imagine Campus | Imgn | Structural | Prakash C | LoD 200 - Schematic Concept | 0.19 | 1 | Prakash C | Lincy | Charan | - | Karthik |  | 0 | 0
OtR OOTA | OTR OOTA |  |  | Package Release | 0.020044 | 1 | [7 empty] | 0 | 0
OTR OOTA | OTR OOTA | Structural |  | Complete Schematic concept | 0.020044 | 1 | [7 empty] | 0 | 0
OTR OOTA | OTR OOTA | Structural | Prakash C | LoD 200 - Schematic Concept | 0.020044 | 1 | Prakash C | Theja | - |  | Samyukta |  | 0 | 0
Blue in Green | BiG |  |  | Package Release | 2.5364 | 2 | [7 empty] | 0 | 0
Blue in Green | BiG | Structural |  | LoD 300 - Pre Construction Set | 2.5364 | 2 | [7 empty] | 0 | 0
Blue in Green | BiG | Structural | Prakash C | LoD 200 - Schematic Concept .v7 [Rework] | 1.0864 | 1 | Prakash C | Lincy | Subrahmanya | - | Darshan |  | 0 | 0
Blue in Green | BiG | Structural | Prakash C | LoD 300 - Pre Construction Set | 1.45 | 1 | Prakash C | Lincy | Subrahmanya | - | Darshan |  | 0 | 0
Vaderahalli | Vdrhl |  |  | Package Release | 4.0202 | 1 | [7 empty] | 0 | 0
Vaderahalli | Vdrhl | Structural |  | LoD 200 - Schematic Concept | 4.0202 | 1 | [7 empty] | 0 | 0
Vaderahalli | Vdrhl | Structural | Prakash C | LoD 200 - Schematic Concept | 4.0202 | 1 | Prakash C | Satish | Alwin | Raghav | Darshan |  | 0 | 0
Note on F80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: North boundary wall FEATURE WALL & TYPICAL STRUCTURAL DETAILS
Note on F81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: WTP upstand details OWC metal structural details

## Goals FY 26-27Q2 Atul P (hidden)
FY 2026-27 Q2 ¦ Design Goals + Billing ¦ Atul P |  |  |  |  | 0.3493 | 29 | [7 empty] | 0 | 0 | 0.3493 | 29
Project | Phase | Discipline | Design Lead | Description | Plan - Billing [Cr.] | Plan - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | Actuals - Billing [Cr.] | Actuals - Pkgs | 0% | 0%
Ongoing Projects |  |  |  |  | 0.3493 | 25 | [7 empty] | 0 | 0
Fullkit Homes | FKH |  |  | Package Release | 0 | 25 | [7 empty] | 0 | 0
TuiG | Tuig [V20] | Architecture |  | Tuig [V20] | 0 | 2 | [7 empty] | 0 | 0
TuiG | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
TuiG | FKH | Architecture | Atul P | Default Marketing BOQ |  | 1 | Atul P
TuiG | Tuig [V30] | Architecture |  | Tuig [V30] |  | 3 | [8 empty] | 0
TuiG | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
TuiG | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
TuiG | FKH | Architecture | Atul P | Default Marketing BOQ |  | 1 | Atul P
TuiG | Tuig [V40] | Architecture |  | Tuig [V40] |  | 3 | [8 empty] | 0
TuiG | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
TuiG | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
TuiG | FKH | Architecture | Atul P | Default Marketing BOQ |  | 1 | Atul P
Harohalli | Harohalli [V20] | Architecture |  | Harohalli [V20] | 0 | 2 | [7 empty] | 0 | 0
Harohalli | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
Harohalli | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
Harohalli | Harohalli [V30] | Architecture |  | Harohalli [V30] |  | 2 | [8 empty] | 0
Harohalli | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
Harohalli | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
Harohalli | Harohalli [V50H] | Architecture |  | Harohalli [V50H] |  | 2 | [8 empty] | 0
Harohalli | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
Harohalli | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
Violet Hill | Violet Hill [P1] | Architecture |  | Violet Hill [P1] |  | 3 | [8 empty] | 0
Violet Hill | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
Violet Hill | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
Violet Hill | FKH | Architecture | Atul P | Default Marketing BOQ |  | 1 | Atul P
Violet Hill | Violet Hill [P2] | Architecture |  | Violet Hill [P2] |  | 3 | [8 empty] | 0
Violet Hill | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
Violet Hill | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
Violet Hill | FKH | Architecture | Atul P | Default Marketing BOQ |  | 1 | Atul P
Shreegaon | Shreegaon [V50H] | Architecture |  | Shreegaon [V50H] |  | 1 | [8 empty] | 0
Shreegaon | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
OTF | OTF [V60] | Architecture |  | OTF [V60] |  | 2 | [8 empty] | 0
OTF | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
OTF | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
OTF | OTF [V25H] | Architecture |  | OTF [V25H] |  | 2 | [8 empty] | 0
OTF | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
OTF | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
Interior Design + Product Development |  |  |  |  | 0.3493 | 4 | [7 empty] | 0 | 0
Interior Design | ID |  |  | Package Release | 0.3493 | 4 | [7 empty] | 0 | 0
Personalised Customisation | PID | Interior Design |  |  | 0.3493 | 4 | [7 empty] | 0 | 0
Personalised Customisation | PID | Interior Design | Atul P | POARR | 0.3493 | 4 | [7 empty] | 0

## Pivot (hidden)
Row Labels | Sum of Plan - Billing [Cr.] | Count of Plan - Pkgs |  | 14.165 | Project Design | 181.8301 | 467
Atul P |  | 26 |  |  |  | Billing | Pkg
Cijey M | 40.648 | 39 |  |  | Atul P |  | 25
Gagan | 33.4452 | 133 |  |  | Cijey M | 40.648 | 39
Manik G | 1.4243 | 20 |  |  | Manik G | 1.4243 | 20
Naveen Y | 29.7315 | 25 |  |  | Gagan | 36.3041 | 147
Om Prakash | 11.5713 | 38 |  |  | MP | 22.1716 | 23
Prakash C | 24.516 | 124 |  |  | MEP | 9.0164 | 76
Saji A | 36.5056 | 47 |  |  | LS | 5.116 | 48
Grand Total | 177.8419 | 452 |  |  | Naveen Y | 29.7315 | 25
[5 empty] | Om Prakash | 11.39 | 38
[5 empty] | Prakash C | 25.8266 | 126
[5 empty] | Saji A | 36.5056 | 47
[5 empty] | Interior Design | 2.98 | 107
[6 empty] | Billing - Q2 | ID GFC - Q2
[5 empty] | Atul P | 0.26 | 3
[5 empty] | Personalised | 0.26 | 3
[5 empty] | Navneet | 1.04 | 90
[5 empty] | Default | - | 14
[5 empty] | Edesign | 0.53 | 69
[5 empty] | Personalised | 0.51 | 7
[5 empty] | Saji | 1.68 | 14
[5 empty] | Personalised | 1.68 | 14
T
T
T
T
T
T

## One liner (hidden)
|  |  | 181.8501 | 447
|  |  | 38.4407 | 269 | #REF!
Project | Phase | Description | Billing | Pkgs
AtR | Ph 1, 2a, 2b, 2c | Release all GFCs to complete the project design | 0.43272 | 8
AtR | Ph 3 | Structural Drawings for all Villas | 1.7289 | 32
AtR | Ph 3 | V45 Default
AtR | Commercial | Release all GFCs to complete the project design | 0.81651 | 8
PoaRR-Res | T1-7 + Villas | LOD 350 V40 Default and it's variants | 4.1292 | 15
PoaRR-Res | T1-7 + Villas | V40 Structural Drawings and Envelope
PoaRR-Res | T1-7 + Villas | Release all GFCs to complete the project design for T1-7 + Villas [Except Sports complex]
PoaRR-Res | T8 | All Structural drawings | 9.6993 | 39
PoaRR-Res | T8 | Default Products [L20, L22 and D35]
itQE | Ph1 | Site development and Clubhouse Structural Drawings | 0.084072 | 3
itQE | Ph2a | Experience Home [ V35 ]
itQE | Ph2a | Release all GFCs to complete the project design | 0.41919 | 5
itQE | Ph2b | All Podium and Tower Structural Drawings | 3.02 | 21
itQE | Ph2b | Site Development + Site MEP Drawings
itQE | Ph2c [T9] | Foundation and SSL 1 Drawings | 0.63298 | 9
OtR | Ph1 | Release all GFCs to complete the project design | 0.87 | 10
TuiG |  | Release all GFCs to complete the project design | 2.4296 | 10
TMFT-Ph 2 | Ph 2 | Release all GFCs to complete the project design | 0.03 | 1
DbtW |  | Release all GFCs to complete the project design | 8.8226 | 15
SftW |  | Release all GFCs to complete the project design | 1.2186 | 17
LGCE Campus |  | Concept to be closed | 0.47796 | 5
MT Plano | MT Plano | Concept to be closed | 1.2668 | 13
MeenaSai Res |  | Pre-Construction Set | 0.141 | 6
NH Homestay |  | Structural GFCs + Masonry + Envelope | 1.2145 | 14
Indira Nagar residence |  | Interiors GFC | 0.004913 | 6
OtR Museum |  | Concept to be closed | 0.56189 | 5
Full kit Homes |  |  |  | 25
Rework Pkgs | Rwrk |  | 0.44 | 2
New Projects |  |  | 143.4093 | 178 | #REF!
OTR-Ph02 | Ph 2 | Package Release [Complete Approvals by Q2] | 1.6886 | 10
TMFT-Ph 3 | Ph 3 | Package Release [LOD 350 -Tower Habitable levels, MP Pkg 2, ISS Pkg 2 by 27'Q1] | 0.62685 | 5
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | LoD 300 [Marketing and Sales, Pre Construction Set], LoD 350 [Experience Home + Project Experience] | 14.2039 | 10
Sarjapur Road [South Block-Resi] | Srjp - Res | Package Release [LOD 350 - Towers, Experience Homes, Clubhouse and Approvals by 27'Q1] | 18.1053 | 13
Sarjapur - C (South Block) | Srjp - C - SB | Package Release [LOD 350 - Towers by 27'Q1] | 15.6918 | 8
Sarjapur - C (North Block) | Srjp - C - NB | Package Release [LOD 350 - Towers by 27'Q1] | 5.2306 | 8
OTF | OTF | Package release [LoD 350 by 27'Q1] | 3.8583 | 18
Harohalli [Plotted] | Harohalli | Package Release [Dsgn Brf, LOD 200, Approvals, Exp, LoD 300, LoD 350 Package 1 -9 by Q1'27] | 7.0172 | 14
Shreegaon [61.6a] | Ph 1 | Package Release [till LoD 300 - Pre Construction Set] | 4.1961 | 13
Violet Hill [21.76a] | Ph 1 | Package Release [till LoD 350 - Infra - Plot Boundary & Enclosures] | 1.5429 | 24
Violet Hill [27.08a] | Ph 2 | Package Release [till LoD 300 - Pre Construction Set] | 1.4612 | 12
Byatarayanpura [behind Mall of Asia] | Byatarayanpura | Package Release [LOD 350 -Tower Pkg 1, MP Pkg 1, ISS Pkg 1, CH Pkg 1 by 27'Q1] | 1.6141 | 1
TR Mills Chamarajpet | TR Mills | Package Release [LOD 300, LOD 350 Exp home by 27'Q1] | 5.965 | 1
KIADB - Mys | KIADB - Mys | Package Release [Complete the project by Q4] | 0 | 8
Imagine Campus | Imgn | Package Release [Complete LoD 100, 200] by 26Q2 | 1.49 | 6
OtR OOTA | OTR OOTA | Package Release [Complete Approvals by Q2] | 0.19417 | 8
DonaPaula | DP | Package Release [LOD 350 -MP, ISS, CH, Tower Habitable levels by 27'Q1] | 7.2667 | 9
Varthur 52a | Varthur 52a | Package Release [LOD 300, LOD 350 Exp home by 27'Q1] | 18.4 | 1
Vaderahalli | Vdrhl | LoD 200 - Schematic Concept | 34.8567 | 9
NH10a Sultanpet | NH10a | Package Release[Dsgn Brf, LOD 200, Approvals, LOD 300, Exp Home] | 0 | 0
NH37a [Acharalahalli] | NH37a Ach | Package Release [Dsgn Brf, LOD 200] | 0 | 0
NH30a [Madakuhosahalli] | NH30a MH | Package release [Dsgn Brf, LOD 200, Approvals, LOD 300, Exp Home] | 0 | 0
Vijayapura | Vijayapura | Package Release [Dsgn Brf, LoD 100] | 0 | 0
Savakanahalli | Svknhli | Package Release [Dsgn Brf, LOD 100] | 0 | 0
Aundh 3a | Aundh [3a] | Package Release [Dsgn Brf, LOD 100] | 0 | 0
Yadgarpalle | Yadgarpalle | Package Release [Dsgn Brf, LOD 100] | 0 | 0
Lonavala | Lonavala | Package Release [Dsgn Brf, LOD 100] | 0 | 0
Jhanjh Lake [Mayfair] | JL - MF | Package Release [Dsgn Brf, LOD 100] | 0 | 0
Sarjapur - Plotted | Srjp-P | Package Release [Dsgn Brf, LoD 100] | 0 | 0
Poinciana | Poinciana | On Hold | 0 | 0
Windmils, SftW | Windmils, SftW | TBD with Kamal | 0 | 0
Saideep reddy Res,Hyd | Saideep Res | Package Release [Complete the Project by Q4] | 0 | 0
5a GTC Indrngr | 5a GTC | Complete the project [except LoD 350 - Interiors] | 0 | 0

## Notes (hidden)
Atr Commercial
Entrance gate to be designed by product design team
Staff dining and food court moved to level 2, concept to be presented to Shibanee ma'am on 14th April
Sarjapur
Sarjapur North Block Schematic to be presented to Shibanee Ma'am on 21st, Fire tower requirement to be checked with liaisioning consultant
MEP constulant to be closed by 15th April
Elevator Consultant PO with
OtF
Boundary Wall and Entrance by 17th Aprl
L22 Workshop | Target closure by 30-May'26
R25 Workshop | by 10-Apr'26
L20, D35 - Signoffs
V80 Workshop | 09-Apr'26 [9.30am]
Violet hill - Sales lounge std |  | Workshop this week
AtR-C [Staff dining] | 14-Apr'26
Srjp-NB [C] | 21-Apr'26
DbtW Workshop on Site Dev + MEP and Schematic
Master Spec to be closed from DBTW and Think design point of view
ATR clubhouse badminton
DbtW clubhouse envelope, the experience home portion
DbtW Skywalk concept closure in May
DbtW Temporary Infrastructure scheme - PD
SFTW need to get back to Shibanee ma'am, based on the
TUIG clubhouse workshop next week
Tower 9, Initital pile load test [Critical]

## Goals, Actuals 2026 Q1 (Remark) (hidden)
[7 empty] | Plan 26Q1 |  |  | Actual 26Q1 |  |  |  | AR | STR | MEP | LDS
| 2026 ¦ Design Goals + Billing | [5 empty] | Billing [Cr.] | Pkgs |  | Billing [Cr.] | Pkgs |  | 419 | 189 | 115 | 73 | 42
| Project | Phase | Discipline | Design Lead | Description |  | 115.481 | 405 |  | 9.4373 | 38 |  | 18 | 4 | 7 | 4 | 3
| Ongoing Projects | [5 empty] | 38.3344 | 255 |  | 6.8335 | 30
| AtR | Ph 1, 2a, 2b, 2c |  |  | Package Release [Complete LoD 350 by Q1] |  | 0.43272 | 8 |  | 0 | 0
| AtR | Ph 1, 2a, 2b, 2c | Architecture |  | Package Release [Complete LoD 350 by Q1] |  | 0.39703 | 4 |  | 0 | 0
| AtR | Ph 1, 2a, 2b | Architecture | Saji A | Clubhouse + Amenities - Clubhouse—Interiors and Facilities |  | 0.27 | 1 |  | 0
Auditorium Drawings
| AtR | Ph 1, 2a, 2b | Architecture | Saji A | Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] |  | 0.045377 | 1 |  | 0
Staff Lounge Drawings
| AtR | Ph 2c | Architecture | Saji A | Master Plan - Site MEP |  | 0.042238 | 1 |  | 0
STP-2 Drawings
UGT-2 Drawings
Panel Room-2 Drawings
| AtR | Ph 2c | Architecture | Saji A | Clubhouse + Amenities - Sporting Facilities |  | 0.039416 | 1 |  | 0
Tennis Court Drawings
| AtR | Ph 1, 2a, 2b, 2c | Structural |  | Package Release [Complete LoD 350 by Q1] |  | 0.021351 | 3 |  | 0 | 0
| AtR | Ph 1, 2a, 2b | Structural | Prakash C | Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] |  | 0.0052867 | 1 |  | 0
| AtR | Ph 2c | Structural | Prakash C | Master Plan - Site MEP |  | 0.010861 | 1 |  | 0
UGT-2 Drawings
Gas Bank-2 Drawings
| AtR | Ph 2c | Structural | Prakash C | Clubhouse + Amenities - Sporting Facilities |  | 0.0052029 | 1 |  | 0
Badminton Court Roof Drawings
| AtR | Ph 1, 2a, 2b, 2c | MEP |  | Package Release [Complete LoD 350 by Q1] |  | 0.014337 | 1 |  | 0 | 0
| AtR | Ph 2c | MEP | Gagan | Master Plan - Site MEP |  | 0.014337 | 1 |  | 0
Gas Bank-2 Drawings
| AtR | Ph 3 |  |  | Package Release [Complete LoD 350 by Q1] |  | 2.5305 | 42 |  | 0.89157 | 12
| AtR | Ph 3 | Architecture |  | Package Release [Complete LoD 350 by Q1] | 0 | 1.8088 | 15 | 0 | 0.68496 | 3 | 0
| AtR | Ph 3 | Architecture | Saji A | Contract + Design brief |  | 0.27398 | 1 |  | 0.27398 | 1
| AtR | Ph 3 | Architecture | Saji A | Schematic Concept |  | 0.27398 | 1 |  | 0.27398 | 1
| AtR | Ph 3 | Architecture | Saji A | Approvals |  | 0.13699 | 1 |  | 0.13699 | 1
| AtR | Ph 3 | Architecture | Saji A | Pre Construction Set |  | 0.27398 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Home Products - V45 Default and it's variants |  | 0.36 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 33 - Foundations and Sub-Grade Structure |  | 0.043983 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 34 - Foundations and Sub-Grade Structure |  | 0.043983 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 29 - Foundations and Sub-Grade Structure |  | 0.065974 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 29 - Building Envelope + Plot Development |  | 0.065974 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 30 - Foundations and Sub-Grade Structure |  | 0.065974 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 30 - Building Envelope + Plot Development |  | 0.065974 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 31 - Building Envelope + Plot Development |  | 0.014661 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 32 - Building Envelope + Plot Development |  | 0.029322 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 34 - Building Envelope + Plot Development |  | 0.043983 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Master Plan - Master Plan |  | 0.05 | 1 |  | 0
| AtR | Ph 3 | Structural |  | Package Release [Complete LoD 350 by Q1] |  | 0.35597 | 15 |  | 0.10442 | 3
| AtR | Ph 3 | Structural | Prakash C | Schematic Concept |  | 0.093422 | 1 |  | 0.093422 | 1
| AtR | Ph 3 | Structural | Prakash C | Pre Construction Set |  | 0.093422 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Foundations and Sub-Grade Structure |  | 0.021107 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Super Structure |  | 0.03166 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Building Envelope + Plot Development |  | 0.0052767 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Foundations and Sub-Grade Structure |  | 0.021107 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Super Structure |  | 0.03166 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Building Envelope + Plot Development |  | 0.0052767 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Foundations and Sub-Grade Structure |  | 0.004 | 1 |  | 0.004 | 1
| AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Super Structure |  | 0.007 | 1 |  | 0.007 | 1
| AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Building Envelope + Plot Development |  | 0.001 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 32 - Building Envelope + Plot Development |  | 0.0023452 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Foundations and Sub-Grade Structure |  | 0.014071 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Super Structure |  | 0.021107 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Building Envelope + Plot Development |  | 0.0035178 | 1 |  | 0
| AtR | Ph 3 | MEP |  | Package Release [Complete LoD 350 by Q1] |  | 0.1936 | 7 |  | 0.024327 | 3
| AtR | Ph 3 | MEP | Gagan | Schematic Concept [V80] |  | 0.0215 | 1 |  | 0.0215 | 1
| AtR | Ph 3 | MEP | Gagan | PreConstruction Set |  | 0.0215 | 1 |  | 0
| AtR | Ph 3 | MEP | Gagan | Villa Block 31 - Foundations and Sub-Grade Structure |  | 0.00094245 | 1 |  | 0.00094245 | 1
| AtR | Ph 3 | MEP | Gagan | Villa Block 32 - Foundations and Sub-Grade Structure |  | 0.0018849 | 1 |  | 0.0018849 | 1
| AtR | Ph 3 | MEP | Gagan | Villa Block 34 - Foundations and Sub-Grade Structure |  | 0.0028274 | 1 |  | 0
| AtR | Ph 3 | MEP | Gagan | Home Products - V45 Default and it's variants |  | 0.10495 | 1 |  | 0
| AtR | Ph 3 | MEP | Gagan | Master Plan - Master Plan |  | 0.04 | 1 |  | 0
| AtR | Ph 3 | Landscape |  | Package Release [Complete LoD 350 by Q1] |  | 0.17213 | 5 |  | 0.077864 | 3
| AtR | Ph 3 | Landscape | Gagan | Schematic Concept |  | 0.047864 | 1 |  | 0.047864 | 1
| AtR | Ph 3 | Landscape | Gagan | Preconstruction Set |  | 0.047864 | 1 |  | 0
| AtR | Ph 3 | Landscape | Gagan | Home Products - V45 Default |  | 0.046405 | 1 |  | 0
| AtR | Ph 3 | Landscape | Gagan | Master Plan |  | 0.02 | 1 |  | 0.02 | 1
| AtR | Ph 3 | Landscape | Gagan | Site Development - 06 Landscape |  | 0.01 | 1 |  | 0.01 | 1
| AtR - C | Com |  |  | Package Release [Complete LoD 350 by Q1] |  | 0.94562 | 9 |  | 0.12911 | 1
| AtR - C | Com | Architecture |  | Package Release [Complete LoD 350 by Q1] |  | 0.36421 | 3 |  | 0 | 0
| AtR - C | Com | Architecture | Naveen Y | Master Plan - Site Development |  | 0.13658 | 1 |  | 0
| AtR - C | Com | Architecture | Naveen Y | Master Plan - Site MEP |  | 0.18211 | 1 |  | 0
| AtR - C | Com | Architecture | Naveen Y | Master Plan - Landscaping |  | 0.045527 | 1 |  | 0
| AtR - C | Com | Structural |  | Package Release [Complete LoD 350 by Q1] |  | 0.4139 | 4 |  | 0.12911 | 1
| AtR - C | Com | Structural | Prakash C | Tower-[Commercial] - Habitable Level 1-2 |  | 0.12911 | 1 |  | 0.12911 | 1
| AtR - C | Com | Structural | Prakash C | Tower-[Commercial] - Habitable Level 3-5 |  | 0.25823 | 1 |  | 0
| AtR - C | Com | Structural | Prakash C | Master Plan - Site Development |  | 0.014486 | 1 |  | 0
| AtR - C | Com | Structural | Prakash C | Master Plan - Site MEP |  | 0.012072 | 1 |  | 0
| AtR - C | Com | MEP |  | Package Release [Complete LoD 350 by Q1] |  | 0.16751 | 2 |  | 0 | 0
| AtR - C | Com | MEP | Gagan | Master Plan - Master Plan |  | 0.038655 | 1 |  | 0
| AtR - C | Com | MEP | Gagan | Master Plan - Site MEP |  | 0.12885 | 1 |  | 0
| TMD Ph2 | Ph 2 |  |  | Childern play area [Complete by Q2] |  | - | 0 |  | - | 0
| TMD Ph2 | Ph 2 |  |  | Childern play area |  | - |  |  | -
| PoaRR-Res | Res |  |  | Package Release [Complete the project by Q1] |  | 3.767 | 15 |  | 0 | 0
| PoaRR-Res | Res | Architecture |  | Complete the project |  | 3.3659 | 8 |  | 0 | 0
| PoaRR-Res | Res | Architecture | Saji A | Villa Cluster 3 - All Levels |  | 0.17 | 1 |  | 0
Chamber Setting Out – Villa Cluster 03
Gas Pipeline Routing
| PoaRR-Res | Res | Architecture | Saji A | Villa Cluster 3 - Building Envelope and Common Areas |  | 0.17 | 1 |  | 0
End Villa Wirecut details
Garden Landscape Detail
Wooden Deck Detail
| PoaRR-Res | Res | Architecture | Saji A | V40 Default and it's variants |  | 1.18 | 1 |  | 0
| PoaRR-Res | Res | Architecture | Saji A | ISS Building Envelope and Common Areas |  | 1.0659 | 1 |  | 0
IBMS Room GFC Set
Part Sections 1, 2, 3
| PoaRR-Res | Res | Architecture | Saji A | Residential - Site Development |  | 0.45 | 1 |  | 0
| PoaRR-Res | Res | Architecture | Saji A | Masterplan - Site MEP |  | 0.15 | 1 |  | 0
West Boundary Wall Detail - 03
V40 Side Compound Wall
| PoaRR-Res | Res | Architecture | Saji A | Masterplan - Landscaping |  | 0.15 | 1 |  | 0
Phase 2 Signage Plan
Phase 2 Signage Details
| PoaRR-Res | Res | Architecture | Saji A | Amenities & Facilities - Sporting Facilities |  | 0.03 | 1 |  | 0
| PoaRR-Res | Res | Structural |  | Complete the project |  | 0.36 | 3 |  | 0 | 0
| PoaRR-Res | Res | Structural | Prakash C | Site Development |  | 0.19 | 1 |  | 0
Enclosure And Fencing Details - 1
Compound Wall And Boundary Walls (Master Plan Showing Boundary Wall Extent Details)
| PoaRR-Res | Res | Structural | Prakash C | Site MEP |  | 0.16 | 1 |  | 0
| PoaRR-Res | Res | Structural | Prakash C | Sporting Facilities |  | 0.01 | 1 |  | 0
| PoaRR-Res | Res | MEP |  | Complete the project |  | 0.0010915 | 3 |  | 0 | 0
| PoaRR-Res | Res | MEP | Gagan | Site MEP |  | 0.36 | 1 |  | 0
| PoaRR-Res | Res | MEP | Gagan | Clubhouse Outdoor Spaces and Pool |  | 0.002183 | 1 |  | 0
Pool Deck Drainage Routing
| PoaRR-Res | Res | MEP | Gagan | Sporting Facilities |  | 0.0010915 | 1 |  | 0
| PoaRR-Res | Res | Landscape |  | Complete the project |  | 0.04 | 1 |  | 0 | 0
| PoaRR-Res | Res | Landscape | Gagan | Amenities & Facilities - Community spaces [Sporting Facilities] |  | 0.04 | 1 |  | 0
| PoaRR-T08 | T08 |  |  | Package Release [Complete the project by Q1] |  | 8.9238 | 28 |  | 0 | 0
| PoaRR-T08 | T08 | Architecture |  | Package Release [Complete the project except Penthouse Defaults] |  | 7.0838 | 18 |  | 0 | 0
| PoaRR-T08 | T08 | Architecture | Saji A | ISS - Foundations & Grade Slab |  | 0.2 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | ISS - Parking Level Subgrade |  | 0.41 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | ISS - Podium Slab |  | 0.61 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | ISS - Building Envelope and Common Areas |  | 0.82 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Habitable Level 01 |  | 0.48 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Building Envelope and Common Areas [Typical Tower Levels] |  | 0.96385 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | L22 Default |  | 0.52 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | L20 Default [Modification for Dry Wall] |  | 0.52 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | D35 Default [Modification for Dry Wall] |  | 0.52 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Master Plan |  | 0.17 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Penthouse Levels |  | 0.48 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Terrace Level |  | 0.24 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] |  | 0.96 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Landscape |  | 0.03 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Site MEP |  | 0.03 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Clubhouse—Outdoor Spaces and Pool |  | 0.015 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Community spaces [Board Walk, Children play area] |  | 0.015 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Site Development |  | 0.1 | 1 |  | 0
| PoaRR-T08 | T08 | Structural |  | Complete the project |  | 1.7 | 7 |  | 0 | 0
| PoaRR-T08 | T08 | Structural | Prakash C | Penthouse Levels |  | 0.2 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | Terrace Level |  | 0.4 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Foundations & Grade Slab |  | 0.32 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Podium Slab |  | 0.32 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Parking Level Subgrade |  | 0.43 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | Site Development |  | 0.02 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | Site MEP |  | 0.01 | 1 |  | 0
| PoaRR-T08 | T08 | MEP |  | Package Release [Complete the project] |  | 0.14 | 3 |  | 0 | 0
| PoaRR-T08 | T08 | MEP | Gagan | ISS - Foundation and Gradeslab |  | 0.02 | 1 |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | L20 Default and it's variants |  | 0.06 | 1 |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | D35 Default and it's variants |  | 0.06 | 1 |  | 0
| PoaRR-T08 | T08 | Landscape |  | Package Release [Complete the project]
| ITQE-Ph1 | Ph 1 |  |  | Package Release [Complete the project by Q1] |  | 0.084072 | 3 |  | 0 | 0
| ITQE-Ph1 | Ph 1 | Architecture |  | Complete the project |  | 0 | 0 |  | 0 | 0
| ITQE-Ph1 | Ph 1 | Structural |  | Complete the project |  | 0.084072 | 3 |  | 0 | 0
| ITQE-Ph1 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site Development |  | 0.060249 | 1 |  | 0
Recharge pit details
| ITQE-Ph1 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Clubhouse—Outdoor Spaces and Pool |  | 0.011912 | 1 |  | 0
Heated pool details
Swimming pool details
Clubhouse storm water tank details
Clubhosue sewage tank details
Filteration room details
| ITQE-Ph1 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Community spaces |  | 0.011912 | 1 |  | 0
Tree Avenue details
| ITQE-Ph1 | Ph 1 | MEP |  | Complete the project
| ITQE-Ph1 | Ph 1 | Landscape |  | Complete the project
| ITQE-Ph2a | Ph 2a |  |  | Package Release [Complete the project by Q1] |  | 0.41919 | 5 |  | 0 | 0
| ITQE-Ph2a | Ph 2a | Architecture |  | Complete the project |  | 0.25 | 2 |  | 0 | 0
| ITQE-Ph2a | Ph 2a | Architecture | Cijey M | Master Plan ¦ Site Development |  | 0.07 | 1 |  | 0
Boundary wall details
| ITQE-Ph2a | Ph 2a | Architecture | Cijey M | Experience Home + Project Experience [ V35 ] |  | 0.18 | 1 |  | 0
Internal Staircase details
| ITQE-Ph2a | Ph 2a | Structural |  | Complete the project |  | 0.16919 | 3 |  | 0 | 0
| ITQE-Ph2a | Ph 2a | Structural | Prakash C | Experience Home + Project Experience [ V35 ] |  | 0.07 | 1 |  | 0
Internal Staircase details
| ITQE-Ph2a | Ph 2a | Structural | Prakash C | Master Plan ¦ Site Development |  | 0.054104 | 1 |  | 0
Recharge pit details
Boundary wall details
| ITQE-Ph2a | Ph 2a | Structural | Prakash C | Master Plan ¦ Site MEP |  | 0.045086 | 1 |  | 0
Electrical room cutout and sleeve details
0 | ITQE-Ph2a | Ph 2a | MEP |  | Complete the project |  |  | 0 |  |  | 0
| ITQE-Ph2a | Ph 2a | Landscape |  | Complete the project |  |  | 0 |  |  | 0
| ITQE-Ph2b | Ph 2b |  |  | Package Release [ Complete the project by Q3] |  | 3.527 | 17 |  | 2.517 | 7
| ITQE-Ph2b | Ph 2b | Architecture |  | Complete the project |  | 2.3754 | 4 |  | 2.3454 | 3
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | ISS 5&6 ¦ Structural Slab 01 [Basement] |  | 0.3 | 1 |  | 0.3 | 1
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | ISS 7 ¦ Structrural Slab 01 [Basement] |  | 0.3 | 1 |  | 0.3 | 1
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | Master Plan ¦ Master Plan |  | 0.03 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | L25 Default and it's variants |  | 1.7454 | 1 |  | 1.7454 | 1
| ITQE-Ph2b | Ph 2b | Structural |  | Complete the project |  | 1.12 | 11 |  | 0.14 | 2
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 05 ¦ Habitable Level - Even |  | 0.07 | 1 |  | 0.07 | 1
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 05 ¦ Habitable Level - Odd |  | 0.07 | 1 |  | 0.07 | 1
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 06 ¦ Habitable Level - Even |  | 0.07 | 1 |  | 0
SSL 22 - Slab details
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 06 ¦ Habitable Level - Odd |  | 0.07 | 1 |  | 0
SSL 21 - Slab details
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 07 ¦ Habitable Level - Even |  | 0.07 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 07 ¦ Habitable Level - Odd |  | 0.07 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS5&6 ¦ Structrural Slab 01 [Basement] |  | 0.13 | 1 |  | 0
SSL 01 - Slab details
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Foundations & Sub¦Grade |  | 0.18 | 1 |  | 0
STP details
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Structrural Slab 01 [Basement] |  | 0.13 | 1 |  | 0
SSL 01 - Slab details
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS5&6 ¦ Podium Slab |  | 0.13 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Podium Slab |  | 0.13 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | MEP |  | Complete the project |  | 0.031656 | 2 |  | 0.031656 | 2
| ITQE-Ph2b | Ph 2b | MEP | Gagan | ISS -5 & 6 ¦ Structrural Slab 01 [Basement] |  | 0.015828 | 1 |  | 0.015828 | 1
| ITQE-Ph2b | Ph 2b | MEP | Gagan | ISS -7 ¦ Structrural Slab 01 [Basement] |  | 0.015828 | 1 |  | 0.015828 | 1
| ITQE-Ph2b | Ph 2b | Landscape |  | Complete the project |  |  | 0 |  |  | 0
| ItQE-Ph2c [T9] | Ph 2c |  |  | Package Release [LoD 350-ISS, Habitable Level 11-20] |  | 0.63298 | 9 |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture |  | LoD 350 - ISS, Habitable Level 11-20 |  | 0.30106 | 3 |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | ISS 9 ¦ Foundations & Grade Slab |  | 0.092092 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | Tower 9 ¦ Foundation and Grade Slab |  | 0.1306 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | Tower 9 ¦ Parking Level-Sub grade |  | 0.078362 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural |  | LoD 350 - ISS, Habitable Level 11-20 |  | 0.2848 | 4 |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | ISS 9 ¦ Earthwork |  | 0.0097618 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | ISS 9 ¦ Foundations & Grade Slab |  | 0.039047 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | Tower 9 ¦ Foundation and Grade Slab |  | 0.118 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | Tower 9 ¦ Parking Level-Sub grade |  | 0.118 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP |  | LoD 350 - ISS, Habitable Level 11-20 |  | 0.047123 | 2 |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP | Gagan | ISS 9 ¦ Foundations & Grade Slab |  | 0.0163 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP | Gagan | Tower 9 ¦ Foundation and Grade Slab |  | 0.030822 | 1 |  | 0
| OTR-Ph01 | Ph 1 |  |  | Package Release [Complete the project by Q1] |  | 1.38 | 11 |  | 0.51 | 1
| OTR-Ph01 | Ph 1 | Architecture |  | Complete the project |  | 0.96 | 5 |  | 0.51 | 1
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | Individual Homes ¦ V25 Default & its Variant |  | 0.51 | 1 |  | 0.51 | 1
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | Villa Block ¦ Building Envelope + Plot Development |  | 0.3 | 1 |  | 0
Exposed Brick masonry details
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Master Plan |  | 0.09 | 1 |  | 0
Site plan setting out drawing
Manhole details
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Site Development |  | 0.03 | 1 |  | 0
West boundary wall details
Entrance area gate details
Security cabin details
PMD room details
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Site MEP |  | 0.03 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Structural |  | Complete the project |  | 0.38 | 5 |  | 0 | 0
| OTR-Ph01 | Ph 1 | Structural | Prakash C | Experience Home + Project Experience |  | 0.08 | 1 |  | 0
Pool filteration details
Approach road details
| OTR-Ph01 | Ph 1 | Structural | Prakash C | Villa Block ¦ Super Structure |  | 0.17 | 1 |  | 0
Living water body
| OTR-Ph01 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site Development |  | 0.03 | 1 |  | 0
West boundary wall details
Entrance area gate details
Road Services chamber details
PMD room details
| OTR-Ph01 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site MEP |  | 0.03 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Community spaces [Board Walk, Children play area] |  | 0.07 | 1 |  | 0
Play area and out door gym equipment foundation details
| OTR-Ph01 | Ph 1 | MEP |  | Complete the project |  | 0.04 | 1 |  | 0 | 0
| OTR-Ph01 | Ph 1 | MEP | Gagan | Master Plan ¦ Site MEP |  | 0.04 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Landscape |  | Complete the project |  |  | 0 |  |  | 0
| TuiG | TuiG |  |  | Package Release [Complete LoD 350 by Q2] |  | 1.49 | 12 |  | 0.51595 | 7
| TuiG | TuiG | Master Planning |  | Package Release [Complete the project]
| TuiG | TuiG | Architecture |  | Package Release [Complete the project] |  | 0.15478 | 1 |  | 0 | 0
| TuiG | TuiG | Architecture | Om Prakash | Clubhouse—Outdoor Spaces and Pool |  | 0.15478 | 1 |  | 0
Swimming pool drawings
Lawn tennis & basket ball details with fencing
| TuiG | TuiG | Structural |  | Package Release [Complete the project] |  | 0.83172 | 4 |  | 0.061982 | 1
| TuiG | TuiG | Structural | Prakash C | Site Development |  | 0.40295 | 1 |  | 0
North Boundary wall
Landscape area - Feature wall & typical structural details
| TuiG | TuiG | Structural | Prakash C | Site MEP |  | 0.33579 | 1 |  | 0
OWC
WTP & STP - Upstand details for equipment
| TuiG | TuiG | Structural | Prakash C | Clubhouse—Outdoor Spaces and Pool |  | 0.030991 | 1 |  | 0
Amphitheatre area drawings
Swimming pool drawings
| TuiG | TuiG | Structural | Prakash C | Sporting Facilities |  | 0.061982 | 1 |  | 0.061982 | 1
| TuiG | TuiG | MEP |  | Package Release [Complete the project] |  | 0.31744 | 4 |  | 0.26787 | 3
| TuiG | TuiG | MEP | Gagan | Clubhouse—Structure and Envelope |  | 0.17351 | 1 |  | 0.17351 | 1
| TuiG | TuiG | MEP | Gagan | Clubhouse—Interior & Facilities |  | 0.074361 | 1 |  | 0.074361 | 1
| TuiG | TuiG | MEP | Gagan | Clubhouse—Outdoor Spaces and Pool |  | 0.049574 | 1 |  | 0
Electrical external lighting layout
Complete swimming pool drawings
| TuiG | TuiG | MEP | Gagan | Sporting Facilities |  | 0.02 | 1 |  | 0.02 | 1
| TuiG | TuiG | Landscape |  | Package Release [Complete the project] |  | 0.1861 | 3 |  | 0.1861 | 3
| TuiG | TuiG | Landscape | Gagan | LoD 350 - Clubhouse—Interiors and Facilities | 0.097354 | 0.032451 | 1 |  | 0.032451 | 1
| TuiG | TuiG | Landscape | Gagan | LoD 350 - Clubhouse— Outdoor Spaces |  | 0.081128 | 1 |  | 0.081128 | 1
| TuiG | TuiG | Landscape | Gagan | Community spaces [Board Walk, Children play area] |  | 0.072519 | 1 |  | 0.072519 | 1
| TMFT-Ph 2 | Ph 2 |  |  | Package Release [Complete LoD 350 by Q4 2025] |  | 0.03 | 1 |  | 0 | 0
| TMFT-Ph 2 | Ph 2 | Structural |  | Complete the project |  | 0.03 | 1 |  | 0 | 0
| TMFT-Ph 2 | Ph 2 | Structural | Prakash C | LoD 350 - Site Development |  | 0.03 | 1 |  | 0
Inspection Chamber [Type III]
| DBTW | DBTW |  |  | Package Release [Complete LoD 350 by Q4 2025] |  | 9.659 | 27 |  | 2.2512 | 1
| DBTW | DBTW | Architecture |  | Complete the project |  | 5.878 | 10 |  | 0 | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site Development |  | 0.22115 | 1 |  | 0
` | DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site MEP |  | 0.073717 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Landscaping |  | 0.073717 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Tower 06 - Foundation and Grade Slab |  | 0.064032 | 1 |  | 0
Setting Out Plan
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Foundations & Grade Slab |  | 0.54995 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Podium Slab |  | 0.27497 | 1 |  | 0
Waterproofing Layout SSL 02
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I20 Default and it's variants |  | 2.2352 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I25 Default and it's variants |  | 2.2352 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Structure and Envelope |  | 0.1125 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Outdoor Spaces and Pool |  | 0.0375 | 1 |  | 0
| DBTW | DBTW | Structural |  | Complete the project |  | 3.7441 | 16 |  | 2.2512 | 1
| DBTW | DBTW | Structural | Prakash C | LoD 300 - Pre Construction Set [Podium] |  | 2.2512 | 1 |  | 2.2512 | 1
| DBTW | DBTW | Structural | Prakash C | LoD 350 - ISS - Foundations & Grade Slab |  | 0.52958 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-1-Habitable Level - Even |  | 0.025613 | 1 |  | 0
Typical Level:Column[Above SSL10] & Beam GFCs[Above SSL8]
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level 01 |  | 0.10834 | 1 |  | 0
SSL 3 - Slab and Sleeve GFCs
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level - Even |  | 0.05417 | 1 |  | 0
Typical Level:Column[Above SSL10] &Slab, Sleeve GFCs
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level 01 |  | 0.10834 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level - Even |  | 0.05417 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level 01 |  | 0.10834 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level - Even |  | 0.05417 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 05-Foundation and Grade Slab |  | 0.10834 | 1 |  | 0
Foundation Layout and Raft Reinforcement Details
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level 01 |  | 0.10834 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level - Even |  | 0.05417 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Foundation and Grade Slab |  | 0.051226 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Parking Level-Sub grade |  | 0.051226 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level 01 |  | 0.051226 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level - Even |  | 0.025613 | 1 |  | 0
| DBTW | DBTW | MEP |  | Complete the project |  | 0.036853 | 1 |  | 0 | 0
| DBTW | DBTW | MEP | Gagan | LoD 350 - Master Plan- Master Plan |  | 0.036853 | 1 |  | 0
| SftW | SftW |  |  | Package Release [Complete the project by Q2] |  | 1.2186 | 17 |  | 0 | 0
| SftW | SftW | Architecture |  | Complete the project |  | 0.85178 | 9 |  | 0 | 0
| SftW | SftW | Architecture | Om Prakash | ISS 01 - Podium Slab |  | 0.25575 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Clubhouse—Structure and Envelope |  | 0.081564 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Master Plan - Master Plan |  | 0.18697 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Clubhouse—Outdoor Spaces and Pool |  | 0.027188 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Master Plan - Site Development |  | 0.11218 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Master Plan - Site MEP |  | 0.037394 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Master Plan - Landscaping |  | 0.037394 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Clubhouse + Amenities - Sporting Facilities |  | 0.027188 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Tower 02 - Terrace Level |  | 0.086149 | 1 |  | 0
| SftW | SftW | Structural |  | Complete the project |  | 0.34546 | 6 |  | 0 | 0
| SftW | SftW | Structural | Prakash C | Tower 2 - Terrace Level |  | 0.20116 | 1 |  | 0
| SftW | SftW | Structural | Prakash C | Master Plan - Site Development |  | 0.058457 | 1 |  | 0
| SftW | SftW | Structural | Prakash C | Master Plan - Site MEP |  | 0.048714 | 1 |  | 0
| SftW | SftW | Structural | Prakash C | Clubhouse—Structure and Envelope |  | 0.025989 | 1 |  | 0
| SftW | SftW | Structural | Prakash C | Clubhouse—Outdoor Spaces and Pool |  | 0.0037128 | 1 |  | 0
| SftW | SftW | Structural | Prakash C | Clubhouse—Sporting Facilities |  | 0.0074255 | 1 |  | 0
| SftW | SftW | MEP |  | Complete the project |  | 0.021398 | 2 |  | 0 | 0
| SftW | SftW | MEP | Gagan | MEP ¦ Master Plan - Site MEP |  | 0.020843 | 1 |  | 0
| SftW | SftW | MEP | Gagan | MEP ¦ Clubhouse—Sporting Facilities |  | 0.00055534 | 1 |  | 0
| SftW | SftW | Landscape |  | Complete the project
| LGCE Campus | LGCE Campus |  |  | Package Release [Complete the project by Q4] |  | 0.38042 | 2 |  | 0 | 0
| LGCE Campus | LGCE Campus | Architecture |  | Complete the project |  | 0.38042 | 2 |  | 0 | 0
| LGCE Campus | LGCE Campus | Architecture | Om Prakash | Design Brief |  | 0.15217 | 1 |  | 0
| LGCE Campus | LGCE Campus | Architecture | Om Prakash | LoD 200 - Schematic Concept |  | 0.22825 | 1 |  | 0
| LGCE Campus | LGCE Campus | Structural |  | Complete the project
| LGCE Campus | LGCE Campus | MEP |  | Complete the project
| LGCE Campus | LGCE Campus | Landscape |  | Complete the project
| Ooty Res | Ooty Res |  |  | Package Release [Complete the project by Q4] |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Architecture |  | Complete the project |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Architecture | Manik G | Design Brief |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Architecture | Manik G | LoD 200 - Schematic Concept |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Architecture | Manik G | Approvals |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Structural |  | Complete the project |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Structural | Prakash C | LoD 200 - Schematic Concept |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | MEP |  | Complete the project |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | MEP | Gagan | LoD 200 - Schematic Concept |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | MEP | Gagan | Approvals |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Landscape |  | Complete the project |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Landscape | Gagan | LoD 200 - Schematic Concept |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Landscape | Gagan | Approvals |  | 0 | 0 |  | 0 | 0
| MT Plano | MT Plano |  |  | Package Release [Complete the project by Q3] |  | 0.69535 | 8 |  | 0 | 0
| MT Plano | MT Plano | Architecture |  | Complete the project |  | 0.5469 | 3 |  | 0 | 0
| MT Plano | MT Plano | Architecture | Manik G | Design Brief |  | 0.15626 | 1 |  | 0
| MT Plano | MT Plano | Architecture | Manik G | LoD 200 - Schematic Concept |  | 0.23439 | 1 |  | 0
| MT Plano | MT Plano | Architecture | Manik G | Approvals |  | 0.15626 | 1 |  | 0
| MT Plano | MT Plano | Structural |  | Complete the project |  | 0.071432 | 1 |  | 0 | 0
| MT Plano | MT Plano | Structural | Manik G | LoD 200 - Schematic Concept |  | 0.071432 | 1 |  | 0
| MT Plano | MT Plano | MEP |  | Complete the project |  | 0.040181 | 2 |  | 0 | 0
| MT Plano | MT Plano | MEP | Manik G | LoD 200 - Schematic Concept |  | 0.02009 | 1 |  | 0
| MT Plano | MT Plano | MEP | Manik G | Approvals |  | 0.02009 | 1 |  | 0
| MT Plano | MT Plano | Landscape |  | Complete the project |  | 0.036832 | 2 |  | 0 | 0
| MT Plano | MT Plano | Landscape | Manik G | LoD 200 - Schematic Concept |  | 0.016742 | 1 |  | 0
| MT Plano | MT Plano | Landscape | Manik G | Approvals |  | 0.02009 | 1 |  | 0
| MeenaSai Res | MS Res |  |  | Complete the project by Q3 |  | 0.141 | 6 |  | 0 | 0
| MeenaSai Res | MS Res | Architecture |  | Complete the project |  | 0.105 | 2 |  | 0 | 0
| MeenaSai Res | MS Res | Architecture | Cijey M | LoD 200 - Schematic Concept |  | 0.063 | 1 |  | 0
| MeenaSai Res | MS Res | Architecture | Cijey M | Approvals |  | 0.042 | 1 |  | 0
| MeenaSai Res | MS Res | Structural |  | Complete the project |  | 0.0192 | 1 |  | 0 | 0
| MeenaSai Res | MS Res | Structural | Prakash C | LoD 200 - Schematic Concept |  | 0.0192 | 1 |  | 0
| MeenaSai Res | MS Res | MEP |  | Complete the project |  | 0.0108 | 2 |  | 0 | 0
| MeenaSai Res | MS Res | MEP | Gagan | LoD 200 - Schematic Concept |  | 0.0054 | 1 |  | 0
| MeenaSai Res | MS Res | MEP | Gagan | Approvals |  | 0.0054 | 1 |  | 0
| MeenaSai Res | MS Res | Landscape |  | Complete the project |  | 0.006 | 1 |  | 0 | 0
| MeenaSai Res | MS Res | Landscape | Gagan | LoD 200 - Schematic Concept |  | 0.006 | 1 |  | 0
| NH Homestay | NH HS |  |  | Complete the project by Q1 [except LoD 350 - Interiors - Q2] |  | 1.233 | 15 |  | 0.01857 | 1
| NH Homestay | NH HS | Architecture |  | Complete the project |  | 0.77994 | 4 |  | 0 | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 300 - Pre Construction set |  | 0.12999 | 1 |  | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Foundation and Structure |  | 0.25998 | 1 |  | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Building Envelope + Plot Development |  | 0.19498 | 1 |  | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Interiors |  | 0.19498 | 1 |  | 0
| NH Homestay | NH HS | Structural |  | Complete the project |  | 0.22284 | 3 |  | 0 | 0
| NH Homestay | NH HS | Structural | Prakash C | LoD 300 - Pre Construction set |  | 0.059424 | 1 |  | 0
| NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Foundation and Structure |  | 0.14856 | 1 |  | 0
| NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Building Envelope + Plot Development |  | 0.014856 | 1 |  | 0
| NH Homestay | NH HS | MEP |  | Complete the project |  | 0.14206 | 5 |  | 0 | 0
| NH Homestay | NH HS | MEP | Gagan | Approvals |  | 0.016713 | 1 |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 300 - Pre Construction set |  | 0.016713 | 1 |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Foundation and Structure |  | 0.058495 | 1 |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Building Envelope + Plot Development |  | 0.025069 | 1 |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Interiors |  | 0.025069 | 1 |  | 0
| NH Homestay | NH HS | Landscape |  | Complete the project |  | 0.088207 | 3 |  | 0.01857 | 1
| NH Homestay | NH HS | Landscape | Gagan | LoD 200 - Schematic Concept |  | 0.01857 | 1 |  | 0.01857 | 1
| NH Homestay | NH HS | Landscape | Gagan | LoD 300 - Pre Construction set |  | 0.01857 | 1 |  | 0
| NH Homestay | NH HS | Landscape | Gagan | LoD 350 - Building Envelope + Plot Development |  | 0.051068 | 1 |  | 0
| Indiranagar Res | Indrng Res |  |  | Package Release [Complete LoD 350 by Q1] |  | 0.004113 | 6 |  | 0 | 0
| Indiranagar Res | Indrng Res | Architecture |  | Complete the project |  | 0.004 | 4 |  | 0 | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block A - Interiors |  | 0.0021 | 1 |  | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block B - Interiors |  | 0.000875 | 1 |  | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block C - Interiors |  | 0.000525 | 1 |  | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 -Block C - Building Envelope + Plot Development |  | 0.0005 | 1 |  | 0
| Indiranagar Res | Indrng Res | Landscape |  | Complete the project |  | 0.000113 | 1 |  | 0 | 0
| Indiranagar Res | Indrng Res | Landscape | Gagan | LoD 350 - Block C- Building Envelope + Plot Development |  | 0.000113 | 1 |  | 0
Ground level and gym roof layouts
| Indiranagar Res | Indrng Res | Structural |  | Complete the project |  | 0.0008 | 1 |  | 0 | 0
| Indiranagar Res | Indrng Res | Structural | Prakash C | LoD 350 -Block C - Building Envelope + Plot Development |  | 0.0008 | 1 |  | 0
Gym spiral Staircase
| OTR Museum | OTR Mus |  |  | Package Release [Complete the project by Q2] |  | 0.43996 | 2 |  | 0 | 0
| OTR Museum | OTR Mus | Architecture |  | Complete the project |  | 0.43996 | 2 |  | 0 | 0
| OTR Museum | OTR Mus | Architecture | Cijey M | Design Brief |  | 0.17598 | 1 |  | 0
| OTR Museum | OTR Mus | Architecture | Cijey M | LoD 200 - Schematic Concept |  | 0.26398 | 1 |  | 0
| OTR Museum | OTR Mus | Structural |  | Complete the project
| OTR Museum | OTR Mus | MEP |  | Complete the project
| OTR Museum | OTR Mus | Landscape |  | Complete the project
| Fullkit Homes | FKH |  |  | Package Release |  | 0 | 11 |  | 0 | 0
| TuiG | FKH | Architecture | Atul P | LoD 350 - TuiG [V20, V30 and V40] |  |  | 3
| Harohalli | FKH | Architecture | Atul P | LoD 350 - Harohalli [V20, V30 and V50C] |  |  | 3
| Violet Hill | FKH | Architecture | Atul P | LoD 350 - Violet Hill [P-1 D, P-2 U] |  |  | 2
| Shreegaon | FKH | Architecture | Atul P | LoD 350 - Shreegaon [V50C] |  |  | 1
| OTF | FKH | Architecture | Atul P | LoD 350 - One Tiny Flower [V50H and V25] |  |  | 2
| Rework Pkgs | Rwrk |  |  |  |  | 0.4 | 1 |  | 0 | 0
| PoaRR-T08 | T08 | Structural | Prakash C | STR Package Release [Parking level subgrade] |  | 0.4 | 1 |  | 0
| New Projects | [5 empty] | 77.1466 | 150 |  | 2.6039 | 8
| OTR-Ph02 | Ph 2 |  |  | Package Release [Except Master plan and Amenities] |  | 1.6886 | 10 |  | 0 | 0
| OTR-Ph02 | Ph 2 | Architecture |  | Complete the Project |  | 1.35 | 5 |  | 0 | 0
| OTR-Ph02 | Ph 2 | Architecture | Cijey M | Contract + Design Brief |  | 0.54 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Cijey M | Schematic Concept |  | 0.43 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Cijey M | Approvals |  | 0.21 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Schematic Concept - CH |  | 0.11 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Approvals - CH |  | 0.06 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Structural |  | Complete the Project |  | 0.17172 | 1 |  | 0 | 0
| OTR-Ph02 | Ph 2 | Structural | Prakash C | Schematic Concept |  | 0.17172 | 1 |  | 0
| OTR-Ph02 | Ph 2 | MEP |  | Complete the Project |  | 0.09558 | 2 |  | 0 | 0
| OTR-Ph02 | Ph 2 | MEP | Gagan | Schematic Concept |  | 0.06372 | 1 |  | 0
| OTR-Ph02 | Ph 2 | MEP | Gagan | Approvals |  | 0.03186 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Landscape |  | Complete the Project |  | 0.07128 | 2 |  | 0 | 0
| OTR-Ph02 | Ph 2 | Landscape | Gagan | Schematic Concept |  | 0.05346 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Landscape | Gagan | Approvals |  | 0.01782 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 |  |  | Package Release [Dsgn Brf, LOD 200, Approvals, LOD 300] |  | 0.77324 | 8 |  | 0 | 0
| TMFT-Ph 3 | Ph 3 | Architecture |  | [Dsgn Brf, LOD 200, Approvals, LOD 300, LOD 350] |  | 0.6182 | 3 |  | 0 | 0
| TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Contract + Design Brief |  | 0.24728 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Schematic Concept |  | 0.24728 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Approvals |  | 0.12364 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | Structural |  | [LOD 200, LOD 300, LOD350] |  | 0.078635 | 1 |  | 0 | 0
| TMFT-Ph 3 | Ph 3 | Structural | Prakash C | Schematic Concept |  | 0.078635 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | MEP |  | [LOD 200, Approvals, LOD 300, LOD 350] |  | 0.043769 | 2 |  | 0 | 0
| TMFT-Ph 3 | Ph 3 | MEP | Gagan | Schematic Concept |  | 0.029179 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | MEP | Gagan | Approvals |  | 0.01459 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | Landscape |  | [LOD 200, Approvals, LOD 300, LOD 350] |  | 0.032641 | 2 |  | 0 | 0
| TMFT-Ph 3 | Ph 3 | Landscape | Gagan | Schematic Concept |  | 0.024481 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | Landscape | Gagan | Approvals |  | 0.0081602 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a |  |  | Package Release [LoD 350-ISS, Habitable Level 2-10] |  | 14.2039 | 10 |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture |  | LoD 350 - ISS, Habitable Level 2-10 |  | 8.7814 | 3 |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Pre Construction Set |  | 4.3907 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Experience Home + Project Experience |  | 2.1953 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Marketing and Sales |  | 2.1953 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural |  | LoD 350 - ISS, Habitable Level 2-10 |  | 3.2579 | 2 |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | Schematic Concept |  | 1.3962 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | Pre Construction Set |  | 1.8617 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP |  | LoD 350 - ISS, Habitable Level 2-10 |  | 1.2953 | 3 |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Schematic Concept |  | 0.5181 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Pre Construction Set |  | 0.5181 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Experience Home + Project Experience |  | 0.25905 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Landscape |  | LoD 350 - ISS, Habitable Level 2-10 |  | 0.86936 | 2 |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Landscape | Gagan | Schematic Concept |  | 0.43468 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Landscape | Gagan | Pre Construction Set |  | 0.43468 | 1 |  | 0
| Sarjapur Road [South Block-Resi] | Srjp - Res |  |  | Package Release [LOD 350 - Towers, Experience Homes, Clubhouse and Approvals by Q4] |  | 18.1053 | 13 |  | 0 | 0
| Srjp - Res | Srjp - Res | Architecture |  | [LOD 350 - Towers, Experience Homes and Approvals] |  | 14.3238 | 6 |  | 0 | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | Contract + Design Brief |  | 4.7746 | 1 |  | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | Schematic Concept |  | 4.364 | 1 |  | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | Approvals |  | 2.2847 | 1 |  | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | Experience Home + Project Experience |  | 2.3873 | 1 |  | 0
| Srjp - Res | Srjp - Res | Architecture | Om Prakash | CH - Schematic Concept |  | 0.4106 | 1 |  | 0
| Srjp - Res | Srjp - Res | Architecture | Om Prakash | CH - Approvals |  | 0.10265 | 1 |  | 0
| Srjp - Res | Srjp - Res | Structural |  | [LOD 350 - Towers, Experience Homes and Approvals] |  | 2.0244 | 2 |  | 0 | 0
| Srjp - Res | Srjp - Res | Structural | Prakash C | Schematic Concept |  | 1.5183 | 1 |  | 0
| Srjp - Res | Srjp - Res | Structural | Prakash C | Experience Home + Project Experience |  | 0.50611 | 1 |  | 0
| Srjp - Res | Srjp - Res | MEP |  | [LOD 350 - Towers, Experience Homes and Approvals] |  | 1.1268 | 3 |  | 0 | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | Schematic Concept |  | 0.5634 | 1 |  | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | Approvals |  | 0.2817 | 1 |  | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | Experience Home + Project Experience |  | 0.2817 | 1 |  | 0
2 | Srjp - Res | Srjp - Res | Landscape |  | [LOD 350, Experience Homes and Approvals] |  | 0.63025 | 2 |  | 0 | 0
| Srjp - Res | Srjp - Res | Landscape | Gagan | Schematic Concept |  | 0.47269 | 1 |  | 0
| Srjp - Res | Srjp - Res | Landscape | Gagan | Experience Home + Project Experience |  | 0.15756 | 1 |  | 0
| Sarjapur - C (South Block) | Srjp - C - SB |  |  | Package Release [LOD 350 - Towers by Q4] |  | 13.4848 | 6 |  | 0 | 0
| Srjp - C - SB | Srjp - C - SB | Architecture |  | [LOD 350 - Towers] |  | 11.0531 | 3 |  | 0 | 0
| Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Contract + Design Brief |  | 3.6844 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Schematic Concept |  | 3.6844 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Approvals |  | 3.6844 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | Structural |  | [LOD 350 - Towers] |  | 1.5622 | 1 |  | 0 | 0
| Srjp - C - SB | Srjp - C - SB | Structural | Prakash C | Schematic Concept |  | 1.5622 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | MEP |  | [LOD 350 - Towers] |  | 0.86951 | 2 |  | 0 | 0
| Srjp - C - SB | Srjp - C - SB | MEP | Gagan | Schematic Concept |  | 0.43476 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | MEP | Gagan | Approvals |  | 0.43476 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | Landscape |  | [LOD 350 - Towers]
| Sarjapur - C (North Block) | Srjp - C - NB |  |  | Package Release [LOD 350 - Towers by Q4] |  | 4.4949 | 6 |  | 0 | 0
| Srjp - C - NB | Srjp - C - NB | Architecture |  | [LOD 350 - Towers] |  | 3.6844 | 3 |  | 0 | 0
| Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Contract + Design Brief |  | 1.2281 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Schematic Concept |  | 1.2281 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Approvals |  | 1.2281 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | Structural |  | [LOD 350 - Towers] |  | 0.52073 | 1 |  | 0 | 0
| Srjp - C - NB | Srjp - C - NB | Structural | Prakash C | Schematic Concept |  | 0.52073 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | MEP |  | [LOD 300] |  | 0.28984 | 2 |  | 0 | 0
| Srjp - C - NB | Srjp - C - NB | MEP | Gagan | Schematic Concept |  | 0.14492 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | MEP | Gagan | Approvals |  | 0.14492 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | Landscape |  | [LOD 300]
| OTF | OTF |  |  | Package release [Except Amenities and Facilities] |  | 3.938 | 19 |  | 0.07965 | 1
| OTF | OTF | Master Planning |  | [Dsgn Brf, LOD 200, Approvals, LOD 300, Project Entrance] |  | 2.7525 | 6 |  | 0 | 0
| OTF | OTF | Master Planning | Naveen Y | Contract + Design Brief [Commercial] |  | 0.3375 | 1 |  | 0
| OTF | OTF | Master Planning | Naveen Y | Schematic Concept |  | 0.58 | 1 |  | 0
| OTF | OTF | Master Planning | Naveen Y | Approvals |  | 0.58 | 1 |  | 0
| OTF | OTF | Master Planning | Naveen Y | Pre Construction Set |  | 0.58 | 1 |  | 0
| OTF | OTF | Master Planning | Naveen Y | Marketing and Sales |  | 0.3375 | 1 |  | 0
| OTF | OTF | Master Planning | Naveen Y | Project Experience + Project Entrance |  | 0.3375 | 1 |  | 0
| OTF | OTF | Architecture |  | [LOD 200, Approvals] |  | 0.285 | 3 |  | 0 | 0
| OTF | OTF | Architecture | Om Prakash | Schematic Concept - CH |  | 0.095 | 1 |  | 0
Clubhouse - Roof design finalisation pending
| OTF | OTF | Architecture | Om Prakash | Approvals - CH |  | 0.095 | 1 |  | 0
| OTF | OTF | Architecture | Om Prakash | Pre Construction set - CH |  | 0.095 | 1 |  | 0
| OTF | OTF | Structural |  | [LOD 200, LOD 300] |  | 0.5724 | 3 |  | 0 | 0
| OTF | OTF | Structural | Prakash C | Schematic Concept |  | 0.1431 | 1 |  | 0
| OTF | OTF | Structural | Prakash C | Pre Construction Set |  | 0.2862 | 1 |  | 0
| OTF | OTF | Structural | Prakash C | Project Experience + Project Entrance |  | 0.1431 | 1 |  | 0
| OTF | OTF | MEP |  | [LOD 200, Approvals, LOD 300] |  | 0.23895 | 4 |  | 0.07965 | 1
| OTF | OTF | MEP | Gagan | Schematic Concept |  | 0.039825 | 1 |  | 0
| OTF | OTF | MEP | Gagan | Approvals |  | 0.07965 | 1 |  | 0.07965 | 1
| OTF | OTF | MEP | Gagan | Pre Construction Set |  | 0.07965 | 1 |  | 0
| OTF | OTF | MEP | Gagan | Project Experience + Project Entrance |  | 0.039825 | 1 |  | 0
| OTF | OTF | Landscape |  | [LOD 200, Approvals, LOD 300] |  | 0.0891 | 3 |  | 0 | 0
| OTF | OTF | Landscape | Gagan | Schematic Concept |  | 0.04455 | 1 |  | 0
Schematic for F&B + workcation block [dependency on architects to provide the layout - work in progress]
| OTF | OTF | Landscape | Gagan | Pre Construction Set |  | 0.022275 | 1 |  | 0
| OTF | OTF | Landscape | Gagan | Project Experience + Project Entrance |  | 0.022275 | 1 |  | 0
| Harohalli [Plotted] | Harohalli |  |  | Package Release [Dsgn Brf, LOD 200, Approvals, Exp, Package 1 -3 by Q4] |  | 5.9872 | 12 |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | Master Planning |  | [Dsgn Brf, LOD 200, Approvals, Exp] |  | 4.52 | 4 |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Contract + Design Brief |  | 0.855 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Schematic Concept |  | 1.405 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Approvals |  | 1.405 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Project Experience |  | 0.855 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Architecture |  | [LOD 200, Approvals]
| Harohalli [Plotted] | Ph 1 | Structural |  | [LOD 200,Exp home] |  | 0.72504 | 2 |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | Structural | Prakash C | Schematic Concept |  | 0.36252 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Structural | Prakash C | Project Experience |  | 0.36252 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | MEP |  | [LOD 200, Approvals] |  | 0.40356 | 3 |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | MEP | Gagan | Schematic Concept |  | 0.10089 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | MEP | Gagan | Approvals |  | 0.20178 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | MEP | Gagan | Project Experience |  | 0.10089 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Landscape |  | [LOD 200, Approvals] |  | 0.33858 | 3 |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Schematic Concept |  | 0.11286 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Approvals |  | 0.16929 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Project Experience |  | 0.05643 | 1 |  | 0
| Shreegaon [70a] | Ph 1 |  |  | Package Release [ Complete the project by Q4] |  | 2.7969 | 9 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | Master Planning |  | Complete the project [Except Master Archives] |  | 2.1842 | 3 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Contract + Design Brief |  | 0.4725 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Schematic Concept |  | 0.85586 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Approvals |  | 0.85586 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Architecture |  | Complete the project [Except Master Archives] |  | 0.089136 | 1 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | Architecture | Om Prakash | Schematic Concept |  | 0.089136 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Structural |  | Complete the project [Except Master Archives] |  | 0.20034 | 1 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | Structural | Prakash C | Schematic Concept |  | 0.20034 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | MEP |  | Complete the project [Except Master Archives] |  | 0.16726 | 2 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | MEP | Gagan | Schematic Concept |  | 0.055755 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | MEP | Gagan | Approvals |  | 0.11151 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Landscape |  | Complete the project [Except Master Archives] |  | 0.15592 | 2 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | Landscape | Gagan | Schematic Concept |  | 0.06237 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Landscape | Gagan | Approvals |  | 0.093555 | 1 |  | 0
| Violet hill | Ph 1 |  |  | Package Release [ Complete the project by Q4] |  | 3.4257 | 21 |  | 2.0642 | 6
| Violet hill | Ph 1 | Master Planning |  | Complete the project [Except Master Archives] |  | 2.4261 | 6 |  | 1.9565 | 4
| Violet hill | Ph 1 | Master Planning | Gagan | Schematic Concept [Rework] |  | 0.55067 | 1 |  | 0.55067 | 1
| Violet hill | Ph 1 | Master Planning | Gagan | Approvals [Rework] |  | 0.55067 | 1 |  | 0.55067 | 1
| Violet hill | Ph 1 | Master Planning | Gagan | Pre Construction Set |  | 0.55067 | 1 |  | 0.55067 | 1
| Violet hill | Ph 1 | Master Planning | Gagan | Project Experience |  | 0.30444 | 1 |  | 0
| Violet hill | Ph 1 | Master Planning | Gagan | Marketing and Sales |  | 0.30444 | 1 |  | 0.30444 | 1
| Violet hill | Ph 1 | Master Planning | Gagan | Structures - Security Cabin and Entrance [Rework] |  | 0.1652 | 1 |  | 0
| Violet hill | Ph 1 | Architecture |  | Complete the project [Except Master Archives] |  | 0.058217 | 1 |  | 0 | 0
| Violet hill | Ph 1 | Architecture | Om Prakash | Schematic Concept |  | 0.058217 | 1 |  | 0
| Violet hill | Ph 1 | Structural |  | Complete the project [Except Master Archives] |  | 0.57471 | 4 |  | 0 | 0
| Violet hill | Ph 1 | Structural | Prakash C | Schematic Concept |  | 0.12908 | 1 |  | 0
| Violet hill | Ph 1 | Structural | Prakash C | Pre Construction Set |  | 0.25817 | 1 |  | 0
| Violet hill | Ph 1 | Structural | Prakash C | Project Experience |  | 0.12908 | 1 |  | 0
| Violet hill | Ph 1 | Structural | Prakash C | Structures - Security Cabin and Entrance [Rework] |  | 0.058371 | 1 |  | 0
| Violet hill | Ph 1 | MEP |  | Complete the project [Except Master Archives] |  | 0.24804 | 5 |  | 0.10777 | 2
| Violet hill | Ph 1 | MEP | Gagan | Schematic Concept |  | 0.035924 | 1 |  | 0.035924 | 1
Appr | Violet hill | Ph 1 | MEP | Gagan | Approvals [Rework] |  | 0.071849 | 1 |  | 0.071849 | 1
| Violet hill | Ph 1 | MEP | Gagan | Pre Construction Set |  | 0.071849 | 1 |  | 0
| Violet hill | Ph 1 | MEP | Gagan | Project Experience |  | 0.035924 | 1 |  | 0
| Violet hill | Ph 1 | MEP | Gagan | Structures - Security Cabin and Entrance |  | 0.03249 | 1 |  | 0
| Violet hill | Ph 1 | Landscape |  | Complete the project [Except Master Archives] |  | 0.11864 | 5 |  | 0 | 0
| Violet hill | Ph 1 | Landscape | Gagan | Schematic Concept |  | 0.040186 | 1 |  | 0
| Violet hill | Ph 1 | Landscape | Gagan | Pre Construction Set |  | 0.020093 | 1 |  | 0
| Violet hill | Ph 1 | Landscape | Gagan | Project Experience |  | 0.020093 | 1 |  | 0
| Violet hill | Ph 1 | Landscape | Gagan | Marketing and Sales |  | 0.020093 | 1 |  | 0
| Violet hill | Ph 1 | Landscape | Gagan | Structures - Security Cabin and Entrance |  | 0.018172 | 1 |  | 0
| Ambegaon | Ambegaon |  |  | Package Release [Dsgn Brf, LOD 200, Approvals]
| Ambegaon | Ph 1 | Master Planning |  | [Dsgn Brf, LOD 200, Approvals, Exp]
| Ambegaon | Ph 1 | Architecture |  | [LOD 200, Approvals]
| Ambegaon | Ph 1 | Structural |  | [LOD 200]
| Ambegaon | Ph 1 | MEP |  | [LOD 200, Approvals]
| Ambegaon | Ph 1 | Landscape |  | [LOD 200, Approvals]
| Mall of Asia | Mall of Asia |  |  | Package Release [Dsgn Brf, LOD 200, Approvals, Exp home] |  | 1.6141 | 1 |  | 0 | 0
| Mall of Asia | Mall of Asia | Architecture |  | [Dsgn Brf, LOD 200, Approvals, LOD 300] |  | 1.6141 | 1 |  | 0 | 0
| Mall of Asia | Mall of Asia | Architecture | Om Prakash | Contract + Design Brief |  | 1.6141 | 1 |  | 0
| Mall of Asia | Mall of Asia | Structural |  | [LOD 200, LOD 300]
| Mall of Asia | Mall of Asia | MEP |  | [ LOD 200, Approvals, LOD 300]
| Mall of Asia | Mall of Asia | Landscape |  | [ LOD 200, Approvals, LOD 300]
| TR Mills Chamarajpet | TR Mills |  |  | Package Release [Dsgn Brf, LOD 200, Approvals, Exp home] |  | 0 | 0 |  | 0 | 0
| TR Mills | TR Mills | Architecture |  | [Dsgn Brf, LOD 200, Approvals, LOD 300]
| TR Mills | TR Mills | Structural |  | [LOD 200, LOD 300]
| TR Mills | TR Mills | MEP |  | [ LOD 200, Approvals, LOD 300]
| TR Mills | TR Mills | Landscape |  | [ LOD 200, Approvals, LOD 300]
| KIADB - Mys | KIADB - Mys |  |  | Package Release [Complete the project by Q4] |  | 0 | 8 |  | 0 | 0
| KIADB - Mys | KIADB - Mys | Master Planning |  | Complete the project by Q4 |  |  | 3 |  |  | 0
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | Contract + Design Brief |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | LoD 200 - Schematic Concept |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | Approvals |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | Structural |  | Complete the project by Q4 |  |  | 1 |  |  | 0
| KIADB - Mys | KIADB - Mys | Structural | Prakash C | LoD 200 - Schematic Concept |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | MEP |  | Complete the project by Q4 |  |  | 2 |  |  | 0
| KIADB - Mys | KIADB - Mys | MEP | Gagan | LoD 200 - Schematic Concept |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | MEP | Gagan | Approvals |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | Landscape |  | Complete the project by Q4 |  |  | 2 |  |  | 0
| KIADB - Mys | KIADB - Mys | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | Landscape | Gagan | Approvals |  |  | 1 |  | 0
| Imagine Campus | Imgn |  |  | Package Release [Complete the project by Q4] |  | 1.95 | 7 |  | 0.46 | 1
| Imagine Campus | Imgn | Architecture |  | Package Release [Complete the project by Q4] |  | 1.61 | 3 |  | 0.46 | 1
| Imagine Campus | Imgn | Architecture | Naveen Y | Design Brief |  | 0.46 | 1 |  | 0.46 | 1
| Imagine Campus | Imgn | Architecture | Naveen Y | LoD 200 - Schematic Concept |  | 0.69 | 1 |  | 0
| Imagine Campus | Imgn | Architecture | Naveen Y | Approvals |  | 0.46 | 1 |  | 0
| Imagine Campus | Imgn | Structural |  | Package Release [Complete the project by Q4] |  | 0.19 | 1 |  | 0 | 0
| Imagine Campus | Imgn | Structural | Prakash C | LoD 200 - Schematic Concept |  | 0.19 | 1 |  | 0
| Imagine Campus | Imgn | MEP |  | Package Release [Complete the project by Q4] | 0 | 0.1 | 2 | 0 | 0 | 0 | 0
| Imagine Campus | Imgn | MEP | Gagan | LoD 200 - Schematic Concept |  | 0.05 | 1 |  | 0
| Imagine Campus | Imgn | MEP | Gagan | Approvals |  | 0.05 | 1 |  | 0
| Imagine Campus | Imgn | Landscape |  | Package Release [Complete the project by Q4] |  | 0.05 | 1 |  | 0 | 0
| Imagine Campus | Imgn | Landscape | Gagan | Approvals |  | 0.05 | 1 |  | 0
| OtR OOTA | OTR OOTA |  |  | Package Release [Complete LOD 100 by Q1] |  | 0.19417 | 8 |  | 0 | 0
| OTR OOTA | OTR OOTA | Architecture |  | Complete the project |  | 0.15346 | 3 |  | 0 | 0
| OTR OOTA | OTR OOTA | Architecture | Manik G | Design Brief |  | 0.043845 | 1 |  | 0
| OTR OOTA | OTR OOTA | Architecture | Manik G | LoD 200 - Schematic Concept |  | 0.065768 | 1 |  | 0
| OTR OOTA | OTR OOTA | Architecture | Manik G | Approvals |  | 0.043845 | 1 |  | 0
| OTR OOTA | OTR OOTA | Structural |  | Complete the project |  | 0.020044 | 1 |  | 0 | 0
| OTR OOTA | OTR OOTA | Structural | Prakash C | LoD 200 - Schematic Concept |  | 0.020044 | 1 |  | 0
| OTR OOTA | OTR OOTA | MEP |  | Complete the project |  | 0.011275 | 2 |  | 0 | 0
| OTR OOTA | OTR OOTA | MEP | Gagan | LoD 200 - Schematic Concept |  | 0.0056373 | 1 |  | 0
| OTR OOTA | OTR OOTA | MEP | Gagan | Approvals |  | 0.0056373 | 1 |  | 0
| OTR OOTA | OTR OOTA | Landscape |  | Complete the project |  | 0.0093954 | 2 |  | 0 | 0
| OTR OOTA | OTR OOTA | Landscape | Gagan | LoD 200 - Schematic Concept |  | 0.0046977 | 1 |  | 0
| OTR OOTA | OTR OOTA | Landscape | Gagan | Approvals |  | 0.0046977 | 1 |  | 0
| DonaPaula | DP |  |  | Package release [LOD 200, Approvals, LOD 300, Experience home by Q2] |  | 4.4898 | 12 |  | 0 | 0
| DonaPaula | DP | Architecture |  | [ Approvals,LOD 300, Exp home, LOD350] |  | 3.41 | 5 |  | 0 | 0
| DonaPaula | DP | Architecture | Naveen Y | Schematic Concept .v7 [Rework] |  | 1.34 | 1 |  | 0
| DonaPaula | DP | Architecture | Naveen Y | Preconstruction |  | 1.34 | 1 |  | 0
| DonaPaula | DP | Architecture | Naveen Y | Approvals |  | 0.67 | 1 |  | 0
| DonaPaula | DP | Architecture | Om Prakash | LoD 200 - Schematic Concept - CH |  | 0.03 | 1 |  | 0
| DonaPaula | DP | Architecture | Om Prakash | LoD 300 - Pre Construction set - CH |  | 0.03 | 1 |  | 0
| DonaPaula | DP | Structural |  | [LOD 200, LOD 300] |  | 0.62985 | 2 |  | 0 | 0
| DonaPaula | DP | Structural | Prakash C | Schematic Concept .v7 [Rework] |  | 0.26985 | 1 |  | 0
| DonaPaula | DP | Structural | Prakash C | Preconstruction |  | 0.36 | 1 |  | 0
| DonaPaula | DP | MEP |  | [LOD 200, LOD 300, Approvals] |  | 0.25 | 3 |  | 0 | 0
| DonaPaula | DP | MEP | Gagan | Schematic Concept |  | 0.1 | 1 |  | 0
| DonaPaula | DP | MEP | Gagan | Approvals |  | 0.05 | 1 |  | 0
| DonaPaula | DP | MEP | Gagan | Preconstruction |  | 0.1 | 1 |  | 0
| DonaPaula | DP | Landscape |  | [LOD 200, LOD 300, Approvals] |  | 0.2 | 2 |  | 0 | 0
| DonaPaula | DP | Landscape | Gagan | Schematic Concept |  | 0.15 | 1 |  | 0
| DonaPaula | DP | Landscape | Gagan | Approvals |  | 0.05 | 1 |  | 0
Note on F90: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed Reply: Play equipment finalisation pending
Note on H91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on K91: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on F314: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Architects needs to confirm, how to proceed with the service platform covering and upstand design. Applicable for all i-towers
Note on F316: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Applicable for all i-towers
Note on F322: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Area kept on hold to be released.
Note on F330: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: External lighting layout awaited from Architect and landscape team. Centralized chiller details awaited from Renew Consultant
Note on F623: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on MOU signoff
Note on F629: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on MOU signoff

## Goals FY 2026Q2 (Revised Plan) (hidden)
| FY 2026-27 ¦ Design Goals + Billing |  |  |  |  | 155.4906 | 353 | [7 empty] | 0.82435 | 11 | 154.6662 | 342
| Project | Phase | Discipline | Design Lead | Description | Plan - Billing [Cr.] | Plan - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson | Remarks | Actuals - Billing [Cr.] | Actuals - Pkgs | 0.5302% | 3.116%
| Ongoing Projects |  |  |  |  | 35.4544 | 256 | [7 empty] | 0.82435 | 11
| AtR | Ph 1, 2a, 2b, 2c |  |  | Package Release | 0.43272 | 8 | [7 empty] | 0 | 0
| AtR | Ph 1, 2a, 2b, 2c | Architecture |  | Package Release [Complete LoD 350 ] | 0.39703 | 4 | [7 empty] | 0 | 0
| AtR | Ph 1, 2a, 2b | Architecture | Saji A | LoD 350 - Clubhouse + Amenities - Clubhouse—Interiors and Facilities | 0.27 | 1 | Saji A | Ayesha | Shreelekha |  |  |  |  | 0
| AtR | Ph 1, 2a, 2b | Architecture | Saji A | LoD 350 - Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] | 0.045377 | 1 | Saji A | Shreenivasa | Kishore |  |  |  |  | 0
| AtR | Ph 2c | Architecture | Saji A | LoD 350 - Master Plan - Site MEP | 0.042238 | 1 | Saji A | Shreenivasa | Kishore |  |  |  |  | 0
| AtR | Ph 2c | Architecture | Saji A | LoD 350 - Clubhouse + Amenities - Sporting Facilities | 0.039416 | 1 | Saji A | Ayesha | Shreelekha |  |  |  |  | 0
| AtR | Ph 1, 2a, 2b, 2c | Structural |  | Package Release [Complete LoD 350 ] | 0.021351 | 3 | [7 empty] | 0 | 0
| AtR | Ph 1, 2a, 2b | Structural | Prakash C | LoD 350 - Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] | 0.0052867 | 1 | Prakash C | Satish H | Alwin | Aniket P | Ambika |  |  | 0
| AtR | Ph 2c | Structural | Prakash C | LoD 350 - Master Plan - Site MEP | 0.010861 | 1 | Prakash C | Satish H | Ajmal/Shahnawaz | Atharv | Prasad |  |  | 0
| AtR | Ph 2c | Structural | Prakash C | LoD 350 - Clubhouse + Amenities - Sporting Facilities | 0.0052029 | 1 | Prakash C | Satish H | Alwin | Aniket P | Prasad |  |  | 0
| AtR | Ph 1, 2a, 2b, 2c | MEP |  | Package Release [Complete LoD 350 ] | 0.014337 | 1 | [7 empty] | 0 | 0
| AtR | Ph 2c | MEP | Gagan | LoD 350 - Master Plan - Site MEP | 0.014337 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Deepu Shreedhar Mahadev |  |  |  | 0
| AtR | Ph 3 |  |  | Package Release | 1.6825 | 31 | [7 empty] | 0 | 0
| AtR | Ph 3 | Architecture |  | Package Release [Complete LoD 350 except V80 ] | 1.1738 | 13 | [7 empty] | 0 | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 300 - Pre Construction Set | 0.27398 | 1 | Saji A | Ayesha | Guruprasad | Kishore |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Home Products - V45 Default and it's variants | 0.36 | 1 | Saji A | Ayesha | Guruprasad | Aaron |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 33 - Foundations and Sub-Grade Structure | 0.043983 | 1 | Saji A | Ayesha | Kishore |  |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 34 - Foundations and Sub-Grade Structure | 0.043983 | 1 | Saji A | Ayesha | Shreelekha |  |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 29 - Foundations and Sub-Grade Structure | 0.065974 | 1 | Saji A | Ayesha | Guruprasad |  |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 29 - Building Envelope + Plot Development | 0.065974 | 1 | Saji A | Ayesha | Guruprasad |  |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 30 - Foundations and Sub-Grade Structure | 0.065974 | 1 | Saji A | Ayesha | Guruprasad |  |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 30 - Building Envelope + Plot Development | 0.065974 | 1 | Saji A | Ayesha | Guruprasad |  |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 31 - Building Envelope + Plot Development | 0.014661 | 1 | Saji A | Ayesha | Guruprasad |  |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 32 - Building Envelope + Plot Development | 0.029322 | 1 | Saji A | Ayesha | Shreelekha |  |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Villa Block 34 - Building Envelope + Plot Development | 0.043983 | 1 | Saji A | Ayesha | Shreelekha |  |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Master Plan - Master Plan | 0.05 | 1 | Saji A | Shreenivasa | Kishore |  |  |  |  | 0
| AtR | Ph 3 | Architecture | Saji A | LoD 350 - Site Development - 02 Road Works | 0.05 | 1 | Saji A | Shreenivasa | Kishore |  |  |  |  | 0
| AtR | Ph 3 | Structural |  | Package Release [Complete LoD 350 except V80 ] | 0.29155 | 13 | [7 empty] | 0 | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 300 - Preconstruction Set | 0.093422 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 29 - Foundations and Sub-Grade Structure | 0.021107 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 29 - Super Structure | 0.03166 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 29 - Building Envelope + Plot Development | 0.0052767 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 30 - Foundations and Sub-Grade Structure | 0.021107 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 30 - Super Structure | 0.03166 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 30 - Building Envelope + Plot Development | 0.0052767 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 31 - Building Envelope + Plot Development | 0.001 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 32 - Building Envelope + Plot Development | 0.0023452 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 34 - Foundations and Sub-Grade Structure | 0.014071 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 34 - Super Structure | 0.021107 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Villa Block 34 - Building Envelope + Plot Development | 0.0035178 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | Structural | Prakash C | LoD 350 - Site Development - 02 Road Works | 0.04 | 1 | Prakash C | Satish H | Mohith |  | Prasad |  |  | 0
| AtR | Ph 3 | MEP |  | Package Release [Complete LoD 350 except V80 ] | 0.16927 | 4 | [7 empty] | 0 | 0
| AtR | Ph 3 | MEP | Gagan | LoD 300 - Preconstruction Set | 0.0215 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| AtR | Ph 3 | MEP | Gagan | LoD 350 - Villa Block 34 - Foundations and Sub-Grade Structure | 0.0028274 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| AtR | Ph 3 | MEP | Gagan | LoD 350 - Home Products - V45 Default and it's variants | 0.10495 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| AtR | Ph 3 | MEP | Gagan | LoD 350 - Master Plan - Master Plan | 0.04 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| AtR | Ph 3 | Landscape |  | Package Release [Complete LoD 350 except V80 ] | 0.047864 | 1 | [7 empty] | 0 | 0
| AtR | Ph 3 | Landscape | Gagan | LoD 300 - Preconstruction Set | 0.047864 | 1 | Gagan | Lajja | Anisha | Chetan Anupa |  |  |  | 0
| AtR | Ph 3 | Landscape | Gagan | LoD 350 - Home Products - V45 Default |  |  | Gagan | Lajja | Anisha | Chetan Anupa |  |  |  | 0
| AtR - C | Com |  |  | Package Release | 0.81651 | 8 | [7 empty] | 0 | 0
| AtR - C | Com | Architecture |  | Package Release [Complete LoD 350 ] | 0.36421 | 3 | [7 empty] | 0 | 0
| AtR - C | Com | Architecture | Naveen Y | LoD 350 - Master Plan - Site Development | 0.13658 | 1 | Naveen Y | Naveen KL | Vasudha C |  |  |  |  | 0
| AtR - C | Com | Architecture | Naveen Y | LoD 350 - Master Plan - Site MEP | 0.18211 | 1 | Naveen Y | Naveen KL | Sathvika D |  |  |  |  | 0
| AtR - C | Com | Architecture | Naveen Y | LoD 350 - Master Plan - Landscaping | 0.045527 | 1 | Naveen Y | Naveen KL | Arshad |  |  |  |  | 0
| AtR - C | Com | Structural |  | Package Release [Complete LoD 350 except Habitable Level 6-10 and Terrace Level ] | 0.28478 | 3 | [7 empty] | 0 | 0
| AtR - C | Com | Structural | Prakash C | LoD 350 - Tower-[Commercial] - Habitable Level 3-5 | 0.25823 | 1 | Prakash C | Vineetha | Sagar+ Shrishail | Rajath |  |  |  | 0
| AtR - C | Com | Structural | Prakash C | LoD 350 - Master Plan - Site Development | 0.014486 | 1 | Prakash C | Vineetha | Dhirender+ Shrishail | Rohit |  |  |  | 0
| AtR - C | Com | Structural | Prakash C | LoD 350 - Master Plan - Site MEP | 0.012072 | 1 | Prakash C | Vineetha | Sagar+Rajath | Namrath |  |  |  | 0
| AtR - C | Com | MEP |  | Package Release [Complete LoD 350 ] | 0.16751 | 2 | [7 empty] | 0 | 0
| AtR - C | Com | MEP | Gagan | LoD 350 - Master Plan - Master Plan | 0.038655 | 1 | Gagan | Salomi | Eranna Praveen | Avinash Deepu |  |  |  | 0
| AtR - C | Com | MEP | Gagan | LoD 350 - Master Plan - Site MEP | 0.12885 | 1 | Gagan | Salomi | Eranna Praveen | Avinash Deepu |  |  |  | 0
| TMD Ph2 | Ph 2 |  |  | Package Release | 0 | 0 | [7 empty] | 0 | 0
| TMD Ph2 | Ph 2 |  |  | LoD 350 - Childern play area | 0 | 0 | [7 empty] | 0 | 0
Play equipment selection pending
| PoaRR-Res | Res |  |  | Package Release | 4.0892 | 14 | [7 empty] | 0 | 0
| PoaRR-Res | Res | Architecture |  | Complete the project | 3.3659 | 8 | [7 empty] | 0 | 0
| PoaRR-Res | Res | Architecture | Saji A | LOD 350 Villa Cluster 3 - All Levels | 0.17 | 1 | Saji A | Gokul | Krishnapriya |  |  |  |  | 0
| PoaRR-Res | Res | Architecture | Saji A | LOD 350 Villa Cluster 3 - Building Envelope and Common Areas | 0.17 | 1 | Saji A | Gokul | Krishnapriya |  |  |  |  | 0
| PoaRR-Res | Res | Architecture | Saji A | LOD 350 V40 Default and it's variants | 1.18 | 1 | Saji A | Nirupama | [5 empty] | 0
| PoaRR-Res | Res | Architecture | Saji A | LOD 350 ISS Building Envelope and Common Areas | 1.0659 | 1 | Saji A | Arshad | Latha |  |  |  |  | 0
| PoaRR-Res | Res | Architecture | Saji A | LOD 350 Residential - Site Development | 0.45 | 1 | Saji A | Sathwik | [5 empty] | 0
| PoaRR-Res | Res | Architecture | Saji A | LOD 350 Masterplan - Site MEP | 0.15 | 1 | Saji A | Sathwik | [5 empty] | 0
| PoaRR-Res | Res | Architecture | Saji A | LOD 350 Masterplan - Landscaping | 0.15 | 1 | Saji A | Sathwik | [5 empty] | 0
| PoaRR-Res | Res | Architecture | Saji A | LOD 350 Amenities & Facilities - Sporting Facilities | 0.03 | 1 | Saji A | Sathwik | Abdul |  |  |  |  | 0
| PoaRR-Res | Res | Structural |  | Complete the project | 0.36 | 3 | [7 empty] | 0 | 0
| PoaRR-Res | Res | Structural | Prakash C | LOD 350 Site Development | 0.19 | 1 | Prakash C | Lincy | Subrahmanya |  | Darshan |  |  | 0
| PoaRR-Res | Res | Structural | Prakash C | LOD 350 Site MEP | 0.16 | 1 | Prakash C | Lincy | Subrahmanya |  | Darshan |  |  | 0
| PoaRR-Res | Res | Structural | Prakash C | LOD 350 Sporting Facilities | 0.01 | 1 | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan |  |  | 0
| PoaRR-Res | Res | MEP |  | Complete the project | 0.36327 | 3 | [7 empty] | 0 | 0
| PoaRR-Res | Res | MEP | Gagan | LOD 350 Site MEP | 0.36 | 1 | Gagan | Salomi | Hareesha Praveen | Byahattimath Shreedhar Mahadev Deepu Ajay |  |  |  | 0
| PoaRR-Res | Res | MEP | Gagan | LOD 350 Clubhouse Outdoor Spaces and Pool | 0.002183 | 1 | Gagan | Salomi | Hareesha Praveen | Byahattimath Shreedhar Mahadev Deepu Ajay |  |  |  | 0
| PoaRR-Res | Res | MEP | Gagan | LOD 350 Sporting Facilities | 0.0010915 | 1 | Gagan | Salomi | Hareesha Praveen | Byahattimath Shreedhar Mahadev Deepu Ajay |  |  |  | 0
| PoaRR-Res | Res | Landscape |  | Complete the project | 0 | 0 | [7 empty] | 0 | 0
| PoaRR-Res | Res | Landscape | Gagan | LOD 350 Amenities & Facilities - Community spaces [Sporting Facilities] |  |  | Gagan | Lajja | Apoorva |  |  |  |  | 0
| PoaRR-T08 | T08 |  |  | Package Release | 9.0478 | 31 | [7 empty] | 0 | 0
| PoaRR-T08 | T08 | Architecture |  | Package Release [Complete the project] | 7.2038 | 20 | [7 empty] | 0 | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 ISS - Foundations & Grade Slab | 0.2 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 ISS - Parking Level Subgrade | 0.41 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 ISS - Podium Slab | 0.61 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 ISS - Building Envelope and Common Areas | 0.82 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Habitable Level 01 | 0.48 | 1 | Saji A | Komal | Mononita |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Building Envelope and Common Areas [Typical Tower Levels] | 0.96385 | 1 | Saji A | Komal | Mononita |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 L22 Default | 0.52 | 1 | Saji A | Mononita | Shahbazz |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 L20 Default [Modification for Dry Wall] | 0.52 | 1 | Saji A | Aardra | Komal |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 D35 Default [Modification for Dry Wall] | 0.52 | 1 | Saji A | Komal | Aardra |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Master Plan | 0.17 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Penthouse Levels | 0.48 | 1 | Saji A | Komal | Mononita |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Terrace Level | 0.24 | 1 | Saji A | Komal | Mononita |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 0.96 | 1 | Saji A | Komal | Mononita |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Clubhouse—Interiors and Facilities | 0.02 | 1 | Saji A | Komal | Mononita |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Landscape | 0.03 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Site MEP | 0.03 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Clubhouse—Outdoor Spaces and Pool | 0.015 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Community spaces [Board Walk, Children play area] | 0.015 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 Site Development | 0.1 | 1 | Saji A | Vivek | Komal |  |  |  |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | LOD 350 R25P Default and It's Variants | 0.1 | 1 | Saji A | Shahbaaz | [5 empty] | 0
| PoaRR-T08 | T08 | Structural |  | Complete the project | 1.7 | 7 | [7 empty] | 0 | 0
| PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 Penthouse Levels | 0.2 | 1 | Prakash C | Lincy | Jayashankar | Subrahmanya | Darshan |  |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 Terrace Level | 0.4 | 1 | Prakash C | Lincy | Jayashankar | Subrahmanya | Darshan |  |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 T08 - ISS - Foundations & Grade Slab | 0.32 | 1 | Prakash C | Lincy | Nadeem | - | Darshan |  |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 T08 - ISS - Podium Slab | 0.32 | 1 | Prakash C | Lincy | Nadeem | - | Darshan |  |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 T08 - ISS - Parking Level Subgrade | 0.43 | 1 | Prakash C | Lincy | Nadeem | Subrahmanya | Karthik |  |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 Site Development | 0.02 | 1 | Prakash C | Lincy | Subrahmanya | - | Karthik |  |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | LOD 350 Site MEP | 0.01 | 1 | Prakash C | Lincy | Subrahmanya | - | Karthik |  |  | 0
| PoaRR-T08 | T08 | MEP |  | Package Release [Complete the project] | 0.144 | 4 | [7 empty] | 0 | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 Penthouse Levels |  |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 Terrace Level |  |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 ISS - Foundation and Gradeslab | 0.02 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 L20 Default and it's variants | 0.06 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 D35 Default and it's variants | 0.06 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 Clubhouse—Interiors and Facilities | 0.004 | 1 | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 Master Plan |  |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 Site MEP |  |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 L22 Default and It's Variants |  |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | LOD 350 R25P Default and It's Variants |  |  | Gagan | Salomi | Hareesha Praveen | Hanumanthraya Shreedhar Sandeep |  |  |  | 0
| PoaRR-T08 | T08 | Landscape |  | Package Release [Complete the project] | 0 | 0 | [7 empty] | 0 | 0
| PoaRR-T08 | T08 | Landscape | Gagan | LOD 350 T08-Clubhouse—Interiors and Facilities |  |  | Gagan | Lajja | Apoorva |  |  |  |  | 0
| PoaRR-T08 | T08 | Landscape | Gagan | LOD 350 R25P Default and It's Variants |  |  | Gagan | Lajja | Apoorva |  |  |  |  | 0
| ITQE-Ph1 | Ph 1 |  |  | Package Release | 0.084072 | 3 |  | Dinakar Venugopal | Aishwarya Hegde | Sheethal Prabhu | Anand Thoppil |  |  | 0.060249 | 1
| ITQE-Ph1 | Ph 1 | Structural |  | Complete the project | 0.084072 | 3 | [7 empty] | 0.060249 | 1
| ITQE-Ph1 | Ph 1 | Structural | Prakash C | LoD 350 - Master Plan ¦ Site Development | 0.060249 | 1 | Prakash C | Satish H | Raghavendra |  | Vinay |  |  | 0.060249 | 1
| ITQE-Ph1 | Ph 1 | Structural | Prakash C | LoD 350 - Amenities & Facilities ¦ Clubhouse—Outdoor Spaces and Pool | 0.011912 | 1 | Prakash C | Satish H | Raghavendra |  | Vinay |  |  | 0
| ITQE-Ph1 | Ph 1 | Structural | Prakash C | LoD 350 - Amenities & Facilities ¦ Community spaces | 0.011912 | 1 | Prakash C | Satish H | Raghavendra |  | Vinay |  |  | 0
| ITQE-Ph2a | Ph 2a |  |  | Package Release | 0.41919 | 5 | [7 empty] | 0.3741 | 4
| ITQE-Ph2a | Ph 2a | Architecture |  | Complete the project | 0.25 | 2 | [7 empty] | 0.25 | 2
| ITQE-Ph2a | Ph 2a | Architecture | Cijey M | LoD 350 - Master Plan ¦ Site Development | 0.07 | 1 | Cijey M | Dinakar Venugopal | Syed Musharaff |  |  |  |  | 0.07 | 1
| ITQE-Ph2a | Ph 2a | Architecture | Cijey M | LoD 350 -Experience Home + Project Experience [ V35 ] | 0.18 | 1 | Cijey M | Theodora Rodrigues | Thomas Pradip Moreira |  |  |  |  | 0.18 | 1
| ITQE-Ph2a | Ph 2a | Structural |  | Complete the project | 0.16919 | 3 | [7 empty] | 0.1241 | 2
| ITQE-Ph2a | Ph 2a | Structural | Prakash C | LoD 350 -Experience Home + Project Experience [ V35 ] | 0.07 | 1 | Prakash C | Satish H | Raghavendra | 0 | Harshitha |  |  | 0.07 | 1
| ITQE-Ph2a | Ph 2a | Structural | Prakash C | LoD 350 - Master Plan ¦ Site Development | 0.054104 | 1 | Prakash C | Satish H | Raghavendra | 0 | Harshitha |  |  | 0.054104 | 1
| ITQE-Ph2a | Ph 2a | Structural | Prakash C | LoD 350 - Master Plan ¦ Site MEP | 0.045086 | 1 | Prakash C | Satish H | Raghavendra | 0 | Harshitha |  |  | 0
| ITQE-Ph2b | Ph 2b |  |  | Package Release | 3.02 | 21 | [7 empty] | 0.28 | 4
| ITQE-Ph2b | Ph 2b | Architecture |  | Complete the project except site development and site MEP | 1.95 | 10 | [7 empty] | 0 | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Tower—06 ¦ Habitable Level 01 | 0.13 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Tower—07 ¦ Habitable Level 01 | 0.13 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Tower—05 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 0.22 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Tower—06 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 0.22 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Tower—07 ¦ Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 0.22 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - Master Plan ¦ Master Plan | 0.03 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - ISS 5&6 ¦ Podium Slab | 0.1 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - ISS 7 ¦ Podium Slab | 0.1 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - ISS 5&6 ¦ Building Envelope and Common Areas | 0.4 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | LoD 350 - ISS 7 ¦ Building Envelope and Common Areas | 0.4 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Hruthika Mylar | Khushi Shetty |  |  | 0
| ITQE-Ph2b | Ph 2b | Structural |  | Complete the project except site development and site MEP & STP | 1.07 | 11 | [7 empty] | 0.28 | 4
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Tower 06 ¦ Habitable Level - Even | 0.07 | 1 | Prakash C | Satish H | Antony |  | Harshitha |  | Closed | 0.07 | 1
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Tower 06 ¦ Habitable Level - Odd | 0.07 | 1 | Prakash C | Satish H | Antony |  | Harshitha |  | Closed | 0.07 | 1
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Tower 07 ¦ Habitable Level - Even | 0.07 | 1 | Prakash C | Satish H | Antony |  | Harshitha |  | 0 | 0.07 | 1
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Tower 07 ¦ Habitable Level - Odd | 0.07 | 1 | Prakash C | Satish H | Antony |  | Harshitha |  | 0 | 0.07 | 1
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - ISS5&6 ¦ Structrural Slab 01 [Basement] | 0.13 | 1 | Prakash C | Satish H | Darshan K |  | Harshitha |  | 0 | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - ISS 7 ¦ Structrural Slab 01 [Basement] | 0.13 | 1 | Prakash C | Satish H | Darshan K |  | Harshitha |  | 0 | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Tower 05 ¦ Terrace Level | 0.09 | 1 | Prakash C | Satish H | Antony |  | Harshitha |  | 0 | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Tower 06 ¦ Terrace Level | 0.09 | 1 | Prakash C | Satish H | Antony |  | Harshitha |  | 0 | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - Tower 07 ¦ Terrace Level | 0.09 | 1 | Prakash C | Satish H | Antony |  | Harshitha |  | 0 | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - ISS5&6 ¦ Podium Slab | 0.13 | 1 | Prakash C | Satish H | Ajmal (after finishing ATR Site MEP works) & New resource hired, joining in July |  | Harshitha |  | 0 | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | LoD 350 - ISS 7 ¦ Podium Slab | 0.13 | 1 | Prakash C | Satish H | Ajmal (after finishing ATR Site MEP works) & New resource hired, joining in July |  | Harshitha |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c |  |  | Package Release | 0.63298 | 9 | [7 empty] | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture |  | LoD 350 - T09 [Foundation & Grade Slab, Parking Lvl Sub Grade], ISS09 [[Foundation & Grade Slab] | 0.30106 | 3 | [7 empty] | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | LoD 350 - Tower 9 ¦ Foundation and Grade Slab | 0.1306 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkisani | Hruthika Mylar |  |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | LoD 350 - Tower 9 ¦ Parking Level-Sub grade | 0.078362 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkisani | Hruthika Mylar |  |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | LoD 350 - ISS 9 ¦ Foundations & Grade Slab | 0.092092 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkisani | Hruthika Mylar |  |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural |  | LoD 350 - T09 [Foundation & Grade Slab, Parking Lvl Sub Grade], ISS09 [[Foundation & Grade Slab] | 0.2848 | 4 | [7 empty] | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | LoD 350 - Tower 9 ¦ Foundation and Grade Slab | 0.118 | 1 | Prakash C | Satish H | Raghavendra |  | Sahana |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | LoD 350 - Tower 9 ¦ Parking Level-Sub grade | 0.118 | 1 | Prakash C | Satish H | Raghavendra |  | Sahana |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | LoD 350 - ISS 9 ¦ Earthwork | 0.0097618 | 1 | Prakash C |  | Outsourced |  |  |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | LoD 350 - ISS 9 ¦ Foundations & Grade Slab | 0.039047 | 1 | Prakash C |  | Outsourced |  |  |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP |  | LoD 350 - T09 [Foundation & Grade Slab], ISS09 [[Foundation & Grade Slab] | 0.047123 | 2 | [7 empty] | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP | Gagan | LoD 350 - Tower 9 ¦ Foundation and Grade Slab | 0.030822 | 1 | Gagan | Salomi | Hareesha Bhavya | Byahattimath Matsarambabu Prem |  |  |  | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP | Gagan | LoD 350 - ISS 9 ¦ Foundations & Grade Slab | 0.0163 | 1 | Gagan | Salomi | Hareesha Bhavya | Byahattimath Matsarambabu Prem |  |  |  | 0
| OTR-Ph01 | Ph 1 |  |  | Package Release | 0.87 | 10 | [7 empty] | 0.08 | 1
| OTR-Ph01 | Ph 1 | Architecture |  | Complete the project | 0.45 | 4 | [7 empty] | 0 | 0
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | LoD 350 - Villa Block ¦ Building Envelope + Plot Development | 0.3 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Akshara Rohit | Saurabh Bothra |  |  | 0
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | LoD 350 - Master Plan ¦ Master Plan | 0.09 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Akshara Rohit | Saurabh Bothra |  |  | 0
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | LoD 350 - Master Plan ¦ Site Development | 0.03 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Akshara Rohit | Saurabh Bothra |  |  | 0
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | LoD 350 - Master Plan ¦ Site MEP | 0.03 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Akshara Rohit | Saurabh Bothra |  |  | 0
| OTR-Ph01 | Ph 1 | Structural |  | Complete the project | 0.38 | 5 | [7 empty] | 0.08 | 1
| OTR-Ph01 | Ph 1 | Structural | Prakash C | LoD 350 - LoD 350 -Experience Home + Project Experience [ V35 ] | 0.08 | 1 | Prakash C | Satish H | Mazhar |  | Samyukta |  | 0 | 0.08 | 1
| OTR-Ph01 | Ph 1 | Structural | Prakash C | LoD 350 - Villa Block ¦ Super Structure | 0.17 | 1 | Prakash C | Satish H | Mazhar |  | Samyukta |  | 0 | 0
| OTR-Ph01 | Ph 1 | Structural | Prakash C | LoD 350 - Master Plan ¦ Site Development | 0.03 | 1 | Prakash C | Satish H | Mazhar |  | Samyukta |  | 0 | 0
| OTR-Ph01 | Ph 1 | Structural | Prakash C | LoD 350 - Master Plan ¦ Site MEP | 0.03 | 1 | Prakash C | Satish H | Mazhar |  | Samyukta |  | 0 | 0
| OTR-Ph01 | Ph 1 | Structural | Prakash C | LoD 350 - LoD 350 - Amenities & Facilities ¦ Community spaces [Board Walk, Children play area] | 0.07 | 1 | Prakash C | Satish H | Mazhar |  | Samyukta |  | 0 | 0
| OTR-Ph01 | Ph 1 | MEP |  | Complete the project | 0.04 | 1 | [7 empty] | 0 | 0
| OTR-Ph01 | Ph 1 | MEP | Gagan | LoD 350 - Master Plan ¦ Site MEP | 0.04 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| TuiG | TuiG |  |  | Package Release | 2.6026 | 9 | [7 empty] | 0 | 0
| TuiG | TuiG | Architecture |  | Package Release [LoD 350 - CH structure & envelope, Interiors] | 1.5478 | 4 | [7 empty] | 0 | 0
| TuiG | TuiG | Architecture | Om Prakash | LoD 350 - Clubhouse—Structure and Envelope | 0.6191 | 1 | Om Prakash | Veeresh N | Ankita Macha | Lavanya |  |  |  | 0
| TuiG | TuiG | Architecture | Om Prakash | LoD 350 - Clubhouse—Interiors and Facilities | 0.6191 | 1 | Om Prakash | Veeresh N | Ankita Macha | Lavanya |  |  |  | 0
| TuiG | TuiG | Architecture | Om Prakash | LoD 350 - Sporting Facilities | 0.15478 | 1 | Om Prakash | Veeresh N | Ankita Macha | Lavanya |  |  |  | 0
| TuiG | TuiG | Architecture | Om Prakash | Clubhouse—Outdoor Spaces and Pool | 0.15478 | 1 | Om Prakash | Veeresh N | Ankita Macha | Lavanya |  |  |  | 0
| TuiG | TuiG | Structural |  | Package Release [LoD 350 - Site dev, Site MEP, CH structure & Envelope] | 1.0053 | 4 | [7 empty] | 0 | 0
| TuiG | TuiG | Structural | Prakash C | LoD 350 - Site Development | 0.40295 | 1 | Prakash C | Satish H | Alwin |  | Shivaraj |  | 0 | 0
| TuiG | TuiG | Structural | Prakash C | LoD 350 - Site MEP | 0.33579 | 1 | Prakash C | Satish H | Alwin |  | Shivaraj |  | 0 | 0
| TuiG | TuiG | Structural | Prakash C | LoD 350 - Clubhouse—Structure and Envelope | 0.21694 | 1 | Prakash C | Satish H | Saurav |  | Shivaraj |  | 0 | 0
| TuiG | TuiG | Structural | Prakash C | LoD 350 - Clubhouse—Outdoor Spaces and Pool | 0.049574 | 1 | Prakash C | Satish H | Saurav |  | Shivaraj |  | 0 | 0
| TuiG | TuiG | MEP |  | Package Release [LoD 350 - CH outdoorspaces & pool] | 0.049574 | 1 | [7 empty] | 0 | 0
| TuiG | TuiG | MEP | Gagan | LoD 350 - Clubhouse—Outdoorspaces & pool | 0.049574 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Antoney Matsarambabu |  |  |  | 0
| TMFT-Ph 2 | Ph 2 |  |  | Package Release | 0.03 | 1 | [7 empty] | 0.03 | 1
| TMFT-Ph 2 | Ph 2 | Structural |  | Complete the project | 0.03 | 1 | [7 empty] | 0.03 | 1
| TMFT-Ph 2 | Ph 2 | Structural | Prakash C | LoD 350 - Site Development | 0.03 | 1 | Prakash C | Vineetha | - |  | Samyukta |  | 0 | 0.03 | 1
| DBTW | DBTW |  |  | Package Release | 7.5282 | 33 | [7 empty] | 0 | 0
| DBTW | DBTW | Architecture |  | Complete the project | 5.7306 | 11 | [7 empty] | 0 | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site Development | 0.073717 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
` | DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site MEP | 0.073717 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Landscaping | 0.073717 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Tower 06 - Foundation and Grade Slab | 0.064032 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Foundations & Grade Slab | 0.54995 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Podium Slab | 0.27497 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I20 Default and it's variants | 2.2352 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I25 Default and it's variants | 2.2352 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - L21 Default and it's variants |  | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Structure and Envelope | 0.1125 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Outdoor Spaces and Pool | 0.0375 | 1 | Om Prakash | CB Raman | Balaji R | Anitha K |  |  |  | 0
| DBTW | DBTW | Structural |  | Complete the project | 1.7608 | 21 | [7 empty] | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - ISS - Foundations & Grade Slab | 0.52958 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-1-Habitable Level - Even | 0.025613 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-1-Habitable Level - Odd | 0.025613 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level 01 | 0.10834 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level - Even | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level - Odd | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level 01 | 0.10834 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level - Even | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level - Odd | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level 01 | 0.10834 | 1 | Prakash C | Satish H | Alwin | Aniket | Prasad |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level - Even | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level - Odd | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 05-Foundation and Grade Slab | 0.10834 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level 01 | 0.10834 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level - Even | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level - Odd | 0.05417 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Foundation and Grade Slab | 0.051226 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Parking Level-Sub grade | 0.051226 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level 01 | 0.051226 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level - Even | 0.025613 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level - Odd | 0.025613 | 1 | Prakash C | Satish H | Alwin | Aniket | Shivaraj |  | 0 | 0
| DBTW | DBTW | MEP |  | Complete the project | 0.036853 | 1 | [7 empty] | 0 | 0
| DBTW | DBTW | MEP | Gagan | LoD 350 - Master Plan- Master Plan | 0.036853 | 1 | Gagan | Salomi | Bhavya Hareesha | Viresh Matsarambabu Byahattimath Hanumanthraya |  |  |  | 0
| SftW | SftW |  |  | Package Release | 1.0951 | 15 | [7 empty] | 0 | 0
| SftW | SftW | Architecture |  | Complete LoD 350 [Podium, Clubhouse & Masterplan] by 26'Q2 | 0.72824 | 7 | [7 empty] | 0 | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - ISS 01 - Podium Slab | 0.25575 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Clubhouse: Structure and Envelope | 0.081564 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Master Plan: Master Plan | 0.18697 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Clubhouse: Outdoor Spaces and Pool | 0.027188 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Master Plan: Site Development | 0.11218 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Master Plan: Site MEP | 0.037394 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Master Plan: Landscaping |  |  | Om Prakash
| SftW | SftW | Architecture | Om Prakash | LoD 350: Clubhouse + Amenities - Sporting Facilities | 0.027188 | 1 | Om Prakash | CB Raman | Anitha K | Tarush Sharma |  |  |  | 0
| SftW | SftW | Architecture | Om Prakash | LoD 350 - Tower 02: Terrace Level |  |  | Om Prakash
| SftW | SftW | Structural |  | Complete LoD 350 [Clubhouse & Masterplan] by 26'Q2 | 0.34546 | 6 | [7 empty] | 0 | 0
| SftW | SftW | Structural | Prakash C | LoD 350 - Tower 2: Terrace Level | 0.20116 | 1 | Prakash C | Vineetha | Shrishail | Rohit | Arun |  | 0 | 0
| SftW | SftW | Structural | Prakash C | LoD 350 - Master Plan: Site Development | 0.058457 | 1 | Prakash C | Satish H | New resource to be Hired |  | Arun |  | 0 | 0
| SftW | SftW | Structural | Prakash C | LoD 350 - Master Plan: Site MEP | 0.048714 | 1 | Prakash C | Satish H | New resource to be Hired |  | Arun |  | 0 | 0
| SftW | SftW | Structural | Prakash C | LoD 350 - Clubhouse: Structure and Envelope | 0.025989 | 1 | Prakash C | Satish H | Shubham |  | Vinay |  | 0 | 0
| SftW | SftW | Structural | Prakash C | LoD 350 - Clubhouse: Outdoor Spaces and Pool | 0.0037128 | 1 | Prakash C | Satish H | Raghavendra |  | Vinay |  | 0 | 0
| SftW | SftW | Structural | Prakash C | LoD 350: Clubhouse + Amenities - Sporting Facilities | 0.0074255 | 1 | Prakash C | Satish H | Shubam(after finishing clubhouse) |  | Vinay |  | 0 | 0
| SftW | SftW | MEP |  | Complete LoD 350 [Clubhouse & Masterplan] by 26'Q2 | 0.021398 | 2 | [7 empty] | 0 | 0
| SftW | SftW | MEP | Gagan | LoD 350 - Master Plan: Site MEP | 0.020843 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Antoney Shreedhar |  |  |  | 0
| SftW | SftW | MEP | Gagan | LoD 350: Clubhouse + Amenities - Sporting Facilities | 0.00055534 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Antoney Shreedhar |  |  |  | 0
| LGCE Campus | LGCE Campus |  |  | Package Release | 0.38042 | 2 | [7 empty] | 0 | 0
| LGCE Campus | LGCE Campus | Architecture |  | Complete LoD 200 by 26'Q2 | 0.38042 | 2 | [7 empty] | 0 | 0
| LGCE Campus | LGCE Campus | Architecture | Om Prakash | LoD 100 - Design Brief | 0.15217 | 1 | Om Prakash | Veeresh N | Ankita Macha |  |  |  |  | 0
| LGCE Campus | LGCE Campus | Architecture | Om Prakash | LoD 200 - Schematic Concept | 0.22825 | 1 | Om Prakash | Veeresh N | Ankita Macha |  |  |  |  | 0
| LGCE Campus | LGCE Campus | Structural |  | Complete LoD 200 by 26'Q2 | 0 | 0 | [7 empty] | 0 | 0
| LGCE Campus | LGCE Campus | Structural | Prakash C | LoD 200 - Schematic Concept |  |  | Prakash C | Vineetha | Sagar | Rohit | karthik |  | 0 | 0
| LGCE Campus | LGCE Campus | MEP |  | Complete LoD 200 by 26'Q2 | 0 | 0 | [7 empty] | 0 | 0
| LGCE Campus | LGCE Campus | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0
| LGCE Campus | LGCE Campus | Landscape |  | Complete LoD 200 by 26'Q2 | 0 | 0 | [7 empty] | 0 | 0
| LGCE Campus | LGCE Campus | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0
| MT Plano | MT Plano |  |  | Package Release | 0.5469 | 3 | [7 empty] | 0 | 0
| MT Plano | MT Plano | Architecture |  | Complete LoD 350 - Foundation and Structure by 26'Q2 | 0.5469 | 3 | [7 empty] | 0 | 0
| MT Plano | MT Plano | Architecture | Manik G | LoD 100 - Design Brief | 0.15626 | 1 | Manik G | [6 empty] | 0
| MT Plano | MT Plano | Architecture | Manik G | LoD 200 - Schematic Concept | 0.23439 | 1 | Manik G | [6 empty] | 0
| MT Plano | MT Plano | Architecture | Manik G | LoD 200 - Approvals | 0.15626 | 1 | Manik G | [6 empty] | 0
| MT Plano | MT Plano | Architecture | Manik G | LoD 300 - Pre Construction set |  |  | Manik G | [6 empty] | 0
| MT Plano | MT Plano | Architecture | Manik G | LoD 350 - Foundation and Structure |  |  | Manik G | [6 empty] | 0
| MT Plano | MT Plano | Structural |  | Complete LoD 300 by 26'Q2 | 0 | 0 | [7 empty] | 0 | 0
| MT Plano | MT Plano | Structural | Manik G | LoD 200 - Schematic Concept |  |  | Manik G | [6 empty] | 0
| MT Plano | MT Plano | Structural | Manik G | LoD 300 - Pre Construction set |  |  | Manik G | [6 empty] | 0
| MT Plano | MT Plano | MEP |  | Complete LoD 300 by 26'Q2 | 0 | 0 | [7 empty] | 0 | 0
| MT Plano | MT Plano | MEP | Manik G | LoD 200 - Schematic Concept |  |  | Manik G | [6 empty] | 0
| MT Plano | MT Plano | MEP | Manik G | LoD 200 - Approvals |  |  | Manik G | [6 empty] | 0
| MT Plano | MT Plano | MEP | Manik G | LoD 300 - Pre Construction set |  |  | Manik G | [6 empty] | 0
| MT Plano | MT Plano | Landscape |  | Complete LoD 300 by 26'Q2 | 0 | 0 | [7 empty] | 0 | 0
| MT Plano | MT Plano | Landscape | Manik G | LoD 200 - Schematic Concept |  |  | Manik G | [6 empty] | 0
| MT Plano | MT Plano | Landscape | Manik G | LoD 200 - Approvals |  |  | Manik G | [6 empty] | 0
| MT Plano | MT Plano | Landscape | Manik G | LoD 300 - Pre Construction set |  |  | Manik G | [6 empty] | 0
| MeenaSai Res | MS Res |  |  | Package Release | 0.0936 | 4 | [7 empty] | 0 | 0
| MeenaSai Res | MS Res | Architecture |  | Complete LoD 200, Approvals by 26'Q2 | 0.063 | 1 | [7 empty] | 0 | 0
| MeenaSai Res | MS Res | Architecture | Cijey M | LoD 200 - Schematic Concept | 0.063 | 1 | Cijey M | Niashinlulu | Syed Musharaff |  |  |  |  | 0
| MeenaSai Res | MS Res | Architecture | Cijey M | LoD 300 - Pre Construction set |  |  | Cijey M | Niashinlulu | Syed Musharaff |  |  |  |  | 0
| MeenaSai Res | MS Res | Structural |  | Complete LoD 200 by 26'Q2 | 0.0192 | 1 | [7 empty] | 0 | 0
| MeenaSai Res | MS Res | Structural | Prakash C | LoD 200 - Schematic Concept | 0.0192 | 1 | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan |  | 0 | 0
| MeenaSai Res | MS Res | Structural | Prakash C | LoD 300 - Pre Construction set |  |  | Prakash C | Lincy | Subrahmanya | Abhishek | Darshan |  | 0 | 0
| MeenaSai Res | MS Res | MEP |  | Complete LoD 200, Approvals by 26'Q2 | 0.0054 | 1 | [7 empty] | 0 | 0
| MeenaSai Res | MS Res | MEP | Gagan | LoD 200 - Schematic Concept | 0.0054 | 1 | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sampath Mahadev |  |  |  | 0
| MeenaSai Res | MS Res | MEP | Gagan | LoD 300 - Pre Construction set |  |  | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sampath Mahadev |  |  |  | 0
| MeenaSai Res | MS Res | Landscape |  | Complete LoD 200 by 26'Q2 | 0.006 | 1 | [7 empty] | 0 | 0
| MeenaSai Res | MS Res | Landscape | Gagan | LoD 200 - Schematic Concept | 0.006 | 1 | Gagan | Lajja | Anisha |  |  |  |  | 0
| MeenaSai Res | MS Res | Landscape | Gagan | LoD 300 - Pre Construction set |  |  | Gagan | Lajja | Anisha |  |  |  |  | 0
| NH Homestay | NH HS |  |  | Package Release | 1.1978 | 13 | [7 empty] | 0 | 0
| NH Homestay | NH HS | Architecture |  | Complete the project | 0.77994 | 4 | [7 empty] | 0 | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 300 - Pre Construction set | 0.12999 | 1 | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira |  |  |  | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Foundation and Structure | 0.25998 | 1 | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira |  |  |  | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Building Envelope + Plot Development | 0.19498 | 1 | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira |  |  |  | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Interiors | 0.19498 | 1 | Cijey M | Theodora Rodrigues | Aishwarya Hegde | Thomas Pradip Moreira |  |  |  | 0
| NH Homestay | NH HS | Structural |  | Complete the project | 0.22284 | 3 | [7 empty] | 0 | 0
| NH Homestay | NH HS | Structural | Prakash C | LoD 300 - Pre Construction set | 0.059424 | 1 | Prakash C | Lincy | Abhishek | Subrahmanya | Darshan |  | 0 | 0
| NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Foundation and Structure | 0.14856 | 1 | Prakash C | Lincy | Abhishek | Subrahmanya | Darshan |  | 0 | 0
| NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Building Envelope + Plot Development | 0.014856 | 1 | Prakash C | Lincy | Abhishek | Subrahmanya | Darshan |  | 0 | 0
| NH Homestay | NH HS | MEP |  | Complete the project | 0.12535 | 4 | [7 empty] | 0 | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 300 - Pre Construction set | 0.016713 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu |  |  |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Foundation and Structure | 0.058495 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu |  |  |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Building Envelope + Plot Development | 0.025069 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu |  |  |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Interiors | 0.025069 | 1 | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Ajay Matsarambabu |  |  |  | 0
| NH Homestay | NH HS | Landscape |  | Complete the project | 0.069638 | 2 | [7 empty] | 0 | 0
| NH Homestay | NH HS | Landscape | Gagan | LoD 300 - Pre Construction set | 0.01857 | 1 | Gagan | Lajja | Anisha | Chetan |  |  |  | 0
| NH Homestay | NH HS | Landscape | Gagan | LoD 350 - Building Envelope + Plot Development | 0.051068 | 1 | Gagan | Lajja | Anisha | Chetan |  |  |  | 0
| Indiranagar Res | Indrng Res |  |  | Package Release | 0.004913 | 6 | [7 empty] | 0 | 0
| Indiranagar Res | Indrng Res | Architecture |  | Complete the project [Complete LoD 350 ] | 0.004 | 4 | [7 empty] | 0 | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block A - Interiors | 0.0021 | 1 | Manik G | [6 empty] | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block B - Interiors | 0.000875 | 1 | Manik G | [6 empty] | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block C - Interiors | 0.000525 | 1 | Manik G | [6 empty] | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 -Block C - Building Envelope + Plot Development | 0.0005 | 1 | Manik G | [6 empty] | 0
| Indiranagar Res | Indrng Res | Landscape |  | Complete the project [Complete LoD 350 ] | 0.000113 | 1 | [7 empty] | 0 | 0
| Indiranagar Res | Indrng Res | Landscape | Gagan | LoD 350 - Block C- Building Envelope + Plot Development | 0.000113 | 1 | Gagan | Lajja | Chetan |  |  |  |  | 0
| Indiranagar Res | Indrng Res | Structural |  | Complete the project [Complete LoD 350 ] | 0.0008 | 1 | [7 empty] | 0 | 0
| Indiranagar Res | Indrng Res | Structural | Prakash C | LoD 350 -Block C - Building Envelope + Plot Development | 0.0008 | 1 | Prakash C | Theja |  | 0 | Vinay |  | 0 | 0
| OTR Museum | OTR Mus |  |  | Package Release | 0.43996 | 2 | [7 empty] | 0 | 0
| OTR Museum | OTR Mus | Architecture |  | Complete Schematic concept | 0.43996 | 2 | [7 empty] | 0 | 0
| OTR Museum | OTR Mus | Architecture | Cijey M | LoD 100 - Design Brief | 0.17598 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
| OTR Museum | OTR Mus | Architecture | Cijey M | LoD 200 - Schematic Concept | 0.26398 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
| OTR Museum | OTR Mus | Structural |  | Complete Schematic concept | 0 | 0 | [7 empty] | 0 | 0
| OTR Museum | OTR Mus | Structural | Prakash C | LoD 200 - Schematic Concept |  |  | Prakash C | Satish H | Mazhar |  |  |  |  | 0
| OTR Museum | OTR Mus | MEP |  | Complete Schematic concept | 0 | 0 | [7 empty] | 0 | 0
| OTR Museum | OTR Mus | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0
| OTR Museum | OTR Mus | Landscape |  | Complete Schematic concept | 0 | 0 | [7 empty] | 0 | 0
| OTR Museum | OTR Mus | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0
| Fullkit Homes | FKH |  |  | Package Release | 0 | 26 | [7 empty] | 0 | 0
| TuiG | Tuig [V20] | Architecture |  | Tuig [V20] | 0 | 3 | [7 empty] | 0 | 0
| TuiG | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
| TuiG | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
| TuiG | FKH | Architecture | Atul P | Default Marketing BOQ |  | 1 | Atul P
| TuiG | Tuig [V30] | Architecture |  | Tuig [V30] |  | 3 | [8 empty] | 0
| TuiG | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
| TuiG | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
| TuiG | FKH | Architecture | Atul P | Default Marketing BOQ |  | 1 | Atul P
| TuiG | Tuig [V40] | Architecture |  | Tuig [V40] |  | 3 | [8 empty] | 0
| TuiG | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
| TuiG | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
| TuiG | FKH | Architecture | Atul P | Default Marketing BOQ |  | 1 | Atul P
| Harohalli | Harohalli [V20] | Architecture |  | Harohalli [V20] | 0 | 2 | [7 empty] | 0 | 0
| Harohalli | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
| Harohalli | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
| Harohalli | Harohalli [V30] | Architecture |  | Harohalli [V30] |  | 2 | [8 empty] | 0
| Harohalli | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
| Harohalli | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
| Harohalli | Harohalli [V50H] | Architecture |  | Harohalli [V50H] |  | 2 | [8 empty] | 0
| Harohalli | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
| Harohalli | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
| Violet Hill | Violet Hill [P1] | Architecture |  | Violet Hill [P1] |  | 3 | [8 empty] | 0
| Violet Hill | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
| Violet Hill | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
| Violet Hill | FKH | Architecture | Atul P | Default Marketing BOQ |  | 1 | Atul P
| Violet Hill | Violet Hill [P2] | Architecture |  | Violet Hill [P2] |  | 3 | [8 empty] | 0
| Violet Hill | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
| Violet Hill | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
| Violet Hill | FKH | Architecture | Atul P | Default Marketing BOQ |  | 1 | Atul P
| Shreegaon | Shreegaon [V50H] | Architecture |  | Shreegaon [V50H] |  | 1 | [8 empty] | 0
| Shreegaon | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
| OTF | OTF [V60] | Architecture |  | OTF [V60] |  | 2 | [8 empty] | 0
| OTF | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
| OTF | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
| OTF | OTF [V25H] | Architecture |  | OTF [V25H] |  | 2 | [8 empty] | 0
| OTF | FKH | Architecture | Atul P | Shell + Interior GFC |  | 1 | Atul P
| OTF | FKH | Architecture | Atul P | Design Specs + GFC |  | 1 | Atul P
| Rework Pkgs | Rwrk |  |  |  | 0.44 | 2 | [7 empty] | 0 | 0
| PoaRR-T08 | T08 | Structural | Prakash C | STR Package Release [LoD 350 - Parking level subgrade] | 0.4 | 1 | Prakash C | Lincy | Charan |  | Darshan |  |  | 0
| ITQE-T05 | T05 | Structural | Prakash C | STR Package Release [LoD 350 - Habitable Level 01] | 0.04 | 1 | Prakash C | Satish | Antony |  | Shivaraj |  |  | 0
| New Projects |  |  |  |  | 120.0361 | 97 | [7 empty] | 0 | 0
| OTR-Ph02 | Ph 2 |  |  | Package Release | 1.35 | 5 | [7 empty] | 0 | 0
| OTR-Ph02 | Ph 2 | Architecture |  | Complete Approvals | 1.35 | 5 | [7 empty] | 0 | 0
| OTR-Ph02 | Ph 2 | Architecture | Cijey M | LoD 100 - Contract + Design Brief | 0.54 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Cijey M | LoD 200 - Schematic Concept | 0.43 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Cijey M | Approvals | 0.21 | 1 | Cijey M | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Om Prakash | LoD 200 - Schematic Concept - CH | 0.11 | 1 | Om Prakash | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Approvals - CH | 0.06 | 1 | Om Prakash | Dinakar Venugopal | Niashinlulu | Saurabh Bothra |  |  |  | 0
| OTR-Ph02 | Ph 2 | Structural |  | Complete Schematic concept | 0 | 0 | [7 empty] | 0 | 0
| OTR-Ph02 | Ph 2 | Structural | Prakash C | LoD 200 - Schematic Concept |  |  | Prakash C | Satish | Mazhar ( If Villa concept is different new resource is required) |  | Samyukta |  | 0 | 0
| OTR-Ph02 | Ph 2 | MEP |  | Complete Approvals | 0 | 0 | [7 empty] | 0 | 0
| OTR-Ph02 | Ph 2 | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Deepu Mahadev |  |  |  | 0
| OTR-Ph02 | Ph 2 | MEP | Gagan | Approvals |  |  | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Deepu Mahadev |  |  |  | 0
| OTR-Ph02 | Ph 2 | Landscape |  | Complete Approvals | 0 | 0 | [7 empty] | 0 | 0
| OTR-Ph02 | Ph 2 | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Lajja | Apoorva |  |  |  |  | 0
| OTR-Ph02 | Ph 2 | Landscape | Gagan | Approvals |  |  | Gagan | Lajja | Apoorva |  |  |  |  | 0
| TMFT-Ph 3 | Ph 3 |  |  | Package Release | 0.24728 | 1 | [7 empty] | 0 | 0
| TMFT-Ph 3 | Ph 3 | Architecture |  | LOD 350 -Tower Habitable levels, MP Pkg 2 | 0.24728 | 1 |  | To be shared - Naveen Y [Clearance on requirement from KS required] | [5 empty] | 0 | 0
| TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | LoD 100 - Contract + Design Brief | 0.24728 | 1 | Om Prakash | [6 empty] | 0
| TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | LoD 200 - Schematic Concept |  |  | Om Prakash | [6 empty] | 0
| TMFT-Ph 3 | Ph 3 | Structural |  | LOD 350 -Tower Habitable levels, MP Pkg 2, ISS Pkg 2 | 0 | 0 | [7 empty] | 0 | 0
| TMFT-Ph 3 | Ph 3 | Structural | Prakash C | LoD 200 - Schematic Concept |  |  | Prakash C | Vineetha | Dhirender | Rajath | Arpitha |  | 0 | 0
| TMFT-Ph 3 | Ph 3 | MEP |  | LOD 350 -Tower Habitable levels, MP Pkg 1, ISS Pkg 2 | 0 | 0 |  | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0 | 0
| TMFT-Ph 3 | Ph 3 | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Subash Shreedhar |  |  |  | 0
| TMFT-Ph 3 | Ph 3 | Landscape |  | LOD 350 - MP Pkg 1 | 0 | 0 |  | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0 | 0
| TMFT-Ph 3 | Ph 3 | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Lajja | Chetan |  |  |  |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a |  |  | Package Release | 12.8164 | 7 | [7 empty] | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture |  | LoD 300 [Marketing and Sales, Pre Construction Set], LoD 350 [Experience Home + Project Experience] | 8.7814 | 3 | [7 empty] | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | LoD 300 - Pre Construction Set | 4.3907 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkineni | Hruthika Mylar |  |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | LoD 350 - Experience Home + Project Experience | 2.1953 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkineni | Hruthika Mylar |  |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | LoD 300 - Marketing and Sales | 2.1953 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Nischala Akkineni | Hruthika Mylar |  |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural |  | LoD 200 [Schematic Concept], LoD 300 [Pre Construction Set] | 3.2579 | 2 | [7 empty] | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | LoD 200 - Schematic Concept | 1.3962 | 1 | Prakash C | Satish | Raghavendra & New Resource |  | Vinay |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | LoD 300 - Pre Construction Set | 1.8617 | 1 | Prakash C | Satish | Raghavendra & New Resource |  | Vinay |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP |  | LoD 200 [Schematic Concept], LoD 300 [Pre Construction Set], LoD 350 [Experience Home + Project Experience] | 0.77715 | 2 | [7 empty] | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | LoD 200 - Schematic Concept | 0.5181 | 1 | Gagan | Salomi | Bhavya Hareesha | Prem Matsarambabu Byahattimath |  |  |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | LoD 300 - Pre Construction Set |  |  | Gagan | Salomi | Bhavya Hareesha | Prem Matsarambabu Byahattimath |  |  |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | LoD 350 - Experience Home + Project Experience | 0.25905 | 1 | Gagan | Salomi | Bhavya Hareesha | Prem Matsarambabu Byahattimath |  |  |  | 0
| Sarjapur Road [South Block-Resi] | Srjp - Res |  |  | Package Release | 17.475 | 11 | [7 empty] | 0 | 0
| Srjp - Res | Srjp - Res | Architecture |  | Complete LoD 200, Approvals & Experience Homes by 26'Q2 | 14.3238 | 6 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | LoD 100 - Contract + Design Brief | 4.7746 | 1 | Cijey M | Theodora Rodrigues | Vidhi Kapadia | Nikita Potadar |  |  |  | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | LoD 200 - Schematic Concept | 4.364 | 1 | Cijey M | Theodora Rodrigues | Vidhi Kapadia | Nikita Potadar |  |  |  | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | LoD 200 - Approvals | 2.2847 | 1 | Cijey M | Theodora Rodrigues | Vidhi Kapadia | Nikita Potadar |  |  |  | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | LoD 350 - Experience Home + Project Experience | 2.3873 | 1 | Cijey M | Theodora Rodrigues | Vidhi Kapadia | Nikita Potadar |  |  |  | 0
| Srjp - Res | Srjp - Res | Architecture | Om Prakash | LoD 200 - CH: Schematic Concept | 0.4106 | 1 | Om Prakash | [6 empty] | 0
| Srjp - Res | Srjp - Res | Architecture | Om Prakash | LoD 200 - CH: Approvals | 0.10265 | 1 | Om Prakash | [6 empty] | 0
| Srjp - Res | Srjp - Res | Structural |  | Complete LoD 200 & Experience Homes by 26'Q2 | 2.0244 | 2 | [7 empty] | 0 | 0
| Srjp - Res | Srjp - Res | Structural | Prakash C | LoD 200 - Schematic Concept | 1.5183 | 1 | Prakash C | Lincy | Jayashankar | Charan | Darshan |  | 0 | 0
| Srjp - Res | Srjp - Res | Structural | Prakash C | LoD 350 - Experience Home + Project Experience | 0.50611 | 1 | Prakash C | Lincy | Jayashankar | Charan | Darshan |  | 0 | 0
| Srjp - Res | Srjp - Res | MEP |  | Complete LoD 200, Approvals & Experience Homes by 26'Q2 | 1.1268 | 3 | [7 empty] | 0 | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | LoD 200 - Schematic Concept | 0.5634 | 1 | Gagan | Salomi | Praveen Hareesha | Ajay Hanumanthraya Byahattimath Matsarambabu Shreedhar |  |  |  | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | LoD 200 - Approvals | 0.2817 | 1 | Gagan | Salomi | Praveen Hareesha | Ajay Hanumanthraya Byahattimath Matsarambabu Shreedhar |  |  |  | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | LoD 350 - Experience Home + Project Experience | 0.2817 | 1 | Gagan | Salomi | Praveen Hareesha | Ajay Hanumanthraya Byahattimath Matsarambabu Shreedhar |  |  |  | 0
2 | Srjp - Res | Srjp - Res | Landscape |  | Complete LoD 200 & Experience Homes by 26'Q2 | 0 | 0 | [7 empty] | 0 | 0
| Srjp - Res | Srjp - Res | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Lajja | Apoorva | Chetan |  |  |  | 0
| Srjp - Res | Srjp - Res | Landscape | Gagan | LoD 350 - Experience Home + Project Experience |  |  | Gagan | Lajja | Apoorva | Chetan |  |  |  | 0
| Sarjapur - C (South Block) | Srjp - C - SB |  |  | Package Release | 14.4575 | 5 | [7 empty] | 0 | 0
| Srjp - C - SB | Srjp - C - SB | Architecture |  | Complete LoD 200, Approvals, Marketing & Sales by 26'Q2 | 12.8953 | 4 | [7 empty] | 0 | 0
| Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | LoD 100 - Contract + Design Brief | 3.6844 | 1 | Naveen Y | Naveen Y | Swathi S |  |  |  |  | 0
| Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | LoD 200 - Schematic Concept | 3.6844 | 1 | Naveen Y | Naveen Y | Swathi S |  |  |  |  | 0
| Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | LoD 200 - Approvals | 3.6844 | 1 | Naveen Y | Akhila G | Swathi S | Shadha |  |  |  | 0
| Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | LoD 200 - Marketing and Sales | 1.8422 | 1 | Naveen Y | Akhila G | Swathi S | Shadha |  |  |  | 0
| Srjp - C - SB | Srjp - C - SB | Structural |  | Complete LoD 200 by 26'Q2 | 1.5622 | 1 | [7 empty] | 0 | 0
| Srjp - C - SB | Srjp - C - SB | Structural | Prakash C | LoD 200 - Schematic Concept | 1.5622 | 1 | Prakash C | Lincy | - | - | Darshan |  | 0 | 0
| Srjp - C - SB | Srjp - C - SB | MEP |  | Complete LoD 200 & Approvals by 26'Q2 | 0 | 0 | [7 empty] | 0 | 0
| Srjp - C - SB | Srjp - C - SB | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Salomi | Praveen Hareesha | Deepu Shreedhar Byahattimath |  |  |  | 0
| Srjp - C - SB | Srjp - C - SB | MEP | Gagan | LoD 200 - Approvals |  |  | Gagan | Salomi | Praveen Hareesha | Deepu Shreedhar Byahattimath |  |  |  | 0
| Srjp - C - SB | Srjp - C - SB | Landscape |  | Complete LoD 200 by 26'Q2 | 0 | 0 | [7 empty] | 0 | 0
| Srjp - C - SB | Srjp - C - SB | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | [6 empty] | 0
| Sarjapur - C (North Block) | Srjp - C - NB |  |  | Package Release | 5.109 | 7 | [7 empty] | 0 | 0
| Srjp - C - NB | Srjp - C - NB | Architecture |  | Complete LoD 200, Approvals, Marketing & Sales by 26'Q2 | 4.2984 | 4 | [7 empty] | 0 | 0
| Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | LoD 100 - Contract + Design Brief | 1.2281 | 1 | Naveen Y | Naveen Y | Fathima S |  |  |  |  | 0
| Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | LoD 200 - Schematic Concept | 1.2281 | 1 | Naveen Y | Naveen Y | Fathima S |  |  |  |  | 0
| Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | LoD 200 - Approvals | 1.2281 | 1 | Naveen Y | Akhila G | Fathima S | Nanditha S |  |  |  | 0
| Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | LoD 200 - Marketing and Sales | 0.61406 | 1 | Naveen Y | Akhila G | Fathima S | Nanditha S |  |  |  | 0
| Srjp - C - NB | Srjp - C - NB | Structural |  | Complete LoD 200 by 26'Q2 | 0.52073 | 1 | [7 empty] | 0 | 0
| Srjp - C - NB | Srjp - C - NB | Structural | Prakash C | LoD 200 - Schematic Concept | 0.52073 | 1 | Prakash C | Lincy | Suganthan | - | Darshan |  | 0 | 0
| Srjp - C - NB | Srjp - C - NB | MEP |  | Complete LoD 200 & Approvals by 26'Q2 | 0.28984 | 2 | [7 empty] | 0 | 0
| Srjp - C - NB | Srjp - C - NB | MEP | Gagan | LoD 200 - Schematic Concept | 0.14492 | 1 | Gagan | Salomi | Praveen Hareesha | Deepu Byahattimath Matsarambabu |  |  |  | 0
| Srjp - C - NB | Srjp - C - NB | MEP | Gagan | LoD 200 - Approvals | 0.14492 | 1 | Gagan | Salomi | Praveen Hareesha | Deepu Byahattimath Matsarambabu |  |  |  | 0
| Srjp - C - NB | Srjp - C - NB | Landscape |  | Complete LoD 200 by 26'Q2 | 0 | 0 | [7 empty] | 0 | 0
| Srjp - C - NB | Srjp - C - NB | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | [6 empty] | 0
| OTF | OTF |  |  | Package Release | 3.699 | 15 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
| OTF | OTF | Master Planning |  | LoD 350 | 2.7525 | 6 | [7 empty] | 0 | 0
| OTF | OTF | Master Planning | Naveen Y | LoD 100 - Contract + Design Brief [Commercial] | 0.3375 | 1 | Naveen Y | Naveen Y | Aswin J |  |  |  |  | 0
| OTF | OTF | Master Planning | Naveen Y | LoD 200 - Schematic Concept | 0.58 | 1 | Naveen Y | Naveen Y | Aswin J |  |  |  |  | 0
| OTF | OTF | Master Planning | Naveen Y | Approvals | 0.58 | 1 | Naveen Y | Aswin J | Mithoon |  |  |  |  | 0
| OTF | OTF | Master Planning | Naveen Y | LoD 300 - Pre Construction Set | 0.58 | 1 | Naveen Y | Aswin J | Mithoon |  |  |  |  | 0
| OTF | OTF | Master Planning | Naveen Y | LoD 200 - Marketing and Sales | 0.3375 | 1 | Naveen Y | Aswin J | Mithoon |  |  |  |  | 0
| OTF | OTF | Master Planning | Naveen Y | LoD 350 - Project Entrance | 0.3375 | 1 | Naveen Y | Aswin J | Mithoon |  |  |  |  | 0
| OTF | OTF | Architecture |  | LoD 350 | 0.285 | 3 | [7 empty] | 0 | 0
| OTF | OTF | Architecture | Om Prakash | LoD 200 - Schematic Concept - CH | 0.095 | 1 | Om Prakash | [6 empty] | 0
| OTF | OTF | Architecture | Om Prakash | Approvals - CH | 0.095 | 1 | Om Prakash | [6 empty] | 0
| OTF | OTF | Architecture | Om Prakash | LoD 300 - Pre Construction set - CH | 0.095 | 1 | Om Prakash | [6 empty] | 0
| OTF | OTF | Structural |  | LoD 350 | 0.5724 | 3 | [7 empty] | 0 | 0
| OTF | OTF | Structural | Prakash C | LoD 200 - Schematic Concept | 0.1431 | 1 | Prakash C | Satish | Alwin | Raghav | Darshan |  | 0 | 0
| OTF | OTF | Structural | Prakash C | LoD 300 - Pre Construction Set | 0.2862 | 1 | Prakash C | Satish | Alwin | Raghav | Darshan |  | 0 | 0
| OTF | OTF | Structural | Prakash C | LoD 350 - Project Entrance | 0.1431 | 1 | Prakash C | Satish | Alwin | Raghav | Darshan |  | 0 | 0
| OTF | OTF | MEP |  | LoD 350 | 0 | 0 | [7 empty] | 0 | 0
| OTF | OTF | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Prem Matsarambabu |  |  |  | 0
| OTF | OTF | MEP | Gagan | LoD 300 - Pre Construction Set |  |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Prem Matsarambabu |  |  |  | 0
| OTF | OTF | MEP | Gagan | LoD 350 - Project Entrance |  |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Prem Matsarambabu |  |  |  | 0
| OTF | OTF | Landscape |  | LoD 350 | 0.0891 | 3 | [7 empty] | 0 | 0
| OTF | OTF | Landscape | Gagan | LoD 200 - Schematic Concept | 0.04455 | 1 | Gagan | Lajja | Aproova | Chetan |  |  |  | 0
| OTF | OTF | Landscape | Gagan | LoD 300 - Pre Construction Set | 0.022275 | 1 | Gagan | Lajja | Aproova | Chetan |  |  |  | 0
| OTF | OTF | Landscape | Gagan | LoD 350 - Project Entrance | 0.022275 | 1 | Gagan | Lajja | Aproova | Chetan |  |  |  | 0
| Harohalli [Plotted] | Harohalli |  |  | Package Release | 6.2751 | 8 | [7 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | Master Planning |  | [Dsgn Brf, LOD 200 - Schematic, Approvals, LoD 350 - Exp, LoD 300 - Pre const] | 4.52 | 4 | [7 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | LoD 100 - Contract + Design Brief | 0.855 | 1 | Gagan | Utpal | Megha |  |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | LoD 200 - Schematic Concept | 1.405 | 1 | Gagan | Utpal | Megha |  |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Approvals | 1.405 | 1 | Gagan | Utpal | Megha |  |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | LoD 350 - Project Experience | 0.855 | 1 | Gagan | Utpal | Megha |  |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | Architecture |  | [LOD 200 - Schematic] | 0.305 | 1 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | Architecture | Om Prakash | LoD 200 - Schematic Concept | 0.305 | 1 | Om Prakash | [6 empty] | 0
| Harohalli [Plotted] | Ph 1 | Structural |  | [LOD 200 - Schematic,LoD 350 - Exp, LoD 300 - Pre const] | 1.4501 | 3 | [7 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | Structural | Prakash C | LoD 200 - Schematic Concept | 0.36252 | 1 | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | Structural | Prakash C | LoD 300 - Pre-construction Set | 0.72504 | 1 | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | Structural | Prakash C | LoD 350 - Project Experience | 0.36252 | 1 | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | MEP |  | [LOD 200 - Schematic, Approvals, LoD 350 - Exp, LoD 300 - Pre const] | 0 | 0 | [7 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Salomi | Eranna Praveen | Avinash Prateesha Deepu |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | MEP | Gagan | Approvals |  |  | Gagan | Salomi | Eranna Praveen | Avinash Prateesha Deepu |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | MEP | Gagan | LoD 350 - Project Experience |  |  | Gagan | Salomi | Eranna Praveen | Avinash Prateesha Deepu |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | Landscape |  | [LOD 200 - Schematic, Approvals, LoD 350 - Exp, LoD 300 - Pre const] | 0 | 0 | [7 empty] | 0 | 0
| Harohalli [Plotted] | Ph 1 | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Lajja | Anisha |  |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Approvals |  |  | Gagan | Lajja | Anisha |  |  |  |  | 0
| Harohalli [Plotted] | Ph 1 | Landscape | Gagan | LoD 350 - Project Experience |  |  | Gagan | Lajja | Anisha |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 |  |  | Package Release | 2.8744 | 6 | [7 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Master Planning |  | Package Release [till LoD 300 - Pre Construction Set] | 2.1842 | 3 | [7 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Master Planning | Gagan | LoD 100 - Contract + Design Brief | 0.4725 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Master Planning | Gagan | LoD 200 - Schematic Concept | 0.85586 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Master Planning | Gagan | LoD 200 - Approvals | 0.85586 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Architecture |  | Package Release [till LoD 200 - Schematic Concept] | 0.089136 | 1 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Architecture | Om Prakash | LoD 200 - Schematic Concept | 0.089136 | 1 | Om Prakash | [6 empty] | 0
| Shreegaon [61.6a] | Ph 1 | Structural |  | Package Release [till LoD 300 - Pre Construction Set] | 0.60102 | 2 | [7 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Structural | Prakash C | LoD 200 - Schematic Concept | 0.20034 | 1 | Prakash C | Satish | Alwin | Raghav | Harshitha |  | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Structural | Prakash C | LoD 300 - Pre Construction Set | 0.40068 | 1 | Prakash C | Satish | Alwin | Raghav | Harshitha |  | 0 | 0
| Shreegaon [61.6a] | Ph 1 | MEP |  | Package Release [till LoD 300 - Pre Construction Set] | 0 | 0 | [7 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | MEP | Gagan | LoD 200 - Approvals |  |  | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | MEP | Gagan | LoD 300 - Pre Construction Set |  |  | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Landscape |  | Package Release [till LoD 300 - Pre Construction Set] | 0 | 0 | [7 empty] | 0 | 0
| Shreegaon [61.6a] | Ph 1 | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Lajja | Anisha |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Landscape | Gagan | LoD 200 - Approvals |  |  | Gagan | Lajja | Anisha |  |  |  |  | 0
| Shreegaon [61.6a] | Ph 1 | Landscape | Gagan | LoD 300 - Pre Construction Set |  |  | Gagan | Lajja | Anisha |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 |  |  | Package Release | 1.3348 | 15 | [7 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Master Planning |  | Package Release [till LoD 350 - Infra - Plot Boundary & Enclosures] | 0.81525 | 5 | [7 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Master Planning | Gagan | LoD 350 - Project Experience [Sales Lounge, Model Road] | 0.13427 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Master Planning | Gagan | LoD 350 - Infra - Grading | 0.24321 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Master Planning | Gagan | LoD 350 - Infra - MEP | 0.1216 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Master Planning | Gagan | LoD 350 - BOQ & Technical Specifications | 0.24321 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Master Planning | Gagan | LoD 350 - Structures - Security Cabin and Entrance [Rework] | 0.072962 | 1 | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Architecture |  | Package Release [till LoD 200 - Approvals] | 0.050686 | 2 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Architecture | Om Prakash | LoD 200 - Schematic Concept | 0.025343 | 1 | Om Prakash | [6 empty] | 0
| Violet Hill [21.76a] | Ph 1 | Architecture | Om Prakash | LoD 200 - Approvals | 0.025343 | 1 | Om Prakash | [6 empty] | 0
| Violet Hill [21.76a] | Ph 1 | Structural |  | Package Release [till LoD 350 - Infra - Plot Boundary & Enclosures] | 0.27392 | 5 | [7 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Structural | Prakash C | LoD 300 - Pre Construction Set | 0.11386 | 1 | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Structural | Prakash C | LoD 350 - Project Experience [Sales Lounge, Model Road] | 0.056932 | 1 | Prakash C | Satish/Lincy | Alwin/Subramanya | Raghav | Prasad |  | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Structural | Prakash C | LoD 350 - Infra - Grading | 0.02578 | 1 | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Structural | Prakash C | LoD 350 - Infra - MEP | 0.05156 | 1 | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Structural | Prakash C | LoD 350 - Structures - Security Cabin and Entrance [Rework] | 0.02578 | 1 | Prakash C | Lincy | Subrahmanya | - | Prasad |  | 0 | 0
| Violet Hill [21.76a] | Ph 1 | MEP |  | Package Release [till LoD 350 - Structures - Security Cabin and Entrance] | 0.19494 | 3 | [7 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | MEP | Gagan | LoD 350 - Project Experience [Sales Lounge, Model Road] |  |  | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | MEP | Gagan | LoD 350 - Infra - MEP | 0.097469 | 1 | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | MEP | Gagan | LoD 350 - BOQ & Technical Specifications | 0.03249 | 1 | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | MEP | Gagan | LoD 350 - Infra - Coordinated | 0.064979 | 1 | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | MEP | Gagan | LoD 350 - Structures - Security Cabin and Entrance [Rework] |  |  | Gagan | Salomi | Eranna Bhavya |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Landscape |  | Package Release [till LoD 350 - Structures - Security Cabin and Entrance] | 0 | 0 | [7 empty] | 0 | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | LoD 350 - Project Experience [Sales Lounge, Model Road] |  |  | Gagan | Lajja | Apoorva Gouri |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | LoD 350 - Infra - MEP |  |  | Gagan | Lajja | Apoorva Gouri |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | LoD 350 - BOQ & Technical Specifications |  |  | Gagan | Lajja | Apoorva Gouri |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | LoD 350 - Infra - Coordinated |  |  | Gagan | Lajja | Apoorva Gouri |  |  |  |  | 0
| Violet Hill [21.76a] | Ph 1 | Landscape | Gagan | LoD 350 - Structures - Security Cabin and Entrance |  |  | Gagan | Lajja | Apoorva Gouri |  |  |  |  | 0
| Violet Hill [27.08a] | Ph 2 |  |  | Package Release | 0 | 0 | [7 empty] | 0 | 0
| Violet Hill [27.08a] | Ph 2 | Master Planning |  | Package Release [till LoD 300 - Pre Construction Set] | 0 | 0 | [7 empty] | 0 | 0
| Violet Hill [27.08a] | Ph 2 | Master Planning | Gagan | LoD 100 - Contract + Design Brief |  |  | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [27.08a] | Ph 2 | Master Planning | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Utpal | Manali |  |  |  |  | 0
| Violet Hill [27.08a] | Ph 2 | Structural |  | Package Release [till LoD 300 - Pre Construction Set] | 0 | 0 | [7 empty] | 0 | 0
| Violet Hill [27.08a] | Ph 2 | Structural | Prakash C | LoD 200 - Schematic Concept |  |  | Prakash C | Satish | Alwin | Raghav | Prasad |  | 0 | 0
| Violet Hill [27.08a] | Ph 2 | MEP |  | Package Release [till LoD 300 - Pre Construction Set] | 0 | 0 | [7 empty] | 0 | 0
| Violet Hill [27.08a] | Ph 2 | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | [6 empty] | 0
| Violet Hill [27.08a] | Ph 2 | Landscape |  | Package Release [till LoD 300 - Pre Construction Set] | 0 | 0 | [7 empty] | 0 | 0
| Violet Hill [27.08a] | Ph 2 | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | [6 empty] | 0
| Byatarayanpura [behind Mall of Asia] | Byatarayanpura |  |  | Package Release | 1.6141 | 1 | [7 empty] | 0 | 0
| Byatarayanpura [behind Mall of Asia] | Byatarayanpura | Architecture |  | LOD 350 -Tower Pkg 1, MP Pkg 1, CH Pkg 1 | 1.6141 | 1 | [7 empty] | 0 | 0
| Byatarayanpura [behind Mall of Asia] | Byatarayanpura | Architecture | Om Prakash | LoD 100 - Contract + Design Brief | 1.6141 | 1 | Om Prakash | Om Prakash | Sreeja | Sinchana |  |  |  | 0
| TR Mills Chamarajpet | TR Mills |  |  | Package Release | 0 | 0 | [7 empty] | 0 | 0
| TR Mills | TR Mills | Architecture |  | LOD 300, LOD 350 Exp home | 0 | 0 | [7 empty] | 0 | 0
| TR Mills | TR Mills | Architecture | Saji A | LoD 100 - Contract + Design Brief |  |  | Saji A | Simran | Arshad |  |  |  |  | 0
| KIADB - Mys | KIADB - Mys |  |  | Package Release | 0 | 3 | [7 empty] | 0 | 0
| KIADB - Mys | KIADB - Mys | Master Planning |  | Complete the project by Q4 | 0 | 3 | [7 empty] | 0 | 0
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | LoD 100 - Contract + Design Brief |  | 1 | Gagan | Utpal | Manali
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | LoD 200 - Schematic Concept |  | 1 | Gagan | Utpal | Manali
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | Approvals |  | 1 | Gagan | Utpal | Manali
| KIADB - Mys | KIADB - Mys | Structural |  | Complete the project by Q4 | 0 | 0 | [7 empty] | 0 | 0
| KIADB - Mys | KIADB - Mys | Structural | Prakash C | LoD 200 - Schematic Concept |  |  | Prakash C | Satish | Alwin | Raghav | Vinay |  | 0
| KIADB - Mys | KIADB - Mys | MEP |  | Complete the project by Q4 | 0 | 0 | [7 empty] | 0 | 0
| KIADB - Mys | KIADB - Mys | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Salomi | Eranna Praveen
| KIADB - Mys | KIADB - Mys | MEP | Gagan | Approvals |  |  | Gagan | Salomi | Eranna Praveen
| KIADB - Mys | KIADB - Mys | Landscape |  | Complete the project by Q4 | 0 | 0 | [7 empty] | 0 | 0
| KIADB - Mys | KIADB - Mys | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Lajja | Anisha
| KIADB - Mys | KIADB - Mys | Landscape | Gagan | Approvals |  |  | Gagan | Lajja | Anisha
| Imagine Campus | Imgn |  |  | Package Release | 1.44 | 4 | [7 empty] | 0 | 0
| Imagine Campus | Imgn | Architecture |  | Package Release [Complete LoD 100, 200] | 1.15 | 2 | [7 empty] | 0 | 0
| Imagine Campus | Imgn | Architecture | Naveen Y | LoD 200 - Schematic Concept | 0.69 | 1 | Naveen Y | Akhila G | Fathima S |  |  |  |  | 0
| Imagine Campus | Imgn | Architecture | Naveen Y | Approvals | 0.46 | 1 | Naveen Y | Akhila G | Fathima S |  |  |  |  | 0
| Imagine Campus | Imgn | Structural |  | Package Release [Complete LoD 200] | 0.19 | 0 | [7 empty] | 0 | 0
| Imagine Campus | Imgn | Structural | Prakash C | LoD 200 - Schematic Concept | 0.19 |  | Prakash C | Lincy | Charan | - | Karthik |  | 0 | 0
| Imagine Campus | Imgn | MEP |  | Package Release [Complete LoD 200] | 0.05 | 1 | [7 empty] | 0 | 0
| Imagine Campus | Imgn | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Salomi | Hareesha Bhavya | Byahattimath Shreedhar Viresh |  |  |  | 0
| Imagine Campus | Imgn | MEP | Gagan | Approvals | 0.05 | 1 | Gagan | Salomi | Hareesha Bhavya | Byahattimath Shreedhar Viresh |  |  |  | 0
| Imagine Campus | Imgn | Landscape |  | Package Release [Complete LoD 200] | 0.05 | 1 | [7 empty] | 0 | 0
| Imagine Campus | Imgn | Landscape | Gagan | Approvals | 0.05 | 1 | Gagan | Lajja | Aproova |  |  |  |  | 0
| OtR OOTA | OTR OOTA |  |  | Package Release | 0.043845 | 1 | [7 empty] | 0 | 0
| OTR OOTA | OTR OOTA | Architecture |  | Complete Approvals | 0.043845 | 1 | [7 empty] | 0 | 0
| OTR OOTA | OTR OOTA | Architecture | Manik G | Lod100 - Design Brief | 0.043845 | 1 | Manik G | [6 empty] | 0
| OTR OOTA | OTR OOTA | Architecture | Manik G | LoD 200 - Schematic Concept |  |  | Manik G | [6 empty] | 0
| OTR OOTA | OTR OOTA | Architecture | Manik G | Approvals |  |  | Manik G | [6 empty] | 0
| OTR OOTA | OTR OOTA | Structural |  | Complete Schematic concept | 0 | 0 | [7 empty] | 0 | 0
| OTR OOTA | OTR OOTA | Structural | Prakash C | LoD 200 - Schematic Concept |  |  | Prakash C | Theja | - |  | Samyukta |  | 0 | 0
| OTR OOTA | OTR OOTA | MEP |  | Complete Approvals | 0 | 0 | [7 empty] | 0 | 0
| OTR OOTA | OTR OOTA | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| OTR OOTA | OTR OOTA | MEP | Gagan | Approvals |  |  | Gagan | Salomi | Eranna Praveen Hareesha | Avinash Sandeep Shreedhar |  |  |  | 0
| OTR OOTA | OTR OOTA | Landscape |  | Complete Approvals | 0 | 0 | [7 empty] | 0 | 0
| OTR OOTA | OTR OOTA | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | Lajja | Anisha |  |  |  |  | 0
| OTR OOTA | OTR OOTA | Landscape | Gagan | Approvals |  |  | Gagan | Lajja | Anisha |  |  |  |  | 0
| DonaPaula | DP |  |  | Package Release | 6.211 | 4 | [7 empty] | 0 | 0
| DonaPaula | DP | Architecture |  | LOD 350 -MP, ISS, CH, Tower Habitable levels | 5.1246 | 4 |  | To be shared - Om Prakash | [5 empty] | 0 | 0
| DonaPaula | DP | Architecture | Naveen Y | LoD 200 - Schematic Concept .v7 [Rework] | 3.3117 | 1 | Naveen Y | Naveen Y | Aswin J |  |  |  |  | 0
| DonaPaula | DP | Architecture | Naveen Y | Approvals | 1.6558 | 1 | Naveen Y | Naveen KL | Aswin J |  |  |  |  | 0
| DonaPaula | DP | Architecture | Om Prakash | LoD 200 - Schematic Concept - CH | 0.10475 | 1 | Om Prakash | [6 empty] | 0
| DonaPaula | DP | Architecture | Om Prakash | Approvals - CH | 0.052375 | 1 | Om Prakash | [6 empty] | 0
| DonaPaula | DP | Structural |  | LOD 350 -MP, ISS, CH, Tower Habitable levels | 1.0864 | 0 | [7 empty] | 0 | 0
| DonaPaula | DP | Structural | Prakash C | LoD 200 - Schematic Concept .v7 [Rework] | 1.0864 |  | Prakash C | Lincy | Subrahmanya | - | Darshan |  | 0 | 0
| DonaPaula | DP | MEP |  | LOD 350 -MP, ISS, CH, Tower Habitable levels | 0 | 0 | [7 empty] | 0 | 0
| DonaPaula | DP | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | [6 empty] | 0
| DonaPaula | DP | MEP | Gagan | Approvals |  |  | Gagan | [6 empty] | 0
| DonaPaula | DP | Landscape |  | LOD 350 -MP, ISS, CH, Tower Habitable levels | 0 | 0 | [7 empty] | 0 | 0
| DonaPaula | DP | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | [6 empty] | 0
| DonaPaula | DP | Landscape | Gagan | Approvals |  |  | Gagan | [6 empty] | 0
| Varthur 52a | Varthur 52a |  |  | Package Release | 18.4 | 1 | [7 empty] | 0 | 0
| Varthur 52a | Varthur 52a | Architecture |  | LOD 300, LOD 350 Exp home | 18.4 | 1 | [7 empty] | 0 | 0
| Varthur 52a | Varthur 52a | Architecture | Saji A | LoD 100 - Contract + Design Brief | 18.4 | 1 | Saji A | Ayesha | [5 empty] | 0
| Vaderahalli | Vdrhl |  |  | Package Release | 26.6887 | 3 | [7 empty] | 0 | 0
| Vaderahalli | Vdrhl-Res | Architecture |  | LoD 200 - Schematic Concept | 12.6421 | 1 | [7 empty] | 0 | 0
| Vaderahalli | Vdrhl-Res | Architecture | Cijey M | LoD 100 - Contract + Design Brief | 6.321 | 1 | Cijey M | Dinakar Venugopal | Akarsh Vagman | Syed Musharaff |  |  |  | 0
| Vaderahalli | Vdrhl-Res | Architecture | Cijey M | LoD 200 - Schematic Concept | 6.321 |  | Cijey M | Dinakar Venugopal | Akarsh Vagman | Syed Musharaff |  |  |  | 0
| Vaderahalli | Vdrhl-Plotted Dev | Master Planning |  | LoD 200 - Schematic Concept | 12.6421 | 1 | [7 empty] | 0 | 0
| Vaderahalli | Vdrhl-Plotted Dev | Master Planning | Gagan | LoD 100 - Contract + Design Brief | 6.321 | 1 | Gagan | Utpal | Amaresh |  |  |  |  | 0
| Vaderahalli | Vdrhl-Plotted Dev | Master Planning | Gagan | LoD 200 - Schematic Concept | 6.321 |  | Gagan | Utpal | Amaresh |  |  |  |  | 0
| Vaderahalli | Vdrhl-Cmrcl | Architecture |  | LoD 200 - Schematic Concept | 1.4045 | 1 | [7 empty] | 0 | 0
| Vaderahalli | Vdrhl-Cmrcl | Architecture | Naveen Y | LoD 100 - Contract + Design Brief | 1.4045 | 1 | Naveen Y | [6 empty] | 0
| Vaderahalli | Vdrhl-Cmrcl | Architecture | Naveen Y | LoD 200 - Schematic Concept |  |  | Naveen Y | [6 empty] | 0
| Vaderahalli | Vdrhl | Structural |  | LoD 200 - Schematic Concept | 0 | 0 | [7 empty] | 0 | 0
| Vaderahalli | Vdrhl | Structural | Prakash C | LoD 200 - Schematic Concept |  |  | Prakash C | Satish | Alwin | Raghav | Darshan |  | 0 | 0
| Vaderahalli | Vdrhl | MEP |  | LoD 200 - Schematic Concept | 0 | 0 |  | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0 | 0
| Vaderahalli | Vdrhl | MEP | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | [6 empty] | 0
| Vaderahalli | Vdrhl | Landscape |  | LoD 200 - Schematic Concept | 0 | 0 |  | Batches to be removed - Can be taken up once the architectural details are received. | [5 empty] | 0 | 0
| Vaderahalli | Vdrhl | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | Gagan | [6 empty] | 0
Note on G70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on H70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on V70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on W70: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed

## Revised Plan PIVOT (hidden)
Row Labels | Count of Plan - Pkgs | Sum of Plan - Billing [Cr.]
Atul P | 26
Cijey M | 37 | 40.648
Gagan | 62 | 24.0471
Manik G | 8 | 0.59475
Naveen Y | 23 | 28.0797
Om Prakash | 38 | 11.5713
Prakash C | 113 | 20.0091
Saji A | 46 | 30.5406
Grand Total | 353 | 155.4906

## Goals, Actuals 2026 Q1 (hidden)
[7 empty] | Plan 26Q1 |  |  | Actual 26Q1 |  |  |  | AR | STR | MEP | LDS
| 2026 ¦ Design Goals + Billing | [5 empty] | Billing [Cr.] | Pkgs |  | Billing [Cr.] | Pkgs |  | 419 | 189 | 115 | 73 | 42
| Project | Phase | Discipline | Design Lead | Description |  | 115.6358 | 422 |  | 9.4373 | 40 |  | 18 | 4 | 7 | 4 | 3
| Ongoing Projects | [5 empty] | 38.4892 | 272 |  | 6.8335 | 32
| AtR | Ph 1, 2a, 2b, 2c |  |  | Package Release [Complete LoD 350 by Q1] |  | 0.43272 | 8 |  | 0 | 0
| AtR | Ph 1, 2a, 2b, 2c | Architecture |  | Package Release [Complete LoD 350 by Q1] |  | 0.39703 | 4 |  | 0 | 0
| AtR | Ph 1, 2a, 2b | Architecture | Saji A | Clubhouse + Amenities - Clubhouse—Interiors and Facilities |  | 0.27 | 1 |  | 0
| AtR | Ph 1, 2a, 2b | Architecture | Saji A | Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] |  | 0.045377 | 1 |  | 0
| AtR | Ph 2c | Architecture | Saji A | Master Plan - Site MEP |  | 0.042238 | 1 |  | 0
| AtR | Ph 2c | Architecture | Saji A | Clubhouse + Amenities - Sporting Facilities |  | 0.039416 | 1 |  | 0
| AtR | Ph 1, 2a, 2b, 2c | Structural |  | Package Release [Complete LoD 350 by Q1] |  | 0.021351 | 3 |  | 0 | 0
| AtR | Ph 1, 2a, 2b | Structural | Prakash C | Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] |  | 0.0052867 | 1 |  | 0
| AtR | Ph 2c | Structural | Prakash C | Master Plan - Site MEP |  | 0.010861 | 1 |  | 0
| AtR | Ph 2c | Structural | Prakash C | Clubhouse + Amenities - Sporting Facilities |  | 0.0052029 | 1 |  | 0
| AtR | Ph 1, 2a, 2b, 2c | MEP |  | Package Release [Complete LoD 350 by Q1] |  | 0.014337 | 1 |  | 0 | 0
| AtR | Ph 2c | MEP | Gagan | Master Plan - Site MEP |  | 0.014337 | 1 |  | 0
| AtR | Ph 3 |  |  | Package Release [Complete LoD 350 by Q1] |  | 2.5305 | 42 |  | 0.89157 | 12
| AtR | Ph 3 | Architecture |  | Package Release [Complete LoD 350 by Q1] | 0 | 1.8088 | 15 | 0 | 0.68496 | 3 | 0
| AtR | Ph 3 | Architecture | Saji A | Contract + Design brief |  | 0.27398 | 1 |  | 0.27398 | 1
| AtR | Ph 3 | Architecture | Saji A | Schematic Concept |  | 0.27398 | 1 |  | 0.27398 | 1
| AtR | Ph 3 | Architecture | Saji A | Approvals |  | 0.13699 | 1 |  | 0.13699 | 1
| AtR | Ph 3 | Architecture | Saji A | Pre Construction Set |  | 0.27398 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Home Products - V45 Default and it's variants |  | 0.36 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 33 - Foundations and Sub-Grade Structure |  | 0.043983 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 34 - Foundations and Sub-Grade Structure |  | 0.043983 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 29 - Foundations and Sub-Grade Structure |  | 0.065974 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 29 - Building Envelope + Plot Development |  | 0.065974 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 30 - Foundations and Sub-Grade Structure |  | 0.065974 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 30 - Building Envelope + Plot Development |  | 0.065974 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 31 - Building Envelope + Plot Development |  | 0.014661 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 32 - Building Envelope + Plot Development |  | 0.029322 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Villa Block 34 - Building Envelope + Plot Development |  | 0.043983 | 1 |  | 0
| AtR | Ph 3 | Architecture | Saji A | Master Plan - Master Plan |  | 0.05 | 1 |  | 0
| AtR | Ph 3 | Structural |  | Package Release [Complete LoD 350 by Q1] |  | 0.35597 | 15 |  | 0.10442 | 3
| AtR | Ph 3 | Structural | Prakash C | Schematic Concept |  | 0.093422 | 1 |  | 0.093422 | 1
| AtR | Ph 3 | Structural | Prakash C | Pre Construction Set |  | 0.093422 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Foundations and Sub-Grade Structure |  | 0.021107 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Super Structure |  | 0.03166 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Building Envelope + Plot Development |  | 0.0052767 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Foundations and Sub-Grade Structure |  | 0.021107 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Super Structure |  | 0.03166 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Building Envelope + Plot Development |  | 0.0052767 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Foundations and Sub-Grade Structure |  | 0.004 | 1 |  | 0.004 | 1
| AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Super Structure |  | 0.007 | 1 |  | 0.007 | 1
| AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Building Envelope + Plot Development |  | 0.001 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 32 - Building Envelope + Plot Development |  | 0.0023452 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Foundations and Sub-Grade Structure |  | 0.014071 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Super Structure |  | 0.021107 | 1 |  | 0
| AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Building Envelope + Plot Development |  | 0.0035178 | 1 |  | 0
| AtR | Ph 3 | MEP |  | Package Release [Complete LoD 350 by Q1] |  | 0.1936 | 7 |  | 0.024327 | 3
| AtR | Ph 3 | MEP | Gagan | Schematic Concept [V80] |  | 0.0215 | 1 |  | 0.0215 | 1
| AtR | Ph 3 | MEP | Gagan | PreConstruction Set |  | 0.0215 | 1 |  | 0
| AtR | Ph 3 | MEP | Gagan | Villa Block 31 - Foundations and Sub-Grade Structure |  | 0.00094245 | 1 |  | 0.00094245 | 1
| AtR | Ph 3 | MEP | Gagan | Villa Block 32 - Foundations and Sub-Grade Structure |  | 0.0018849 | 1 |  | 0.0018849 | 1
| AtR | Ph 3 | MEP | Gagan | Villa Block 34 - Foundations and Sub-Grade Structure |  | 0.0028274 | 1 |  | 0
| AtR | Ph 3 | MEP | Gagan | Home Products - V45 Default and it's variants |  | 0.10495 | 1 |  | 0
| AtR | Ph 3 | MEP | Gagan | Master Plan - Master Plan |  | 0.04 | 1 |  | 0
| AtR | Ph 3 | Landscape |  | Package Release [Complete LoD 350 by Q1] |  | 0.17213 | 5 |  | 0.077864 | 3
| AtR | Ph 3 | Landscape | Gagan | Schematic Concept |  | 0.047864 | 1 |  | 0.047864 | 1
| AtR | Ph 3 | Landscape | Gagan | Preconstruction Set |  | 0.047864 | 1 |  | 0
| AtR | Ph 3 | Landscape | Gagan | Home Products - V45 Default |  | 0.046405 | 1 |  | 0
| AtR | Ph 3 | Landscape | Gagan | Master Plan |  | 0.02 | 1 |  | 0.02 | 1
| AtR | Ph 3 | Landscape | Gagan | Site Development - 06 Landscape |  | 0.01 | 1 |  | 0.01 | 1
| AtR - C | Com |  |  | Package Release [Complete LoD 350 by Q1] |  | 0.94562 | 9 |  | 0.12911 | 1
| AtR - C | Com | Architecture |  | Package Release [Complete LoD 350 by Q1] |  | 0.36421 | 3 |  | 0 | 0
| AtR - C | Com | Architecture | Naveen Y | Master Plan - Site Development |  | 0.13658 | 1 |  | 0
| AtR - C | Com | Architecture | Naveen Y | Master Plan - Site MEP |  | 0.18211 | 1 |  | 0
| AtR - C | Com | Architecture | Naveen Y | Master Plan - Landscaping |  | 0.045527 | 1 |  | 0
| AtR - C | Com | Structural |  | Package Release [Complete LoD 350 by Q1] |  | 0.4139 | 4 |  | 0.12911 | 1
| AtR - C | Com | Structural | Prakash C | Tower-[Commercial] - Habitable Level 1-2 |  | 0.12911 | 1 |  | 0.12911 | 1
| AtR - C | Com | Structural | Prakash C | Tower-[Commercial] - Habitable Level 3-5 |  | 0.25823 | 1 |  | 0
| AtR - C | Com | Structural | Prakash C | Master Plan - Site Development |  | 0.014486 | 1 |  | 0
| AtR - C | Com | Structural | Prakash C | Master Plan - Site MEP |  | 0.012072 | 1 |  | 0
| AtR - C | Com | MEP |  | Package Release [Complete LoD 350 by Q1] |  | 0.16751 | 2 |  | 0 | 0
| AtR - C | Com | MEP | Gagan | Master Plan - Master Plan |  | 0.038655 | 1 |  | 0
| AtR - C | Com | MEP | Gagan | Master Plan - Site MEP |  | 0.12885 | 1 |  | 0
| TMD Ph2 | Ph 2 |  |  | Childern play area [Complete by Q2] |  | - | 0 |  | - | 0
| TMD Ph2 | Ph 2 |  |  | Childern play area |  | - |  |  | -
| PoaRR-Res | Res |  |  | Package Release [Complete the project by Q1] |  | 3.767 | 15 |  | 0 | 0
| PoaRR-Res | Res | Architecture |  | Complete the project |  | 3.3659 | 8 |  | 0 | 0
| PoaRR-Res | Res | Architecture | Saji A | Villa Cluster 3 - All Levels |  | 0.17 | 1 |  | 0
| PoaRR-Res | Res | Architecture | Saji A | Villa Cluster 3 - Building Envelope and Common Areas |  | 0.17 | 1 |  | 0
| PoaRR-Res | Res | Architecture | Saji A | V40 Default and it's variants |  | 1.18 | 1 |  | 0
| PoaRR-Res | Res | Architecture | Saji A | ISS Building Envelope and Common Areas |  | 1.0659 | 1 |  | 0
| PoaRR-Res | Res | Architecture | Saji A | Residential - Site Development |  | 0.45 | 1 |  | 0
| PoaRR-Res | Res | Architecture | Saji A | Masterplan - Site MEP |  | 0.15 | 1 |  | 0
| PoaRR-Res | Res | Architecture | Saji A | Masterplan - Landscaping |  | 0.15 | 1 |  | 0
| PoaRR-Res | Res | Architecture | Saji A | Amenities & Facilities - Sporting Facilities |  | 0.03 | 1 |  | 0
| PoaRR-Res | Res | Structural |  | Complete the project |  | 0.36 | 3 |  | 0 | 0
| PoaRR-Res | Res | Structural | Prakash C | Site Development |  | 0.19 | 1 |  | 0
| PoaRR-Res | Res | Structural | Prakash C | Site MEP |  | 0.16 | 1 |  | 0
| PoaRR-Res | Res | Structural | Prakash C | Sporting Facilities |  | 0.01 | 1 |  | 0
| PoaRR-Res | Res | MEP |  | Complete the project |  | 0.0010915 | 3 |  | 0 | 0
| PoaRR-Res | Res | MEP | Gagan | Site MEP |  | 0.36 | 1 |  | 0
| PoaRR-Res | Res | MEP | Gagan | Clubhouse Outdoor Spaces and Pool |  | 0.002183 | 1 |  | 0
| PoaRR-Res | Res | MEP | Gagan | Sporting Facilities |  | 0.0010915 | 1 |  | 0
| PoaRR-Res | Res | Landscape |  | Complete the project |  | 0.04 | 1 |  | 0 | 0
| PoaRR-Res | Res | Landscape | Gagan | Amenities & Facilities - Community spaces [Sporting Facilities] |  | 0.04 | 1 |  | 0
| PoaRR-T08 | T08 |  |  | Package Release [Complete the project by Q1] |  | 8.9238 | 28 |  | 0 | 0
| PoaRR-T08 | T08 | Architecture |  | Package Release [Complete the project except Penthouse Defaults] |  | 7.0838 | 18 |  | 0 | 0
| PoaRR-T08 | T08 | Architecture | Saji A | ISS - Foundations & Grade Slab |  | 0.2 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | ISS - Parking Level Subgrade |  | 0.41 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | ISS - Podium Slab |  | 0.61 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | ISS - Building Envelope and Common Areas |  | 0.82 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Habitable Level 01 |  | 0.48 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Building Envelope and Common Areas [Typical Tower Levels] |  | 0.96385 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | L22 Default |  | 0.52 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | L20 Default [Modification for Dry Wall] |  | 0.52 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | D35 Default [Modification for Dry Wall] |  | 0.52 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Master Plan |  | 0.17 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Penthouse Levels |  | 0.48 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Terrace Level |  | 0.24 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] |  | 0.96 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Landscape |  | 0.03 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Site MEP |  | 0.03 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Clubhouse—Outdoor Spaces and Pool |  | 0.015 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Community spaces [Board Walk, Children play area] |  | 0.015 | 1 |  | 0
| PoaRR-T08 | T08 | Architecture | Saji A | Site Development |  | 0.1 | 1 |  | 0
| PoaRR-T08 | T08 | Structural |  | Complete the project |  | 1.7 | 7 |  | 0 | 0
| PoaRR-T08 | T08 | Structural | Prakash C | Penthouse Levels |  | 0.2 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | Terrace Level |  | 0.4 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Foundations & Grade Slab |  | 0.32 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Podium Slab |  | 0.32 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Parking Level Subgrade |  | 0.43 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | Site Development |  | 0.02 | 1 |  | 0
| PoaRR-T08 | T08 | Structural | Prakash C | Site MEP |  | 0.01 | 1 |  | 0
| PoaRR-T08 | T08 | MEP |  | Package Release [Complete the project] |  | 0.14 | 3 |  | 0 | 0
| PoaRR-T08 | T08 | MEP | Gagan | ISS - Foundation and Gradeslab |  | 0.02 | 1 |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | L20 Default and it's variants |  | 0.06 | 1 |  | 0
| PoaRR-T08 | T08 | MEP | Gagan | D35 Default and it's variants |  | 0.06 | 1 |  | 0
| PoaRR-T08 | T08 | Landscape |  | Package Release [Complete the project]
| ITQE-Ph1 | Ph 1 |  |  | Package Release [Complete the project by Q1] |  | 0.084072 | 3 |  | 0 | 0
| ITQE-Ph1 | Ph 1 | Architecture |  | Complete the project |  | 0 | 0 |  | 0 | 0
| ITQE-Ph1 | Ph 1 | Structural |  | Complete the project |  | 0.084072 | 3 |  | 0 | 0
| ITQE-Ph1 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site Development |  | 0.060249 | 1 |  | 0
| ITQE-Ph1 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Clubhouse—Outdoor Spaces and Pool |  | 0.011912 | 1 |  | 0
| ITQE-Ph1 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Community spaces |  | 0.011912 | 1 |  | 0
| ITQE-Ph1 | Ph 1 | MEP |  | Complete the project
| ITQE-Ph1 | Ph 1 | Landscape |  | Complete the project
| ITQE-Ph2a | Ph 2a |  |  | Package Release [Complete the project by Q1] |  | 0.41919 | 5 |  | 0 | 0
| ITQE-Ph2a | Ph 2a | Architecture |  | Complete the project |  | 0.25 | 2 |  | 0 | 0
| ITQE-Ph2a | Ph 2a | Architecture | Cijey M | Master Plan ¦ Site Development |  | 0.07 | 1 |  | 0
| ITQE-Ph2a | Ph 2a | Architecture | Cijey M | Experience Home + Project Experience [ V35 ] |  | 0.18 | 1 |  | 0
| ITQE-Ph2a | Ph 2a | Structural |  | Complete the project |  | 0.16919 | 3 |  | 0 | 0
| ITQE-Ph2a | Ph 2a | Structural | Prakash C | Experience Home + Project Experience [ V35 ] |  | 0.07 | 1 |  | 0
| ITQE-Ph2a | Ph 2a | Structural | Prakash C | Master Plan ¦ Site Development |  | 0.054104 | 1 |  | 0
| ITQE-Ph2a | Ph 2a | Structural | Prakash C | Master Plan ¦ Site MEP |  | 0.045086 | 1 |  | 0
0 | ITQE-Ph2a | Ph 2a | MEP |  | Complete the project |  |  | 0 |  |  | 0
| ITQE-Ph2a | Ph 2a | Landscape |  | Complete the project |  |  | 0 |  |  | 0
| ITQE-Ph2b | Ph 2b |  |  | Package Release [ Complete the project by Q3] |  | 3.527 | 17 |  | 2.517 | 7
| ITQE-Ph2b | Ph 2b | Architecture |  | Complete the project |  | 2.3754 | 4 |  | 2.3454 | 3
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | ISS 5&6 ¦ Structural Slab 01 [Basement] |  | 0.3 | 1 |  | 0.3 | 1
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | ISS 7 ¦ Structrural Slab 01 [Basement] |  | 0.3 | 1 |  | 0.3 | 1
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | Master Plan ¦ Master Plan |  | 0.03 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Architecture | Cijey M | L25 Default and it's variants |  | 1.7454 | 1 |  | 1.7454 | 1
| ITQE-Ph2b | Ph 2b | Structural |  | Complete the project |  | 1.12 | 11 |  | 0.14 | 2
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 05 ¦ Habitable Level - Even |  | 0.07 | 1 |  | 0.07 | 1
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 05 ¦ Habitable Level - Odd |  | 0.07 | 1 |  | 0.07 | 1
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 06 ¦ Habitable Level - Even |  | 0.07 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 06 ¦ Habitable Level - Odd |  | 0.07 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 07 ¦ Habitable Level - Even |  | 0.07 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 07 ¦ Habitable Level - Odd |  | 0.07 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS5&6 ¦ Structrural Slab 01 [Basement] |  | 0.13 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Foundations & Sub¦Grade |  | 0.18 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Structrural Slab 01 [Basement] |  | 0.13 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS5&6 ¦ Podium Slab |  | 0.13 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Podium Slab |  | 0.13 | 1 |  | 0
| ITQE-Ph2b | Ph 2b | MEP |  | Complete the project |  | 0.031656 | 2 |  | 0.031656 | 2
| ITQE-Ph2b | Ph 2b | MEP | Gagan | ISS -5 & 6 ¦ Structrural Slab 01 [Basement] |  | 0.015828 | 1 |  | 0.015828 | 1
| ITQE-Ph2b | Ph 2b | MEP | Gagan | ISS -7 ¦ Structrural Slab 01 [Basement] |  | 0.015828 | 1 |  | 0.015828 | 1
| ITQE-Ph2b | Ph 2b | Landscape |  | Complete the project |  |  | 0 |  |  | 0
| ItQE-Ph2c [T9] | Ph 2c |  |  | Package Release [LoD 350-ISS, Habitable Level 11-20] |  | 0.63298 | 9 |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture |  | LoD 350 - ISS, Habitable Level 11-20 |  | 0.30106 | 3 |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | ISS 9 ¦ Foundations & Grade Slab |  | 0.092092 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | Tower 9 ¦ Foundation and Grade Slab |  | 0.1306 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | Tower 9 ¦ Parking Level-Sub grade |  | 0.078362 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural |  | LoD 350 - ISS, Habitable Level 11-20 |  | 0.2848 | 4 |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | ISS 9 ¦ Earthwork |  | 0.0097618 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | ISS 9 ¦ Foundations & Grade Slab |  | 0.039047 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | Tower 9 ¦ Foundation and Grade Slab |  | 0.118 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | Tower 9 ¦ Parking Level-Sub grade |  | 0.118 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP |  | LoD 350 - ISS, Habitable Level 11-20 |  | 0.047123 | 2 |  | 0 | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP | Gagan | ISS 9 ¦ Foundations & Grade Slab |  | 0.0163 | 1 |  | 0
| ItQE-Ph2c [T9] | Ph 2c | MEP | Gagan | Tower 9 ¦ Foundation and Grade Slab |  | 0.030822 | 1 |  | 0
| OTR-Ph01 | Ph 1 |  |  | Package Release [Complete the project by Q1] |  | 1.38 | 11 |  | 0.51 | 1
| OTR-Ph01 | Ph 1 | Architecture |  | Complete the project |  | 0.96 | 5 |  | 0.51 | 1
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | Individual Homes ¦ V25 Default & its Variant |  | 0.51 | 1 |  | 0.51 | 1
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | Villa Block ¦ Building Envelope + Plot Development |  | 0.3 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Master Plan |  | 0.09 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Site Development |  | 0.03 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Site MEP |  | 0.03 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Structural |  | Complete the project |  | 0.38 | 5 |  | 0 | 0
| OTR-Ph01 | Ph 1 | Structural | Prakash C | Experience Home + Project Experience |  | 0.08 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Structural | Prakash C | Villa Block ¦ Super Structure |  | 0.17 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site Development |  | 0.03 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site MEP |  | 0.03 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Community spaces [Board Walk, Children play area] |  | 0.07 | 1 |  | 0
| OTR-Ph01 | Ph 1 | MEP |  | Complete the project |  | 0.04 | 1 |  | 0 | 0
| OTR-Ph01 | Ph 1 | MEP | Gagan | Master Plan ¦ Site MEP |  | 0.04 | 1 |  | 0
| OTR-Ph01 | Ph 1 | Landscape |  | Complete the project |  |  | 0 |  |  | 0
| TuiG | TuiG |  |  | Package Release [Complete LoD 350 by Q2] |  | 1.6448 | 13 |  | 0.51595 | 7
| TuiG | TuiG | Master Planning |  | Package Release [Complete the project]
| TuiG | TuiG | Architecture |  | Package Release [Complete the project] |  | 0.30955 | 2 |  | 0 | 0
| TuiG | TuiG | Architecture | Om Prakash | Clubhouse—Outdoor Spaces and Pool |  | 0.15478 | 1 |  | 0
| TuiG | TuiG | Architecture | Om Prakash | Community spaces [Board Walk, Children play area] |  | 0.15478 | 1 |  | 0
| TuiG | TuiG | Structural |  | Package Release [Complete the project] |  | 0.83172 | 4 |  | 0.061982 | 1
| TuiG | TuiG | Structural | Prakash C | Site Development |  | 0.40295 | 1 |  | 0
| TuiG | TuiG | Structural | Prakash C | Site MEP |  | 0.33579 | 1 |  | 0
| TuiG | TuiG | Structural | Prakash C | Clubhouse—Outdoor Spaces and Pool |  | 0.030991 | 1 |  | 0
| TuiG | TuiG | Structural | Prakash C | Sporting Facilities |  | 0.061982 | 1 |  | 0.061982 | 1
| TuiG | TuiG | MEP |  | Package Release [Complete the project] |  | 0.31744 | 4 |  | 0.26787 | 3
| TuiG | TuiG | MEP | Gagan | Clubhouse—Structure and Envelope |  | 0.17351 | 1 |  | 0.17351 | 1
| TuiG | TuiG | MEP | Gagan | Clubhouse—Interior & Facilities |  | 0.074361 | 1 |  | 0.074361 | 1
| TuiG | TuiG | MEP | Gagan | Clubhouse—Outdoor Spaces and Pool |  | 0.049574 | 1 |  | 0
| TuiG | TuiG | MEP | Gagan | Sporting Facilities |  | 0.02 | 1 |  | 0.02 | 1
| TuiG | TuiG | Landscape |  | Package Release [Complete the project] |  | 0.1861 | 3 |  | 0.1861 | 3
| TuiG | TuiG | Landscape | Gagan | LoD 350 - Clubhouse—Interiors and Facilities | 0.097354 | 0.032451 | 1 |  | 0.032451 | 1
| TuiG | TuiG | Landscape | Gagan | LoD 350 - Clubhouse— Outdoor Spaces |  | 0.081128 | 1 |  | 0.081128 | 1
| TuiG | TuiG | Landscape | Gagan | Community spaces [Board Walk, Children play area] |  | 0.072519 | 1 |  | 0.072519 | 1
| TMFT-Ph 2 | Ph 2 |  |  | Package Release [Complete LoD 350 by Q4 2025] |  | 0.03 | 1 |  | 0 | 0
| TMFT-Ph 2 | Ph 2 | Structural |  | Complete the project |  | 0.03 | 1 |  | 0 | 0
| TMFT-Ph 2 | Ph 2 | Structural | Prakash C | LoD 350 - Site Development |  | 0.03 | 1 |  | 0
| DBTW | DBTW |  |  | Package Release [Complete LoD 350 by Q4 2025] |  | 9.659 | 27 |  | 2.2512 | 1
| DBTW | DBTW | Architecture |  | Complete the project |  | 5.878 | 10 |  | 0 | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site Development |  | 0.22115 | 1 |  | 0
` | DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site MEP |  | 0.073717 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Landscaping |  | 0.073717 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Tower 06 - Foundation and Grade Slab |  | 0.064032 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Foundations & Grade Slab |  | 0.54995 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Podium Slab |  | 0.27497 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I20 Default and it's variants |  | 2.2352 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I25 Default and it's variants |  | 2.2352 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Structure and Envelope |  | 0.1125 | 1 |  | 0
| DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Outdoor Spaces and Pool |  | 0.0375 | 1 |  | 0
| DBTW | DBTW | Structural |  | Complete the project |  | 3.7441 | 16 |  | 2.2512 | 1
| DBTW | DBTW | Structural | Prakash C | LoD 300 - Pre Construction Set [Podium] |  | 2.2512 | 1 |  | 2.2512 | 1
| DBTW | DBTW | Structural | Prakash C | LoD 350 - ISS - Foundations & Grade Slab |  | 0.52958 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-1-Habitable Level - Even |  | 0.025613 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level 01 |  | 0.10834 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level - Even |  | 0.05417 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level 01 |  | 0.10834 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level - Even |  | 0.05417 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level 01 |  | 0.10834 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level - Even |  | 0.05417 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 05-Foundation and Grade Slab |  | 0.10834 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level 01 |  | 0.10834 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level - Even |  | 0.05417 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Foundation and Grade Slab |  | 0.051226 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Parking Level-Sub grade |  | 0.051226 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level 01 |  | 0.051226 | 1 |  | 0
| DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level - Even |  | 0.025613 | 1 |  | 0
| DBTW | DBTW | MEP |  | Complete the project |  | 0.036853 | 1 |  | 0 | 0
| DBTW | DBTW | MEP | Gagan | LoD 350 - Master Plan- Master Plan |  | 0.036853 | 1 |  | 0
| SftW | SftW |  |  | Package Release [Complete the project by Q2] |  | 1.2186 | 17 |  | 0 | 0
| SftW | SftW | Architecture |  | Complete the project |  | 0.85178 | 9 |  | 0 | 0
| SftW | SftW | Architecture | Om Prakash | ISS 01 - Podium Slab |  | 0.25575 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Clubhouse—Structure and Envelope |  | 0.081564 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Master Plan - Master Plan |  | 0.18697 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Clubhouse—Outdoor Spaces and Pool |  | 0.027188 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Master Plan - Site Development |  | 0.11218 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Master Plan - Site MEP |  | 0.037394 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Master Plan - Landscaping |  | 0.037394 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Clubhouse + Amenities - Sporting Facilities |  | 0.027188 | 1 |  | 0
| SftW | SftW | Architecture | Om Prakash | Tower 02 - Terrace Level |  | 0.086149 | 1 |  | 0
| SftW | SftW | Structural |  | Complete the project |  | 0.34546 | 6 |  | 0 | 0
| SftW | SftW | Structural | Prakash C | Tower 2 - Terrace Level |  | 0.20116 | 1 |  | 0
| SftW | SftW | Structural | Prakash C | Master Plan - Site Development |  | 0.058457 | 1 |  | 0
| SftW | SftW | Structural | Prakash C | Master Plan - Site MEP |  | 0.048714 | 1 |  | 0
| SftW | SftW | Structural | Prakash C | Clubhouse—Structure and Envelope |  | 0.025989 | 1 |  | 0
| SftW | SftW | Structural | Prakash C | Clubhouse—Outdoor Spaces and Pool |  | 0.0037128 | 1 |  | 0
| SftW | SftW | Structural | Prakash C | Clubhouse—Sporting Facilities |  | 0.0074255 | 1 |  | 0
| SftW | SftW | MEP |  | Complete the project |  | 0.021398 | 2 |  | 0 | 0
| SftW | SftW | MEP | Gagan | MEP ¦ Master Plan - Site MEP |  | 0.020843 | 1 |  | 0
| SftW | SftW | MEP | Gagan | MEP ¦ Clubhouse—Sporting Facilities |  | 0.00055534 | 1 |  | 0
| SftW | SftW | Landscape |  | Complete the project
| LGCE Campus | LGCE Campus |  |  | Package Release [Complete the project by Q4] |  | 0.38042 | 2 |  | 0 | 0
| LGCE Campus | LGCE Campus | Architecture |  | Complete the project |  | 0.38042 | 2 |  | 0 | 0
| LGCE Campus | LGCE Campus | Architecture | Om Prakash | Design Brief |  | 0.15217 | 1 |  | 0
| LGCE Campus | LGCE Campus | Architecture | Om Prakash | LoD 200 - Schematic Concept |  | 0.22825 | 1 |  | 0
| LGCE Campus | LGCE Campus | Structural |  | Complete the project
| LGCE Campus | LGCE Campus | MEP |  | Complete the project
| LGCE Campus | LGCE Campus | Landscape |  | Complete the project
| Ooty Res | Ooty Res |  |  | Package Release [Complete the project by Q4] |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Architecture |  | Complete the project |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Architecture | Manik G | Design Brief |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Architecture | Manik G | LoD 200 - Schematic Concept |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Architecture | Manik G | Approvals |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Structural |  | Complete the project |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Structural | Prakash C | LoD 200 - Schematic Concept |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | MEP |  | Complete the project |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | MEP | Gagan | LoD 200 - Schematic Concept |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | MEP | Gagan | Approvals |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Landscape |  | Complete the project |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Landscape | Gagan | LoD 200 - Schematic Concept |  | 0 | 0 |  | 0 | 0
| Ooty Res | Ooty Res | Landscape | Gagan | Approvals |  | 0 | 0 |  | 0 | 0
| MT Plano | MT Plano |  |  | Package Release [Complete the project by Q3] |  | 0.69535 | 8 |  | 0 | 0
| MT Plano | MT Plano | Architecture |  | Complete the project |  | 0.5469 | 3 |  | 0 | 0
| MT Plano | MT Plano | Architecture | Manik G | Design Brief |  | 0.15626 | 1 |  | 0
| MT Plano | MT Plano | Architecture | Manik G | LoD 200 - Schematic Concept |  | 0.23439 | 1 |  | 0
| MT Plano | MT Plano | Architecture | Manik G | Approvals |  | 0.15626 | 1 |  | 0
| MT Plano | MT Plano | Structural |  | Complete the project |  | 0.071432 | 1 |  | 0 | 0
| MT Plano | MT Plano | Structural | Manik G | LoD 200 - Schematic Concept |  | 0.071432 | 1 |  | 0
| MT Plano | MT Plano | MEP |  | Complete the project |  | 0.040181 | 2 |  | 0 | 0
| MT Plano | MT Plano | MEP | Manik G | LoD 200 - Schematic Concept |  | 0.02009 | 1 |  | 0
| MT Plano | MT Plano | MEP | Manik G | Approvals |  | 0.02009 | 1 |  | 0
| MT Plano | MT Plano | Landscape |  | Complete the project |  | 0.036832 | 2 |  | 0 | 0
| MT Plano | MT Plano | Landscape | Manik G | LoD 200 - Schematic Concept |  | 0.016742 | 1 |  | 0
| MT Plano | MT Plano | Landscape | Manik G | Approvals |  | 0.02009 | 1 |  | 0
| MeenaSai Res | MS Res |  |  | Complete the project by Q3 |  | 0.141 | 6 |  | 0 | 0
| MeenaSai Res | MS Res | Architecture |  | Complete the project |  | 0.105 | 2 |  | 0 | 0
| MeenaSai Res | MS Res | Architecture | Cijey M | LoD 200 - Schematic Concept |  | 0.063 | 1 |  | 0
| MeenaSai Res | MS Res | Architecture | Cijey M | Approvals |  | 0.042 | 1 |  | 0
| MeenaSai Res | MS Res | Structural |  | Complete the project |  | 0.0192 | 1 |  | 0 | 0
| MeenaSai Res | MS Res | Structural | Prakash C | LoD 200 - Schematic Concept |  | 0.0192 | 1 |  | 0
| MeenaSai Res | MS Res | MEP |  | Complete the project |  | 0.0108 | 2 |  | 0 | 0
| MeenaSai Res | MS Res | MEP | Gagan | LoD 200 - Schematic Concept |  | 0.0054 | 1 |  | 0
| MeenaSai Res | MS Res | MEP | Gagan | Approvals |  | 0.0054 | 1 |  | 0
| MeenaSai Res | MS Res | Landscape |  | Complete the project |  | 0.006 | 1 |  | 0 | 0
| MeenaSai Res | MS Res | Landscape | Gagan | LoD 200 - Schematic Concept |  | 0.006 | 1 |  | 0
| NH Homestay | NH HS |  |  | Complete the project by Q1 [except LoD 350 - Interiors - Q2] |  | 1.233 | 15 |  | 0.01857 | 1
| NH Homestay | NH HS | Architecture |  | Complete the project |  | 0.77994 | 4 |  | 0 | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 300 - Pre Construction set |  | 0.12999 | 1 |  | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Foundation and Structure |  | 0.25998 | 1 |  | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Building Envelope + Plot Development |  | 0.19498 | 1 |  | 0
| NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Interiors |  | 0.19498 | 1 |  | 0
| NH Homestay | NH HS | Structural |  | Complete the project |  | 0.22284 | 3 |  | 0 | 0
| NH Homestay | NH HS | Structural | Prakash C | LoD 300 - Pre Construction set |  | 0.059424 | 1 |  | 0
| NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Foundation and Structure |  | 0.14856 | 1 |  | 0
| NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Building Envelope + Plot Development |  | 0.014856 | 1 |  | 0
| NH Homestay | NH HS | MEP |  | Complete the project |  | 0.14206 | 5 |  | 0 | 0
| NH Homestay | NH HS | MEP | Gagan | Approvals |  | 0.016713 | 1 |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 300 - Pre Construction set |  | 0.016713 | 1 |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Foundation and Structure |  | 0.058495 | 1 |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Building Envelope + Plot Development |  | 0.025069 | 1 |  | 0
| NH Homestay | NH HS | MEP | Gagan | LoD 350 - Interiors |  | 0.025069 | 1 |  | 0
| NH Homestay | NH HS | Landscape |  | Complete the project |  | 0.088207 | 3 |  | 0.01857 | 1
| NH Homestay | NH HS | Landscape | Gagan | LoD 200 - Schematic Concept |  | 0.01857 | 1 |  | 0.01857 | 1
| NH Homestay | NH HS | Landscape | Gagan | LoD 300 - Pre Construction set |  | 0.01857 | 1 |  | 0
| NH Homestay | NH HS | Landscape | Gagan | LoD 350 - Building Envelope + Plot Development |  | 0.051068 | 1 |  | 0
| Indiranagar Res | Indrng Res |  |  | Package Release [Complete LoD 350 by Q1] |  | 0.004113 | 6 |  | 0 | 0
| Indiranagar Res | Indrng Res | Architecture |  | Complete the project |  | 0.004 | 4 |  | 0 | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block A - Interiors |  | 0.0021 | 1 |  | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block B - Interiors |  | 0.000875 | 1 |  | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 - Block C - Interiors |  | 0.000525 | 1 |  | 0
| Indiranagar Res | Indrng Res | Architecture | Manik G | LoD 350 -Block C - Building Envelope + Plot Development |  | 0.0005 | 1 |  | 0
| Indiranagar Res | Indrng Res | Landscape |  | Complete the project |  | 0.000113 | 1 |  | 0 | 0
| Indiranagar Res | Indrng Res | Landscape | Gagan | LoD 350 - Block C- Building Envelope + Plot Development |  | 0.000113 | 1 |  | 0
| Indiranagar Res | Indrng Res | Structural |  | Complete the project |  | 0.0008 | 1 |  | 0 | 0
| Indiranagar Res | Indrng Res | Structural | Prakash C | LoD 350 -Block C - Building Envelope + Plot Development |  | 0.0008 | 1 |  | 0
| OTR Museum | OTR Mus |  |  | Package Release [Complete the project by Q2] |  | 0.43996 | 2 |  | 0 | 0
| OTR Museum | OTR Mus | Architecture |  | Complete the project |  | 0.43996 | 2 |  | 0 | 0
| OTR Museum | OTR Mus | Architecture | Cijey M | Design Brief |  | 0.17598 | 1 |  | 0
| OTR Museum | OTR Mus | Architecture | Cijey M | LoD 200 - Schematic Concept |  | 0.26398 | 1 |  | 0
| OTR Museum | OTR Mus | Structural |  | Complete the project
| OTR Museum | OTR Mus | MEP |  | Complete the project
| OTR Museum | OTR Mus | Landscape |  | Complete the project
| Fullkit Homes | FKH |  |  | Package Release |  | 0 | 27 |  | 0 | 2
| TuiG | FKH | Architecture | Atul P | LoD 350 - TuiG [V20, V30 and V40] |  |  | 9 |  |  | 2
| Harohalli | FKH | Architecture | Atul P | LoD 350 - Harohalli [V20, V30 and V50C] |  |  | 9
| Violet Hill | FKH | Architecture | Atul P | LoD 350 - Violet Hill [P-1 D, P-2 U] |  |  | 2
| Shreegaon | FKH | Architecture | Atul P | LoD 350 - Shreegaon [V50C] |  |  | 1
| OTF | FKH | Architecture | Atul P | LoD 350 - One Tiny Flower [V50H and V25] |  |  | 6
| Rework Pkgs | Rwrk |  |  |  |  | 0.4 | 1 |  | 0 | 0
| PoaRR-T08 | T08 | Structural | Prakash C | STR Package Release [Parking level subgrade] |  | 0.4 | 1 |  | 0
| New Projects | [5 empty] | 77.1466 | 150 |  | 2.6039 | 8
| OTR-Ph02 | Ph 2 |  |  | Package Release [Except Master plan and Amenities] |  | 1.6886 | 10 |  | 0 | 0
| OTR-Ph02 | Ph 2 | Architecture |  | Complete the Project |  | 1.35 | 5 |  | 0 | 0
| OTR-Ph02 | Ph 2 | Architecture | Cijey M | Contract + Design Brief |  | 0.54 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Cijey M | Schematic Concept |  | 0.43 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Cijey M | Approvals |  | 0.21 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Schematic Concept - CH |  | 0.11 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Approvals - CH |  | 0.06 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Structural |  | Complete the Project |  | 0.17172 | 1 |  | 0 | 0
| OTR-Ph02 | Ph 2 | Structural | Prakash C | Schematic Concept |  | 0.17172 | 1 |  | 0
| OTR-Ph02 | Ph 2 | MEP |  | Complete the Project |  | 0.09558 | 2 |  | 0 | 0
| OTR-Ph02 | Ph 2 | MEP | Gagan | Schematic Concept |  | 0.06372 | 1 |  | 0
| OTR-Ph02 | Ph 2 | MEP | Gagan | Approvals |  | 0.03186 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Landscape |  | Complete the Project |  | 0.07128 | 2 |  | 0 | 0
| OTR-Ph02 | Ph 2 | Landscape | Gagan | Schematic Concept |  | 0.05346 | 1 |  | 0
| OTR-Ph02 | Ph 2 | Landscape | Gagan | Approvals |  | 0.01782 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 |  |  | Package Release [Dsgn Brf, LOD 200, Approvals, LOD 300] |  | 0.77324 | 8 |  | 0 | 0
| TMFT-Ph 3 | Ph 3 | Architecture |  | [Dsgn Brf, LOD 200, Approvals, LOD 300, LOD 350] |  | 0.6182 | 3 |  | 0 | 0
| TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Contract + Design Brief |  | 0.24728 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Schematic Concept |  | 0.24728 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Approvals |  | 0.12364 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | Structural |  | [LOD 200, LOD 300, LOD350] |  | 0.078635 | 1 |  | 0 | 0
| TMFT-Ph 3 | Ph 3 | Structural | Prakash C | Schematic Concept |  | 0.078635 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | MEP |  | [LOD 200, Approvals, LOD 300, LOD 350] |  | 0.043769 | 2 |  | 0 | 0
| TMFT-Ph 3 | Ph 3 | MEP | Gagan | Schematic Concept |  | 0.029179 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | MEP | Gagan | Approvals |  | 0.01459 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | Landscape |  | [LOD 200, Approvals, LOD 300, LOD 350] |  | 0.032641 | 2 |  | 0 | 0
| TMFT-Ph 3 | Ph 3 | Landscape | Gagan | Schematic Concept |  | 0.024481 | 1 |  | 0
| TMFT-Ph 3 | Ph 3 | Landscape | Gagan | Approvals |  | 0.0081602 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a |  |  | Package Release [LoD 350-ISS, Habitable Level 2-10] |  | 14.2039 | 10 |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture |  | LoD 350 - ISS, Habitable Level 2-10 |  | 8.7814 | 3 |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Pre Construction Set |  | 4.3907 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Experience Home + Project Experience |  | 2.1953 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Marketing and Sales |  | 2.1953 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural |  | LoD 350 - ISS, Habitable Level 2-10 |  | 3.2579 | 2 |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | Schematic Concept |  | 1.3962 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | Pre Construction Set |  | 1.8617 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP |  | LoD 350 - ISS, Habitable Level 2-10 |  | 1.2953 | 3 |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Schematic Concept |  | 0.5181 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Pre Construction Set |  | 0.5181 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Experience Home + Project Experience |  | 0.25905 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Landscape |  | LoD 350 - ISS, Habitable Level 2-10 |  | 0.86936 | 2 |  | 0 | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Landscape | Gagan | Schematic Concept |  | 0.43468 | 1 |  | 0
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Landscape | Gagan | Pre Construction Set |  | 0.43468 | 1 |  | 0
| Sarjapur Road [South Block-Resi] | Srjp - Res |  |  | Package Release [LOD 350 - Towers, Experience Homes, Clubhouse and Approvals by Q4] |  | 18.1053 | 13 |  | 0 | 0
| Srjp - Res | Srjp - Res | Architecture |  | [LOD 350 - Towers, Experience Homes and Approvals] |  | 14.3238 | 6 |  | 0 | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | Contract + Design Brief |  | 4.7746 | 1 |  | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | Schematic Concept |  | 4.364 | 1 |  | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | Approvals |  | 2.2847 | 1 |  | 0
| Srjp - Res | Srjp - Res | Architecture | Cijey M | Experience Home + Project Experience |  | 2.3873 | 1 |  | 0
| Srjp - Res | Srjp - Res | Architecture | Om Prakash | CH - Schematic Concept |  | 0.4106 | 1 |  | 0
| Srjp - Res | Srjp - Res | Architecture | Om Prakash | CH - Approvals |  | 0.10265 | 1 |  | 0
| Srjp - Res | Srjp - Res | Structural |  | [LOD 350 - Towers, Experience Homes and Approvals] |  | 2.0244 | 2 |  | 0 | 0
| Srjp - Res | Srjp - Res | Structural | Prakash C | Schematic Concept |  | 1.5183 | 1 |  | 0
| Srjp - Res | Srjp - Res | Structural | Prakash C | Experience Home + Project Experience |  | 0.50611 | 1 |  | 0
| Srjp - Res | Srjp - Res | MEP |  | [LOD 350 - Towers, Experience Homes and Approvals] |  | 1.1268 | 3 |  | 0 | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | Schematic Concept |  | 0.5634 | 1 |  | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | Approvals |  | 0.2817 | 1 |  | 0
| Srjp - Res | Srjp - Res | MEP | Gagan | Experience Home + Project Experience |  | 0.2817 | 1 |  | 0
2 | Srjp - Res | Srjp - Res | Landscape |  | [LOD 350, Experience Homes and Approvals] |  | 0.63025 | 2 |  | 0 | 0
| Srjp - Res | Srjp - Res | Landscape | Gagan | Schematic Concept |  | 0.47269 | 1 |  | 0
| Srjp - Res | Srjp - Res | Landscape | Gagan | Experience Home + Project Experience |  | 0.15756 | 1 |  | 0
| Sarjapur - C (South Block) | Srjp - C - SB |  |  | Package Release [LOD 350 - Towers by Q4] |  | 13.4848 | 6 |  | 0 | 0
| Srjp - C - SB | Srjp - C - SB | Architecture |  | [LOD 350 - Towers] |  | 11.0531 | 3 |  | 0 | 0
| Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Contract + Design Brief |  | 3.6844 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Schematic Concept |  | 3.6844 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Approvals |  | 3.6844 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | Structural |  | [LOD 350 - Towers] |  | 1.5622 | 1 |  | 0 | 0
| Srjp - C - SB | Srjp - C - SB | Structural | Prakash C | Schematic Concept |  | 1.5622 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | MEP |  | [LOD 350 - Towers] |  | 0.86951 | 2 |  | 0 | 0
| Srjp - C - SB | Srjp - C - SB | MEP | Gagan | Schematic Concept |  | 0.43476 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | MEP | Gagan | Approvals |  | 0.43476 | 1 |  | 0
| Srjp - C - SB | Srjp - C - SB | Landscape |  | [LOD 350 - Towers]
| Sarjapur - C (North Block) | Srjp - C - NB |  |  | Package Release [LOD 350 - Towers by Q4] |  | 4.4949 | 6 |  | 0 | 0
| Srjp - C - NB | Srjp - C - NB | Architecture |  | [LOD 350 - Towers] |  | 3.6844 | 3 |  | 0 | 0
| Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Contract + Design Brief |  | 1.2281 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Schematic Concept |  | 1.2281 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Approvals |  | 1.2281 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | Structural |  | [LOD 350 - Towers] |  | 0.52073 | 1 |  | 0 | 0
| Srjp - C - NB | Srjp - C - NB | Structural | Prakash C | Schematic Concept |  | 0.52073 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | MEP |  | [LOD 300] |  | 0.28984 | 2 |  | 0 | 0
| Srjp - C - NB | Srjp - C - NB | MEP | Gagan | Schematic Concept |  | 0.14492 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | MEP | Gagan | Approvals |  | 0.14492 | 1 |  | 0
| Srjp - C - NB | Srjp - C - NB | Landscape |  | [LOD 300]
| OTF | OTF |  |  | Package release [Except Amenities and Facilities] |  | 3.938 | 19 |  | 0.07965 | 1
| OTF | OTF | Master Planning |  | [Dsgn Brf, LOD 200, Approvals, LOD 300, Project Entrance] |  | 2.7525 | 6 |  | 0 | 0
| OTF | OTF | Master Planning | Naveen Y | Contract + Design Brief [Commercial] |  | 0.3375 | 1 |  | 0
| OTF | OTF | Master Planning | Naveen Y | Schematic Concept |  | 0.58 | 1 |  | 0
| OTF | OTF | Master Planning | Naveen Y | Approvals |  | 0.58 | 1 |  | 0
| OTF | OTF | Master Planning | Naveen Y | Pre Construction Set |  | 0.58 | 1 |  | 0
| OTF | OTF | Master Planning | Naveen Y | Marketing and Sales |  | 0.3375 | 1 |  | 0
| OTF | OTF | Master Planning | Naveen Y | Experience Home + Project Entrance |  | 0.3375 | 1 |  | 0
| OTF | OTF | Architecture |  | [LOD 200, Approvals] |  | 0.285 | 3 |  | 0 | 0
| OTF | OTF | Architecture | Om Prakash | Schematic Concept - CH |  | 0.095 | 1 |  | 0
| OTF | OTF | Architecture | Om Prakash | Approvals - CH |  | 0.095 | 1 |  | 0
| OTF | OTF | Architecture | Om Prakash | Pre Construction set - CH |  | 0.095 | 1 |  | 0
| OTF | OTF | Structural |  | [LOD 200, LOD 300] |  | 0.5724 | 3 |  | 0 | 0
| OTF | OTF | Structural | Prakash C | Schematic Concept |  | 0.1431 | 1 |  | 0
| OTF | OTF | Structural | Prakash C | Pre Construction Set |  | 0.2862 | 1 |  | 0
| OTF | OTF | Structural | Prakash C | Project Experience |  | 0.1431 | 1 |  | 0
| OTF | OTF | MEP |  | [LOD 200, Approvals, LOD 300] |  | 0.23895 | 4 |  | 0.07965 | 1
| OTF | OTF | MEP | Gagan | Schematic Concept |  | 0.039825 | 1 |  | 0
| OTF | OTF | MEP | Gagan | Approvals |  | 0.07965 | 1 |  | 0.07965 | 1
| OTF | OTF | MEP | Gagan | Pre Construction Set |  | 0.07965 | 1 |  | 0
| OTF | OTF | MEP | Gagan | Experience Home + Project Experience |  | 0.039825 | 1 |  | 0
| OTF | OTF | Landscape |  | [LOD 200, Approvals, LOD 300] |  | 0.0891 | 3 |  | 0 | 0
| OTF | OTF | Landscape | Gagan | Schematic Concept |  | 0.04455 | 1 |  | 0
| OTF | OTF | Landscape | Gagan | Pre Construction Set |  | 0.022275 | 1 |  | 0
| OTF | OTF | Landscape | Gagan | Project Experience |  | 0.022275 | 1 |  | 0
| Harohalli [Plotted] | Harohalli |  |  | Package Release [Dsgn Brf, LOD 200, Approvals, Exp, Package 1 -3 by Q4] |  | 5.9872 | 12 |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | Master Planning |  | [Dsgn Brf, LOD 200, Approvals, Exp] |  | 4.52 | 4 |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Contract + Design Brief |  | 0.855 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Schematic Concept |  | 1.405 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Approvals |  | 1.405 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Project Experience |  | 0.855 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Architecture |  | [LOD 200, Approvals]
| Harohalli [Plotted] | Ph 1 | Structural |  | [LOD 200,Exp home] |  | 0.72504 | 2 |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | Structural | Prakash C | Schematic Concept |  | 0.36252 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Structural | Prakash C | Project Experience |  | 0.36252 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | MEP |  | [LOD 200, Approvals] |  | 0.40356 | 3 |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | MEP | Gagan | Schematic Concept |  | 0.10089 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | MEP | Gagan | Approvals |  | 0.20178 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | MEP | Gagan | Project Experience |  | 0.10089 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Landscape |  | [LOD 200, Approvals] |  | 0.33858 | 3 |  | 0 | 0
| Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Schematic Concept |  | 0.11286 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Approvals |  | 0.16929 | 1 |  | 0
| Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Project Experience |  | 0.05643 | 1 |  | 0
| Shreegaon [70a] | Ph 1 |  |  | Package Release [ Complete the project by Q4] |  | 2.7969 | 9 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | Master Planning |  | Complete the project [Except Master Archives] |  | 2.1842 | 3 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Contract + Design Brief |  | 0.4725 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Schematic Concept |  | 0.85586 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Approvals |  | 0.85586 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Architecture |  | Complete the project [Except Master Archives] |  | 0.089136 | 1 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | Architecture | Om Prakash | Schematic Concept |  | 0.089136 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Structural |  | Complete the project [Except Master Archives] |  | 0.20034 | 1 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | Structural | Prakash C | Schematic Concept |  | 0.20034 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | MEP |  | Complete the project [Except Master Archives] |  | 0.16726 | 2 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | MEP | Gagan | Schematic Concept |  | 0.055755 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | MEP | Gagan | Approvals |  | 0.11151 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Landscape |  | Complete the project [Except Master Archives] |  | 0.15592 | 2 |  | 0 | 0
| Shreegaon [70a] | Ph 1 | Landscape | Gagan | Schematic Concept |  | 0.06237 | 1 |  | 0
| Shreegaon [70a] | Ph 1 | Landscape | Gagan | Approvals |  | 0.093555 | 1 |  | 0
| Violet hill | Ph 1 |  |  | Package Release [ Complete the project by Q4] |  | 3.4257 | 21 |  | 2.0642 | 6
| Violet hill | Ph 1 | Master Planning |  | Complete the project [Except Master Archives] |  | 2.4261 | 6 |  | 1.9565 | 4
| Violet hill | Ph 1 | Master Planning | Gagan | Schematic Concept [Rework] |  | 0.55067 | 1 |  | 0.55067 | 1
| Violet hill | Ph 1 | Master Planning | Gagan | Approvals [Rework] |  | 0.55067 | 1 |  | 0.55067 | 1
| Violet hill | Ph 1 | Master Planning | Gagan | Pre Construction Set |  | 0.55067 | 1 |  | 0.55067 | 1
| Violet hill | Ph 1 | Master Planning | Gagan | Project Experience |  | 0.30444 | 1 |  | 0
| Violet hill | Ph 1 | Master Planning | Gagan | Marketing and Sales |  | 0.30444 | 1 |  | 0.30444 | 1
| Violet hill | Ph 1 | Master Planning | Gagan | Structures - Security Cabin and Entrance [Rework] |  | 0.1652 | 1 |  | 0
| Violet hill | Ph 1 | Architecture |  | Complete the project [Except Master Archives] |  | 0.058217 | 1 |  | 0 | 0
| Violet hill | Ph 1 | Architecture | Om Prakash | Schematic Concept |  | 0.058217 | 1 |  | 0
| Violet hill | Ph 1 | Structural |  | Complete the project [Except Master Archives] |  | 0.57471 | 4 |  | 0 | 0
| Violet hill | Ph 1 | Structural | Prakash C | Schematic Concept |  | 0.12908 | 1 |  | 0
| Violet hill | Ph 1 | Structural | Prakash C | Pre Construction Set |  | 0.25817 | 1 |  | 0
| Violet hill | Ph 1 | Structural | Prakash C | Project Experience |  | 0.12908 | 1 |  | 0
| Violet hill | Ph 1 | Structural | Prakash C | Structures - Security Cabin and Entrance [Rework] |  | 0.058371 | 1 |  | 0
| Violet hill | Ph 1 | MEP |  | Complete the project [Except Master Archives] |  | 0.24804 | 5 |  | 0.10777 | 2
| Violet hill | Ph 1 | MEP | Gagan | Schematic Concept |  | 0.035924 | 1 |  | 0.035924 | 1
Appr | Violet hill | Ph 1 | MEP | Gagan | Approvals [Rework] |  | 0.071849 | 1 |  | 0.071849 | 1
| Violet hill | Ph 1 | MEP | Gagan | Pre Construction Set |  | 0.071849 | 1 |  | 0
| Violet hill | Ph 1 | MEP | Gagan | Project Experience |  | 0.035924 | 1 |  | 0
| Violet hill | Ph 1 | MEP | Gagan | Structures - Security Cabin and Entrance |  | 0.03249 | 1 |  | 0
| Violet hill | Ph 1 | Landscape |  | Complete the project [Except Master Archives] |  | 0.11864 | 5 |  | 0 | 0
| Violet hill | Ph 1 | Landscape | Gagan | Schematic Concept |  | 0.040186 | 1 |  | 0
| Violet hill | Ph 1 | Landscape | Gagan | Pre Construction Set |  | 0.020093 | 1 |  | 0
| Violet hill | Ph 1 | Landscape | Gagan | Project Experience |  | 0.020093 | 1 |  | 0
| Violet hill | Ph 1 | Landscape | Gagan | Marketing and Sales |  | 0.020093 | 1 |  | 0
| Violet hill | Ph 1 | Landscape | Gagan | Structures - Security Cabin and Entrance |  | 0.018172 | 1 |  | 0
| Ambegaon | Ambegaon |  |  | Package Release [Dsgn Brf, LOD 200, Approvals]
| Ambegaon | Ph 1 | Master Planning |  | [Dsgn Brf, LOD 200, Approvals, Exp]
| Ambegaon | Ph 1 | Architecture |  | [LOD 200, Approvals]
| Ambegaon | Ph 1 | Structural |  | [LOD 200]
| Ambegaon | Ph 1 | MEP |  | [LOD 200, Approvals]
| Ambegaon | Ph 1 | Landscape |  | [LOD 200, Approvals]
| Mall of Asia | Mall of Asia |  |  | Package Release [Dsgn Brf, LOD 200, Approvals, Exp home] |  | 1.6141 | 1 |  | 0 | 0
| Mall of Asia | Mall of Asia | Architecture |  | [Dsgn Brf, LOD 200, Approvals, LOD 300] |  | 1.6141 | 1 |  | 0 | 0
| Mall of Asia | Mall of Asia | Architecture | Om Prakash | Contract + Design Brief |  | 1.6141 | 1 |  | 0
| Mall of Asia | Mall of Asia | Structural |  | [LOD 200, LOD 300]
| Mall of Asia | Mall of Asia | MEP |  | [ LOD 200, Approvals, LOD 300]
| Mall of Asia | Mall of Asia | Landscape |  | [ LOD 200, Approvals, LOD 300]
| TR Mills Chamarajpet | TR Mills |  |  | Package Release [Dsgn Brf, LOD 200, Approvals, Exp home] |  | 0 | 0 |  | 0 | 0
| TR Mills | TR Mills | Architecture |  | [Dsgn Brf, LOD 200, Approvals, LOD 300]
| TR Mills | TR Mills | Structural |  | [LOD 200, LOD 300]
| TR Mills | TR Mills | MEP |  | [ LOD 200, Approvals, LOD 300]
| TR Mills | TR Mills | Landscape |  | [ LOD 200, Approvals, LOD 300]
| KIADB - Mys | KIADB - Mys |  |  | Package Release [Complete the project by Q4] |  | 0 | 8 |  | 0 | 0
| KIADB - Mys | KIADB - Mys | Master Planning |  | Complete the project by Q4 |  |  | 3 |  |  | 0
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | Contract + Design Brief |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | LoD 200 - Schematic Concept |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | Master Planning | Gagan | Approvals |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | Structural |  | Complete the project by Q4 |  |  | 1 |  |  | 0
| KIADB - Mys | KIADB - Mys | Structural | Prakash C | LoD 200 - Schematic Concept |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | MEP |  | Complete the project by Q4 |  |  | 2 |  |  | 0
| KIADB - Mys | KIADB - Mys | MEP | Gagan | LoD 200 - Schematic Concept |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | MEP | Gagan | Approvals |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | Landscape |  | Complete the project by Q4 |  |  | 2 |  |  | 0
| KIADB - Mys | KIADB - Mys | Landscape | Gagan | LoD 200 - Schematic Concept |  |  | 1 |  | 0
| KIADB - Mys | KIADB - Mys | Landscape | Gagan | Approvals |  |  | 1 |  | 0
| Imagine Campus | Imgn |  |  | Package Release [Complete the project by Q4] |  | 1.95 | 7 |  | 0.46 | 1
| Imagine Campus | Imgn | Architecture |  | Package Release [Complete the project by Q4] |  | 1.61 | 3 |  | 0.46 | 1
| Imagine Campus | Imgn | Architecture | Naveen Y | Design Brief |  | 0.46 | 1 |  | 0.46 | 1
| Imagine Campus | Imgn | Architecture | Naveen Y | LoD 200 - Schematic Concept |  | 0.69 | 1 |  | 0
| Imagine Campus | Imgn | Architecture | Naveen Y | Approvals |  | 0.46 | 1 |  | 0
| Imagine Campus | Imgn | Structural |  | Package Release [Complete the project by Q4] |  | 0.19 | 1 |  | 0 | 0
| Imagine Campus | Imgn | Structural | Prakash C | LoD 200 - Schematic Concept |  | 0.19 | 1 |  | 0
| Imagine Campus | Imgn | MEP |  | Package Release [Complete the project by Q4] | 0 | 0.1 | 2 | 0 | 0 | 0 | 0
| Imagine Campus | Imgn | MEP | Gagan | LoD 200 - Schematic Concept |  | 0.05 | 1 |  | 0
| Imagine Campus | Imgn | MEP | Gagan | Approvals |  | 0.05 | 1 |  | 0
| Imagine Campus | Imgn | Landscape |  | Package Release [Complete the project by Q4] |  | 0.05 | 1 |  | 0 | 0
| Imagine Campus | Imgn | Landscape | Gagan | Approvals |  | 0.05 | 1 |  | 0
| OtR OOTA | OTR OOTA |  |  | Package Release [Complete LOD 100 by Q1] |  | 0.19417 | 8 |  | 0 | 0
| OTR OOTA | OTR OOTA | Architecture |  | Complete the project |  | 0.15346 | 3 |  | 0 | 0
| OTR OOTA | OTR OOTA | Architecture | Manik G | Design Brief |  | 0.043845 | 1 |  | 0
| OTR OOTA | OTR OOTA | Architecture | Manik G | LoD 200 - Schematic Concept |  | 0.065768 | 1 |  | 0
| OTR OOTA | OTR OOTA | Architecture | Manik G | Approvals |  | 0.043845 | 1 |  | 0
| OTR OOTA | OTR OOTA | Structural |  | Complete the project |  | 0.020044 | 1 |  | 0 | 0
| OTR OOTA | OTR OOTA | Structural | Prakash C | LoD 200 - Schematic Concept |  | 0.020044 | 1 |  | 0
| OTR OOTA | OTR OOTA | MEP |  | Complete the project |  | 0.011275 | 2 |  | 0 | 0
| OTR OOTA | OTR OOTA | MEP | Gagan | LoD 200 - Schematic Concept |  | 0.0056373 | 1 |  | 0
| OTR OOTA | OTR OOTA | MEP | Gagan | Approvals |  | 0.0056373 | 1 |  | 0
| OTR OOTA | OTR OOTA | Landscape |  | Complete the project |  | 0.0093954 | 2 |  | 0 | 0
| OTR OOTA | OTR OOTA | Landscape | Gagan | LoD 200 - Schematic Concept |  | 0.0046977 | 1 |  | 0
| OTR OOTA | OTR OOTA | Landscape | Gagan | Approvals |  | 0.0046977 | 1 |  | 0
| DonaPaula | DP |  |  | Package release [LOD 200, Approvals, LOD 300, Experience home by Q2] |  | 4.4898 | 12 |  | 0 | 0
| DonaPaula | DP | Architecture |  | [ Approvals,LOD 300, Exp home, LOD350] |  | 3.41 | 5 |  | 0 | 0
| DonaPaula | DP | Architecture | Naveen Y | Schematic Concept .v7 [Rework] |  | 1.34 | 1 |  | 0
| DonaPaula | DP | Architecture | Naveen Y | Preconstruction |  | 1.34 | 1 |  | 0
| DonaPaula | DP | Architecture | Naveen Y | Approvals |  | 0.67 | 1 |  | 0
| DonaPaula | DP | Architecture | Om Prakash | LoD 200 - Schematic Concept - CH |  | 0.03 | 1 |  | 0
| DonaPaula | DP | Architecture | Om Prakash | LoD 300 - Pre Construction set - CH |  | 0.03 | 1 |  | 0
| DonaPaula | DP | Structural |  | [LOD 200, LOD 300] |  | 0.62985 | 2 |  | 0 | 0
| DonaPaula | DP | Structural | Prakash C | Schematic Concept .v7 [Rework] |  | 0.26985 | 1 |  | 0
| DonaPaula | DP | Structural | Prakash C | Preconstruction |  | 0.36 | 1 |  | 0
| DonaPaula | DP | MEP |  | [LOD 200, LOD 300, Approvals] |  | 0.25 | 3 |  | 0 | 0
| DonaPaula | DP | MEP | Gagan | Schematic Concept |  | 0.1 | 1 |  | 0
| DonaPaula | DP | MEP | Gagan | Approvals |  | 0.05 | 1 |  | 0
| DonaPaula | DP | MEP | Gagan | Preconstruction |  | 0.1 | 1 |  | 0
| DonaPaula | DP | Landscape |  | [LOD 200, LOD 300, Approvals] |  | 0.2 | 2 |  | 0 | 0
| DonaPaula | DP | Landscape | Gagan | Schematic Concept |  | 0.15 | 1 |  | 0
| DonaPaula | DP | Landscape | Gagan | Approvals |  | 0.05 | 1 |  | 0
Note on F80: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on H81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on K81: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Package is closed
Note on F546: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on MOU signoff
Note on F552: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Based on MOU signoff

## 26Q1 Cijey M (hidden)
2026 Q1 ¦ Design Goals + Billing |  |  |  |  | Billing [Cr.] | Pkgs
Project | Phase | Discipline | Design Lead | Description | 28.9833 | 32
Cijey M |  |  |  |  | 28.9833 | 32
ITQE-Ph1 | Ph 1 | Architecture | Cijey M | Design Packages - ITQE-Ph1 | 0 | 0
ITQE-Ph2a | Ph 2a | Architecture | Cijey M | Design Packages - ITQE-Ph2a | 0.25 | 2
ITQE-Ph2a | Ph 2a | Architecture | Cijey M | Master Plan ¦ Site Development | 0.07 | 1
ITQE-Ph2a | Ph 2a | Architecture | Cijey M | Experience Home + Project Experience [ V35 ] | 0.18 | 1
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | Design Packages - ITQE-Ph2b | 2.3754 | 4
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | ISS 5&6 ¦ Structural Slab 01 [Basement] | 0.3 | 1
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | ISS 7 ¦ Structrural Slab 01 [Basement] | 0.3 | 1
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | Master Plan ¦ Master Plan | 0.03 | 1
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | L25 Default and it's variants | 1.7454 | 1
ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | Design Packages - ItQE-Ph2c [T9] | 0.30106 | 3
ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | ISS 9 ¦ Foundations & Grade Slab | 0.092092 | 1
ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | Tower 9 ¦ Foundation and Grade Slab | 0.1306 | 1
ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | Tower 9 ¦ Parking Level-Sub grade | 0.078362 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Design Packages - ItQE-Ph3a [T10-12 & 31 Villas] | 8.7814 | 3
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Pre Construction Set | 4.3907 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Experience Home + Project Experience | 2.1953 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Marketing and Sales | 2.1953 | 1
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Design Packages - OTR-Ph01 | 0.96 | 5
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Individual Homes ¦ V25 Default & its Variant | 0.51 | 1
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Villa Block ¦ Building Envelope + Plot Development | 0.3 | 1
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Master Plan | 0.09 | 1
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Site Development | 0.03 | 1
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Site MEP | 0.03 | 1
MeenaSai Res | MS Res | Architecture | Cijey M | Design Packages - MeenaSai Res | 0.105 | 2
MeenaSai Res | MS Res | Architecture | Cijey M | LoD 200 - Schematic Concept | 0.063 | 1
MeenaSai Res | MS Res | Architecture | Cijey M | Approvals | 0.042 | 1
NH Homestay | NH HS | Architecture | Cijey M | Design Packages - NH Homestay | 0.77994 | 4
NH Homestay | NH HS | Architecture | Cijey M | LoD 300 - Pre Construction set | 0.12999 | 1
NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Foundation and Structure | 0.25998 | 1
NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Building Envelope + Plot Development | 0.19498 | 1
NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Interiors | 0.19498 | 1
OTR Museum | OTR Mus | Architecture | Cijey M | Design Packages - OTR Museum | 0.43996 | 2
OTR Museum | OTR Mus | Architecture | Cijey M | Design Brief | 0.17598 | 1
OTR Museum | OTR Mus | Architecture | Cijey M | LoD 200 - Schematic Concept | 0.26398 | 1
OTR-Ph02 | Ph 2 | Architecture | Cijey M | Design Packages - OTR-Ph02 | 1.18 | 3
OTR-Ph02 | Ph 2 | Architecture | Cijey M | Contract + Design Brief | 0.54 | 1
OTR-Ph02 | Ph 2 | Architecture | Cijey M | Schematic Concept | 0.43 | 1
OTR-Ph02 | Ph 2 | Architecture | Cijey M | Approvals | 0.21 | 1
Srjp - Res | Srjp - Res | Architecture | Cijey M | Design Packages - Srjp - Res | 13.8106 | 4
Srjp - Res | Srjp - Res | Architecture | Cijey M | Contract + Design Brief | 4.7746 | 1
Srjp - Res | Srjp - Res | Architecture | Cijey M | Schematic Concept | 4.364 | 1
Srjp - Res | Srjp - Res | Architecture | Cijey M | Approvals | 2.2847 | 1
Srjp - Res | Srjp - Res | Architecture | Cijey M | Experience Home + Project Experience | 2.3873 | 1

## 26Q1 Saji A (hidden)
| 2026 Q1 ¦ Design Goals + Billing |  |  |  |  | Billing [Cr.] | Pkgs
| Project | Phase | Discipline | Design Lead | Description | 12.6556 | 45
Priority | Saji A |  |  |  |  | 12.6556 | 45
| AtR | Ph 1, 2a, 2b | Architecture | Saji A | Design Packages - AtR | 0.31538 | 2
1 | AtR | Ph 1, 2a, 2b | Architecture | Saji A | Clubhouse + Amenities - Clubhouse—Interiors and Facilities | 0.27 | 1
1 | AtR | Ph 1, 2a, 2b | Architecture | Saji A | Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] | 0.045377 | 1
| AtR | Ph 2c | Architecture | Saji A | Design Packages - AtR | 0.081655 | 2
1 | AtR | Ph 2c | Architecture | Saji A | Master Plan - Site MEP | 0.042238 | 1
1 | AtR | Ph 2c | Architecture | Saji A | Clubhouse + Amenities - Sporting Facilities | 0.039416 | 1
| AtR | Ph 3 | Architecture | Saji A | Design Packages - AtR | 1.8088 | 15
1 | AtR | Ph 3 | Architecture | Saji A | Contract + Design brief | 0.27398 | 1
1 | AtR | Ph 3 | Architecture | Saji A | Schematic Concept | 0.27398 | 1
1 | AtR | Ph 3 | Architecture | Saji A | Approvals | 0.13699 | 1
1 | AtR | Ph 3 | Architecture | Saji A | Pre Construction Set | 0.27398 | 1
1 | AtR | Ph 3 | Architecture | Saji A | Home Products - V45 Default and it's variants | 0.36 | 1
1 | AtR | Ph 3 | Architecture | Saji A | Villa Block 34 - Foundations and Sub-Grade Structure | 0.043983 | 1
1 | AtR | Ph 3 | Architecture | Saji A | Villa Block 29 - Foundations and Sub-Grade Structure | 0.065974 | 1
1 | AtR | Ph 3 | Architecture | Saji A | Villa Block 30 - Foundations and Sub-Grade Structure | 0.065974 | 1
2 | AtR | Ph 3 | Architecture | Saji A | Villa Block 33 - Foundations and Sub-Grade Structure | 0.043983 | 1
2 | AtR | Ph 3 | Architecture | Saji A | Villa Block 29 - Building Envelope + Plot Development | 0.065974 | 1
2 | AtR | Ph 3 | Architecture | Saji A | Villa Block 30 - Building Envelope + Plot Development | 0.065974 | 1
2 | AtR | Ph 3 | Architecture | Saji A | Villa Block 31 - Building Envelope + Plot Development | 0.014661 | 1
2 | AtR | Ph 3 | Architecture | Saji A | Villa Block 32 - Building Envelope + Plot Development | 0.029322 | 1
2 | AtR | Ph 3 | Architecture | Saji A | Villa Block 34 - Building Envelope + Plot Development | 0.043983 | 1
2 | AtR | Ph 3 | Architecture | Saji A | Master Plan - Master Plan | 0.05 | 1
| PoaRR-Res | Res | Architecture | Saji A | Design Packages - PoaRR-Res | 3.3659 | 8
1 | PoaRR-Res | Res | Architecture | Saji A | Villa Cluster 3 - All Levels | 0.17 | 1
1 | PoaRR-Res | Res | Architecture | Saji A | Villa Cluster 3 - Building Envelope and Common Areas | 0.17 | 1
1 | PoaRR-Res | Res | Architecture | Saji A | V40 Default and it's variants | 1.18 | 1
1 | PoaRR-Res | Res | Architecture | Saji A | ISS Building Envelope and Common Areas | 1.0659 | 1
1 | PoaRR-Res | Res | Architecture | Saji A | Residential - Site Development | 0.45 | 1
1 | PoaRR-Res | Res | Architecture | Saji A | Masterplan - Site MEP | 0.15 | 1
1 | PoaRR-Res | Res | Architecture | Saji A | Masterplan - Landscaping | 0.15 | 1
1 | PoaRR-Res | Res | Architecture | Saji A | Amenities & Facilities - Sporting Facilities | 0.03 | 1
| PoaRR-T08 | T08 | Architecture | Saji A | Design Packages - PoaRR-T08 | 7.0838 | 18
1 | PoaRR-T08 | T08 | Architecture | Saji A | ISS - Foundations & Grade Slab | 0.2 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | ISS - Parking Level Subgrade | 0.41 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | ISS - Podium Slab | 0.61 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | ISS - Building Envelope and Common Areas | 0.82 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | Habitable Level 01 | 0.48 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | Building Envelope and Common Areas [Typical Tower Levels] | 0.96385 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | L20 Default [Modification for Dry Wall] | 0.52 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | D35 Default [Modification for Dry Wall] | 0.52 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | Master Plan | 0.17 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | Landscape | 0.03 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | Site MEP | 0.03 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | Clubhouse—Outdoor Spaces and Pool | 0.015 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | Community spaces [Board Walk, Children play area] | 0.015 | 1
1 | PoaRR-T08 | T08 | Architecture | Saji A | Site Development | 0.1 | 1
2 | PoaRR-T08 | T08 | Architecture | Saji A | L22 Default | 0.52 | 1
2 | PoaRR-T08 | T08 | Architecture | Saji A | Penthouse Levels | 0.48 | 1
2 | PoaRR-T08 | T08 | Architecture | Saji A | Terrace Level | 0.24 | 1
2 | PoaRR-T08 | T08 | Architecture | Saji A | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 0.96 | 1
| TR Mills | TR Mills | Architecture | Saji A | Design Packages - TR Mills | 0 | 0

## 26Q1 Naveen Y (hidden)
2026 Q1 ¦ Design Goals + Billing |  |  |  |  | Billing [Cr.] | Pkgs
Project | Phase | Discipline | Design Lead | Description | 23.4324 | 24
Naveen Y |  |  |  |  | 23.4324 | 24
AtR - C | Com | Architecture | Naveen Y | Design Packages - AtR - C | 0.36421 | 3
AtR - C | Com | Architecture | Naveen Y | Master Plan - Site Development | 0.13658 | 1
AtR - C | Com | Architecture | Naveen Y | Master Plan - Site MEP | 0.18211 | 1
AtR - C | Com | Architecture | Naveen Y | Master Plan - Landscaping | 0.045527 | 1
Imagine Campus | Imgn | Architecture | Naveen Y | Design Packages - Imagine Campus | 1.61 | 3
Imagine Campus | Imgn | Architecture | Naveen Y | Design Brief | 0.46 | 1
Imagine Campus | Imgn | Architecture | Naveen Y | LoD 200 - Schematic Concept | 0.69 | 1
Imagine Campus | Imgn | Architecture | Naveen Y | Approvals | 0.46 | 1
TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Design Packages - TMFT-Ph 3 | 0.6182 | 3
TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Contract + Design Brief | 0.24728 | 1
TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Schematic Concept | 0.24728 | 1
TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Approvals | 0.12364 | 1
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Design Packages - Srjp - C - NB | 3.6844 | 3
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Contract + Design Brief | 1.2281 | 1
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Schematic Concept | 1.2281 | 1
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Approvals | 1.2281 | 1
OTF | OTF | Architecture | Naveen Y | Design Packages - OTF | 2.7525 | 6
OTF | OTF | Master Planning | Naveen Y | Contract + Design Brief [Commercial] | 0.3375 | 1
OTF | OTF | Master Planning | Naveen Y | Schematic Concept | 0.58 | 1
OTF | OTF | Master Planning | Naveen Y | Approvals | 0.58 | 1
OTF | OTF | Master Planning | Naveen Y | Pre Construction Set | 0.58 | 1
OTF | OTF | Master Planning | Naveen Y | Marketing and Sales | 0.3375 | 1
OTF | OTF | Master Planning | Naveen Y | Experience Home + Project Entrance | 0.3375 | 1
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Design Packages - Srjp - C - SB | 11.0531 | 3
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Contract + Design Brief | 3.6844 | 1
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Schematic Concept | 3.6844 | 1
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Approvals | 3.6844 | 1
DonaPaula | DP | Architecture | Naveen Y | Design Packages - DonaPaula | 3.35 | 3
DonaPaula | DP | Architecture | Naveen Y | Schematic Concept .v7 [Rework] | 1.34 | 1
DonaPaula | DP | Architecture | Naveen Y | Preconstruction | 1.34 | 1
DonaPaula | DP | Architecture | Naveen Y | Approvals | 0.67 | 1

## 26Q1 Om Prakash (hidden)
2026 Q1 ¦ Design Goals + Billing |  |  |  |  | Billing [Cr.] | Pkgs
Project | Phase | Discipline | Design Lead | Description | 10.2095 | 35
Om Prakash |  |  |  |  | 10.2095 | 35
TuiG | TuiG | Architecture | Om Prakash | Design Packages - TuiG | 0.30955 | 2
TuiG | TuiG | Architecture | Om Prakash | Clubhouse—Outdoor Spaces and Pool | 0.15478 | 1
TuiG | TuiG | Architecture | Om Prakash | Community spaces [Board Walk, Children play area] | 0.15478 | 1
DBTW | DBTW | Architecture | Om Prakash | Design Packages - DBTW | 5.878 | 10
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site Development | 0.22115 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site MEP | 0.073717 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Landscaping | 0.073717 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Tower 06 - Foundation and Grade Slab | 0.064032 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Foundations & Grade Slab | 0.54995 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Podium Slab | 0.27497 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I20 Default and it's variants | 2.2352 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I25 Default and it's variants | 2.2352 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Structure and Envelope | 0.1125 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Outdoor Spaces and Pool | 0.0375 | 1
SftW | SftW | Architecture | Om Prakash | Design Packages - SftW | 0.85178 | 9
SftW | SftW | Architecture | Om Prakash | ISS 01 - Podium Slab | 0.25575 | 1
SftW | SftW | Architecture | Om Prakash | Clubhouse—Structure and Envelope | 0.081564 | 1
SftW | SftW | Architecture | Om Prakash | Master Plan - Master Plan | 0.18697 | 1
SftW | SftW | Architecture | Om Prakash | Clubhouse—Outdoor Spaces and Pool | 0.027188 | 1
SftW | SftW | Architecture | Om Prakash | Master Plan - Site Development | 0.11218 | 1
SftW | SftW | Architecture | Om Prakash | Master Plan - Site MEP | 0.037394 | 1
SftW | SftW | Architecture | Om Prakash | Master Plan - Landscaping | 0.037394 | 1
SftW | SftW | Architecture | Om Prakash | Clubhouse + Amenities - Sporting Facilities | 0.027188 | 1
SftW | SftW | Architecture | Om Prakash | Tower 02 - Terrace Level | 0.086149 | 1
LGCE Campus | LGCE Campus | Architecture | Om Prakash | Design Packages - LGCE Campus | 0.38042 | 2
LGCE Campus | LGCE Campus | Architecture | Om Prakash | Design Brief | 0.15217 | 1
LGCE Campus | LGCE Campus | Architecture | Om Prakash | LoD 200 - Schematic Concept | 0.22825 | 1
Srjp - Res | Srjp - Res | Architecture | Om Prakash | Design Packages - Srjp - Res | 0.51325 | 2
Srjp - Res | Srjp - Res | Architecture | Om Prakash | CH - Schematic Concept | 0.4106 | 1
Srjp - Res | Srjp - Res | Architecture | Om Prakash | CH - Approvals | 0.10265 | 1
OTF | OTF | Architecture | Om Prakash | Design Packages - OTF | 0.285 | 3
OTF | OTF | Architecture | Om Prakash | Schematic Concept - CH | 0.095 | 1
OTF | OTF | Architecture | Om Prakash | Approvals - CH | 0.095 | 1
OTF | OTF | Architecture | Om Prakash | Pre Construction set - CH | 0.095 | 1
Harohalli [Plotted] | Ph 1 | Architecture | Om Prakash | Design Packages - Harohalli [Plotted] | 0 | 0
Shreegaon [70a] | Ph 1 | Architecture | Om Prakash | Design Packages - Shreegaon [70a] | 0.089136 | 1
Shreegaon [70a] | Ph 1 | Architecture | Om Prakash | Schematic Concept | 0.089136 | 1
Violet hill | Ph 1 | Architecture | Om Prakash | Design Packages - Violet hill | 0.058217 | 1
Violet hill | Ph 1 | Architecture | Om Prakash | Schematic Concept | 0.058217 | 1
Ambegaon | Ph 1 | Architecture | Om Prakash | Design Packages - Ambegaon | 0 | 0
Mall of Asia | Mall of Asia | Architecture | Om Prakash | Design Packages - Mall of Asia | 1.6141 | 1
Mall of Asia | Mall of Asia | Architecture | Om Prakash | Contract + Design Brief | 1.6141 | 1
OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Design Packages - OTR-Ph02 | 0.17 | 2
OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Schematic Concept - CH | 0.11 | 1
OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Approvals - CH | 0.06 | 1
DonaPaula | DP | Architecture | Om Prakash | Design Packages - DonaPaula | 0.06 | 2
DonaPaula | DP | Architecture | Om Prakash | LoD 200 - Schematic Concept - CH | 0.03 | 1
DonaPaula | DP | Architecture | Om Prakash | LoD 300 - Pre Construction set - CH | 0.03 | 1

## 26Q1 Manik G (hidden)
2026 Q1 ¦ Design Goals + Billing |  |  |  |  | Billing [Cr.] | Pkgs
Project | Phase | Discipline | Design Lead | Description | 0.8528 | 42
Manik G |  |  |  |  | 0.8528 | 42
Ooty Res | Ooty Res | Architecture | Manik G | Design Packages - Ooty Res | 0 | 0
MT Plano - Villa #03 | Villa #3 Uma&Kush | Architecture | Manik G | Design Packages - MT Plano | 0.69535 | 9
MT Plano - Villa #03 | Villa #3 Uma&Kush | Architecture | Manik G | Design Brief | 0.15626 | 1
MT Plano - Villa #03 | Villa #3 Uma&Kush | Architecture | Manik G | LoD 200 - Schematic Concept | 0.23439 | 1
MT Plano - Villa #03 | Villa #3 Uma&Kush | Architecture | Manik G | Approvals | 0.15626 | 1
MT Plano - Villa #03 | Villa #3 Uma&Kush | Architecture | Manik G | LoD 200 - Schematic Concept [Structural design] | 0.071432 | 1
MT Plano - Villa #03 | Villa #3 Uma&Kush | Architecture | Manik G | LoD 200 - Schematic Concept [MEP design] | 0.02009 | 1
MT Plano - Villa #03 | Villa #3 Uma&Kush | Architecture | Manik G | Approvals [MEP design] | 0.02009 | 1
MT Plano - Villa #03 | Villa #3 Uma&Kush | Architecture | Manik G | LoD 200 - Schematic Concept [Landscape design] | 0.016742 | 1
MT Plano - Villa #03 | Villa #3 Uma&Kush | Architecture | Manik G | Approvals [Landscape design] | 0.02009 | 1
MT Plano | MT Plano | Architecture | Manik G | Default Unit Development - Type A : #1, #2, #8 & #9 |  | 1
Indiranagar Res | Indiranagar Res | Architecture | Manik G | Design Packages - Indiranagar Res | 0.004 | 4
Indiranagar Res | Indiranagar Res | Architecture | Manik G | LoD 350 - Block A - Interiors | 0.0021 | 1
Indiranagar Res | Indiranagar Res | Architecture | Manik G | LoD 350 - Block B - Interiors | 0.000875 | 1
Indiranagar Res | Indiranagar Res | Architecture | Manik G | LoD 350 - Block C - Interiors | 0.000525 | 1
Indiranagar Res | Indiranagar Res | Architecture | Manik G | LoD 350 -Block C - Building Envelope + Plot Development | 0.0005 | 1 | Site : Boundary Wall, Security Cabin, Swimming Pool & Site MEP
OTR OOTA | OTR OOTA | Architecture | Manik G | Design Packages - OTR OOTA | 0.15346 | 3
OTR OOTA | OTR OOTA | Architecture | Manik G | Design Brief | 0.043845 | 1
OTR OOTA | OTR OOTA | Architecture | Manik G | LoD 200 - Schematic Concept | 0.065768 | 1
OTR OOTA | OTR OOTA | Architecture | Manik G | Approvals | 0.043845 | 1
Tapestry | Tapestry | Architecture | Manik G | Design Packages - Tapestry | 0 | 10
Tapestry | Tapestry | Architecture | Manik G | Villa #01 : V50-EH v3 - Experience Home |  | 1
Tapestry | Tapestry | Architecture | Manik G | Villa #02 : V50D v3 Spec Home |  | 1
Tapestry | Tapestry | Architecture | Manik G | Villa #11 : V50D v3 Spec Home |  | 1
Tapestry | Tapestry | Architecture | Manik G | Villa #12 : V50 v3 Client - Prabhash |  | 1
Tapestry | Tapestry | Architecture | Manik G | Villa #06 : V50-EH v3 Spec Home |  | 1
Tapestry | Tapestry | Architecture | Manik G | Villa #24 : V40D v4 Spec Home |  | 1
Tapestry | Tapestry | Architecture | Manik G | Villa #25 : V40D v4 Spec Home |  | 1
Tapestry | Tapestry | Architecture | Manik G | Villa #26 : V40D v4 Spec Home |  | 1
Tapestry | Tapestry | Architecture | Manik G | Villa #27 : V40D v4 Spec Home |  | 1
Tapestry | Tapestry | Architecture | Manik G | Villa #05 : V50-EH v3 Spec Home |  | 1
Windmills, Hyd | W+O,CZ | Architecture | Manik G | Windmills & Oota @ Hyderabad | 0 | 5
Windmills, Hyd | W+O,CZ | Architecture | Manik G | Handover - Décor & Furnishing |  | 1
Windmills, Hyd | W+O,CZ | Architecture | Manik G | Oota |  | 1
Windmills, Hyd | W+O,CZ | Architecture | Manik G | PDR |  | 1
Windmills, Hyd | W+O,CZ | Architecture | Manik G | Brewery |  | 1
Windmills, Hyd | W+O,CZ | Architecture | Manik G | Office under the ramp |  | 1
OB2 - Experience Center | EC, OB2 | Architecture | Manik G | OB2 - Experience Center | 0 | 2
OB2 - Experience Center | EC, OB2 | Architecture | Manik G | Contract + Design Brief |  | 1
OB2 - Experience Center | EC, OB2 | Architecture | Manik G | Schematic Concept |  | 1
The Foundation School-2 | tFS-2 | Architecture | Manik G | The Foundation School-2 | 0 | 3
The Foundation School-2 | tFS-2 | Architecture | Manik G | Block A : Lvl 3 |  | 1
The Foundation School-2 | tFS-2 | Architecture | Manik G | Block C : Lvl 1 |  | 1
The Foundation School-2 | tFS-2 | Architecture | Manik G | Block C : Lvl 2 |  | 1
Windmills@SftW | W+B, SftW | Architecture | Manik G | Windmills & Brewery @ SftW, Pune | 0 | 1
Windmills@SftW | W+B, SftW | Architecture | Manik G | Contract + Design Brief |  | 1
TEHPL@various locations | TEHPL@various locations | Architecture | Manik G | TEHPL @ various locations | 0 | 3
TEHPL@various locations | TEHPL@various locations | Architecture | Manik G | Windmills Café @ Lobby, OB2 |  | 1
TEHPL@various locations | TEHPL@various locations | Architecture | Manik G | Malaguena @ Terrace, OB2 |  | 1
TEHPL@various locations | TEHPL@various locations | Architecture | Manik G | Terrace Garden revamp - Windmills, OB2 |  | 1
TEHPL@OTF | TEHPL@OTF | Architecture | Manik G | TEHPL @ OTF | 0 | 2
TEHPL@OTF | TEHPL@OTF | Architecture | Manik G | Contract + Design Brief |  | 1
TEHPL@OTF | TEHPL@OTF | Architecture | Manik G | Schematic Concept |  | 1

## 26Q1 Atul L (hidden)
2026 Q1 ¦ Design Goals + Billing |  |  |  |  | Billing [Cr.] | Pkgs
Project | Phase | Discipline | Design Lead | Description | 0 | 13
Atul L |  |  |  |  | 0 | 13
TuiG | FKH | Architecture | Atul L | LoD 350 - TuiG [V20, V30 and V40] |  | 6
Harohalli | FKH | Architecture | Atul L | LoD 350 - Harohalli [V20, V30 and V50C] |  | 2
TS | FKH | Architecture | Atul L | Design Standards_Master Tech Spec + Design Guidelines |  | 1
TS | FKH | Architecture | Atul L | Introduction to Design (4 topics)/Content for S&K Instagram Page |  | 1
PoaRR | FKH | Architecture | Atul L | V40 personalised customisation_066 |  | 1
PoaRR | FKH | Architecture | Atul L | V40 personalised customisation_051 |  | 1
KM | FKH | Architecture | Atul L | IP_Design Copyright and Patent |  | 1

## 26Q1 Prakash C (hidden)
| 2026 Q1 ¦ Design Goals + Billing |  |  |  |  | Billing [Cr.] | Pkgs
| Project | Phase | Discipline | Design Lead | Description | 20.9552 | 114
Priority | Prakash C |  |  |  |  | 20.9552 | 114
| AtR | Ph 1, 2a, 2b | Structural | Prakash C | Design Packages - AtR | 0.0052867 | 1
1 | AtR | Ph 1, 2a, 2b | Structural | Prakash C | Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] | 0.0052867 | 1
| AtR | Ph 2c | Structural | Prakash C | Design Packages - AtR | 0.016064 | 2
1 | AtR | Ph 2c | Structural | Prakash C | Master Plan - Site MEP | 0.010861 | 1
1 | AtR | Ph 2c | Structural | Prakash C | Clubhouse + Amenities - Sporting Facilities | 0.0052029 | 1
| AtR | Ph 3 | Structural | Prakash C | Design Packages - AtR | 0.35597 | 15
1 | AtR | Ph 3 | Structural | Prakash C | Schematic Concept | 0.093422 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Pre Construction Set | 0.093422 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Foundations and Sub-Grade Structure | 0.021107 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Super Structure | 0.03166 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Building Envelope + Plot Development | 0.0052767 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Foundations and Sub-Grade Structure | 0.021107 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Super Structure | 0.03166 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Building Envelope + Plot Development | 0.0052767 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Foundations and Sub-Grade Structure | 0.004 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Super Structure | 0.007 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Building Envelope + Plot Development | 0.001 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 32 - Building Envelope + Plot Development | 0.0023452 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Foundations and Sub-Grade Structure | 0.014071 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Super Structure | 0.021107 | 1
1 | AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Building Envelope + Plot Development | 0.0035178 | 1
| AtR - C | Com | Structural | Prakash C | Design Packages - AtR - C | 0.4139 | 4
1 | AtR - C | Com | Structural | Prakash C | Tower-[Commercial] - Habitable Level 1-2 | 0.12911 | 1
1 | AtR - C | Com | Structural | Prakash C | Tower-[Commercial] - Habitable Level 3-5 | 0.25823 | 1
1 | AtR - C | Com | Structural | Prakash C | Master Plan - Site Development | 0.014486 | 1
1 | AtR - C | Com | Structural | Prakash C | Master Plan - Site MEP | 0.012072 | 1
| PoaRR-Res | Res | Structural | Prakash C | Design Packages - PoaRR-Res | 0.36 | 3
1 | PoaRR-Res | Res | Structural | Prakash C | Site Development | 0.19 | 1
1 | PoaRR-Res | Res | Structural | Prakash C | Site MEP | 0.16 | 1
1 | PoaRR-Res | Res | Structural | Prakash C | Sporting Facilities | 0.01 | 1
| PoaRR-T08 | T08 | Structural | Prakash C | Design Packages - PoaRR-T08 | 2.1 | 8
2 | PoaRR-T08 | T08 | Structural | Prakash C | Penthouse Levels | 0.2 | 1
2 | PoaRR-T08 | T08 | Structural | Prakash C | Terrace Level | 0.4 | 1
1 | PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Foundations & Grade Slab | 0.32 | 1
1 | PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Podium Slab | 0.32 | 1
1 | PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Parking Level Subgrade | 0.43 | 1
1 | PoaRR-T08 | T08 | Structural | Prakash C | Site Development | 0.02 | 1
1 | PoaRR-T08 | T08 | Structural | Prakash C | Site MEP | 0.01 | 1
1 | PoaRR-T08 | T08 | Structural | Prakash C | STR Package Release [Parking level subgrade] | 0.4 | 1
| ITQE-Ph1 | Ph 1 | Structural | Prakash C | Design Packages - ITQE-Ph1 | 0.084072 | 3
1 | ITQE-Ph1 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site Development | 0.060249 | 1
1 | ITQE-Ph1 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Clubhouse—Outdoor Spaces and Pool | 0.011912 | 1
1 | ITQE-Ph1 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Community spaces | 0.011912 | 1
| ITQE-Ph2a | Ph 2a | Structural | Prakash C | Design Packages - ITQE-Ph2a | 0.16919 | 3
1 | ITQE-Ph2a | Ph 2a | Structural | Prakash C | Experience Home + Project Experience [ V35 ] | 0.07 | 1
1 | ITQE-Ph2a | Ph 2a | Structural | Prakash C | Master Plan ¦ Site Development | 0.054104 | 1
1 | ITQE-Ph2a | Ph 2a | Structural | Prakash C | Master Plan ¦ Site MEP | 0.045086 | 1
| ITQE-Ph2b | Ph 2b | Structural | Prakash C | Design Packages - ITQE-Ph2b | 1.12 | 11
1 | ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 05 ¦ Habitable Level - Even | 0.07 | 1
1 | ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 05 ¦ Habitable Level - Odd | 0.07 | 1
1 | ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 06 ¦ Habitable Level - Even | 0.07 | 1
1 | ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 06 ¦ Habitable Level - Odd | 0.07 | 1
1 | ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 07 ¦ Habitable Level - Even | 0.07 | 1
1 | ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 07 ¦ Habitable Level - Odd | 0.07 | 1
1 | ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS5&6 ¦ Structrural Slab 01 [Basement] | 0.13 | 1
1 | ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Foundations & Sub¦Grade | 0.18 | 1
1 | ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Structrural Slab 01 [Basement] | 0.13 | 1
1 | ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS5&6 ¦ Podium Slab | 0.13 | 1
1 | ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Podium Slab | 0.13 | 1
| ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | Design Packages - ItQE-Ph2c [T9] | 0.2848 | 4
2 | ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | ISS 9 ¦ Earthwork | 0.0097618 | 1
2 | ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | ISS 9 ¦ Foundations & Grade Slab | 0.039047 | 1
2 | ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | Tower 9 ¦ Foundation and Grade Slab | 0.118 | 1
2 | ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | Tower 9 ¦ Parking Level-Sub grade | 0.118 | 1
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | Design Packages - ItQE-Ph3a [T10-12 & 31 Villas] | 3.2579 | 2
2 | ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | Schematic Concept | 1.3962 | 1
2 | ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | Pre Construction Set | 1.8617 | 1
| ITQE-T05 | T05 | Structural | Prakash C | Design Packages - ITQE-T05 | 0 | 0
| OTR-Ph01 | Ph 1 | Structural | Prakash C | Design Packages - OTR-Ph01 | 0.38 | 5
1 | OTR-Ph01 | Ph 1 | Structural | Prakash C | Experience Home + Project Experience | 0.08 | 1
1 | OTR-Ph01 | Ph 1 | Structural | Prakash C | Villa Block ¦ Super Structure | 0.17 | 1
1 | OTR-Ph01 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site Development | 0.03 | 1
2 | OTR-Ph01 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site MEP | 0.03 | 1
2 | OTR-Ph01 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Community spaces [Board Walk, Children play area] | 0.07 | 1
| TuiG | TuiG | Structural | Prakash C | Design Packages - TuiG | 0.82974 | 4
1 | TuiG | TuiG | Structural | Prakash C | Site Development | 0.40295 | 1
1 | TuiG | TuiG | Structural | Prakash C | Site MEP | 0.33579 | 1
1 | TuiG | TuiG | Structural | Prakash C | Clubhouse—Outdoor Spaces and Pool | 0.030991 | 1
1 | TuiG | TuiG | Structural | Prakash C | Sporting Facilities | 0.06 | 1
| TMFT-Ph 2 | Ph 2 | Structural | Prakash C | Design Packages - TMFT-Ph 2 | 0.03 | 1
1 | TMFT-Ph 2 | Ph 2 | Structural | Prakash C | LoD 350 - Site Development | 0.03 | 1
| DBTW | DBTW | Structural | Prakash C | Design Packages - DBTW | 3.6899 | 16
1 | DBTW | DBTW | Structural | Prakash C | LoD 300 - Pre Construction Set [Podium] | 2.2512 | 1
1 | DBTW | DBTW | Structural | Prakash C | LoD 350 - ISS - Foundations & Grade Slab | 0.52958 | 1
2 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-1-Habitable Level - Even | 0.025613 | 1
1 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level 01 | 0.10834 | 1
2 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level - Even | 0.05417 | 1
1 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level 01 | 0.10834 | 1
2 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level - Even | 0.05417 | 1
1 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level 01 | 0.10834 | 1
2 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level - Even | 0.05417 | 1
1 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 05-Foundation and Grade Slab | 0.10834 | 1
2 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level 01 | 0.05417 | 1
2 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 05-Habitable Level - Even | 0.05417 | 1
1 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Foundation and Grade Slab | 0.051226 | 1
2 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Parking Level-Sub grade | 0.051226 | 1
2 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level 01 | 0.051226 | 1
2 | DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level - Even | 0.025613 | 1
| SftW | SftW | Structural | Prakash C | Design Packages - SftW | 0.34546 | 6
1 | SftW | SftW | Structural | Prakash C | Tower 2 - Terrace Level | 0.20116 | 1
1 | SftW | SftW | Structural | Prakash C | Master Plan - Site Development | 0.058457 | 1
1 | SftW | SftW | Structural | Prakash C | Master Plan - Site MEP | 0.048714 | 1
1 | SftW | SftW | Structural | Prakash C | Clubhouse—Structure and Envelope | 0.025989 | 1
1 | SftW | SftW | Structural | Prakash C | Clubhouse—Outdoor Spaces and Pool | 0.0037128 | 1
1 | SftW | SftW | Structural | Prakash C | Clubhouse—Sporting Facilities | 0.0074255 | 1
| LGCE Campus | LGCE Campus | Structural | Prakash C | Design Packages - LGCE Campus | 0 | 0
| Ooty Res | Ooty Res | Structural | Prakash C | Design Packages - Ooty Res | 0 | 0
| MT Plano | MT Plano | Structural | Prakash C | Design Packages - MT Plano | 0 | 0
| MeenaSai Res | MS Res | Structural | Prakash C | Design Packages - MeenaSai Res | 0.0192 | 1
2 | MeenaSai Res | MS Res | Structural | Prakash C | LoD 200 - Schematic Concept | 0.0192 | 1
| NH Homestay | NH HS | Structural | Prakash C | Design Packages - NH Homestay | 0.22284 | 3
1 | NH Homestay | NH HS | Structural | Prakash C | LoD 300 - Pre Construction set | 0.059424 | 1
1 | NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Foundation and Structure | 0.14856 | 1
1 | NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Building Envelope + Plot Development | 0.014856 | 1
| OTR Museum | OTR Mus | Structural | Prakash C | Design Packages - OTR Museum | 0 | 0
| KIADB - Mys | KIADB - Mys | Structural | Prakash C | Design Packages - KIADB - Mys | 0 | 1
3 | KIADB - Mys | KIADB - Mys | Structural | Prakash C | LoD 200 - Schematic Concept |  | 1
| Imagine Campus | Imgn | Structural | Prakash C | Design Packages - Imagine Campus | 0.19 | 1
2 | Imagine Campus | Imgn | Structural | Prakash C | LoD 200 - Schematic Concept | 0.19 | 1
| OTR-Ph02 | Ph 2 | Structural | Prakash C | Design Packages - OTR-Ph02 | 0.17172 | 1
3 | OTR-Ph02 | Ph 2 | Structural | Prakash C | Schematic Concept | 0.17172 | 1
| TMFT-Ph 3 | Ph 3 | Structural | Prakash C | Design Packages - TMFT-Ph 3 | 0.078635 | 1
3 | TMFT-Ph 3 | Ph 3 | Structural | Prakash C | Schematic Concept | 0.078635 | 1
| Srjp - Res | Srjp - Res | Structural | Prakash C | Design Packages - Srjp - Res | 2.0244 | 2
1 | Srjp - Res | Srjp - Res | Structural | Prakash C | Schematic Concept | 1.5183 | 1
1 | Srjp - Res | Srjp - Res | Structural | Prakash C | Experience Home + Project Experience | 0.50611 | 1
| Srjp - C - SB | Srjp - C - SB | Structural | Prakash C | Design Packages - Srjp - C - SB | 1.5622 | 1
1 | Srjp - C - SB | Srjp - C - SB | Structural | Prakash C | Schematic Concept | 1.5622 | 1
| Srjp - C - NB | Srjp - C - NB | Structural | Prakash C | Design Packages - Srjp - C - NB | 0.52073 | 1
1 | Srjp - C - NB | Srjp - C - NB | Structural | Prakash C | Schematic Concept | 0.52073 | 1
| OTF | OTF | Structural | Prakash C | Design Packages - OTF | 0.5724 | 3
1 | OTF | OTF | Structural | Prakash C | Schematic Concept | 0.1431 | 1
1 | OTF | OTF | Structural | Prakash C | Pre Construction Set | 0.2862 | 1
1 | OTF | OTF | Structural | Prakash C | Project Experience | 0.1431 | 1
| Harohalli [Plotted] | Ph 1 | Structural | Prakash C | Design Packages - Harohalli [Plotted] | 0.72504 | 2
2 | Harohalli [Plotted] | Ph 1 | Structural | Prakash C | Schematic Concept | 0.36252 | 1
2 | Harohalli [Plotted] | Ph 1 | Structural | Prakash C | Project Experience | 0.36252 | 1
| Shreegaon [70a] | Ph 1 | Structural | Prakash C | Design Packages - Shreegaon [70a] | 0.20034 | 1
3 | Shreegaon [70a] | Ph 1 | Structural | Prakash C | Schematic Concept | 0.20034 | 1
| Violet hill | Ph 1 | Structural | Prakash C | Design Packages - Violet hill | 0.57471 | 4
1 | Violet hill | Ph 1 | Structural | Prakash C | Schematic Concept | 0.12908 | 1
1 | Violet hill | Ph 1 | Structural | Prakash C | Pre Construction Set | 0.25817 | 1
1 | Violet hill | Ph 1 | Structural | Prakash C | Project Experience | 0.12908 | 1
1 | Violet hill | Ph 1 | Structural | Prakash C | Structures - Security Cabin and Entrance [Rework] | 0.058371 | 1
| Ambegaon | Ph 1 | Structural | Prakash C | Design Packages - Ambegaon | 0 | 0
| Mall of Asia | Mall of Asia | Structural | Prakash C | Design Packages - Mall of Asia | 0 | 0
| TR Mills | TR Mills | Structural | Prakash C | Design Packages - TR Mills | 0 | 0
| Indiranagar Res | Indrng Res | Structural | Prakash C | Design Packages - Indiranagar Res | 0.0008 | 1
1 | Indiranagar Res | Indrng Res | Structural | Prakash C | LoD 350 -Block C - Building Envelope + Plot Development | 0.0008 | 1
| OTR OOTA | OTR OOTA | Structural | Prakash C | Design Packages - OTR OOTA | 0.020044 | 1
3 | OTR OOTA | OTR OOTA | Structural | Prakash C | LoD 200 - Schematic Concept | 0.020044 | 1
| DonaPaula | DP | Structural | Prakash C | Design Packages - DonaPaula | 0.62985 | 2
2 | DonaPaula | DP | Structural | Prakash C | Schematic Concept .v7 [Rework] | 0.26985 | 1
2 | DonaPaula | DP | Structural | Prakash C | Preconstruction | 0.36 | 1

## 26Q1 Gaganjit S (hidden)
| 2026 Q1 ¦ Design Goals + Billing |  |  |  |  | Billing [Cr.] | Pkgs
| Project | Phase | Discipline | Design Lead | Description | 18.6746 | 127
Priority | Gaganjit S |  |  |  |  | 18.6746 | 127
| AtR | Ph 2c | MEP | Gaganjit S | Design Packages - AtR | 0.014337 | 1
1 | AtR | Ph 2c | MEP | Gaganjit S | Master Plan - Site MEP | 0.014337 | 1
| AtR | Ph 3 |  | Gaganjit S | Design Packages - AtR | 0.36573 | 12
1 | AtR | Ph 3 | MEP | Gaganjit S | Schematic Concept [V80] | 0.0215 | 1
1 | AtR | Ph 3 | MEP | Gaganjit S | PreConstruction Set | 0.0215 | 1
1 | AtR | Ph 3 | MEP | Gaganjit S | Villa Block 31 - Foundations and Sub-Grade Structure | 0.00094245 | 1
1 | AtR | Ph 3 | MEP | Gaganjit S | Villa Block 32 - Foundations and Sub-Grade Structure | 0.0018849 | 1
1 | AtR | Ph 3 | MEP | Gaganjit S | Villa Block 34 - Foundations and Sub-Grade Structure | 0.0028274 | 1
1 | AtR | Ph 3 | MEP | Gaganjit S | Home Products - V45 Default and it's variants | 0.10495 | 1
1 | AtR | Ph 3 | MEP | Gaganjit S | Master Plan - Master Plan | 0.04 | 1
1 | AtR | Ph 3 | Landscape | Gaganjit S | Schematic Concept | 0.047864 | 1
1 | AtR | Ph 3 | Landscape | Gaganjit S | Preconstruction Set | 0.047864 | 1
2 | AtR | Ph 3 | Landscape | Gaganjit S | Home Products - V45 Default | 0.046405 | 1
2 | AtR | Ph 3 | Landscape | Gaganjit S | Master Plan | 0.02 | 1
2 | AtR | Ph 3 | Landscape | Gaganjit S | Site Development - 06 Landscape | 0.01 | 1
| AtR - C | Com |  | Gaganjit S | Design Packages - AtR - C | 0.16751 | 2
1 | AtR - C | Com | MEP | Gaganjit S | Master Plan - Master Plan | 0.038655 | 1
1 | AtR - C | Com | MEP | Gaganjit S | Master Plan - Site MEP | 0.12885 | 1
| PoaRR-Res | Res |  | Gaganjit S | Design Packages - PoaRR-Res | 0.40327 | 4
1 | PoaRR-Res | Res | MEP | Gaganjit S | Site MEP | 0.36 | 1
1 | PoaRR-Res | Res | MEP | Gaganjit S | Clubhouse Outdoor Spaces and Pool | 0.002183 | 1
1 | PoaRR-Res | Res | MEP | Gaganjit S | Sporting Facilities | 0.0010915 | 1
1 | PoaRR-Res | Res | Landscape | Gaganjit S | Amenities & Facilities - Community spaces [Sporting Facilities] | 0.04 | 1
| PoaRR-T08 | T08 |  | Gaganjit S | Design Packages - PoaRR-T08 | 0.14 | 3
1 | PoaRR-T08 | T08 | MEP | Gaganjit S | ISS - Foundation and Gradeslab | 0.02 | 1
1 | PoaRR-T08 | T08 | MEP | Gaganjit S | L20 Default and it's variants | 0.06 | 1
1 | PoaRR-T08 | T08 | MEP | Gaganjit S | D35 Default and it's variants | 0.06 | 1
| ITQE-Ph2b | Ph 2b |  | Gaganjit S | Design Packages - ITQE-Ph2b | 0.031656 | 2
1 | ITQE-Ph2b | Ph 2b | MEP | Gaganjit S | ISS -5 & 6 ¦ Structrural Slab 01 [Basement] | 0.015828 | 1
1 | ITQE-Ph2b | Ph 2b | MEP | Gaganjit S | ISS -7 ¦ Structrural Slab 01 [Basement] | 0.015828 | 1
| ItQE-Ph2c [T9] | Ph 2c |  | Gaganjit S | Design Packages - ItQE-Ph2c [T9] | 0.047123 | 2
2 | ItQE-Ph2c [T9] | Ph 2c | MEP | Gaganjit S | ISS 9 ¦ Foundations & Grade Slab | 0.0163 | 1
2 | ItQE-Ph2c [T9] | Ph 2c | MEP | Gaganjit S | Tower 9 ¦ Foundation and Grade Slab | 0.030822 | 1
| ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a |  | Gaganjit S | Design Packages - ItQE-Ph3a [T10-12 & 31 Villas] | 2.1646 | 5
2 | ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Schematic Concept | 0.5181 | 1
2 | ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Pre Construction Set | 0.5181 | 1
2 | ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Experience Home + Project Experience | 0.25905 | 1
2 | ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Landscape | Gagan | Schematic Concept | 0.43468 | 1
2 | ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Landscape | Gagan | Pre Construction Set | 0.43468 | 1
| OTR-Ph01 | Ph 1 |  | Gaganjit S | Design Packages - OTR-Ph01 | 0.04 | 1
2 | OTR-Ph01 | Ph 1 | MEP | Gaganjit S | Master Plan ¦ Site MEP | 0.04 | 1
| TuiG | TuiG |  | Gaganjit S | Design Packages - TuiG | 0.32421 | 4
1 | TuiG | TuiG | MEP | Gagan | Clubhouse—Structure and Envelope | 0.17351 | 1
1 | TuiG | TuiG | MEP | Gagan | Clubhouse—Outdoor Spaces and Pool | 0.049574 | 1
1 | TuiG | TuiG | MEP | Gagan | Sporting Facilities | 0.02 | 1
1 | TuiG | TuiG | Landscape | Gagan | Community spaces [Board Walk, Children play area] | 0.081128 | 1
| DBTW | DBTW |  | Gaganjit S | Design Packages - DBTW | 0.036853 | 1
2 | DBTW | DBTW | MEP | Gaganjit S | LoD 350 - Master Plan- Master Plan | 0.036853 | 1
| SftW | SftW |  | Gaganjit S | Design Packages - SftW | 0.021398 | 2
1 | SftW | SftW | MEP | Gaganjit S | MEP ¦ Master Plan - Site MEP | 0.020843 | 1
1 | SftW | SftW | MEP | Gaganjit S | MEP ¦ Clubhouse—Sporting Facilities | 0.00055534 | 1
| LGCE Campus | LGCE Campus |  | Gaganjit S | Design Packages - LGCE Campus | 0 | 0
| Ooty Res | Ooty Res |  | Gaganjit S | Design Packages - Ooty Res | 0 | 0
| MT Plano | MT Plano |  | Gaganjit S | Design Packages - MT Plano | 0 | 0
| MeenaSai Res | MS Res |  | Gaganjit S | Design Packages - MeenaSai Res | 0.0168 | 3
2 | MeenaSai Res | MS Res | MEP | Gagan | LoD 200 - Schematic Concept | 0.0054 | 1
| MeenaSai Res | MS Res | MEP | Gagan | Approvals | 0.0054 | 1
2 | MeenaSai Res | MS Res | Landscape | Gagan | LoD 200 - Schematic Concept | 0.006 | 1
| NH Homestay | NH HS |  | Gaganjit S | Design Packages - NH Homestay | 0.23027 | 8
| NH Homestay | NH HS | MEP | Gagan | Approvals | 0.016713 | 1
1 | NH Homestay | NH HS | MEP | Gagan | LoD 300 - Pre Construction set | 0.016713 | 1
1 | NH Homestay | NH HS | MEP | Gagan | LoD 350 - Foundation and Structure | 0.058495 | 1
1 | NH Homestay | NH HS | MEP | Gagan | LoD 350 - Building Envelope + Plot Development | 0.025069 | 1
2 | NH Homestay | NH HS | MEP | Gagan | LoD 350 - Interiors | 0.025069 | 1
1 | NH Homestay | NH HS | Landscape | Gagan | LoD 200 - Schematic Concept | 0.01857 | 1
1 | NH Homestay | NH HS | Landscape | Gagan | LoD 300 - Pre Construction set | 0.01857 | 1
2 | NH Homestay | NH HS | Landscape | Gagan | LoD 350 - Building Envelope + Plot Development | 0.051068 | 1
| Indiranagar Res | Indrng Res |  | Gaganjit S | Design Packages - Indiranagar Res | 0.000113 | 1
2 | Indiranagar Res | Indrng Res | Landscape | Gagan | LoD 350 - Block C- Building Envelope + Plot Development | 0.000113 | 1
| OTR Museum | OTR Mus |  | Gaganjit S | Design Packages - OTR Museum | 0 | 0
| KIADB - Mys | KIADB - Mys |  | Gaganjit S | Design Packages - KIADB - Mys | 0 | 7
3 | KIADB - Mys | KIADB - Mys | Master Planning | Gagan | Contract + Design Brief |  | 1
3 | KIADB - Mys | KIADB - Mys | Master Planning | Gagan | LoD 200 - Schematic Concept |  | 1
3 | KIADB - Mys | KIADB - Mys | Master Planning | Gagan | Approvals |  | 1
3 | KIADB - Mys | KIADB - Mys | MEP | Gagan | LoD 200 - Schematic Concept |  | 1
3 | KIADB - Mys | KIADB - Mys | MEP | Gagan | Approvals |  | 1
3 | KIADB - Mys | KIADB - Mys | Landscape | Gagan | LoD 200 - Schematic Concept |  | 1
3 | KIADB - Mys | KIADB - Mys | Landscape | Gagan | Approvals |  | 1
| Imagine Campus | Imgn |  | Gaganjit S | Design Packages - Imagine Campus | 0.15 | 3
2 | Imagine Campus | Imgn | MEP | Gagan | LoD 200 - Schematic Concept | 0.05 | 1
2 | Imagine Campus | Imgn | MEP | Gagan | Approvals | 0.05 | 1
2 | Imagine Campus | Imgn | Landscape | Gagan | Approvals | 0.05 | 1
| OTR-Ph02 | Ph 2 |  | Gaganjit S | Design Packages - OTR-Ph02 | 0.16686 | 4
3 | OTR-Ph02 | Ph 2 | MEP | Gaganjit S | Schematic Concept | 0.06372 | 1
3 | OTR-Ph02 | Ph 2 | MEP | Gaganjit S | Approvals | 0.03186 | 1
3 | OTR-Ph02 | Ph 2 | Landscape | Gaganjit S | Schematic Concept | 0.05346 | 1
3 | OTR-Ph02 | Ph 2 | Landscape | Gaganjit S | Approvals | 0.01782 | 1
| TMFT-Ph 3 | Ph 3 |  | Gaganjit S | Design Packages - TMFT-Ph 3 | 0.07641 | 4
3 | TMFT-Ph 3 | Ph 3 | MEP | Gaganjit S | Schematic Concept | 0.029179 | 1
3 | TMFT-Ph 3 | Ph 3 | MEP | Gaganjit S | Approvals | 0.01459 | 1
3 | TMFT-Ph 3 | Ph 3 | Landscape | Gaganjit S | Schematic Concept | 0.024481 | 1
3 | TMFT-Ph 3 | Ph 3 | Landscape | Gaganjit S | Approvals | 0.0081602 | 1
| Srjp - Res | Srjp - Res |  | Gaganjit S | Design Packages - Srjp - Res | 1.7571 | 5
1 | Srjp - Res | Srjp - Res | MEP | Gaganjit S | Schematic Concept | 0.5634 | 1
1 | Srjp - Res | Srjp - Res | MEP | Gaganjit S | Approvals | 0.2817 | 1
1 | Srjp - Res | Srjp - Res | MEP | Gaganjit S | Experience Home + Project Experience | 0.2817 | 1
1 | Srjp - Res | Srjp - Res | Landscape | Gaganjit S | Schematic Concept | 0.47269 | 1
1 | Srjp - Res | Srjp - Res | Landscape | Gaganjit S | Experience Home + Project Experience | 0.15756 | 1
| Srjp - C - SB | Srjp - C - SB |  | Gaganjit S | Design Packages - Srjp - C - SB | 0.86951 | 2
1 | Srjp - C - SB | Srjp - C - SB | MEP | Gaganjit S | Schematic Concept | 0.43476 | 1
1 | Srjp - C - SB | Srjp - C - SB | MEP | Gaganjit S | Approvals | 0.43476 | 1
| Srjp - C - NB | Srjp - C - NB |  | Gaganjit S | Design Packages - Srjp - C - NB | 0.28984 | 2
1 | Srjp - C - NB | Srjp - C - NB | MEP | Gaganjit S | Schematic Concept | 0.14492 | 1
1 | Srjp - C - NB | Srjp - C - NB | MEP | Gaganjit S | Approvals | 0.14492 | 1
| OTF | OTF |  | Gaganjit S | Design Packages - OTF | 0.32805 | 7
1 | OTF | OTF | MEP | Gagan | Schematic Concept | 0.039825 | 1
1 | OTF | OTF | MEP | Gagan | Approvals | 0.07965 | 1
1 | OTF | OTF | MEP | Gagan | Pre Construction Set | 0.07965 | 1
1 | OTF | OTF | MEP | Gagan | Experience Home + Project Experience | 0.039825 | 1
1 | OTF | OTF | Landscape | Gagan | Schematic Concept | 0.04455 | 1
1 | OTF | OTF | Landscape | Gagan | Pre Construction Set | 0.022275 | 1
1 | OTF | OTF | Landscape | Gagan | Project Experience | 0.022275 | 1
| Harohalli [Plotted] | Ph 1 |  | Gaganjit S | Design Packages - Harohalli [Plotted] | 5.2621 | 10
2 | Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Contract + Design Brief | 0.855 | 1
2 | Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Schematic Concept | 1.405 | 1
2 | Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Approvals | 1.405 | 1
2 | Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Project Experience | 0.855 | 1
2 | Harohalli [Plotted] | Ph 1 | MEP | Gagan | Schematic Concept | 0.10089 | 1
2 | Harohalli [Plotted] | Ph 1 | MEP | Gagan | Approvals | 0.20178 | 1
2 | Harohalli [Plotted] | Ph 1 | MEP | Gagan | Project Experience | 0.10089 | 1
2 | Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Schematic Concept | 0.11286 | 1
2 | Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Approvals | 0.16929 | 1
2 | Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Project Experience | 0.05643 | 1
| Shreegaon [70a] | Ph 1 |  | Gaganjit S | Design Packages - Shreegaon [70a] | 2.5074 | 7
3 | Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Contract + Design Brief | 0.4725 | 1
3 | Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Schematic Concept | 0.85586 | 1
3 | Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Approvals | 0.85586 | 1
3 | Shreegaon [70a] | Ph 1 | MEP | Gagan | Schematic Concept | 0.055755 | 1
3 | Shreegaon [70a] | Ph 1 | MEP | Gagan | Approvals | 0.11151 | 1
3 | Shreegaon [70a] | Ph 1 | Landscape | Gagan | Schematic Concept | 0.06237 | 1
3 | Shreegaon [70a] | Ph 1 | Landscape | Gagan | Approvals | 0.093555 | 1
| Violet hill | Ph 1 |  | Gaganjit S | Design Packages - Violet hill | 2.7928 | 16
1 | Violet hill | Ph 1 | Master Planning | Gagan | Schematic Concept [Rework] | 0.55067 | 1
1 | Violet hill | Ph 1 | Master Planning | Gagan | Approvals [Rework] | 0.55067 | 1
1 | Violet hill | Ph 1 | Master Planning | Gagan | Pre Construction Set | 0.55067 | 1
1 | Violet hill | Ph 1 | Master Planning | Gagan | Project Experience | 0.30444 | 1
1 | Violet hill | Ph 1 | Master Planning | Gagan | Marketing and Sales | 0.30444 | 1
1 | Violet hill | Ph 1 | Master Planning | Gagan | Structures - Security Cabin and Entrance [Rework] | 0.1652 | 1
1 | Violet hill | Ph 1 | MEP | Gagan | Schematic Concept | 0.035924 | 1
1 | Violet hill | Ph 1 | MEP | Gagan | Approvals [Rework] | 0.071849 | 1
1 | Violet hill | Ph 1 | MEP | Gagan | Pre Construction Set | 0.071849 | 1
1 | Violet hill | Ph 1 | MEP | Gagan | Project Experience | 0.035924 | 1
1 | Violet hill | Ph 1 | MEP | Gagan | Structures - Security Cabin and Entrance | 0.03249 | 1
1 | Violet hill | Ph 1 | Landscape | Gagan | Schematic Concept | 0.040186 | 1
1 | Violet hill | Ph 1 | Landscape | Gagan | Pre Construction Set | 0.020093 | 1
1 | Violet hill | Ph 1 | Landscape | Gagan | Project Experience | 0.020093 | 1
1 | Violet hill | Ph 1 | Landscape | Gagan | Marketing and Sales | 0.020093 | 1
1 | Violet hill | Ph 1 | Landscape | Gagan | Structures - Security Cabin and Entrance | 0.018172 | 1
| Ambegaon | Ph 1 |  | Gaganjit S | Design Packages - Ambegaon | 0 | 0
| Mall of Asia | Mall of Asia |  | Gaganjit S | Design Packages - Mall of Asia | 0 | 0
| TR Mills | TR Mills |  | Gaganjit S | Design Packages - TR Mills | 0 | 0
| OTR OOTA | OTR OOTA |  | Gaganjit S | Design Packages - OTR OOTA | 0.02067 | 4
3 | OTR OOTA | OTR OOTA | MEP | Gagan | LoD 200 - Schematic Concept | 0.0056373 | 1
3 | OTR OOTA | OTR OOTA | MEP | Gagan | Approvals | 0.0056373 | 1
3 | OTR OOTA | OTR OOTA | Landscape | Gagan | LoD 200 - Schematic Concept | 0.0046977 | 1
3 | OTR OOTA | OTR OOTA | Landscape | Gagan | Approvals | 0.0046977 | 1
| DonaPaula | DP |  | Gaganjit S | Design Packages - DonaPaula | 0.45 | 5
2 | DonaPaula | DP | MEP | Gagan | Schematic Concept | 0.1 | 1
2 | DonaPaula | DP | MEP | Gagan | Approvals | 0.05 | 1
2 | DonaPaula | DP | MEP | Gagan | Preconstruction | 0.1 | 1
2 | DonaPaula | DP | Landscape | Gagan | Schematic Concept | 0.15 | 1
2 | DonaPaula | DP | Landscape | Gagan | Approvals | 0.05 | 1

## 26Q1 Navneet K (hidden)
| 2026 Q1 ¦ Design Goals + Billing |  |  |  |  | Billing [Cr.] | Pkgs
| Project | Phase | Discipline | Design Lead | Description | 2.0858 | 151
Priority | Navneet K |  |  |  |  | 2.0858 | 151
| ID Product Launch | PD Launch | Interior Design | Navneet K | Home product launch [ItQE L25 - 632, OtR V25 - 525] | 0.9256 | 2 |  | 0.4392
1 | ItQE | L25 | Interior Design | Navneet K | Home product launch [ItQE L25 - 632 options] | 0.5056 | 1 |  | 0.4392
1 | OtR | V25 | Interior Design | Navneet K | Home product launch [OtR V25 - 525 options] | 0.42 | 1
| Interior Design GFCs | ID-GFC | Interior Design | Navneet K | Interior Design GFCs [149 Nos] | 1.1602 | 149 | 46 | 0.44551
| Personalised | Personalised | Interior Design | Navneet K | Personalised [10 Nos] | 0.66198 | 10 | 2 | 0.20408
| E-Design | E-Design | Interior Design | Navneet K | E-Build, E-Design, Online [107 Nos] | 0.4982 | 107 | 39 | 0.24143
| Default | Default | Interior Design | Navneet K | Default [32 Nos] | 0 | 32 | 5
Note on E9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: L25 Options - 600 ¦ V25 Options - 900
Note on G9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: L25 Options - 600 ¦ V25 Options - 900

## 26Q1 Leaderwise (hidden)
2026 Q1 ¦ Design Goals + Billing |  |  |  |  | Billing [Cr.] | Pkgs
Project | Phase | Discipline | Design Lead | Description | 115.6801 | 402
Cijey M |  |  |  |  | 28.9833 | 32
ITQE-Ph1 | Ph 1 | Architecture | Cijey M | Design Packages - ITQE-Ph1 | 0 | 0
ITQE-Ph2a | Ph 2a | Architecture | Cijey M | Design Packages - ITQE-Ph2a | 0.25 | 2
ITQE-Ph2a | Ph 2a | Architecture | Cijey M | Master Plan ¦ Site Development | 0.07 | 1
ITQE-Ph2a | Ph 2a | Architecture | Cijey M | Experience Home + Project Experience [ V35 ] | 0.18 | 1
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | Design Packages - ITQE-Ph2b | 2.3754 | 4
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | ISS 5&6 ¦ Structural Slab 01 [Basement] | 0.3 | 1
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | ISS 7 ¦ Structrural Slab 01 [Basement] | 0.3 | 1
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | Master Plan ¦ Master Plan | 0.03 | 1
ITQE-Ph2b | Ph 2b | Architecture | Cijey M | L25 Default and it's variants | 1.7454 | 1
ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | Design Packages - ItQE-Ph2c [T9] | 0.30106 | 3
ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | ISS 9 ¦ Foundations & Grade Slab | 0.092092 | 1
ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | Tower 9 ¦ Foundation and Grade Slab | 0.1306 | 1
ItQE-Ph2c [T9] | Ph 2c | Architecture | Cijey M | Tower 9 ¦ Parking Level-Sub grade | 0.078362 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Design Packages - ItQE-Ph3a [T10-12 & 31 Villas] | 8.7814 | 3
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Pre Construction Set | 4.3907 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Experience Home + Project Experience | 2.1953 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Architecture | Cijey M | Marketing and Sales | 2.1953 | 1
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Design Packages - OTR-Ph01 | 0.96 | 5
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Individual Homes ¦ V25 Default & its Variant | 0.51 | 1
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Villa Block ¦ Building Envelope + Plot Development | 0.3 | 1
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Master Plan | 0.09 | 1
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Site Development | 0.03 | 1
OTR-Ph01 | Ph 1 | Architecture | Cijey M | Master Plan ¦ Site MEP | 0.03 | 1
MeenaSai Res | MS Res | Architecture | Cijey M | Design Packages - MeenaSai Res | 0.105 | 2
MeenaSai Res | MS Res | Architecture | Cijey M | LoD 200 - Schematic Concept | 0.063 | 1
MeenaSai Res | MS Res | Architecture | Cijey M | Approvals | 0.042 | 1
NH Homestay | NH HS | Architecture | Cijey M | Design Packages - NH Homestay | 0.77994 | 4
NH Homestay | NH HS | Architecture | Cijey M | LoD 300 - Pre Construction set | 0.12999 | 1
NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Foundation and Structure | 0.25998 | 1
NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Building Envelope + Plot Development | 0.19498 | 1
NH Homestay | NH HS | Architecture | Cijey M | LoD 350 - Interiors | 0.19498 | 1
OTR Museum | OTR Mus | Architecture | Cijey M | Design Packages - OTR Museum | 0.43996 | 2
OTR Museum | OTR Mus | Architecture | Cijey M | Design Brief | 0.17598 | 1
OTR Museum | OTR Mus | Architecture | Cijey M | LoD 200 - Schematic Concept | 0.26398 | 1
OTR-Ph02 | Ph 2 | Architecture | Cijey M | Design Packages - OTR-Ph02 | 1.18 | 3
OTR-Ph02 | Ph 2 | Architecture | Cijey M | Contract + Design Brief | 0.54 | 1
OTR-Ph02 | Ph 2 | Architecture | Cijey M | Schematic Concept | 0.43 | 1
OTR-Ph02 | Ph 2 | Architecture | Cijey M | Approvals | 0.21 | 1
Srjp - Res | Srjp - Res | Architecture | Cijey M | Design Packages - Srjp - Res | 13.8106 | 4
Srjp - Res | Srjp - Res | Architecture | Cijey M | Contract + Design Brief | 4.7746 | 1
Srjp - Res | Srjp - Res | Architecture | Cijey M | Schematic Concept | 4.364 | 1
Srjp - Res | Srjp - Res | Architecture | Cijey M | Approvals | 2.2847 | 1
Srjp - Res | Srjp - Res | Architecture | Cijey M | Experience Home + Project Experience | 2.3873 | 1
Saji A |  |  |  |  | 12.6556 | 45
AtR | Ph 1, 2a, 2b | Architecture | Saji A | Design Packages - AtR | 0.31538 | 2
AtR | Ph 1, 2a, 2b | Architecture | Saji A | Clubhouse + Amenities - Clubhouse—Interiors and Facilities | 0.27 | 1
AtR | Ph 1, 2a, 2b | Architecture | Saji A | Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] | 0.045377 | 1
AtR | Ph 2c | Architecture | Saji A | Design Packages - AtR | 0.081655 | 2
AtR | Ph 2c | Architecture | Saji A | Master Plan - Site MEP | 0.042238 | 1
AtR | Ph 2c | Architecture | Saji A | Clubhouse + Amenities - Sporting Facilities | 0.039416 | 1
AtR | Ph 3 | Architecture | Saji A | Design Packages - AtR | 1.8088 | 15
AtR | Ph 3 | Architecture | Saji A | Contract + Design brief | 0.27398 | 1
AtR | Ph 3 | Architecture | Saji A | Schematic Concept | 0.27398 | 1
AtR | Ph 3 | Architecture | Saji A | Approvals | 0.13699 | 1
AtR | Ph 3 | Architecture | Saji A | Pre Construction Set | 0.27398 | 1
AtR | Ph 3 | Architecture | Saji A | Home Products - V45 Default and it's variants | 0.36 | 1
AtR | Ph 3 | Architecture | Saji A | Villa Block 33 - Foundations and Sub-Grade Structure | 0.043983 | 1
AtR | Ph 3 | Architecture | Saji A | Villa Block 34 - Foundations and Sub-Grade Structure | 0.043983 | 1
AtR | Ph 3 | Architecture | Saji A | Villa Block 29 - Foundations and Sub-Grade Structure | 0.065974 | 1
AtR | Ph 3 | Architecture | Saji A | Villa Block 29 - Building Envelope + Plot Development | 0.065974 | 1
AtR | Ph 3 | Architecture | Saji A | Villa Block 30 - Foundations and Sub-Grade Structure | 0.065974 | 1
AtR | Ph 3 | Architecture | Saji A | Villa Block 30 - Building Envelope + Plot Development | 0.065974 | 1
AtR | Ph 3 | Architecture | Saji A | Villa Block 31 - Building Envelope + Plot Development | 0.014661 | 1
AtR | Ph 3 | Architecture | Saji A | Villa Block 32 - Building Envelope + Plot Development | 0.029322 | 1
AtR | Ph 3 | Architecture | Saji A | Villa Block 34 - Building Envelope + Plot Development | 0.043983 | 1
AtR | Ph 3 | Architecture | Saji A | Master Plan - Master Plan | 0.05 | 1
PoaRR-Res | Res | Architecture | Saji A | Design Packages - PoaRR-Res | 3.3659 | 8
PoaRR-Res | Res | Architecture | Saji A | Villa Cluster 3 - All Levels | 0.17 | 1
PoaRR-Res | Res | Architecture | Saji A | Villa Cluster 3 - Building Envelope and Common Areas | 0.17 | 1
PoaRR-Res | Res | Architecture | Saji A | V40 Default and it's variants | 1.18 | 1
PoaRR-Res | Res | Architecture | Saji A | ISS Building Envelope and Common Areas | 1.0659 | 1
PoaRR-Res | Res | Architecture | Saji A | Residential - Site Development | 0.45 | 1
PoaRR-Res | Res | Architecture | Saji A | Masterplan - Site MEP | 0.15 | 1
PoaRR-Res | Res | Architecture | Saji A | Masterplan - Landscaping | 0.15 | 1
PoaRR-Res | Res | Architecture | Saji A | Amenities & Facilities - Sporting Facilities | 0.03 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Design Packages - PoaRR-T08 | 7.0838 | 18
PoaRR-T08 | T08 | Architecture | Saji A | ISS - Foundations & Grade Slab | 0.2 | 1
PoaRR-T08 | T08 | Architecture | Saji A | ISS - Parking Level Subgrade | 0.41 | 1
PoaRR-T08 | T08 | Architecture | Saji A | ISS - Podium Slab | 0.61 | 1
PoaRR-T08 | T08 | Architecture | Saji A | ISS - Building Envelope and Common Areas | 0.82 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Habitable Level 01 | 0.48 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Building Envelope and Common Areas [Typical Tower Levels] | 0.96385 | 1
PoaRR-T08 | T08 | Architecture | Saji A | L22 Default | 0.52 | 1
PoaRR-T08 | T08 | Architecture | Saji A | L20 Default [Modification for Dry Wall] | 0.52 | 1
PoaRR-T08 | T08 | Architecture | Saji A | D35 Default [Modification for Dry Wall] | 0.52 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Master Plan | 0.17 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Penthouse Levels | 0.48 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Terrace Level | 0.24 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Building Envelope and Common Areas [Penthouse Levels And Terrace Level] | 0.96 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Landscape | 0.03 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Site MEP | 0.03 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Clubhouse—Outdoor Spaces and Pool | 0.015 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Community spaces [Board Walk, Children play area] | 0.015 | 1
PoaRR-T08 | T08 | Architecture | Saji A | Site Development | 0.1 | 1
TR Mills | TR Mills | Architecture | Saji A | Design Packages - TR Mills | 0 | 0
Naveen Y |  |  |  |  | 23.4324 | 24
AtR - C | Com | Architecture | Naveen Y | Design Packages - AtR - C | 0.36421 | 3
AtR - C | Com | Architecture | Naveen Y | Master Plan - Site Development | 0.13658 | 1
AtR - C | Com | Architecture | Naveen Y | Master Plan - Site MEP | 0.18211 | 1
AtR - C | Com | Architecture | Naveen Y | Master Plan - Landscaping | 0.045527 | 1
Imagine Campus | Imgn | Architecture | Naveen Y | Design Packages - Imagine Campus | 1.61 | 3
Imagine Campus | Imgn | Architecture | Naveen Y | Design Brief | 0.46 | 1
Imagine Campus | Imgn | Architecture | Naveen Y | LoD 200 - Schematic Concept | 0.69 | 1
Imagine Campus | Imgn | Architecture | Naveen Y | Approvals | 0.46 | 1
TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Design Packages - TMFT-Ph 3 | 0.6182 | 3
TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Contract + Design Brief | 0.24728 | 1
TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Schematic Concept | 0.24728 | 1
TMFT-Ph 3 | Ph 3 | Architecture | Naveen Y | Approvals | 0.12364 | 1
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Design Packages - Srjp - C - NB | 3.6844 | 3
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Contract + Design Brief | 1.2281 | 1
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Schematic Concept | 1.2281 | 1
Srjp - C - NB | Srjp - C - NB | Architecture | Naveen Y | Approvals | 1.2281 | 1
OTF | OTF | Architecture | Naveen Y | Design Packages - OTF | 2.7525 | 6
OTF | OTF | Master Planning | Naveen Y | Contract + Design Brief [Commercial] | 0.3375 | 1
OTF | OTF | Master Planning | Naveen Y | Schematic Concept | 0.58 | 1
OTF | OTF | Master Planning | Naveen Y | Approvals | 0.58 | 1
OTF | OTF | Master Planning | Naveen Y | Pre Construction Set | 0.58 | 1
OTF | OTF | Master Planning | Naveen Y | Marketing and Sales | 0.3375 | 1
OTF | OTF | Master Planning | Naveen Y | Experience Home + Project Entrance | 0.3375 | 1
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Design Packages - Srjp - C - SB | 11.0531 | 3
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Contract + Design Brief | 3.6844 | 1
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Schematic Concept | 3.6844 | 1
Srjp - C - SB | Srjp - C - SB | Architecture | Naveen Y | Approvals | 3.6844 | 1
DonaPaula | DP | Architecture | Naveen Y | Design Packages - DonaPaula | 3.35 | 3
DonaPaula | DP | Architecture | Naveen Y | Schematic Concept .v7 [Rework] | 1.34 | 1
DonaPaula | DP | Architecture | Naveen Y | Preconstruction | 1.34 | 1
DonaPaula | DP | Architecture | Naveen Y | Approvals | 0.67 | 1
Om Prakash |  |  |  |  | 10.2095 | 35
TuiG | TuiG | Architecture | Om Prakash | Design Packages - TuiG | 0.30955 | 2
TuiG | TuiG | Architecture | Om Prakash | Clubhouse—Outdoor Spaces and Pool | 0.15478 | 1
TuiG | TuiG | Architecture | Om Prakash | Community spaces [Board Walk, Children play area] | 0.15478 | 1
DBTW | DBTW | Architecture | Om Prakash | Design Packages - DBTW | 5.878 | 10
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site Development | 0.22115 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Site MEP | 0.073717 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Master Plan - Landscaping | 0.073717 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Tower 06 - Foundation and Grade Slab | 0.064032 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Foundations & Grade Slab | 0.54995 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - ISS - Podium Slab | 0.27497 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I20 Default and it's variants | 2.2352 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Home Products - I25 Default and it's variants | 2.2352 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Structure and Envelope | 0.1125 | 1
DBTW | DBTW | Architecture | Om Prakash | LoD 350 - Clubhouse—Outdoor Spaces and Pool | 0.0375 | 1
SftW | SftW | Architecture | Om Prakash | Design Packages - SftW | 0.85178 | 9
SftW | SftW | Architecture | Om Prakash | ISS 01 - Podium Slab | 0.25575 | 1
SftW | SftW | Architecture | Om Prakash | Clubhouse—Structure and Envelope | 0.081564 | 1
SftW | SftW | Architecture | Om Prakash | Master Plan - Master Plan | 0.18697 | 1
SftW | SftW | Architecture | Om Prakash | Clubhouse—Outdoor Spaces and Pool | 0.027188 | 1
SftW | SftW | Architecture | Om Prakash | Master Plan - Site Development | 0.11218 | 1
SftW | SftW | Architecture | Om Prakash | Master Plan - Site MEP | 0.037394 | 1
SftW | SftW | Architecture | Om Prakash | Master Plan - Landscaping | 0.037394 | 1
SftW | SftW | Architecture | Om Prakash | Clubhouse + Amenities - Sporting Facilities | 0.027188 | 1
SftW | SftW | Architecture | Om Prakash | Tower 02 - Terrace Level | 0.086149 | 1
LGCE Campus | LGCE Campus | Architecture | Om Prakash | Design Packages - LGCE Campus | 0.38042 | 2
LGCE Campus | LGCE Campus | Architecture | Om Prakash | Design Brief | 0.15217 | 1
LGCE Campus | LGCE Campus | Architecture | Om Prakash | LoD 200 - Schematic Concept | 0.22825 | 1
Srjp - Res | Srjp - Res | Architecture | Om Prakash | Design Packages - Srjp - Res | 0.51325 | 2
Srjp - Res | Srjp - Res | Architecture | Om Prakash | CH - Schematic Concept | 0.4106 | 1
Srjp - Res | Srjp - Res | Architecture | Om Prakash | CH - Approvals | 0.10265 | 1
OTF | OTF | Architecture | Om Prakash | Design Packages - OTF | 0.285 | 3
OTF | OTF | Architecture | Om Prakash | Schematic Concept - CH | 0.095 | 1
OTF | OTF | Architecture | Om Prakash | Approvals - CH | 0.095 | 1
OTF | OTF | Architecture | Om Prakash | Pre Construction set - CH | 0.095 | 1
Harohalli [Plotted] | Ph 1 | Architecture | Om Prakash | Design Packages - Harohalli [Plotted] | 0 | 0
Shreegaon [70a] | Ph 1 | Architecture | Om Prakash | Design Packages - Shreegaon [70a] | 0.089136 | 1
Shreegaon [70a] | Ph 1 | Architecture | Om Prakash | Schematic Concept | 0.089136 | 1
Violet hill | Ph 1 | Architecture | Om Prakash | Design Packages - Violet hill | 0.058217 | 1
Violet hill | Ph 1 | Architecture | Om Prakash | Schematic Concept | 0.058217 | 1
Ambegaon | Ph 1 | Architecture | Om Prakash | Design Packages - Ambegaon | 0 | 0
Mall of Asia | Mall of Asia | Architecture | Om Prakash | Design Packages - Mall of Asia | 1.6141 | 1
Mall of Asia | Mall of Asia | Architecture | Om Prakash | Contract + Design Brief | 1.6141 | 1
OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Design Packages - OTR-Ph02 | 0.17 | 2
OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Schematic Concept - CH | 0.11 | 1
OTR-Ph02 | Ph 2 | Architecture | Om Prakash | Approvals - CH | 0.06 | 1
DonaPaula | DP | Architecture | Om Prakash | Design Packages - DonaPaula | 0.06 | 2
DonaPaula | DP | Architecture | Om Prakash | LoD 200 - Schematic Concept - CH | 0.03 | 1
DonaPaula | DP | Architecture | Om Prakash | LoD 300 - Pre Construction set - CH | 0.03 | 1
Manik G |  |  |  |  | 0.8528 | 15
Ooty Res | Ooty Res | Architecture | Manik G | Design Packages - Ooty Res | 0 | 0
MT Plano | MT Plano | Architecture | Manik G | Design Packages - MT Plano | 0.69535 | 8
MT Plano | MT Plano | Architecture | Manik G | Design Brief | 0.15626 | 1
MT Plano | MT Plano | Architecture | Manik G | LoD 200 - Schematic Concept | 0.23439 | 1
MT Plano | MT Plano | Architecture | Manik G | Approvals | 0.15626 | 1
MT Plano | MT Plano | Architecture | Manik G | LoD 200 - Schematic Concept | 0.071432 | 1
MT Plano | MT Plano | Architecture | Manik G | LoD 200 - Schematic Concept | 0.02009 | 1
MT Plano | MT Plano | Architecture | Manik G | Approvals | 0.02009 | 1
MT Plano | MT Plano | Architecture | Manik G | LoD 200 - Schematic Concept | 0.016742 | 1
MT Plano | MT Plano | Architecture | Manik G | Approvals | 0.02009 | 1
Indiranagar Res | Indiranagar Res | Architecture | Manik G | Design Packages - Indiranagar Res | 0.004 | 4
Indiranagar Res | Indiranagar Res | Architecture | Manik G | LoD 350 - Block A - Interiors | 0.0021 | 1
Indiranagar Res | Indiranagar Res | Architecture | Manik G | LoD 350 - Block B - Interiors | 0.000875 | 1
Indiranagar Res | Indiranagar Res | Architecture | Manik G | LoD 350 - Block C - Interiors | 0.000525 | 1
Indiranagar Res | Indiranagar Res | Architecture | Manik G | LoD 350 -Block C - Building Envelope + Plot Development | 0.0005 | 1
OTR OOTA | OTR OOTA | Architecture | Manik G | Design Packages - OTR OOTA | 0.15346 | 3
OTR OOTA | OTR OOTA | Architecture | Manik G | Design Brief | 0.043845 | 1
OTR OOTA | OTR OOTA | Architecture | Manik G | LoD 200 - Schematic Concept | 0.065768 | 1
OTR OOTA | OTR OOTA | Architecture | Manik G | Approvals | 0.043845 | 1
Atul L |  |  |  |  | 0 | 11
TuiG | FKH | Architecture | Atul L | TuiG [M20, M30 and M40] |  | 3
Harohalli | FKH | Architecture | Atul L | Harohalli [M30, M40 and V50] |  | 3
Violet Hill | FKH | Architecture | Atul L | Violet Hill [Product?] |  | 2
Shreegaon | FKH | Architecture | Atul L | Shreegaon [V50] |  | 1
OTF | FKH | Architecture | Atul L | One Tiny Flower [V50 D and V50 U] |  | 2
Prakash C |  |  |  |  | 20.872 | 113
AtR | Ph 1, 2a, 2b | Structural | Prakash C | Design Packages - AtR | 0.0052867 | 1
AtR | Ph 1, 2a, 2b | Structural | Prakash C | Clubhouse + Amenities - Community spaces [Staff Lounge, Children play area] | 0.0052867 | 1
AtR | Ph 2c | Structural | Prakash C | Design Packages - AtR | 0.016064 | 2
AtR | Ph 2c | Structural | Prakash C | Master Plan - Site MEP | 0.010861 | 1
AtR | Ph 2c | Structural | Prakash C | Clubhouse + Amenities - Sporting Facilities | 0.0052029 | 1
AtR | Ph 3 | Structural | Prakash C | Design Packages - AtR | 0.35597 | 15
AtR | Ph 3 | Structural | Prakash C | Schematic Concept | 0.093422 | 1
AtR | Ph 3 | Structural | Prakash C | Pre Construction Set | 0.093422 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Foundations and Sub-Grade Structure | 0.021107 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Super Structure | 0.03166 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 29 - Building Envelope + Plot Development | 0.0052767 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Foundations and Sub-Grade Structure | 0.021107 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Super Structure | 0.03166 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 30 - Building Envelope + Plot Development | 0.0052767 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Foundations and Sub-Grade Structure | 0.004 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Super Structure | 0.007 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 31 - Building Envelope + Plot Development | 0.001 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 32 - Building Envelope + Plot Development | 0.0023452 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Foundations and Sub-Grade Structure | 0.014071 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Super Structure | 0.021107 | 1
AtR | Ph 3 | Structural | Prakash C | Villa Block 34 - Building Envelope + Plot Development | 0.0035178 | 1
AtR - C | Com | Structural | Prakash C | Design Packages - AtR - C | 0.4139 | 4
AtR - C | Com | Structural | Prakash C | Tower-[Commercial] - Habitable Level 1-2 | 0.12911 | 1
AtR - C | Com | Structural | Prakash C | Tower-[Commercial] - Habitable Level 3-5 | 0.25823 | 1
AtR - C | Com | Structural | Prakash C | Master Plan - Site Development | 0.014486 | 1
AtR - C | Com | Structural | Prakash C | Master Plan - Site MEP | 0.012072 | 1
PoaRR-Res | Res | Structural | Prakash C | Design Packages - PoaRR-Res | 0.36 | 3
PoaRR-Res | Res | Structural | Prakash C | Site Development | 0.19 | 1
PoaRR-Res | Res | Structural | Prakash C | Site MEP | 0.16 | 1
PoaRR-Res | Res | Structural | Prakash C | Sporting Facilities | 0.01 | 1
PoaRR-T08 | T08 | Structural | Prakash C | Design Packages - PoaRR-T08 | 2.1 | 8
PoaRR-T08 | T08 | Structural | Prakash C | Penthouse Levels | 0.2 | 1
PoaRR-T08 | T08 | Structural | Prakash C | Terrace Level | 0.4 | 1
PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Foundations & Grade Slab | 0.32 | 1
PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Podium Slab | 0.32 | 1
PoaRR-T08 | T08 | Structural | Prakash C | T08 - ISS - Parking Level Subgrade | 0.43 | 1
PoaRR-T08 | T08 | Structural | Prakash C | Site Development | 0.02 | 1
PoaRR-T08 | T08 | Structural | Prakash C | Site MEP | 0.01 | 1
PoaRR-T08 | T08 | Structural | Prakash C | STR Package Release [Parking level subgrade] | 0.4 | 1
ITQE-Ph1 | Ph 1 | Structural | Prakash C | Design Packages - ITQE-Ph1 | 0.084072 | 3
ITQE-Ph1 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site Development | 0.060249 | 1
ITQE-Ph1 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Clubhouse—Outdoor Spaces and Pool | 0.011912 | 1
ITQE-Ph1 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Community spaces | 0.011912 | 1
ITQE-Ph2a | Ph 2a | Structural | Prakash C | Design Packages - ITQE-Ph2a | 0.16919 | 3
ITQE-Ph2a | Ph 2a | Structural | Prakash C | Experience Home + Project Experience [ V35 ] | 0.07 | 1
ITQE-Ph2a | Ph 2a | Structural | Prakash C | Master Plan ¦ Site Development | 0.054104 | 1
ITQE-Ph2a | Ph 2a | Structural | Prakash C | Master Plan ¦ Site MEP | 0.045086 | 1
ITQE-Ph2b | Ph 2b | Structural | Prakash C | Design Packages - ITQE-Ph2b | 1.12 | 11
ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 05 ¦ Habitable Level - Even | 0.07 | 1
ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 05 ¦ Habitable Level - Odd | 0.07 | 1
ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 06 ¦ Habitable Level - Even | 0.07 | 1
ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 06 ¦ Habitable Level - Odd | 0.07 | 1
ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 07 ¦ Habitable Level - Even | 0.07 | 1
ITQE-Ph2b | Ph 2b | Structural | Prakash C | Tower 07 ¦ Habitable Level - Odd | 0.07 | 1
ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS5&6 ¦ Structrural Slab 01 [Basement] | 0.13 | 1
ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Foundations & Sub¦Grade | 0.18 | 1
ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Structrural Slab 01 [Basement] | 0.13 | 1
ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS5&6 ¦ Podium Slab | 0.13 | 1
ITQE-Ph2b | Ph 2b | Structural | Prakash C | ISS 7 ¦ Podium Slab | 0.13 | 1
ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | Design Packages - ItQE-Ph2c [T9] | 0.2848 | 4
ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | ISS 9 ¦ Earthwork | 0.0097618 | 1
ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | ISS 9 ¦ Foundations & Grade Slab | 0.039047 | 1
ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | Tower 9 ¦ Foundation and Grade Slab | 0.118 | 1
ItQE-Ph2c [T9] | Ph 2c | Structural | Prakash C | Tower 9 ¦ Parking Level-Sub grade | 0.118 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | Design Packages - ItQE-Ph3a [T10-12 & 31 Villas] | 3.2579 | 2
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | Schematic Concept | 1.3962 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Structural | Prakash C | Pre Construction Set | 1.8617 | 1
ITQE-T05 | T05 | Structural | Prakash C | Design Packages - ITQE-T05 | 0 | 0
OTR-Ph01 | Ph 1 | Structural | Prakash C | Design Packages - OTR-Ph01 | 0.38 | 5
OTR-Ph01 | Ph 1 | Structural | Prakash C | Experience Home + Project Experience | 0.08 | 1
OTR-Ph01 | Ph 1 | Structural | Prakash C | Villa Block ¦ Super Structure | 0.17 | 1
OTR-Ph01 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site Development | 0.03 | 1
OTR-Ph01 | Ph 1 | Structural | Prakash C | Master Plan ¦ Site MEP | 0.03 | 1
OTR-Ph01 | Ph 1 | Structural | Prakash C | Amenities & Facilities ¦ Community spaces [Board Walk, Children play area] | 0.07 | 1
TuiG | TuiG | Structural | Prakash C | Design Packages - TuiG | 0.80073 | 4
TuiG | TuiG | Structural | Prakash C | Site Development | 0.40295 | 1
TuiG | TuiG | Structural | Prakash C | Site MEP | 0.33579 | 1
TuiG | TuiG | Structural | Prakash C | Clubhouse—Outdoor Spaces and Pool | 0.030991 | 1
TuiG | TuiG | Structural | Prakash C | Community spaces [Board Walk, Children play area] | 0.030991 | 1
TMFT-Ph 2 | Ph 2 | Structural | Prakash C | Design Packages - TMFT-Ph 2 | 0.03 | 1
TMFT-Ph 2 | Ph 2 | Structural | Prakash C | LoD 350 - Site Development | 0.03 | 1
DBTW | DBTW | Structural | Prakash C | Design Packages - DBTW | 3.6358 | 15
DBTW | DBTW | Structural | Prakash C | LoD 300 - Pre Construction Set [Podium] | 2.2512 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - ISS - Foundations & Grade Slab | 0.52958 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-1-Habitable Level - Even | 0.025613 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level 01 | 0.10834 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-2-Habitable Level - Even | 0.05417 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level 01 | 0.10834 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-3-Habitable Level - Even | 0.05417 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level 01 | 0.10834 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-4-Habitable Level - Even | 0.05417 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level 01 | 0.10834 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower-5-Habitable Level - Even | 0.05417 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Foundation and Grade Slab | 0.051226 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Parking Level-Sub grade | 0.051226 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level 01 | 0.051226 | 1
DBTW | DBTW | Structural | Prakash C | LoD 350 - Tower 06-Habitable Level - Even | 0.025613 | 1
SftW | SftW | Structural | Prakash C | Design Packages - SftW | 0.34546 | 6
SftW | SftW | Structural | Prakash C | Tower 2 - Terrace Level | 0.20116 | 1
SftW | SftW | Structural | Prakash C | Master Plan - Site Development | 0.058457 | 1
SftW | SftW | Structural | Prakash C | Master Plan - Site MEP | 0.048714 | 1
SftW | SftW | Structural | Prakash C | Clubhouse—Structure and Envelope | 0.025989 | 1
SftW | SftW | Structural | Prakash C | Clubhouse—Outdoor Spaces and Pool | 0.0037128 | 1
SftW | SftW | Structural | Prakash C | Clubhouse—Sporting Facilities | 0.0074255 | 1
LGCE Campus | LGCE Campus | Structural | Prakash C | Design Packages - LGCE Campus | 0 | 0
Ooty Res | Ooty Res | Structural | Prakash C | Design Packages - Ooty Res | 0 | 0
MT Plano | MT Plano | Structural | Prakash C | Design Packages - MT Plano | 0 | 0
MeenaSai Res | MS Res | Structural | Prakash C | Design Packages - MeenaSai Res | 0.0192 | 1
MeenaSai Res | MS Res | Structural | Prakash C | LoD 200 - Schematic Concept | 0.0192 | 1
NH Homestay | NH HS | Structural | Prakash C | Design Packages - NH Homestay | 0.22284 | 3
NH Homestay | NH HS | Structural | Prakash C | LoD 300 - Pre Construction set | 0.059424 | 1
NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Foundation and Structure | 0.14856 | 1
NH Homestay | NH HS | Structural | Prakash C | LoD 350 - Building Envelope + Plot Development | 0.014856 | 1
OTR Museum | OTR Mus | Structural | Prakash C | Design Packages - OTR Museum | 0 | 0
KIADB - Mys | KIADB - Mys | Structural | Prakash C | Design Packages - KIADB - Mys | 0 | 1
KIADB - Mys | KIADB - Mys | Structural | Prakash C | LoD 200 - Schematic Concept |  | 1
Imagine Campus | Imgn | Structural | Prakash C | Design Packages - Imagine Campus | 0.19 | 1
Imagine Campus | Imgn | Structural | Prakash C | LoD 200 - Schematic Concept | 0.19 | 1
OTR-Ph02 | Ph 2 | Structural | Prakash C | Design Packages - OTR-Ph02 | 0.17172 | 1
OTR-Ph02 | Ph 2 | Structural | Prakash C | Schematic Concept | 0.17172 | 1
TMFT-Ph 3 | Ph 3 | Structural | Prakash C | Design Packages - TMFT-Ph 3 | 0.078635 | 1
TMFT-Ph 3 | Ph 3 | Structural | Prakash C | Schematic Concept | 0.078635 | 1
Srjp - Res | Srjp - Res | Structural | Prakash C | Design Packages - Srjp - Res | 2.0244 | 2
Srjp - Res | Srjp - Res | Structural | Prakash C | Schematic Concept | 1.5183 | 1
Srjp - Res | Srjp - Res | Structural | Prakash C | Experience Home + Project Experience | 0.50611 | 1
Srjp - C - SB | Srjp - C - SB | Structural | Prakash C | Design Packages - Srjp - C - SB | 1.5622 | 1
Srjp - C - SB | Srjp - C - SB | Structural | Prakash C | Schematic Concept | 1.5622 | 1
Srjp - C - NB | Srjp - C - NB | Structural | Prakash C | Design Packages - Srjp - C - NB | 0.52073 | 1
Srjp - C - NB | Srjp - C - NB | Structural | Prakash C | Schematic Concept | 0.52073 | 1
OTF | OTF | Structural | Prakash C | Design Packages - OTF | 0.5724 | 3
OTF | OTF | Structural | Prakash C | Schematic Concept | 0.1431 | 1
OTF | OTF | Structural | Prakash C | Pre Construction Set | 0.2862 | 1
OTF | OTF | Structural | Prakash C | Project Experience | 0.1431 | 1
Harohalli [Plotted] | Ph 1 | Structural | Prakash C | Design Packages - Harohalli [Plotted] | 0.72504 | 2
Harohalli [Plotted] | Ph 1 | Structural | Prakash C | Schematic Concept | 0.36252 | 1
Harohalli [Plotted] | Ph 1 | Structural | Prakash C | Project Experience | 0.36252 | 1
Shreegaon [70a] | Ph 1 | Structural | Prakash C | Design Packages - Shreegaon [70a] | 0.20034 | 1
Shreegaon [70a] | Ph 1 | Structural | Prakash C | Schematic Concept | 0.20034 | 1
Violet hill | Ph 1 | Structural | Prakash C | Design Packages - Violet hill | 0.57471 | 4
Violet hill | Ph 1 | Structural | Prakash C | Schematic Concept | 0.12908 | 1
Violet hill | Ph 1 | Structural | Prakash C | Pre Construction Set | 0.25817 | 1
Violet hill | Ph 1 | Structural | Prakash C | Project Experience | 0.12908 | 1
Violet hill | Ph 1 | Structural | Prakash C | Structures - Security Cabin and Entrance [Rework] | 0.058371 | 1
Ambegaon | Ph 1 | Structural | Prakash C | Design Packages - Ambegaon | 0 | 0
Mall of Asia | Mall of Asia | Structural | Prakash C | Design Packages - Mall of Asia | 0 | 0
TR Mills | TR Mills | Structural | Prakash C | Design Packages - TR Mills | 0 | 0
Indiranagar Res | Indrng Res | Structural | Prakash C | Design Packages - Indiranagar Res | 0.0008 | 1
Indiranagar Res | Indrng Res | Structural | Prakash C | LoD 350 -Block C - Building Envelope + Plot Development | 0.0008 | 1
OTR OOTA | OTR OOTA | Structural | Prakash C | Design Packages - OTR OOTA | 0.020044 | 1
OTR OOTA | OTR OOTA | Structural | Prakash C | LoD 200 - Schematic Concept | 0.020044 | 1
DonaPaula | DP | Structural | Prakash C | Design Packages - DonaPaula | 0.62985 | 2
DonaPaula | DP | Structural | Prakash C | Schematic Concept .v7 [Rework] | 0.26985 | 1
DonaPaula | DP | Structural | Prakash C | Preconstruction | 0.36 | 1
Gaganjit S |  |  |  |  | 18.6746 | 127
AtR | Ph 2c | MEP | Gaganjit S | Design Packages - AtR | 0.014337 | 1
AtR | Ph 2c | MEP | Gaganjit S | Master Plan - Site MEP | 0.014337 | 1
AtR | Ph 3 |  | Gaganjit S | Design Packages - AtR | 0.36573 | 12
AtR | Ph 3 | MEP | Gaganjit S | Schematic Concept [V80] | 0.0215 | 1
AtR | Ph 3 | MEP | Gaganjit S | PreConstruction Set | 0.0215 | 1
AtR | Ph 3 | MEP | Gaganjit S | Villa Block 31 - Foundations and Sub-Grade Structure | 0.00094245 | 1
AtR | Ph 3 | MEP | Gaganjit S | Villa Block 32 - Foundations and Sub-Grade Structure | 0.0018849 | 1
AtR | Ph 3 | MEP | Gaganjit S | Villa Block 34 - Foundations and Sub-Grade Structure | 0.0028274 | 1
AtR | Ph 3 | MEP | Gaganjit S | Home Products - V45 Default and it's variants | 0.10495 | 1
AtR | Ph 3 | MEP | Gaganjit S | Master Plan - Master Plan | 0.04 | 1
AtR | Ph 3 | Landscape | Gaganjit S | Schematic Concept | 0.047864 | 1
AtR | Ph 3 | Landscape | Gaganjit S | Preconstruction Set | 0.047864 | 1
AtR | Ph 3 | Landscape | Gaganjit S | Home Products - V45 Default | 0.046405 | 1
AtR | Ph 3 | Landscape | Gaganjit S | Master Plan | 0.02 | 1
AtR | Ph 3 | Landscape | Gaganjit S | Site Development - 06 Landscape | 0.01 | 1
AtR - C | Com |  | Gaganjit S | Design Packages - AtR - C | 0.16751 | 2
AtR - C | Com | MEP | Gaganjit S | Master Plan - Master Plan | 0.038655 | 1
AtR - C | Com | MEP | Gaganjit S | Master Plan - Site MEP | 0.12885 | 1
PoaRR-Res | Res |  | Gaganjit S | Design Packages - PoaRR-Res | 0.40327 | 4
PoaRR-Res | Res | MEP | Gaganjit S | Site MEP | 0.36 | 1
PoaRR-Res | Res | MEP | Gaganjit S | Clubhouse Outdoor Spaces and Pool | 0.002183 | 1
PoaRR-Res | Res | MEP | Gaganjit S | Sporting Facilities | 0.0010915 | 1
PoaRR-Res | Res | Landscape | Gaganjit S | Amenities & Facilities - Community spaces [Sporting Facilities] | 0.04 | 1
PoaRR-T08 | T08 |  | Gaganjit S | Design Packages - PoaRR-T08 | 0.14 | 3
PoaRR-T08 | T08 | MEP | Gaganjit S | ISS - Foundation and Gradeslab | 0.02 | 1
PoaRR-T08 | T08 | MEP | Gaganjit S | L20 Default and it's variants | 0.06 | 1
PoaRR-T08 | T08 | MEP | Gaganjit S | D35 Default and it's variants | 0.06 | 1
ITQE-Ph2b | Ph 2b |  | Gaganjit S | Design Packages - ITQE-Ph2b | 0.031656 | 2
ITQE-Ph2b | Ph 2b | MEP | Gaganjit S | ISS -5 & 6 ¦ Structrural Slab 01 [Basement] | 0.015828 | 1
ITQE-Ph2b | Ph 2b | MEP | Gaganjit S | ISS -7 ¦ Structrural Slab 01 [Basement] | 0.015828 | 1
ItQE-Ph2c [T9] | Ph 2c |  | Gaganjit S | Design Packages - ItQE-Ph2c [T9] | 0.047123 | 2
ItQE-Ph2c [T9] | Ph 2c | MEP | Gaganjit S | ISS 9 ¦ Foundations & Grade Slab | 0.0163 | 1
ItQE-Ph2c [T9] | Ph 2c | MEP | Gaganjit S | Tower 9 ¦ Foundation and Grade Slab | 0.030822 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a |  | Gaganjit S | Design Packages - ItQE-Ph3a [T10-12 & 31 Villas] | 2.1646 | 5
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Schematic Concept | 0.5181 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Pre Construction Set | 0.5181 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | MEP | Gagan | Experience Home + Project Experience | 0.25905 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Landscape | Gagan | Schematic Concept | 0.43468 | 1
ItQE-Ph3a [T10-12 & 31 Villas] | Ph 3a | Landscape | Gagan | Pre Construction Set | 0.43468 | 1
OTR-Ph01 | Ph 1 |  | Gaganjit S | Design Packages - OTR-Ph01 | 0.04 | 1
OTR-Ph01 | Ph 1 | MEP | Gaganjit S | Master Plan ¦ Site MEP | 0.04 | 1
TuiG | TuiG |  | Gaganjit S | Design Packages - TuiG | 0.32421 | 4
TuiG | TuiG | MEP | Gagan | Clubhouse—Structure and Envelope | 0.17351 | 1
TuiG | TuiG | MEP | Gagan | Clubhouse—Outdoor Spaces and Pool | 0.049574 | 1
TuiG | TuiG | MEP | Gagan | Sporting Facilities | 0.02 | 1
TuiG | TuiG | Landscape | Gagan | Community spaces [Board Walk, Children play area] | 0.081128 | 1
DBTW | DBTW |  | Gaganjit S | Design Packages - DBTW | 0.036853 | 1
DBTW | DBTW | MEP | Gaganjit S | LoD 350 - Master Plan- Master Plan | 0.036853 | 1
SftW | SftW |  | Gaganjit S | Design Packages - SftW | 0.021398 | 2
SftW | SftW | MEP | Gaganjit S | MEP ¦ Master Plan - Site MEP | 0.020843 | 1
SftW | SftW | MEP | Gaganjit S | MEP ¦ Clubhouse—Sporting Facilities | 0.00055534 | 1
LGCE Campus | LGCE Campus |  | Gaganjit S | Design Packages - LGCE Campus | 0 | 0
Ooty Res | Ooty Res |  | Gaganjit S | Design Packages - Ooty Res | 0 | 0
MT Plano | MT Plano |  | Gaganjit S | Design Packages - MT Plano | 0 | 0
MeenaSai Res | MS Res |  | Gaganjit S | Design Packages - MeenaSai Res | 0.0168 | 3
MeenaSai Res | MS Res | MEP | Gagan | LoD 200 - Schematic Concept | 0.0054 | 1
MeenaSai Res | MS Res | MEP | Gagan | Approvals | 0.0054 | 1
MeenaSai Res | MS Res | Landscape | Gagan | LoD 200 - Schematic Concept | 0.006 | 1
NH Homestay | NH HS |  | Gaganjit S | Design Packages - NH Homestay | 0.23027 | 8
NH Homestay | NH HS | MEP | Gagan | Approvals | 0.016713 | 1
NH Homestay | NH HS | MEP | Gagan | LoD 300 - Pre Construction set | 0.016713 | 1
NH Homestay | NH HS | MEP | Gagan | LoD 350 - Foundation and Structure | 0.058495 | 1
NH Homestay | NH HS | MEP | Gagan | LoD 350 - Building Envelope + Plot Development | 0.025069 | 1
NH Homestay | NH HS | MEP | Gagan | LoD 350 - Interiors | 0.025069 | 1
NH Homestay | NH HS | Landscape | Gagan | LoD 200 - Schematic Concept | 0.01857 | 1
NH Homestay | NH HS | Landscape | Gagan | LoD 300 - Pre Construction set | 0.01857 | 1
NH Homestay | NH HS | Landscape | Gagan | LoD 350 - Building Envelope + Plot Development | 0.051068 | 1
Indiranagar Res | Indrng Res |  | Gaganjit S | Design Packages - Indiranagar Res | 0.000113 | 1
Indiranagar Res | Indrng Res | Landscape | Gagan | LoD 350 - Block C- Building Envelope + Plot Development | 0.000113 | 1
OTR Museum | OTR Mus |  | Gaganjit S | Design Packages - OTR Museum | 0 | 0
KIADB - Mys | KIADB - Mys |  | Gaganjit S | Design Packages - KIADB - Mys | 0 | 7
KIADB - Mys | KIADB - Mys | Master Planning | Gagan | Contract + Design Brief |  | 1
KIADB - Mys | KIADB - Mys | Master Planning | Gagan | LoD 200 - Schematic Concept |  | 1
KIADB - Mys | KIADB - Mys | Master Planning | Gagan | Approvals |  | 1
KIADB - Mys | KIADB - Mys | MEP | Gagan | LoD 200 - Schematic Concept |  | 1
KIADB - Mys | KIADB - Mys | MEP | Gagan | Approvals |  | 1
KIADB - Mys | KIADB - Mys | Landscape | Gagan | LoD 200 - Schematic Concept |  | 1
KIADB - Mys | KIADB - Mys | Landscape | Gagan | Approvals |  | 1
Imagine Campus | Imgn |  | Gaganjit S | Design Packages - Imagine Campus | 0.15 | 3
Imagine Campus | Imgn | MEP | Gagan | LoD 200 - Schematic Concept | 0.05 | 1
Imagine Campus | Imgn | MEP | Gagan | Approvals | 0.05 | 1
Imagine Campus | Imgn | Landscape | Gagan | Approvals | 0.05 | 1
OTR-Ph02 | Ph 2 |  | Gaganjit S | Design Packages - OTR-Ph02 | 0.16686 | 4
OTR-Ph02 | Ph 2 | MEP | Gaganjit S | Schematic Concept | 0.06372 | 1
OTR-Ph02 | Ph 2 | MEP | Gaganjit S | Approvals | 0.03186 | 1
OTR-Ph02 | Ph 2 | Landscape | Gaganjit S | Schematic Concept | 0.05346 | 1
OTR-Ph02 | Ph 2 | Landscape | Gaganjit S | Approvals | 0.01782 | 1
TMFT-Ph 3 | Ph 3 |  | Gaganjit S | Design Packages - TMFT-Ph 3 | 0.07641 | 4
TMFT-Ph 3 | Ph 3 | MEP | Gaganjit S | Schematic Concept | 0.029179 | 1
TMFT-Ph 3 | Ph 3 | MEP | Gaganjit S | Approvals | 0.01459 | 1
TMFT-Ph 3 | Ph 3 | Landscape | Gaganjit S | Schematic Concept | 0.024481 | 1
TMFT-Ph 3 | Ph 3 | Landscape | Gaganjit S | Approvals | 0.0081602 | 1
Srjp - Res | Srjp - Res |  | Gaganjit S | Design Packages - Srjp - Res | 1.7571 | 5
Srjp - Res | Srjp - Res | MEP | Gaganjit S | Schematic Concept | 0.5634 | 1
Srjp - Res | Srjp - Res | MEP | Gaganjit S | Approvals | 0.2817 | 1
Srjp - Res | Srjp - Res | MEP | Gaganjit S | Experience Home + Project Experience | 0.2817 | 1
Srjp - Res | Srjp - Res | Landscape | Gaganjit S | Schematic Concept | 0.47269 | 1
Srjp - Res | Srjp - Res | Landscape | Gaganjit S | Experience Home + Project Experience | 0.15756 | 1
Srjp - C - SB | Srjp - C - SB |  | Gaganjit S | Design Packages - Srjp - C - SB | 0.86951 | 2
Srjp - C - SB | Srjp - C - SB | MEP | Gaganjit S | Schematic Concept | 0.43476 | 1
Srjp - C - SB | Srjp - C - SB | MEP | Gaganjit S | Approvals | 0.43476 | 1
Srjp - C - NB | Srjp - C - NB |  | Gaganjit S | Design Packages - Srjp - C - NB | 0.28984 | 2
Srjp - C - NB | Srjp - C - NB | MEP | Gaganjit S | Schematic Concept | 0.14492 | 1
Srjp - C - NB | Srjp - C - NB | MEP | Gaganjit S | Approvals | 0.14492 | 1
OTF | OTF |  | Gaganjit S | Design Packages - OTF | 0.32805 | 7
OTF | OTF | MEP | Gagan | Schematic Concept | 0.039825 | 1
OTF | OTF | MEP | Gagan | Approvals | 0.07965 | 1
OTF | OTF | MEP | Gagan | Pre Construction Set | 0.07965 | 1
OTF | OTF | MEP | Gagan | Experience Home + Project Experience | 0.039825 | 1
OTF | OTF | Landscape | Gagan | Schematic Concept | 0.04455 | 1
OTF | OTF | Landscape | Gagan | Pre Construction Set | 0.022275 | 1
OTF | OTF | Landscape | Gagan | Project Experience | 0.022275 | 1
Harohalli [Plotted] | Ph 1 |  | Gaganjit S | Design Packages - Harohalli [Plotted] | 5.2621 | 10
Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Contract + Design Brief | 0.855 | 1
Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Schematic Concept | 1.405 | 1
Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Approvals | 1.405 | 1
Harohalli [Plotted] | Ph 1 | Master Planning | Gagan | Project Experience | 0.855 | 1
Harohalli [Plotted] | Ph 1 | MEP | Gagan | Schematic Concept | 0.10089 | 1
Harohalli [Plotted] | Ph 1 | MEP | Gagan | Approvals | 0.20178 | 1
Harohalli [Plotted] | Ph 1 | MEP | Gagan | Project Experience | 0.10089 | 1
Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Schematic Concept | 0.11286 | 1
Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Approvals | 0.16929 | 1
Harohalli [Plotted] | Ph 1 | Landscape | Gagan | Project Experience | 0.05643 | 1
Shreegaon [70a] | Ph 1 |  | Gaganjit S | Design Packages - Shreegaon [70a] | 2.5074 | 7
Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Contract + Design Brief | 0.4725 | 1
Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Schematic Concept | 0.85586 | 1
Shreegaon [70a] | Ph 1 | Master Planning | Gagan | Approvals | 0.85586 | 1
Shreegaon [70a] | Ph 1 | MEP | Gagan | Schematic Concept | 0.055755 | 1
Shreegaon [70a] | Ph 1 | MEP | Gagan | Approvals | 0.11151 | 1
Shreegaon [70a] | Ph 1 | Landscape | Gagan | Schematic Concept | 0.06237 | 1
Shreegaon [70a] | Ph 1 | Landscape | Gagan | Approvals | 0.093555 | 1
Violet hill | Ph 1 |  | Gaganjit S | Design Packages - Violet hill | 2.7928 | 16
Violet hill | Ph 1 | Master Planning | Gagan | Schematic Concept [Rework] | 0.55067 | 1
Violet hill | Ph 1 | Master Planning | Gagan | Approvals [Rework] | 0.55067 | 1
Violet hill | Ph 1 | Master Planning | Gagan | Pre Construction Set | 0.55067 | 1
Violet hill | Ph 1 | Master Planning | Gagan | Project Experience | 0.30444 | 1
Violet hill | Ph 1 | Master Planning | Gagan | Marketing and Sales | 0.30444 | 1
Violet hill | Ph 1 | Master Planning | Gagan | Structures - Security Cabin and Entrance [Rework] | 0.1652 | 1
Violet hill | Ph 1 | MEP | Gagan | Schematic Concept | 0.035924 | 1
Violet hill | Ph 1 | MEP | Gagan | Approvals [Rework] | 0.071849 | 1
Violet hill | Ph 1 | MEP | Gagan | Pre Construction Set | 0.071849 | 1
Violet hill | Ph 1 | MEP | Gagan | Project Experience | 0.035924 | 1
Violet hill | Ph 1 | MEP | Gagan | Structures - Security Cabin and Entrance | 0.03249 | 1
Violet hill | Ph 1 | Landscape | Gagan | Schematic Concept | 0.040186 | 1
Violet hill | Ph 1 | Landscape | Gagan | Pre Construction Set | 0.020093 | 1
Violet hill | Ph 1 | Landscape | Gagan | Project Experience | 0.020093 | 1
Violet hill | Ph 1 | Landscape | Gagan | Marketing and Sales | 0.020093 | 1
Violet hill | Ph 1 | Landscape | Gagan | Structures - Security Cabin and Entrance | 0.018172 | 1
Ambegaon | Ph 1 |  | Gaganjit S | Design Packages - Ambegaon | 0 | 0
Mall of Asia | Mall of Asia |  | Gaganjit S | Design Packages - Mall of Asia | 0 | 0
TR Mills | TR Mills |  | Gaganjit S | Design Packages - TR Mills | 0 | 0
OTR OOTA | OTR OOTA |  | Gaganjit S | Design Packages - OTR OOTA | 0.02067 | 4
OTR OOTA | OTR OOTA | MEP | Gagan | LoD 200 - Schematic Concept | 0.0056373 | 1
OTR OOTA | OTR OOTA | MEP | Gagan | Approvals | 0.0056373 | 1
OTR OOTA | OTR OOTA | Landscape | Gagan | LoD 200 - Schematic Concept | 0.0046977 | 1
OTR OOTA | OTR OOTA | Landscape | Gagan | Approvals | 0.0046977 | 1
DonaPaula | DP |  | Gaganjit S | Design Packages - DonaPaula | 0.45 | 5
DonaPaula | DP | MEP | Gagan | Schematic Concept | 0.1 | 1
DonaPaula | DP | MEP | Gagan | Approvals | 0.05 | 1
DonaPaula | DP | MEP | Gagan | Preconstruction | 0.1 | 1
DonaPaula | DP | Landscape | Gagan | Schematic Concept | 0.15 | 1
DonaPaula | DP | Landscape | Gagan | Approvals | 0.05 | 1