## New Projects - Goals FY 26- (2)
FY 2026-27 Q3 ¦ Design Goals + Billing |  |  |  |  | 0 | 2 | 0 | 0
Project | Description | Release date | Responsible | Remarks | Plan - Billing [Cr.] | Plan - Pkgs | Actuals - Billing [Cr.] | Actuals - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson
KIADB - Mys |  |  |  |  | 0 | 2 | 0 | 0
Master planning | LoD 200 - Schematic Concept & Approvals |  |  |  | 0 | 1 | 0 | 0
KIADB - Mys | LoD 100 - Contract + Design Brief | 2026-10-21 | Gagan |  |  | 1 |  |  | Gagan | Utpal | Manali
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Architecture | LoD 200 - Schematic Concept & Approvals |  |  |  | 0 | 1 | 0 | 0
KIADB - Mys | LoD 100 - Contract + Design Brief | 2026-10-21 | Naveen Y |  |  | 1 |  |  | Naveen Y | Swathi | Manali
Step 1 | DP Submitted & Scrutiny in progress |  | Chandan
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | Package Release |  |  |  | 0.89413 | 9 | 0 | 0
Architecture | LoD 200 - Schematic Concept, Approvals |  |  |  | 0.74184 | 4 | 0 | 0
TMFT-Ph 3 | LoD 100 - Contract + Design Brief | 2026-10-08 | Om Prakash |  | 0.24728 | 1 | 0 |  | Om Prakash | Aparna
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | LoD 200 - Schematic Concept | 2026-12-02 | Om Prakash |  | 0.24728 | 1 | 0 |  | Om Prakash | Aparna
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | Approvals | 2026-12-17 | Om Prakash |  | 0.12364 | 1 | 0 |  | Om Prakash | Aparna
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | LoD 200 - Marketing and Sales | 2026-12-31 | Om Prakash |  | 0.12364 | 1 | 0 |  | Om Prakash | Aparna
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Structural | LoD 200 - Schematic Concept |  |  |  | 0.078635 | 1 | 0 | 0
TMFT-Ph 3 | LoD 200 - Schematic Concept | 2026-12-02 | Prakash C |  | 0.078635 | 1 | 0 |  | Prakash C | Vineetha | Dhirender | Rajath | Arpitha
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
MEP | LoD 200 - Schematic Concept, Approvals |  |  |  | 0.039179 | 2 | 0 | 0
TMFT-Ph 3 | LoD 200 - Schematic Concept | 2026-12-02 | Gagan |  | 0.029179 | 1 | 0 |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Subash Shreedhar
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | Approvals | 2026-12-04 | Gagan |  | 0.01 | 1 | 0 |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Subash Shreedhar
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Landscape | LoD 200 - Schematic Concept, Approvals |  |  |  | 0.034481 | 2 | 0 | 0
TMFT-Ph 3 | LoD 200 - Schematic Concept | 2026-12-02 | Gagan |  | 0.024481 | 1 | 0 |  | Gagan | Lajja | Chetan
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | Approvals | 2026-12-04 | Gagan |  | 0.01 | 1 | 0 |  | Gagan | Lajja | Chetan
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Byatarayanpura [behind Mall of Asia] | Package Release |  |  |  | 1.6141 | 1 | 0 | 0
Architecture | LoD 100 - Contract + Design Brief |  |  |  | 1.6141 | 1 | 0 | 0
Byatarayanpura [behind Mall of Asia] | LoD 100 - Contract + Design Brief | 2026-10-31 | Om Prakash |  | 1.6141 | 1 | 0 |  | Om Prakash | Om Prakash | Sreeja | Sinchana
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TR Mills Chamarajpet | Package Release |  |  |  | 5.965 | 1 | 0 | 0
Architecture | LoD 100 - Contract + Design Brief |  |  |  | 5.965 | 1 | 0 | 0
TR Mills | LoD 100 - Contract + Design Brief | 2026-10-31 | Saji A |  | 5.965 | 1 | 0 |  | Saji A | Simran | Arshad
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Varthur 52a | Package Release |  |  |  | 18.4 | 1 | 0 | 0
Architecture | LoD 100 - Contract + Design Brief |  |  |  | 18.4 | 1 | 0 | 0
Varthur 52a | LoD 100 - Contract + Design Brief | 2026-10-31 | Saji A |  | 18.4 | 1 | 0 |  | Saji A | Ayesha
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Nandi Hills 10a Sultanpete | Package Release |  |  |  | 0 | 1 | 0 | 0
Architecture | LoD 100 - Contract + Design Brief |  |  |  | 0 | 1 | 0 | 0
Nandi Hills 10a Sultanpete | LoD 100 - Contract + Design Brief | 2026-11-30 | Cijey M |  |  | 1 | 0 |  | Cijey M | Theodora
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Harohalli |  |  |  |  | 0.855 | 1 | 0 | 0
Master planning | LoD 200 - Schematic Concept & Approvals |  |  |  | 0.855 | 1 | 0 | 0
Harohalli | LoD 100 - Contract + Design Brief | 2026-10-15 | Gagan |  | 0.855 | 1 |  |  | Gagan | Utpal | Megha
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] |  |  |  |  | 0 | 12 | 0 | 0
Architecture | LoD 100 - Contract + Design Brief |  |  |  | 0 | 4 | 0 | 0
Misty [Nava Raipur] | LoD 100 - Contract + Design Brief | 2026-11-15 | Om Prakash |  |  | 1 |  |  | Om Prakash | Sreeja P
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | LoD 200 - Schematic Concept | 2026-11-30 | Om Prakash |  |  | 1 |  |  | Om Prakash | Sreeja P
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | LoD 300 - Pre Construction | 2026-12-15 | Om Prakash |  |  | 1 |  |  | Om Prakash | Sreeja P
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | Approvals | 2026-11-30 | Om Prakash |  |  | 1 |  |  | Om Prakash | Sreeja P
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Structural |  |  |  |  | 0 | 2 | 0 | 0
Misty [Nava Raipur] | LoD 200 - Schematic Concept | 2026-12-15 | Prakash C |  |  | 1 |  |  | Prakash C | Lincy R | Charan U T
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | LoD 300 - Pre Construction | 2026-12-30 | Prakash C |  |  | 1 |  |  | Prakash C | Lincy R | Charan U T
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
MEP |  |  |  |  | 0 | 3 | 0 | 0
Misty [Nava Raipur] | LoD 200 - Schematic Concept | 2026-12-15 | Gagan |  |  | 1 |  |  | Gagan | Salomi | Hareesha Bhavya Rinu Vallivel
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | LoD 300 - Pre Construction | 2026-12-30 | Gagan |  |  | 1 |  |  | Gagan | Salomi | Hareesha Bhavya Rinu Vallivel
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | Approvals | 2026-11-30 | Gagan |  |  | 1 |  |  | Gagan | Salomi | Hareesha Bhavya Rinu Vallivel
Step 2 | Task Description |  | User 2
Landscape |  |  |  |  | 0 | 3 | 0 | 0
Misty [Nava Raipur] | LoD 200 - Schematic Concept | 2026-12-20 | Gagan |  |  | 1 |  |  | Gagan | Lajja S | Anisha A
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | LoD 300 - Pre Construction | 2026-12-30 | Gagan |  |  | 1 |  |  | Gagan | Lajja S | Anisha A
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | Approvals | 2026-11-30 | Gagan |  |  | 1 |  |  | Gagan | Lajja S | Anisha A
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2

## New Projects - Goals FY 26-27Q3
FY 2026-27 Q3 ¦ Design Goals + Billing |  |  |  |  | 0 | 2 | 0 | 0
Project | Description | Release date | Responsible | Remarks | Plan - Billing [Cr.] | Plan - Pkgs | Actuals - Billing [Cr.] | Actuals - Pkgs | Design Lead | Lead | Person 1 | Person 2 | Person 3 | Draftperson
KIADB - Mys |  |  |  |  | 0 | 2 | 0 | 0
Master planning | LoD 200 - Schematic Concept & Approvals |  |  |  | 0 | 1 | 0 | 0
KIADB - Mys | LoD 100 - Contract + Design Brief | 2026-10-21 | Gagan |  |  | 1 |  |  | Gagan | Utpal | Manali
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Architecture | LoD 200 - Schematic Concept & Approvals |  |  |  | 0 | 1 | 0 | 0
KIADB - Mys | LoD 100 - Contract + Design Brief | 2026-10-21 | Naveen Y |  |  | 1 |  |  | Naveen Y | Swathi | Manali
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | Package Release |  |  |  | 0.89413 | 9 | 0 | 0
Architecture | LoD 200 - Schematic Concept, Approvals |  |  |  | 0.74184 | 4 | 0 | 0
TMFT-Ph 3 | LoD 100 - Contract + Design Brief | 2026-10-08 | Om Prakash |  | 0.24728 | 1 | 0 |  | Om Prakash | Aparna
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | LoD 200 - Schematic Concept | 2026-12-02 | Om Prakash |  | 0.24728 | 1 | 0 |  | Om Prakash | Aparna
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | Approvals | 2026-12-17 | Om Prakash |  | 0.12364 | 1 | 0 |  | Om Prakash | Aparna
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | LoD 200 - Marketing and Sales | 2026-12-31 | Om Prakash |  | 0.12364 | 1 | 0 |  | Om Prakash | Aparna
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Structural | LoD 200 - Schematic Concept |  |  |  | 0.078635 | 1 | 0 | 0
TMFT-Ph 3 | LoD 200 - Schematic Concept | 2026-12-02 | Prakash C |  | 0.078635 | 1 | 0 |  | Prakash C | Vineetha | Dhirender | Rajath | Arpitha
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
MEP | LoD 200 - Schematic Concept, Approvals |  |  |  | 0.039179 | 2 | 0 | 0
TMFT-Ph 3 | LoD 200 - Schematic Concept | 2026-12-02 | Gagan |  | 0.029179 | 1 | 0 |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Subash Shreedhar
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | Approvals | 2026-12-04 | Gagan |  | 0.01 | 1 | 0 |  | Gagan | Salomi | Eranna Bhavya Hareesha | Avinash Subash Shreedhar
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Landscape | LoD 200 - Schematic Concept, Approvals |  |  |  | 0.034481 | 2 | 0 | 0
TMFT-Ph 3 | LoD 200 - Schematic Concept | 2026-12-02 | Gagan |  | 0.024481 | 1 | 0 |  | Gagan | Lajja | Chetan
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TMFT-Ph 3 | Approvals | 2026-12-04 | Gagan |  | 0.01 | 1 | 0 |  | Gagan | Lajja | Chetan
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Byatarayanpura [behind Mall of Asia] | Package Release |  |  |  | 1.6141 | 1 | 0 | 0
Architecture | LoD 100 - Contract + Design Brief |  |  |  | 1.6141 | 1 | 0 | 0
Byatarayanpura [behind Mall of Asia] | LoD 100 - Contract + Design Brief | 2026-10-31 | Om Prakash |  | 1.6141 | 1 | 0 |  | Om Prakash | Om Prakash | Sreeja | Sinchana
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
TR Mills Chamarajpet | Package Release |  |  |  | 5.965 | 1 | 0 | 0
Architecture | LoD 100 - Contract + Design Brief |  |  |  | 5.965 | 1 | 0 | 0
TR Mills | LoD 100 - Contract + Design Brief | 2026-10-31 | Saji A |  | 5.965 | 1 | 0 |  | Saji A | Simran | Arshad
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Varthur 52a | Package Release |  |  |  | 18.4 | 1 | 0 | 0
Architecture | LoD 100 - Contract + Design Brief |  |  |  | 18.4 | 1 | 0 | 0
Varthur 52a | LoD 100 - Contract + Design Brief | 2026-10-31 | Saji A |  | 18.4 | 1 | 0 |  | Saji A | Ayesha
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Nandi Hills 10a Sultanpete | Package Release |  |  |  | 0 | 1 | 0 | 0
Architecture | LoD 100 - Contract + Design Brief |  |  |  | 0 | 1 | 0 | 0
Nandi Hills 10a Sultanpete | LoD 100 - Contract + Design Brief | 2026-11-30 | Cijey M |  |  | 1 | 0 |  | Cijey M | Theodora
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Harohalli |  |  |  |  | 0.855 | 1 | 0 | 0
Master planning | LoD 200 - Schematic Concept & Approvals |  |  |  | 0.855 | 1 | 0 | 0
Harohalli | LoD 100 - Contract + Design Brief | 2026-10-15 | Gagan |  | 0.855 | 1 |  |  | Gagan | Utpal | Megha
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] |  |  |  |  | 0 | 12 | 0 | 0
Architecture | LoD 100 - Contract + Design Brief |  |  |  | 0 | 4 | 0 | 0
Misty [Nava Raipur] | LoD 100 - Contract + Design Brief | 2026-11-15 | Om Prakash |  |  | 1 |  |  | Om Prakash | Sreeja P
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | LoD 200 - Schematic Concept | 2026-11-30 | Om Prakash |  |  | 1 |  |  | Om Prakash | Sreeja P
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | LoD 300 - Pre Construction | 2026-12-15 | Om Prakash |  |  | 1 |  |  | Om Prakash | Sreeja P
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | Approvals | 2026-11-30 | Om Prakash |  |  | 1 |  |  | Om Prakash | Sreeja P
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Structural |  |  |  |  | 0 | 2 | 0 | 0
Misty [Nava Raipur] | LoD 200 - Schematic Concept | 2026-12-15 | Prakash C |  |  | 1 |  |  | Prakash C | Lincy R | Charan U T
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | LoD 300 - Pre Construction | 2026-12-30 | Prakash C |  |  | 1 |  |  | Prakash C | Lincy R | Charan U T
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
MEP |  |  |  |  | 0 | 3 | 0 | 0
Misty [Nava Raipur] | LoD 200 - Schematic Concept | 2026-12-15 | Gagan |  |  | 1 |  |  | Gagan | Salomi | Hareesha Bhavya Rinu Vallivel
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | LoD 300 - Pre Construction | 2026-12-30 | Gagan |  |  | 1 |  |  | Gagan | Salomi | Hareesha Bhavya Rinu Vallivel
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | Approvals | 2026-11-30 | Gagan |  |  | 1 |  |  | Gagan | Salomi | Hareesha Bhavya Rinu Vallivel
Step 2 | Task Description |  | User 2
Landscape |  |  |  |  | 0 | 3 | 0 | 0
Misty [Nava Raipur] | LoD 200 - Schematic Concept | 2026-12-20 | Gagan |  |  | 1 |  |  | Gagan | Lajja S | Anisha A
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | LoD 300 - Pre Construction | 2026-12-30 | Gagan |  |  | 1 |  |  | Gagan | Lajja S | Anisha A
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2
Misty [Nava Raipur] | Approvals | 2026-11-30 | Gagan |  |  | 1 |  |  | Gagan | Lajja S | Anisha A
Step 1 | Task Description |  | User 1
Step 2 | Task Description |  | User 2